## Preamble
1.0 - PREAMBLE
1 | The content of this document is in reference to the appointment of a Multi-discipline consultancy company to undertake the design services as detailed within the tender documents for the design and execution of the Stone Parish Council Recreational Ground Enhancement works from planning through to completion and hand over.
2 | The multi-discipline company may take the form of a lead consultant and appointed sub-consultants. It is envisaged that the Lead Consultant will be an Architect and that the intended appointed multi-discipline company will be engaged under a RIBA Professional Services Contract.
3 | The Pre-Qualification Questionnaire and Evaluation submission must be completed and returned forming the summary document to the Tenderer submission.
4 | The Tenderer is required to submit the following:-
- Completed questionnaire and evaluation submission
- Demonstration of relevant experience
- CV's of proposed personnel
- Fee proposal
- Completed form of tender
- Completed declaration form
5 | The Tenderer is free to append any documentation & proposals as they see appropriate to further demonstrate information referred to within their submission.
6 | A scoring matrix contained herein will be used to assess the tender returns.
7 | Confirmative questions must be answered in order to achieve a pass. Those tenderers who are not able to achieve a pass shall be disqualified from the tender analysis.
8 | Qualitative questions shall be rated on the following criteria:-
- 0 = No response / Not provided
- 5 = Below expectations
- 10 = Met expectations
- 15 = Above expectations
- 20 = Exceed expectations
9 | Quantitative questions shall be based on a sliding scale of the range between the highest and lowest tender submission and allocated the available score accordingly. For example if there are 5 tender returns with fee proposals between £5k - £20k the most cost effective shall be rated with the highest available score whilst most expensive the lowest.
10 | Both Qualitative and Quantitative assessment shall be carried out entirely at the discretion of SPC and its representatives.
11 | For clarity, Project Management and Quantity Surveying services shall appointed directly by Stone Parish Council.
12 | For clarity, ground investigation services, topographical surveys, CCTV surveys, etc shall be undertaken by direct appointment of Stone Parish Council.

## Summary
2.0 - SUMMARY
Item | Section | Maximum points available | Weighting
3.1 | Company and Director details | Pass / Fail | Pass / Fail
3.2 | Demonstration of Competency
3.2.1 | Architectural Services / Lead Consultant | 20 | 15%
3.2.2 | Landscape Architect Services | 20 | 15%
3.2.3 | Structural & Civil Engineering | 20 | 8%
3.2.4 | Mechanical, Electrical & Plumbing | 20 | 8%
3.2.5 | Principle Designer | 20 | 4%
3.3 | Proposed Personnel | 20 | 10%
3.4 | Satisfaction of minimum services criteria | Pass / Fail | Pass / Fail
3.5 | Fee proposal | 20 | 40%
3.6 | Satisfaction of minimum insurance criteria | Pass / Fail | Pass / Fail
3.7 | References | Pass / Fail | Pass / Fail
|  | 140 | 100%

## 3.1 - Company details
3.1 - COMPANY DETAILS (CONFORMATIVE QUESTION) |  | SCORING CRITERA
3.1.1 | LEAD CONSULTANT DETAILS - ARCHITECTURAL SERVICES | PASS | FAIL
Company Registered Name:-
Company Trading Name (if different):-
Company Registered Address:-
Company Trading Address (if different):-
Company Registered No:-
Point of contact:-
Position:-
Telephone:-
Email:-
Primary business activity:-
Year Established:-
3.1.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
Company Registered Name:-
Company Trading Name (if different):-
Company Registered Address:-
Company Trading Address (if different):-
Company Registered No:-
Point of contact:-
Position:-
Telephone:-
Email:-
Primary business activity:-
Year Established:-
3.1.3 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
Company Registered Name:-
Company Trading Name (if different):-
Company Registered Address:-
Company Trading Address (if different):-
Company Registered No:-
Point of contact:-
Position:-
Telephone:-
Email:-
Primary business activity:-
Year Established:-
3.1.4 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
Company Registered Name:-
Company Trading Name (if different):-
Company Registered Address:-
Company Trading Address (if different):-
Company Registered No:-
Point of contact:-
Position:-
Telephone:-
Email:-
Primary business activity:-
Year Established:-
3.1.5 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
Company Registered Name:-
Company Trading Name (if different):-
Company Registered Address:-
Company Trading Address (if different):-
Company Registered No:-
Point of contact:-
Position:-
Telephone:-
Email:-
Primary business activity:-
Year Established:-

## 3.2 - Compentency
3.2 - DEMONSTRATION OF COMPETENCY - (QUALITATIVE QUESTION) | [5 empty] | SCORING CRITERA
3.1.1 | LEAD CONSULTANT DETAILS - ARCHITECTURAL SERVICES |  |  |  |  | 0 | 5 | 10 | 15 | 20
Ref | Project Name | Project Client | Project description | Consultany Service Provided | Further Info Appended Y/N
1
2
3
3.1.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES |  |  |  |  | 0 | 5 | 10 | 15 | 20
Ref | Project Name | Project Client | Project description | Consultany Service Provided | Further Info Appended Y/N
1
2
3
3.1.2 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES |  |  |  |  | 0 | 5 | 10 | 15 | 20
Ref | Project Name | Project Client | Project description | Consultany Service Provided | Further Info Appended Y/N
1
2
3
3.1.2 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES |  |  |  |  | 0 | 5 | 10 | 15 | 20
Ref | Project Name | Project Client | Project description | Consultany Service Provided | Further Info Appended Y/N
1
2
3
3.1.2 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER |  |  |  |  | 0 | 5 | 10 | 15 | 20
Ref | Project Name | Project Client | Project description | Consultany Service Provided | Further Info Appended Y/N
1
2
3

## 3.3 - CV's
3.3 - PROPOSED PERSONNEL (QUALITATIVE QUESTION) |  | SCORING CRITERA
Include details of personnel only if it is the intention that they will be allocated to this project - Note CV's of the proposed member of staff must be enclosed as part of the submission.
3.3.1 | LEAD CONSULTANT DETAILS - ARCHITECTURAL SERVICES | 0 | 5 | 10 | 15 | 20
Principle point of contact
Name:-
Office location:-
Full or Part Time:-
Position:-
Period at current Employer:-
Does the proposed resource have relevant experience?
3.3.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
Principle point of contact
Name:-
Office location:-
Full or Part Time:-
Position:-
Period at current Employer:-
Does the proposed resource have relevant experience?
3.3.3 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
Principle point of contact
Name:-
Office location:-
Full or Part Time:-
Position:-
Period at current Employer:-
Does the proposed resource have relevant experience?
3.3.4 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
Principle point of contact
Name:-
Office location:-
Full or Part Time:-
Position:-
Period at current Employer:-
Does the proposed resource have relevant experience?
3.3.5 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
Principle point of contact
Name:-
Office location:-
Full or Part Time:-
Position:-
Period at current Employer:-
Does the proposed resource have relevant experience?

## 3.4 - Services
3.4 - SATISFACTION OF MINIMUM SERVICES CRITERIA (CONFORMATIVE QUESTION) |  |  | SCORING CRITERA
NB:- the following identifies the minimum services input required. - Tick to confirm inclusion.
3.4.1 |  | ARCHITECTURAL SERVICES | Pass | Fail
Stage 0 | - | Receive Client's instruction and information about the Project
| - | Assist the Client in defining the Client's strategic requirements and the preparation of the strategic brief
| - | Contribute to the Project programme
| - | Review feedback from previous or similar projects
Stage 1 | - | Inspect the site and carry out an initial appraisal of the proposed works and potential
| - | Develop initial project brief with project team including project objectives, quality objectives, project budget and other parameters or constraints
| - | Review of planning consent and inform the planning consultant on discharge of planning conditions and reserved matters outstanding.
| - | Provide information for approximate estimate of Order of Costs prepared by QS
Stage 2 | - | Prepare concept design and show outline proposals for structural and building services systems, and include outline specifications.
| - | Provide information for approximate estimates of construction costs Cost Plan
| - | Contribute to completion of the final project brief
| - | Prepare stage report in accordance with agreed information exchanges and submit to the Client.
Stage 3 | - | Develop the approved concept design to show spatial arrangements, type of construction, materials, appearance and updated outline specifications in sufficient detail to coordinate the structural and building services of the project.
| - | Investigate effect of statutory standards and construction safety on Concept design.
| - | Provide information for estimate of construction costs
| - | Prepare stage report in accordance with agreed information exchanges and submit to Client
| - | Liaise with planning authorities as appropriate.
Stage 4a | - | Prepare technical designs and specifications sufficient to construct the project.
| - | Liaise with consultant team as necessary.
| - | Liaise with specialist sub-contractors as required.
| - | Submit building regulations submission and alter design ifnormation to reflect any subsequent comments
| - | Prepare production information including detailed specification in sufficient detail to enable tenders to be obtained.
| - | Provide information for updating estimate of construction costs
| - | Review design information provided by others and ensure this is coordinated and integrated with the project information.
Stage 4b | - | Assist / Contribute to appraisal and report on tenders / negotiations
Stage 5 | - | Contribute to pre-contract meeting with all parties
| - | Carry out site inspections and review against specification and reasonable expectations of quality and advise QS / PM of findings.
| - | Attend regular site and progress meetings (allow for 6nr site meetings)
| - | Liaise with design team and contractor and update drawings as required to enable construction
| - | Assist with updating the construction & H&S strategy / plan.
Stage 6 | - | Provide 'Final issue Construction' drawings showing the building and appropriate information, where applicable for the H&S file and Building O&M's.
| - | Provide information to agree the final account
| - | Advise on the resolution of defects, responsibilities and response times.
| - | Review compliance with statutory and contract requirements
| - | Give general advice on O&M's
3.4.2 |  | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
Stage 0 | - | Receive Client's instruction and information about the Project
| - | Assist the Client in defining the Client's strategic requirements and the preparation of the strategic brief
| - | Contribute to the Project programme
| - | Review feedback from previous or similar projects
Stage 1 | - | Review of planned information and advise Client on failings of Client brief.
| - | Inspect the site and carry out an initial appraisal of the proposed works and potential
| - | Develop initial project brief with project team including project objectives, quality objectives, project budget and other parameters or constraints
| - | Review of planning consent and inform the planning consultant on discharge of planning conditions and reserved matters outstanding.
| - | Provide information for approximate estimate of Order of Costs prepared by QS
Stage 2 | - | Input into Architects developed GA's.
| - | Prepare outline materials palette for soft & hard landscape elements
| - | Provide outline planting strategy plan
| - | Provide sketch concept design for MUGA and nature walk & other REC use areas.
| - | Coordinate with Architect.
| - | Provide cost information to QS.
Stage 3 | - | Input into Architects developed GA's.
| - | Prepare and provide developed planting plans for areas of soft am hard landscaping areas
| - | Provide sketch developed design for MUGA and nature walk & other REC use areas.
| - | Coordinate with Architect.
| - | Assist in discharge of planning conditions & reserved matters as required.
| - | Provide cost information to QS.
| - | Attend design team meetings.
Stage 4 | - | Input into Architects developed GA's.
| - | Prepare and provide supporting technical details for landscape elements
| - | Prepare planting plans and phasing strategy for tendering
| - | Coordinate with Architect.
| - | Provide cost information to QS.
Stage 5 | - | Contribute to pre-contract meeting with all parties
| - | Carry out site inspections and review against specification and reasonable expectations of quality and advise QS / PM of findings. (Allow 4nr site inspections)
| - | Liaise with design team and contractor and update drawings as required to enable construction
| - | Assist with updating the construction & H&S strategy / plan.
Stage 6 | - | Provide 'Final issue Construction' drawings showing the building and appropriate information, where applicable for the H&S file and Building O&M's.
| - | Provide information to agree the final account
| - | Advise on the resolution of defects, responsibilities and response times.
| - | Give general advice on O&M's
3.4.3 |  | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
Stage 0 | - | Receive Client's instruction and information about the Project
| - | Assist the Client in defining the Client's strategic requirements and the preparation of the strategic brief
| - | Contribute to the Project programme
| - | Review feedback from previous or similar projects
Stage 1 | - | Review of planned information and advise Client on failings of Client brief.
| - | Inspect the site and carry out an initial appraisal of the proposed works and potential
| - | Develop initial project brief with project team including project objectives, quality objectives, project budget and other parameters or constraints
| - | Review of planning consent and inform the planning consultant on discharge of planning conditions and reserved matters outstanding.
| - | Provide information for approximate estimate of Order of Costs prepared by QS
Stage 2 | - | Input into Architects developed GA's.
| - | Prepare sketch design information in relation to structural and Civil design.
| - | Coordinate with Architect.
Stage 3 | - | Input into Architects developed GA's.
| - | Prepare detailed design information in relation to structural and Civil design.
| - | Coordinate with Architect.
| - | Assist in discharge of planning conditions & reserved matters as required.
| - | Attend design team meetings.
Stage 4 | - | Input into Architects developed GA's.
| - | Prepare technical design information in relation to structural and Civil design.
| - | Coordinate with Architect.
Stage 5 | - | Contribute to pre-contract meeting with all parties
| - | Carry out site inspections and review against specification and reasonable expectations of quality and advise QS / PM of findings. (Allow 2nr site visits)
| - | Liaise with design team and contractor and update drawings as required to enable construction
| - | Assist with updating the construction & H&S strategy / plan.
Stage 6 | - | Provide 'Final issue Construction' drawings showing the building and appropriate information, where applicable for the H&S file and Building O&M's.
| - | Advise on the resolution of defects, responsibilities and response times.
| - | Give general advice on O&M's
3.4.4 |  | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
Stage 0 | - | Receive Client's instruction and information about the Project
Carry out a brief survey of the site to assess any services related issues relating to surrounding outbuildings, historical importance, listing, local infrastructure, aspect, shading and aesthetics.
| - | Contribute to the Project programme
| - | Review feedback from previous or similar projects
Stage 1 | - | To initially consider ADL2A (Part L) and ADLF(Part F) building regulation issues as relevant to this scheme.
| - | Consider any other facets of project which are likely to have a fundamental impact on building design, format and servicing
| - | To carry out a desktop study as to the best and most appropriate primary fuel source and method of heat generation.
| - | To advise on use and application of Low and Zero Carbon technologies (for example, Solar Thermal, Solar PV, Ground and Air Heat Pump technologies)
| - | To provide preliminary advice on the M&E services associated with the scheme
| - | To issue a summary pre-design report with sketch plans and concept schematics, summarising our thoughts, findings, preliminary proposals and confirming the general concept and extent of design. All of course subject to input and discussion with the client.
| - | Provide information for approximate estimate of Order of Costs prepared by QS
Stage 2 | - | Input into Architects developed GA's.
| - | Undertake SAP's calculations.
| - | Provide a “performance based” design of the required mechanical and electrical services installations. Designs will be carried out in accordance with all relevant guidelines, legislation and British Standards.
| - | Coordinate with Architect.
Stage 3 | - | Coordination of all the above services with each other, structural details and other aspects of the building, and ensure the system designs “work” in terms of routing and spatial coordination.
| - | Prepare detailed design information in relation to MEP
| - | Coordinate with Architect.
| - | Assist in discharge of planning conditions & reserved matters as required.
| - | Attend design team meetings.
| - | Provide upon request copies of all relevant calculations and design criteria.
Stage 4 | - | Input into Architects developed GA's.
| - | Prepare technical design information in relation to MEP for purposes of Tender
| - | Carry out analysis and recommendations based on tender returns received.
| - | Answer contractors, suppliers and/or your own queries during the design and tender process.
| - | Provide design phase risk assessments in compliance with the Construction (Design & Management) Regulations.
| - | Coordinate with Architect.
Stage 5 | - | Contribute to pre-contract meeting with all parties
| - | Carry out site inspections and review against specification and reasonable expectations of quality and advise QS / PM of findings. (Allow 2nr site visits)
| - | Liaise with design team and contractor and update drawings as required to enable construction
| - | Ensure that relevant commissioning is carried out in accordance with specification
| - | Assist with updating the construction & H&S strategy / plan.
Stage 6 | - | Provide 'Final issue Construction' drawings showing the building and appropriate information, where applicable for the H&S file and Building O&M's.
| - | Advise on the resolution of defects, responsibilities and response times.
| - | Give general advice on O&M's
3.4.5 |  | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
| - | Advise the client of their duties and other duty holder under the Regulations.
| - | Advise the client on the measures the client should take to comply with the regulations and assist the client in undertaking those measures.
| - | Advise the client with regard to skills, knowledge and experience of design and contracting organisations not already appointed.
| - | As far as it is within the Principal Designers control, assist the client to identify and collate pre-construction information and provide to designers/contractors appointed during this design stage.
| - | Identify, with a view to elimination or control, so far as reasonably practicable, foreseeable risks within the design to the planning application stage.
| - | Check designers comply with their duties under Regulation 9 of the Regulations.
| - | Ensure that all parties co-operate with the client and within the design team and attend one design team meeting.
| - | As far as reasonably practicable monitor the pre-construction phase and co-ordinate matters relating to health and safety taking into account the general principles of prevention.
| - | Advise on the co-ordination of design work where relevant to Health and Safety
| - | Advise the client on Health and Safety considerations affecting procurement methods and approaches to design and construction.
| - | Produce a pre-construction information document to support tender documentation.
| - | Prepare a draft Health and Safety File for completion by the Principal Contractor.
| - | Liaise with the Principal Contractor and share any information relevant to the planning, management and monitoring of the construction phase including co-ordination of health and safety matters. Assist the Principal Contractor by providing information obtained from designers pursuant to regulation 9(3)(b) of the CDM Regulations.
| - | Issue HSE Notifications (where required)
| - | Check that a suitable Construction Phase Plan is in place as required by Regulation 12 of the CDM regulations before construction work commences.
| - | Check the facilities required by schedule 2 of the CDM regulations are in place and check that those facilities are being maintained throughout the project
| - | Include two visits to site during the construction phase

## 3.5 - Fees
3.5 - FEE PROPOSALS (QUANTITATIVE QUESTION) |  |  | Stage 0 | Stage 1 | Stage 2 | Stage 3 | Stage 4a | Stage 4a | Stage 5 | Stage 6 | Total
3.5.1 | ARCHITECTURAL SERVICES
| Total fixed fee for Architectural Services | [9 empty] | 0
| List below schedule of rates applicable for works in addition to agreed scope | Hourly rate
| - Discipline 1 | Insert rate
| - Discipline 2 | Insert rate
| - Discipline 3 | Insert rate
| - Discipline 4 | Insert rate
3.5.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
| Total fixed fee for Landscpe Architectural Services | [9 empty] | 0
| List below schedule of rates applicable for works in addition to agreed scope | Hourly rate
| - Discipline 1 | Insert rate
| - Discipline 2 | Insert rate
| - Discipline 3 | Insert rate
| - Discipline 4 | Insert rate
3.5.3 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
| Total fixed fee for Structural & Civil Engineering Services | [9 empty] | 0
| List below schedule of rates applicable for works in addition to agreed scope | Hourly rate
| - Discipline 1 | Insert rate
| - Discipline 2 | Insert rate
| - Discipline 3 | Insert rate
| - Discipline 4 | Insert rate
3.5.4 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
| Total fixed fee for Mechanical, Electrical & Plumbing Services | [9 empty] | 0
| List below schedule of rates applicable for works in addition to agreed scope | Hourly rate
| - Discipline 1 | Insert rate
| - Discipline 2 | Insert rate
| - Discipline 3 | Insert rate
| - Discipline 4 | Insert rate
3.5.5 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
| Total fixed fee for Principle Designer Services | [9 empty] | 0
| List below schedule of rates applicable for works in addition to agreed scope | Hourly rate
| - Discipline 1 | Insert rate
| - Discipline 2 | Insert rate
| - Discipline 3 | Insert rate
| - Discipline 4 | Insert rate
3.5.6 | OTHER FEES NOT INCLUDED IN THE ABOVE
Hourly rate
|  | Total of all fees (Excl VAT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5.7 | SCHEDULE OF INSTALLMENTS
Schedule below the installments associated with the above fees
| RIBA Stage 0 |  | 0 | [7 empty] | 0
| RIBA Stage 1 |  |  | 0 | [6 empty] | 0
| RIBA Stage 2 |  |  |  | 0 | [5 empty] | 0
| RIBA Stage 3 |  |  |  |  | 0 |  |  |  |  | 0
| RIBA Stage 4a | [5 empty] | 0 |  |  |  | 0
| RIBA Stage 4a | [6 empty] | 0 |  |  | 0
| RIBA Stage 5 | [7 empty] | 0 |  | 0
| RIBA Stage 6 | [8 empty] | 0 | 0
|  | Total of all fees (Excl VAT) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 3.6 - Insurances
3.6 - MINIMUM INSURANCE CRITERIA (CONFORMATIVE QUESTION) |  |  | SCORING CRITERA
Confirm by ticking highlighted cells
3.6.1 | ARCHITECTURAL SERVICES |  | PASS | FAIL
| Professional Indemnity | 5000000
| Employers Liability | 10000000
| Public Liability | 5000000
3.6.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
| Professional Indemnity | 1000000
| Employers Liability | 10000000
| Public Liability | 5000000
3.6.3 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
| Professional Indemnity | 1000000
| Employers Liability | 10000000
| Public Liability | 5000000
3.6.4 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
| Professional Indemnity | 1000000
| Employers Liability | 10000000
| Public Liability | 5000000
3.6.5 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
| Professional Indemnity | 1000000
| Employers Liability | 10000000
| Public Liability | 5000000

## 3.7 - References
3.7 - REFERENCES (CONFORMATIVE QUESTION) |  | SCORING CRITERA
3.7.1 | ARCHITECTURAL SERVICES | PASS | FAIL
Ref 1 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
Ref 2 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
3.7.2 | CONSULTANT / SUB-CONSULTANT DETAILS - LANDSCAPE ARCHITECTURAL SERVICES
Ref 1 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
Ref 2 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
3.7.3 | CONSULTANT / SUB-CONSULTANT DETAILS - STRUCTURAL & CIVIL ENGINEERING SERVICES
Ref 1 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
Ref 2 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
3.7.4 | CONSULTANT / SUB-CONSULTANT DETAILS - MECHANCIAL, ELECTRICAL & PLUMBING SERVICES
Ref 1 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
Ref 2 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
3.7.5 | CONSULTANT / SUB-CONSULTANT DETAILS - PRINCIPLE DESIGNER
Ref 1 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-
Ref 2 | Reference company name:-
Reference name:-
Position:-
Telephone:-
Email:-