## Pricing Summary Option B
D C Hudson & Partners LLP Chartered Architects
PRICING SUMMARY FOR OPTION B
for
Proposed Single Storey Side & Rear Extensions & Alterations
at
Leybourne Village Hall, Little Market Row, Leybourne, Kent ME19 5QL
See DCH&P Scheme Drawing 1828/12/A
Architect: | D C Hudson & Partner LLP
Client: | Leybourne Parish Council, Leybourne Village Hall, Little Market Row, Leybourne, Kent ME19 5QL
The total contract sum is to be distributed against the following items, providing a value for each item, or items of work listed. This will enable a fair assessment of extra or omitted items to the contract, and will assist in the preparation of monthly valuations.
Please note that the following sections relate to the main construction specification but only have a summary of the text, although all the work described in the specification shall be included in the cost. In some cases, specific items of work are separated out.
Depending upon the Contractors method of pricing, some paragraphs can be linked together against a cost for those combined paragraphs.
N.B. Where reference is made to a drawing, unless stated otherwise this will only be the drawing number and not any specific revision.
£
P.00 | Preliminary Items & Conditions of Working
P.01-P36 | Inclusive
P38-P40 | Inclusive
P41 | Air Test, Certificates, Warranties & Information for SBEM
P37 | Day Works. When submitting your tender, please include proposed labour rates for future reference in case needed, by completing separate form together with percentage additions where requested.
£
1 | DEMOLITION/DISMANTLING
1.01 | Hard Services
1.02 | Paths
1.03 | Drainage
1.04 | Minimise effect of demolition work on surrounding area
1.05 | Demolition works to comply with current Legislation
1.06 | Provide Statements, Assessments & Plans etc. before work starts
1.07 | Keep site, clean, tidy and safe and stockpile materials for reuse and remove unwanted materials from site
1.08 | Recycle where possible if not needed for new construction
2 | TREES
2.07-2.15 | Protection and reinstatement of existing trees
3 | SITE & GENERAL CLEARANCE
3.01 | Removal of topsoil and vegetable matter retaining sufficient topsoil for reinstatement upon completion
3.02/3.03 | Surplus topsoil, waste material and subsoil to be removed from site
3.04 | Protect existing drains and services and reinstate where damaged
4 | EXISTING SERVICES
4.01 | Undertake CAT scan to check for existing services
5 | FOUNDATIONS & SUBSTRUCTURE
5.01 | Concrete trench fill foundations details as shown on ABP drawing F437-A1-01/C and to a minimum average depth of 1.5 metres
5.02 | Construction of substructure up to DPC level
6 | GROUND FLOOR CONSTRUCTION
6.01 | Supply and installation of suspended beam and block floor and damp proof courses
6.02 | Construction of ground bearing slabs where shown for paths at side and rear
6.03 | Preparation of ground beneath/weed killer/sand/permeable geotex membrane/air space/ventilation
6.04 | Screed
6.05 | 150mm thick insulation tape joints with polythene separating layer
7 | EXTERNAL WALLS
7.01 | Supply and construction of external walls of facing brickwork/cavity/blockwork including cavity ties/insulation/closing cavities/damp proof course/closing cavities with Thermabate around openings and wall plate (see Section 9)
7.02 | Weatherboarding - Hardie Plank
7.03 | Footpath retaining walls at rear
8 | INTERNAL WALLS
8.01 | Construct the internal walls in 100mm blockwork and left ready for plastering - see Section 10
8.02 | Generally the ceiling finishes will be the underside of the roof sheets, but within the toilets, kitchen and general reception allow for timber joisted ceilings finished with 12mm plasterboard and taped ready to receive skim coat plaster - See Section 10 - with insulation over
9 | LINTELS
9.01 | Galvanised steel lintels complete with stopped ends, DPC cavity trays and weep holes in external brickwork
9.02 | Precast concrete lintels for internal blockwork partitions and in external walls over openings below ground level.
10 | PLASTER FINISHES
10.01 | Plaster ceilings to toilets and kitchen
10.02 | Plaster ceiling to entrance hall
10.03 | Plaster finish to timber studwork partitions
10.04 | 2 coat hardwall plaster to internal blockwork partitions
11 | STEEL FRAME
11.01 | Supply, design and erect the steel frame complete with all fixtures, fittings and junctions, complete with protective coatings and intumescent paint, all in accordance with the specification and drawings and design prepared by the Alan Baxter Partnership.
12 | ROOF & GUTTERS
12.01 | Supply, design and install Kingspan roof sheeting complete with all fixtures, fittings, flashings, valleys, ridges, and gutters, all as specified and details on Fulkers drawings.
13 | PLASTERBOARD
13.01 | Include costs in other sections e.g. Section 8.
14 | WINDOWS & GLAZING
14.01 | Supply, design and install all PVC-U windows complete with glazing and ironmongery, together with window boards.
15 | EXTERNAL DOORS
15.01 | Supply, design and install all external doors including glazing, ironmongery and thresholds.
16 | INTERNAL DOORS
16.01 | Supply and install all internal doors including lining, stops, fixings, architraves and ironmongery.
16.02 | Design, supply and install sliding partition - allow a provisional sum of £15,000 - OPTION B ONLY | 15000
16.03 | Design, supply and install shutters to kitchens and bars
17 | FLOOR FINISHES
17.01 | Supply and install skirtings to main hall and entrance lobby
17.02 | Floor finishes to toilets, kitchen, bar area and stores
17.03 | Floor finishes to main hall and entrance lobby
18 | PAINTING & DECORATING
18.01 | Decorate internal face of external walls
18.02 | Decorate internal walls
18.03 | Decorate ceilings to toilets, kitchen and entrance
18.04 | Decorate window boards
18.05 | Decorate skirtings
18.06 | Decorate linings, stops and architraves to openings
19 | WALL FINISHES
19.01 | Altro Whiterock finishes to walls and flat surfaces in kitchen
19.02 | Ceramic tiles to toilets - allow provisional sum of £3,000 to supply | 3000
19.03 | Allow to fix and grout wall tiling complete with edgings and trims
19.04 | Finishes to altered areas
20 | FITTINGS & FURNISHINGS
20.01 | Allow a provisional sum of £20,000 to design, supply, and install new kitchen and bar area fixtures and fittings | 20000
21 | ELECTRICAL INSTALLATION
21.01 | Design, supply and install lighting installation to new and altered areas |  | £
21.02 | Design, supply and install power to new and altered areas
21.03 | Allow to upgrade existing supply to 3 phase
22 | PLUMBING, HEATING & HOT WATER INSTALLATIONS
22.01 | Supply and install rainwater downpipes to roddable gulleys
22.02 | Install sanitary fittings to toilets and kitchen including hot and cold water supplies
22.03 | Supply sanitary fittings to toilets and kitchen
22.04 | Hot water storage to toilets
22.05 | Hot water storage for kitchen
22.06 | Hot water storage to bar areas
22.07 | Ventilation to toilets
22.08 | Ventilation to kitchen
22.09 | Allow a provisional sum of £1,000 for supply and fixing of mirrors | 1000
22.1 | Allow a provisional sum of £1,000 to supply and fit toilet roll holders/hooks/dispensers/stops | 1000
23 | EXTERNAL WORKS
23.01 | New and altered paths to rear and side
23.02 | Grass areas
23.03 | Allow a provisional sum of £3,000 for boundary fences and new front gates | 3000
24 | FOUL & SURFACE WATER DRAINAGE
24.01 | Supply and install all new below ground foul water drainage for new building and altered areas
24.02 | Supply and install all below ground surface water water drainage to new and altered areas
25 | SOAKAWAYS
25.01 | Supply and install pre-cast ring soakaway
26 | WORK REQUIRED TO DIVERT PUBLIC FOUL SEWER & RELATED SURFACE WATER WORKS
26.01 | Works in respect of diverting the public foul sewer - Manholes F1, F2, F3 & F5
26.03 | Alterations to existing surface water drainage to accommodate new surface water drainage (priced under item 24.02)
27 | STAGE (OPTION A ONLY) | NIL
28 | CHANGES TO EXISTING STRUCTURE
28.01 | Undertake alterations to existing structure as described on Fulkers drawings 17-1607/04 & 05 ready to receive finishes and services detailed elsewhere
29 | CONTINGENCY SUM | 50000
TOTAL TENDER FIGURE excluding VAT
including all Provisional Sums and Prime Cost sums and Contingency sums
but excluding all costs in (Brackets)
SEPARATE PRICES
10.05 | Provide an alternative price for omitted plaster finish to all areas except toilets and replacing with fairfaced blockwork ready to decorate direct - separate price
26.02 | Installation and associated works for attenuation tank (if required) - separate price
CONTRACTOR COMMENTS:
ANY POSSIBLE COST SAVINGS (PLEASE LIST HERE OR ON A SEPARATE SHEET)
EXCLUSIONS INCLUDE
A) | Asbestos Removal in relation to existing storage garages
B) | Dismantle and dispose of outbuildings
C) | CCTV Installation both to New & Existing Buildings
D) | Fire Extinguishers & Fire Warning System
E) | Signage (Except door signs integral with door schedule)
F) | Access Control Systems
G) | Heating/Air Conditioning - Modular Units
H) | Intruder Alarm
I) | Stage Curtains
J) | Loose Furniture
K) | Fees for Building Regulations
L) | Professional Fees
M) | Client Supply and Fix Items
N) | Fees for SBEM
E&OE