13 April 2017

# Dear Bidders,

Request for Quotation: Support for  Healthcare Simulation Modelling, Project Ref - PRJ 417

I am writing to you on behalf of Camden CCG. We currently have a requirement for support with Healthcare Simulation Modelling, the details of which are set out in the Annex A to this RFQ letter.

We need our chosen supplier to commence the work in the week commencing 9th May 2017 and finish the work on or before 6th August 2017.

Please note the attached (Annex B) NHS Standard Contract 2016-17 / Terms and Conditions for the Supply of Services will apply to any contract awarded as a result of this quotation exercise.

If you are interested in quoting for this requirement, please reply with a ‘bid response document’ to the following email box nelcsu.clinical-procurement@nhs.net by 12:00 pm on 28/04/2017  with the following information:

- Full name and address of supplier, our reference number and your contact details;

- Details of services to be supplied including details in response to the requirements set out in the Annex A / the evaluation criteria to this letter and a referee (preferably public sector);

- Expected delivery / start / finish date, and a project time table;

- Total price excluding VAT (Annex C);

- Confirmation of acceptance of the terms and conditions of contract (Annex B);

- Annex D – Conflict of Interest Declaration.

The CCG is seeking quotations from a number of suppliers. The following criteria will apply to the selection of the successful supplier:

| # | Evaluation Criteria |  | Weight |
| --- | --- | --- | --- |
| 1 | Proposed Approach |  | 90% |
|  | 1.1 | Clear Methodology including development of the model, validation, scenario analysis, outputs and reporting. | 25% |
|  | 1.2 | Project Delivery Plan including timeline for deliverables | 10% |
|  | 1.3 | Proven experience and capability in the field (provide details of previous experience of carrying out similar projects including population health modelling and healthcare simulation modelling) | 25% |
|  | 1.4 | How you would work with the CCG sustainable insights team to ensure robust handover and skill transfer, so that the CCG can continue to use the model beyond the project end date? | 20% |
|  | 1.5 | Flexibility of the tool to adapt to different modelling scenarios | 5% |
|  | 1.6 | Organisational capacity to undertake the work given other commitments | 5% |
| 2 | Price |  | 10% |
|  | Proposed Approach + Price = |  | 100% |

Each scored section in Table 1 will be scored based on Table below

Table 2: Scoring criteria

| Grade | Grade Level | Definition of Grade |
| --- | --- | --- |
| 0 | Unacceptable | No response or partial response and poor evidence provided in support of it. Does not give the Authority confidence in the ability of the Bidder to deliver the Contract and meet the Authority’s Requirements. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract and meet the Authority’s Requirements. |
| 2 | Minor reservations | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail and/or evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract and meet the Authority’s Requirements. |
| 3 | Satisfactory | Response is comprehensive and supported by good standard of evidence. Gives the Authority confidence in the ability of the Bidder to deliver the Contract. Meets the Authority’s Requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the Authority a high level of confidence in the ability of the Bidder to deliver the Contract. Exceeds the Authority’s Requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the Authority a very high level of confidence in the ability of the Bidder to deliver the Contract. Exceeds the Authority’s Requirements in most respects. |

The Quotation must be submitted in a PDF format, with pricing submitted in a separate file (or submit one priced and one unpriced bid).  Quotations received after the above date and time may not be considered.

It would be appreciated if you could advise, within 3 days of receiving this RFQ, if you intend to submit a bid or your reasons for not submitting a bid.

If the panel feels at any point that there is not sufficient evidence to score a bidder on any evaluation point then they may, at their discretion, seek clarification from any and all bidders. Bidder clarifications will at all times take account of the commercial confidence of bidders.

If a bidder scores a ‘0’ on any sub-section then they may be eliminated at the discretion of the panel, dependent on how service critical the panel deems that sub-section to be. If a bidder scores ‘0’ on an entire section of the evaluation, the bidder will be automatically eliminated from any further evaluation.

The pass-mark for the qualitative evaluation (Questions 1.1 – 1.5) element is 50%. Within the context of the overall of the Qualitiy/ Technical and Price Score this equates to 45% - the quality/ technical constituting an overall weighting of 90%.

If a bidder does not attain this pass mark overall then their bid will be rejected regardless of the price submission element of their bid.

This process ensures that NEL Commissioning Support Unit, Camden CCG attain a minimum acceptable service quality. Following submission of bids, a moderation / evaluation meeting may be held. Following the moderation meeting, Camden CCG  and NELCSU reserve the right to invite the bidders scoring over 50% of the quality/technical score to a post bid submission clarification meeting / interview to establish confidence in the Evaluation Panel that you will be able to deliver what you have stated.

In the event of a tie (where two or more top scoring Bidders had the same total weighted score including both quality and price), the CCG will select from amongst those Bidders, the submission of the Bidder with the highest weighted score in the quality/ technical section of the evaluation.

Your response must be valid for acceptance for 90 days from the deadline for receipt of quotations. Your response constitutes an offer and if Camden CCG accepts that offer then your status will become the “preferred bidder” in the matter of this procurement.

Respondents accept that Camden CCG  is subject to the Freedom of Information Act and government transparency obligations which may require Camden CCG to disclose information received from you to third parties.

This RFQ letter and your response do not give rise to any contractual obligation or liability unless and until such time as Camden CCG issues a letter referencing this Request for a Quotation with a signed contract and a valid Purchase Order number accepting your quotation. The  Camden CCG does not make any commitment to purchase and shall have no liability for your costs in responding to this Request for a Quotation.

## Canvassing and contacts

Bidders shall not in connection with this Procurement:

- Offer any inducement, fee or reward to any officer or employee of NELCSU or or Camden CCG or any person acting as an advisor or as an agent to NELCSU or Camden CCG in connection with this Procurement.

- Do anything which would constitute a breach of the Bribery Act 2010

- Canvass any of the persons referred to above in connection with the Procurement

No attempt should be made to contact NELCSU or Camden CCG staff, except the Project or Procurement Team on matters direct relevant concerning or within the procurement process; or to contact NELCSU / Camden CCG advisers or other NHS/DoH bodies as part of the procurement process. Any enquiries made to persons other than the NEL Commissioning Support Unit Project or Procurement Team will be regarded as prima facie evidence of canvassing.

## Conflicts of interest

In order to ensure a fair and competitive procurement process, Camden CCG requires that all actual or potential conflicts of interest that a potential bidder may have are identified and resolved to the satisfaction of the CCG.

Potential Applicants should notify the CCG and NEL Commissioning Support Unit  Procurement  of any actual or potential conflicts of interest in their response to the RFQ. If the potential bidder becomes aware of an actual or potential conflict of interest following submission of the application it should immediately notify the CCG and NEL Commissioning Support Unit by completing the Conflict of Interest form (see Annex D) for this procurement. Such notifications should provide details of the actual or potential conflict of interest.

If, following consultation with the potential bidder or bidders, such actual or potential conflict(s) are not resolved to the satisfaction of the CCG, Camden CCG reserves the right to exclude at any time any potential Applicants(s) from the Procurement process should any actual or potential conflict(s) of interest be found by the CCG to confer an unfair competitive advantage on one or more potential bidder(s), or otherwise to undermine a fair procurement process.

Examples of potential conflicts of interest are (without limitation) as follows:

A Bidding organisation, or any person employed or engaged by or otherwise connected with a Bidding organisation, is currently carrying out any work for the CCG, NHS England and/or the Department of Health (DH), or has done so within the last six (6) months;

A Bidding organisation is providing services for more than one Potential Bidder, in respect of this Procurement.

The ‘Conflict of Interest Declaration’, provided in Annex D, must be completed by an authorised signatory, in his / her own name, on behalf of the Bidding organisation and attached in response to this section of this RFQ.

The CCG should be immediately notified, in the event that any actual or potential conflict of interest comes to a potential Bidder’s attention at any time following the submission of the potential Bidder’s ‘Conflicts of Interest Declaration’ and bid documents.

If you have any queries about this letter or the requirement, please contact the under signed at nelcsu.clinical-procurement@nhs.net .

If you are unable to meet this requirement or are otherwise not intending to provide a quote, I would be grateful if you could let me know as soon as possible.

Yours sincerely,

Darren Lewis

Interim Procurement Manager

NEL Commissioning Support Unit

Annex A

Specification / Project Brief

For

Whole System Health care simulation model

## Introduction:

Camden CCG are looking to procure support to develop a model that will simulate the impact of service transformations on patient activity,spend and population health across the Camden local care system, using a system dynamics approach. This will enable commissioners and providers to make informed decisions about the changes being made.

## Objective:

The purpose of the model is to understand the current spend, activity and capacity across the health and care system in Camden, to model the impact of planned changes as a result of the Local Care Strategy. The tool needs to not just focus on activity in silos but have the sensitivity to show that out of hospital is about the management and co-ordination of those people with diseases. The software should be able to model people within their population segments as well as model the associated activity for these segments.  For example, this could be 1000 patients in segment X could be treated out of hospital and this would release Y resource (based on activity * price).

## Scope and Function:

## Function:

The model will need to

- Provide a baseline of current spend, activity and workforce capacity across the system showing the amount spent on different services, pathways and also population segments as defined in the sustainable insights population health management tool e.g the model should be able to identify/isolate

  - The amount spent on community services versus primary care versus acute hospital settings and the associated activity (will need to define the ‘units’ of activity)

  - The spend and activity associated with particular pathways e.g MSK, dermatology, maternity, trauma and injury

  - The activity and spend associated with different population segments, defined by level of risk/service use and demographic information such as age and sex. The suggestion is to use the groups set out in the Camden population health management tool.

- Be able to forecast changes to activity, finance and capacity as a result of demographic changes

- Forecast the impact of planned service changes on activity, spend and capacity e.g

  - Where a pathway is remodelled resulting in functions previously delivered in an acute setting to now be delivered in the primary and community settings, the model should be able to estimate the change in activity, spend and required capacity in different parts of the system.

  - Where a pathway is remodelled to improve health outcomes, the model should be able to forecast the impact on population health segments and predicted movement between the population segment (e.g number of people move to a lower risk category/level of service use). It should also be able to model the impact on demand (and therefore activity, spend and capacity)

## Scope:

The model should be able to account for:

- Population: The whole population including all patients registered with Camden GP practices and all social care users

- Activity: all activity relating to Camden population through core NHS core contracts (acute, community, OOH & 111, urgent care), Primary Care, diagnostics where this is outside the core contracts, social work assessment services, statutory social services provision including homecare, residential and nursing care and supported living. While all this activity may form baseline for the model, the scope (of the initial phase) for impact assessment and activity forecasting will be limited only to those population for whom Camden CCG is responsible. Therefore resource planning will be limited to those areas where Camden CCG has control. This can be expanded in the following phases. The model should use the same assumptions as the annual operating plan for consistency and read across.

- Spend: All commissioner spend relating to health and social care where it related to the activity above. This is likely to include CCG budget and parts of local authority and NHS England budgets.

- Workforce capacity: a facility within the model to build in associated clinical workforce capacity in the future.

## C. Test Scenarios:

It is proposed that the initial scenarios used to test the model are:

- Integrated primary care teams – understanding the required capacity for an integrated care team, and the impact on activity at each healthcare setting in the system (that are built in the baseline model) and the potential impact on population health.

- Development of admissions avoidance services – understanding required capacity across various admissions avoidance services and impact on admissions of different population groups

## Deliverables:

Develop a functional model that the CCG can further develop and adapt to support future transformation work e.g through adding further data sets and developing new scenarios for testing.

Key deliverables include:

    - Design and build a validated baseline simulation model of the whole system of Camden population using healthcare services incorporating impact of demographic change. This needs to be done by integrating population segments as defined by Camden CCG. Clearly state the assumptions made for building such model.

    - Provide Activity and spend outputs at each of point of  delivery(PoD) in the current system.   Provide forecast of activity if no new initiatives are taken.  Also include a provision to easily manipulate assumptions made (e.g. Population growth) to build the baseline model. Conduct and interpret the sensitivity analysis of the baseline model.

    - Conduct a workshop to communicate model to key stakeholders and develop test scenarios.

    - Develop simulation of test scenarios.

    - Workshop to present simulation findings to key stakeholders and incorporate changes proposed in the workshop.

    - Work in close contact with sustainable insights to work through the assumptions and to transfer the developmental knowledge applied in building the baseline model and test scenarios. Training of CCG staff to be able to use the model and develop further test scenarios.

## Governance

The supplier will report to the Head of Insights at the CCG for sign off of all deliverables

## Proposed Timetable

Supplier start date: 9th May 2017

Baseline simulation complete: 8th  June 2017

Test scenarios complete:6th July  2017

Project end date: 6th August 2017

Annex B

NHS Terms and Conditions for Supply of Services

Annex C

Financial Submissions

Financial Envelope - The financial envelope available for this work is within the range of £55,000 – £60,000 ex.VAT

Bidders must provide a detailed break down of the project cost here (please note that there should be no heading entitled miscellaneous) and which should include the following:

| Breakdown of All Costs (£) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Items | Details | No. of Days | Rate (per day, if applicable) | Total (ex.VAT) | Total (inc.VAT) |
| Simulation Build Cost |  |  |  |  |  |
| Software |  |  |  |  |  |
| Workshops Cost |  |  |  |  |  |
| Training Costs |  |  |  |  |  |
| Any Additonal Management Costs (please give details ) |  |  |  |  |  |
| Additional Items (optional – not assessed as part of price evaluation) | Details | No. of Days | Rate (per day, if applicable) | Total (ex.VAT) | Total (inc.VAT) |
| On-going Suppport |  |  |  |  |  |
| Total Project Cost/ Final Bid Price Submission |  |  |  |  |  |

All costs must be inclusive of travel and related expenses to the Base location. An estimate of the overall costs for expenses must be submitted to enable comparison of bids on an equal basis.

All prices exclude VAT.

If submitting your proposal as a pdf document, please submit your prices in a separate file.

NEL Commissioning Support Unit and Camden CCG, is requesting that bidders submit a breakdown of total cost for all the work / services as detailed in the Service Specification.

The lowest price (within the limit of the Financial Envelope) will be awarded the maximum score for price with other bids scored proportionately  against that.

## Expenses

## Any expenses claimed will be:

- Reasonably and necessarily incurred as a result of carrying out the contracted services, with due regard to economy.

- Be detailed separately on the invoice and accompanied by the relevant receipts

- Have been agreed in advance with the CCG.

- Travelling time to the CCG(s) premises is non-chargeable.

### Reimbursement of expenses will be at cost and should be in line with the [NHS Agenda for Change standard Rates identified below or at travel and subsistence rates identified by the Provider by the CCG] (please delete as appropriate)

- Actual rail travel costs based on standard class travel

- Car mileage allowance at the standard rate of 40 pence per mile or equivalent if public transport cost is lower.

- Taxi fares will only be reimbursed where public transport or use of a private car was unsuitable or inappropriate.

# ANNEX D

Declaration of conflict of interests

(Bidders/Contractors)

Project Name: Support for Healthcare Simulation Modelling, Ref PRJ 417

NHS Camden Clinical Commissioning Group Bidders/potential contractors/service providers declaration form: financial and other interests

This form is required to be completed in accordance with the CCG’s Constitution, and s140 of the NHS Act 2006 (as amended by the Health and Social Care Act 2012) and the NHS (Procurement, Patient Choice and Competition) (No2) Regulations 2013 and related guidance.

Notes:

- All potential bidders/contractors/service providers, including sub-contractors, members of a consortium, advisers or other associated parties (Relevant Organisation) are required to identify any potential conflicts of interest that could arise if the Relevant Organisation were to take part in any procurement process and/or provide services under, or otherwise enter into any contract with, the CCG, or with NHS England in circumstances where the CCG is jointly commissioning the service with, or acting under a delegation from, NHS England. If any assistance is required in order to complete this form, then the Relevant Organisation should contact Darren Lewis at NEL Commissioning Support Unit, e-mail darren.lewis5@nhs.net .

- The completed form should be sent to Darren Lewis at NEL Commissioning Support Unit, e-mail darren.lewis5@nhs.net .

- Any changes to interests declared either during the procurement process or during the term of any contract subsequently entered into by the Relevant Organisation and the CCG must notified to the CCG by completing a new declaration form and submitting it to [specify].

- Relevant Organisations completing this declaration form must provide sufficient detail of each interest so that the CCG, NHS England and also a member of the public would be able to understand clearly the sort of financial or other interest the person concerned has and the circumstances in which a conflict of interest with the business or running of the CCG or NHS England (including the award of a contract) might arise.

- If in doubt as to whether a conflict of interests could arise, a declaration of the interest should be made.

Interests that must be declared (whether such interests are those of the Relevant Person themselves or of a family member, close friend or other acquaintance of the Relevant Person), include the following:

- the Relevant Organisation or any person employed or engaged by or otherwise connected with a Relevant Organisation (Relevant Person) has provided or is providing services or other work for the CCG or NHS England;

- a Relevant Organisation or Relevant Person is providing services or other work for any other potential bidder in respect of this project or procurement process;

- the Relevant Organisation or any Relevant Person has any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions.

Declarations:

| Name of Relevant Organisation: |  |
| --- | --- |
| Interests |  |
| Type of Interest | Details |
| Provision of services or other work for the CCG or NHS England |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |

| Name of Relevant Person | [complete for all Relevant Persons] |  |
| --- | --- | --- |
| Interests |  |  |
| Type of Interest | Details | Personal interest or that of a family member, close friend or other acquaintance? |
| Provision of services or other work for the CCG or NHS England |  |  |
| Provision of services or other work for any other potential bidder in respect of this project or procurement process |  |  |
| Any other connection with the CCG or NHS England, whether personal or professional, which the public could perceive may impair or otherwise influence the CCG’s or any of its members’ or employees’ judgements, decisions or actions |  |  |

Form Completion

| I declare that to the best of my knowledge and belief, the above information is complete and correct. I undertake to update as necessary the information. I understand that the information will be used in the evaluation process to assess my organisation’s suitability to be included in the tender evaluation process, and that giving false information may result in my organisation being disqualified from the process, at this or whatever stage it becomes known to the Commissioners. |  |
| --- | --- |
| Signed: |  |
| Name: |  |
| Position: |  |
| Bidder: |  |
| Date: |  |