## Sheet1
RFQ FY20-08 B Westcott Innovation centre Q&A
1 | There is a document within the tender package with reference to modular buildings. Simply put, modular units wont work with the spans of the office space, mainly for transport as they are too wide. Therefore, we will be pricing for a panelised LSF solution instead. Can you confirm I have understood correctly?
A number of Modular Building companies have confirmed the design is achievable using standard units.
2 | I can’t seem to find the make up or specification for the “Modular units internal facing walling Finish tapered edge boards. Decorated as per specification” I have looked on the room data sheets and it references NBS M60-110 which is for painting plasterboard. Am I right in thinking the wall would be modular panels on the reception/link side and plasterboard on the other side to working spaces? Please could you give a specification for the wall construction for the partitions marked in green on the attached and if there is a preferred product/supplier please could I also have these details.
Please see the attached drawing no.1
3 | As for the perimeter walling which will be the sandwich metal cladding is this to be left as the metal cladding finish internally or would this also require a plaster finish achieved with joist work?
Please see the attached drawing no.1
4 | Is there a tender requirement for a BREEAM rating or to price in the use of renewable energies
BREEAM was not a requirement. The M&E systems are only basic so renewable energies may not be applicable. If the Contractor has any ideas for any options with renewable energies I would suggest they put this forward as an option with a cost for the Client to consider.
5 | Does the overall construction have to include modular/off site systems or can the construction be "Traditional" construction throughout
Traditional' construction techniques may be used for the entire project provided they can meet the project timeline.
6 | Is there any existing drainage drawings
No, the landlord will be bringing new services to the perimiter of the plot, invert levels are to be agreed with the landlord during the design period.
7 | Ditto road/infrastructure details
The landlord will be bringing a new road to the perimiter of the plot, we are awating the detailed design for this.
8 | Who will be carrying out the top coat on the new and improved roads
The landlord will be responisble for all work outwith the boundary of the plot
9 | Could you please forward us a copy of the planning conditions including the conditions that we are requested to discharge
Full planning permission has not been granted at this time, the application is registered as 19/01811/APP with Aylesbury Vale Planning Office
10 | Could you please forward us details of the reception desk that we are requested to install only
This will require power & data only, the supplier of the reception desk will be responsible for installation
11 | Drawing 478_001-FC-0102 Revision 1 indicates the locations of the existing services, could you please confirm that the existing services have the capacity to serve the new development.
The new services will be installed by the landlord, the exact capacity and location is to be agreed, but they will be suitable for this development.
12 | Ditto the diameter and depths of the existing foul and surface water drainage connections
Please see answer to question 6
13 | Are any Foul Water spurs needed to accommodate the technical space, i.e. Zones 1, 2 and 3.
Not at this point in time
14 | Ditto are spurs required for the Plant Room area
This is dependent on the plant and equipment specified as part of the contractors design.
15 | Drawing 478_001-FC-0102 Revision 1, does the required hoarding have to be a solid hoarding or is Heras fencing acceptable
Heras fencing will be adequate
16 | What is the proposed surface finish beneath the site compound area upon completion of our works
Topsoil and grass seed.
17 | Preliminaries section A20 clause 1.1 and clause 2.3 has dates for completion of sections and possession of the site, are these dates still current/required.
Contractors should submit a programme with their tender showing the best dates they can achieve
18 | Please confirm that Architects tender drawing 478_001-FC-0200 Revision 2 supersedes Architects tender drawing 478_001-FC-0200 Revision 1 in its entirety.
Yes
19 | Please confirm the Room Data Sheets contained in Volume 3 Section 1 Architect dated 03/07/2019 supersedes all other room data sheets in their entirety
Yes, although only rooms G01,Z1 and X1 were amended
20 | Provide details on the incoming electricity supply size to the building
250kva
21 | Ditto water supply
To be agreed with landlord
22 | "U" value of roof cladding, varying indications highlighted in green on the attached document, please confirm the required “U” value
Minimum as drawing 0300 but to achieve building regulation compliance overall.
23 | "U" value of wall cladding, varying indications highlighted in orange, a 170mm bracket is requested which would indicated a 0.26 "U" value but also refers to the clause for insulation which shows a 0.18 "U" value, please confirm “U” value requirement
Minumum 'U' values as drawing 0300 but to achieve building regulation compliance overall. Wall / roof build up to be contractor design to achieve this minimum and comply with building regulations.
24 | Will a door and ironmongery schedule, and door detail drawing be issued during the course of the tender period
No - See room data sheets and specifications.
25 | Which RIBA Stage is the project currently at
RIBA stage 2
26 | Water to the workshop area, is it to have CAT 5 protection i.e break tank & booster pumps?
Not required.
27 | Can traditional build be used instead of modular for the office space?
See answer to question 5