## Sheet1
Clarifying Questions for Toilet Refurb WTC01 2025 | Clarifying Questions responses
We will need more than 1 week to procure all goods, how will this be allowed for once the contractor is to be appointed, especially the doors | Westbury Town Council recognises that this may present a time-constraint issue for some contractors and therefore requests that contractors propose an anticipated mobilisation date within their tender submissions.
At Warminster Road there are currently only 2 areas, one to be unisex and the other to be a disabled / accessible, the latter to have the baby change? Also, what is to happen to the areas D, E, F? | There are no plans to refurbish D,E,F they are identified for the plans. Yes to have the baby changing area within the disabled/accessible unit.
At High Street, there are to be 4 toilets, 3 unisex and the other to be disabled / accessible, the latter to have the baby change? | Yes to have the baby changing area within the disabled/accessible unit.
Existing external doors to be replaced - please confirm | Doors are to be replaced
What sort of door card payment please as per page 22 | Companies are requested to present their proposals on a design-and-build basis.
Doors - what type of payment system do you want, for DocM do they need card entry and RADAR key entry? if they have a RADAR key is it free? | Companies are requested to present their proposals on a design-and-build basis. We would propose a RADAR key entry for disabled access.
Cost for using car parking spaces and size, how long and what is the lead time to arrange taking over spaces with the council so as to not delay the start date, as per 110, PCNs and charges as per 260? | At present, it is the responsibility of the contractor to liaise with Wiltshire Council to secure a suitable compound area. As Westbury Town Council does not know the size of compound required, we are unable to make any request in advance. We have approached Wiltshire Council with the intention of securing an agreed area at a reduced cost or free of charge; however, no agreement has been confirmed prior to the release of these clarification responses.
Are there any structural issues as per 130 of tender docs | There are no known structural issues relating to the public toilets. However, compliance with the relevant legislation is required, as the wall on Warminster Road forms part of the boundary with a neighbouring property.
Asbestos, some cubicles we did not have access too neither did the asbestos contractor, please let us know what we need to allow for these in the unlikely event we find asbestos or other surprises, | An asbestos report has been published which identifies an asbestos-containing pipe at the Warminster Road site. This pipe is enclosed within brickwork and presents no immediate concern. Since the publication of the tender, Westbury Town Council has determined that the pipe may be removed at a later date, as the planned refurbishment works will not affect this area or any other areas not highlighted in the report. Access to all relevant areas will be provided. For clarity, no further asbestos survey is required, nor should contractors include the removal of this pipe within their tender submissions.
240 Japanese knotweed an issue? | This is only advising contractors to notify Westbury Town Council if Japanese knot weed has been identified during the project time, there is no knowledge of any existing Japanese knotweed at either sites.
Page 23 - what do you want to do with ceilings | It stipulates Paint - Crown easy clean Bathroom Mid Sheen Emulsion with MOULDGUARD+ technology
Page 23 - non Armitage shanks products considered? | Companies are requested to present their proposals on a design-and-build basis. After risk assessment was carried out stainless steel is a preferred option for products
Page 24 - how can we quote for CCTV, need spec and details please | CCTV cameras are to be installed at a later date with a company called Smart they will attend during the project and contractors are asked to liaise with the company to allow them access during refurbishment to install CAT6 cables for the CCTV
Page 24 - external areas, the works are vague can we have specifics pls with quants | Fascias and soffits are to be made good, repainted where required vinyl lettering to be replaced at each site " public Toilets" etc, railings can be left as these will be painted by town council
Page 24 - signage - what is required externally, type, size, quantity etc | The signage is to identify Unisex, Disabled/accessible on the doors, also replace the vinyl public toilet signage on fascia boards.
Page 26 says contractor liable for the building reg fees, normally the client would be | As per spec contractor to allow for this in the tender.
Drainage survey been undertaken? If not, do you want to allow a provisional sum for this and clearance, it is likely there will be blockages. | All Survey Reports were published on contract finder, Mechanical, electrical, and asbestos.
Page 27 windows - please confirm what works are needed | No works on Windows required
Page 28 lightning is mentioned, also fire stopping, sealing, protection, smoke and fire damper systems | Unsure what question is being asked
Page 34 security arm barrier commissioning certificate, automatic gear door commissioning certification - presume not required | That is correct as neither are being requested for installation
Section 190 refers to one photograph | Unsure what question is being asked
Can we fence part of the side alley at the High St, do we need to contact anyone and what is the notice period to do this | Any restrictions to public footpath or access will need approval from Wiltshire Council Highway department as mentioned in line 9 and 63 , Westbury Town Council are awaiting on Wiltshire Council for what support they can offer.
Item 450 pressure testing required? | As per specifications
Item 480 EPC is mentioned, is this needed? | As per specifications
Page 10 of the ACMS asbestos survey mentions room 004 and 005 excluded and must presume asbestos present, how do we allow for this? | An asbestos report has been published which identifies an asbestos-containing pipe at the Warminster Road site. This pipe is enclosed within brickwork and presents no immediate concern. Since the publication of the tender, Westbury Town Council has determined that the pipe may be removed at a later date, as the planned refurbishment works will not affect this area or any other areas not highlighted in the report. Access to all relevant areas will be provided. For clarity, no further asbestos survey is required, nor should contractors include the removal of this pipe within their tender submissions.”
Item 2.4 fire detection system needed? | Westbury Town Council has confirmed that no fire alarm system is required following a risk assessment
Item 2.6 underfloor heating is mentioned, what is the plan with this please | Companies are requested to present their proposals on a design-and-build basis.
5 Summary are we to quote for every item e.g. rainwater goods | Companies are requested to present their proposals on a design-and-build basis.
Do you want plastic or stainless steel baby change units | Companies are requested to present their proposals on a design-and-build basis.
Why wall mounted basins? Would you consider built in wall system? | Companies are requested to present their proposals on a design-and-build basis.
Smoke detectors - what is the existing fire alarm provider, we would need to work with them, as cannot just install smoke detectors without their input | Westbury Town Council have since decided that no fire alarm system is required as a risk assessment has been carried out
What type of taps would you require, standard or PIR, same with flushes | Companies are requested to present their proposals on a design-and-build basis.
Small power is mentioned, more details pls, locations, spec etc | Unsure what is being asked, there is a power supply in services areas however this may not be suitable for the potential works contractors may need to carry out their work
What works are to happen in the stores, service areas, i.e. lighting, décor, sinks etc | Only public toilets cubicles are required for refurbishment, stores/service area is not required for refurb outside what is mentioned in tender documents for drainage and M&E requirements
What type of mirrors if any would you like | Companies are requested to present their proposals on a design-and-build basis.
What make / model / type of toilet roll holder, soap dispensers would you like | Companies are requested to present their proposals on a design-and-build basis. Due to reducing a fire risk, stainless steel is a preferred option
Contactless entry/payments:
Who will provide the merchant account, and where should the funds settle (target bank account)? | The town council banks with Lloyds and currently uses I Zettle for remote payment.
Do you want a separate, lockable space for the payment electronics, with segregated cabling to reduce tampering risk? | Companies are requested to present their proposals on a design-and-build basis.
CCTV:
What coverage do you want—entrances/approaches only, or full perimeter? | CCTV cameras are to be installed at a later date with a company called SMART they will attend during the project this will be managed via CDM/PM etc to allow them access during refurbishment to install CAT6 cables for the CCTV
Fixed domes or PTZ control?
Please share the SMART CCTV standards/integration details and a commissioning contact for password setup.
Is off-site viewing required, and who should have access?
External lighting: Do you prefer dusk-to-dawn with PIR, a time clock, or both? | Dusk to Dawn is fine with PIR
Asbestos and drainage:
Please confirm the Contractor is to arrange an R&D asbestos survey for any uninspected areas and include it in our price. | An asbestos report has been published which identifies an asbestos-containing pipe at the Warminster Road site. This pipe is enclosed within brickwork and presents no immediate concern. Since the publication of the tender, Westbury Town Council has determined that the pipe may be removed at a later date, as the planned refurbishment works will not affect this area or any other areas not highlighted in the report. Access to all relevant areas will be provided. For clarity, no further asbestos survey is required, nor should contractors include the removal of this pipe within their tender submissions.
Do you have an existing CCTV drainage survey? If yes, can you share the report/stills/video? | Drainage survey report was carried out and included in the published tender documents
If not, should we allow for jet/clean and a CCTV survey pre-start?
Are any drainage/as-built drawings or manhole schedules available, or should we obtain statutory records ourselves?
Power, fire and resilience:
If the PV/battery provisional sum is not taken, do you want a UPS to keep access control live during outages? | Please include a cost but show this separately.
Should the fire alarm be monitored to the Fire Brigade/call centre, or is it local only? | Westbury Town Council have since decided that no fire alarm system is required as a risk assessment has been carried out
During isolations, we expect a brief outage affecting nearby EV points (about an hour). Who should we notify, and how much notice do you need? | This will be via Wiltshire Council, through the parking department points of contact can be arranged on awarding of contract, where possible Westbury Town Council can liaise with Wiltshire Council on this matter.
Opening hours and public interface:
Should we supply opening-hours signage, or will the Council provide branded signs? | Signage required is that on the doors to indicate Unisex/disabled/accessible etc. Building signage is to replace Vinyl Public Toilet signabe and icons, Westbury TC will nnotify local premises etc and the Town on the closure, the public toilest are already limited to one cubical
Will the Council handle public notices about the closure? Is any temporary provision needed during the works?
Commercials and logistics:
Payment process: frequency of valuations, application format, certification/payment periods, retention and release, and whether materials on/off site are payable (and any vesting requirements). | This will follow Minor works JCT Contract
The £250,000 headline—does this include or exclude VAT? Also, should our prices be stated exclusive of VAT? | £250,000 is excluding VAT
Car-park occupation: if we need bays for compound/welfare, are any fees to Wiltshire Council paid by the Contractor or by Westbury Town Council? Please confirm permit route, notice and restrictions. | At present, it is the responsibility of the contractor to liaise with Wiltshire Council to secure a suitable compound area. As Westbury Town Council does not know the size of compound required, we are unable to make any request in advance. We have approached Wiltshire Council with the intention of securing an agreed area at a reduced cost or free of charge; however, no agreement has been confirmed prior to the release of these clarification responses.
Items currently stored on site: Will these be removed by the Council before we take possession, or should we allow them to be removed/disposed of? If disposal is ours, are there any items to be retained? | Yes all items will be removed from the cubical prior to commencement of the refurbishment.
Doors: We understand replacement is now preferred over repainting. Please confirm the specification (material, performance, any fire rating, glazing/vision panels, ironmongery, finish/colour, access-control integration) and whether this sits within the £250,000 budget or is a priced variation. | Replacement of doors is preferred as they are beyond salvaging, Specifications is for companies to propose as a design and build tender.