Order Schedule 20 (Brief)

# PURPOSE

## The Cabinet Office (CO) requires a delivery partner to support the delivery of Civil Service Live (CS Live), the Government's largest, annual learning and development event.

## This tender is subject to CCS rights of early termination under the terms and conditions of the CCS Framework Agreement.

# BACKGROUND TO THE BUYER

## The Cabinet Office (The Authority) supports the Prime Minister, and ensures the effective running of government. The Authority is also the corporate headquarters for government, in partnership with His Majesty’s Treasury, and takes the lead in certain critical policy areas.

# BACKGROUND TO REQUIREMENT/OVERVIEW OF REQUIREMENT

## The Cabinet Office is responsible for delivery of CS Live, where thousands of civil servants come together to learn, network and share best practice. The event is delivered via collaboration across the whole Civil Service, with the 19 largest departments in HMG contributing financially and over 30 Permanent Secretaries speaking at the events.

## Our Civil Service Events portfolio is the cornerstone of building a confident, innovative and effective institution that delivers Mission-driven Government and the Plan for Change. Through strategic engagement with nearly 25,000 civil servants annually, we exist to work with staff to highlight how their work contributes to government missions, engage them in strengthening their commitment to public service and the Civil Service Code, and inspire them to take calculated risks, collaborate across boundaries, and champion Mission-driven Government.

# Our events portfolio will be a catalyst for creating a Civil Service where staff feel proud of their contribution to the public good, understand how their work delivers the government's five missions, and are equipped with the capability, opportunity and motivation to work collaboratively, innovatively and ethically whilst maintaining cost-effectiveness and inclusive access.

## These are high profile events in the Civil Service calendar. The successful Supplier must be able to provide a highly professional and proactive team to deliver this tender and have the flexibility to manage changing requirements with ease and professionalism.

## Its purpose is to deliver cost effective and tailored learning events to HMG.

## The events should be innovative in execution and design. Have a motivating feel, incorporating cutting-edge digital formats and technology, while providing delegates with a mix of parallel plenary and syndicate sessions, 1-2-1 mentoring sessions, networking sessions, and an exhibition.

## The content will be developed by internal Government departments and approved and signed off by Cabinet Office as the Authority.

## The successful Supplier must be able to provide a highly professional and proactive team to deliver this contract and have the flexibility to manage changing requirements with ease and professionalism.

## The Supplier will need to have proven experience in putting together not only large-scale events but hybrid event delivery and on demand content hosting.

## The Supplier will be able to outsource aspects of delivery but will be held responsible for managing subcontractors and ensuring the quality and timing of service provision.

# DEFINITIONS

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## AV | ## Means; Audio Visual |
| ## CO | ## Means; Cabinet Office |
| ## CS | ## Means; Civil Service |
| ## DDA | ## Means; Disability Discrimination Act |
| ## GDPR | ## Means; General Data Protection Regulations |
| ## HMG | ## Means; His Majesty’s Government |
| ## OGD | ## Means; Other Government Departments |
| ## SCS | ## Means; Senior Civil Servant |
| ## SRO | ## Means; Senior Responsible Officer |
| ## WCAG | ## Means; Web Content Accessibility Guidelines |

# THE REQUIREMENT

# The proposed format for 2026 is as follows:

| Date | Venue | Target audience (attending a half day event, either morning or afternoon) | Event format |
| --- | --- | --- | --- |
| Wednesday 10 June 2026 | EICC, Edinburgh | 5,000 | - In person only: Up to 50 sessions and 60 exhibition stands (usually 3m x 2m) and up to 10 Hub stands (6m x 6m, each running silent running, bitesize sessions to audiences of circa 30 people.) |
| Tuesday 14 and Wednesday 15 July 2026 | Excel, London | 9,000 | - In person only: Up to 300 sessions and 75 exhibition stands (usually 3m x 2m) and up to 10 Hub stands (6m x 6m, each running silent running, bitesize sessions to audiences of circa 30 people.) |
| TBC September 2026 | Venue TBC - Newcastle | 1,000 | Per event: - In-person: Up to 14 sessions 30 exhibition stands (table-top or very low cost stands). - Online: Up to 7 live-streamed sessions with capacity for up to 10,000 staff per session. |
| TBC October 2026 | Venue TBC - Manchester | 1,000 |  |
| TBC November 2026 | Venue TBC - Exeter | 1,000 |  |
| TBC January 2027 | Venue TBC - Cardiff | 1,000 |  |
| TBC February 2027 | Venue TBC - Belfast | 1,000 |  |
| TBC March 2027 | Venue TBC - Leeds, Sheffield or York | 1,000 |  |
| TBC May 2027 | Venue TBC - Midlands | 1,000 |  |
| 10 days | 9 venues | 21,000 in person attendees and up to 12,000 online attendees. Total = 34,000 attendees |  |

## It is anticipated that the events will follow a similar format for 2027 - 8.

## The client retains the right to amend the schedule.

## This contract is initially for a period from 16 January 2026 up to 30 August 2027 and has an option for one, 21-month extension period.

## The Services required under this Contract and format set out for the first 21-month delivery period may be refined (to the extent permitted) by the Cabinet Office. The contract extensions will be agreed based on the Budget approved.

## The Contract is structured to offer Contracting Authorities flexibility and choice for the format (e.g., number of events, location and format) of future years if contract is extended. It will be a matter of judgement for the Contracting Authorities to decide which particular format is most appropriate to meet their specific requirements and best deliver their business needs

## The Authority expects the Client to provide a final, itemised budget for each event within 60 days of each event being delivered.

## The Authority expects the Client to provide a final reconciled budget for the full project submitted 60 days after the final event.

## If applicable, payment for any extensions shall be based upon the contract price subject to fair and reasonable adjustment to be mutually agreed between CO and the Supplier.

# SCOPE OF REQUIREMENT

## The event Supplier is required to:

### provide event management and production services for the series of events;

### record 7 sessions of content from each of the 7 smaller events and provide a content library for session recordings to make these available from one month after each of the hybrid events until 3 months following the final event in May 2027 (49 x 45 minute sessions in total);

## The Supplier will be responsible for the following services:

### Strategic planning and design and delivery: End to end event advice, strategy, planning, design, delivery, management and production;

### Staffing of the event (HMG will provide volunteer staff of 150+ each day to help with people flow/management, room set-up etc. (75 in the morning, 75 in the afternoon for the large scale events and c 30 in the morning and 30 in the afternoon of the small scale events.);

### All co-ordination, e.g. dealing with enquiries, main point of contact for all parties involved, stage management and speaker liaison;

### Act as lead Supplier for other sub-contractors;

### Ensuring that arrangements have been made for delegates with any specific requirements/disabilities including access, induction loops, signers, etc, including the production of accessibility reports.

### Ensuring best practice approaches are adopted in light of sustainability.

### Event Project Management (to include, but not limited to, development and management of a detailed delivery plan, attendance at key meetings, allocation of tasks to individuals, management of subcontractors’ delivery schedules, risk management, input into the event format and approach)

### Financial management and settlement, licences, insurance, and the review of Terms and Conditions for services they procure on our behalf;

### Speaker and exhibitor liaison and coordination;

### Advance and on-site delegate & database management including registration;

### The provision of trackable links to allow us to identify how delegates access the registration platform;

### Advance and on-site venue and catering management;

### Advance and on-site exhibition management;

### Security for the events, to ensure the safety of all staff and stakeholders at the events;

### Advance and on-site technical, design and production services, print and production of event materials;

### Advance and on-site venue surveys, health and safety/risk assessments and post-event research and evaluation;

### Procuring (if unable to deliver in-house) and managing a recording session content and making it into an accessible and engaging content library post event;

### Necessary support, liaison with the Authority, and attendance at Authority meetings;

### Website development; hosting and updating a public-facing website, a web-based application form, compliance with Disability Discrimination Act best practice and WCAG guidelines on accessibility. The Authority would require sign-off of any and all website content;

    - Creating or updating branding and design of key event assets (including, but not limited to website, PowerPoint templates, logo, signage, gobos, brochures, TBC event app, branded lectern graphics, email templates.)

    - Translation for the Cardiff event, including the production of bilingual registration platforms, agendas, event signage, emails, securing a simultaneous translation service for 10% of the event content, bilingual presentation template, bilingual presentations for 10% of the event content.

## The Authority would handle:

### promotion of the events (including delegate attraction, recruitment) and would require sign-off of any and all communications the delivery partner produces;

### content creation

### securing senior Civil Service speakers;

### securing funding to cover costs;

    - the event communications strategy

### speaker / contributor recruitment.

    - securing free of charge translation services (excluding simultaneous translators).

## The Authority requires that the Supplier delivers the following for all events:

### Management of the delegate, exhibitor, speaker and volunteer registration to include:

### load testing of the platform to ensure servers can maintain seamless delivery in peak periods.

### session booking to create a bespoke agenda for each delegate, with smart tagging of sessions to aid session selection and the option to revise booking;

### confirmation of the booking, including personalised agendas and travel details, and

### delegate confirmation emails/badges which include a summary of the individuals’ agenda;

### the option for delegates to cancel their bookings easily (ideally within two clicks).

### Translation of the platform for the Cardiff event and all associated emails

### the function to ensure delegates cannot double book themselves on sessions running concurrently;

### waiting-list functionality to address cancellations;

### safe storage of individuals’ data;

### interaction with a fast badging/registration facility at registration;

### interaction with scanning technology to record attendance at sessions/exhibition stands;

### interaction with evaluation software to allow targeted evaluation of sessions;

### reporting functionality including analytics reports which can be scheduled on a weekly basis, or on request.

### the ability to do block registration/bulk upload for speakers/VIP/event staff

### Management of a telephone helpline and email address and staff resourcing to support this;

### Due diligence of any external speakers; any Private Sector Delegates must be vetted using Good Industry Practice and the Security Policy; and comply with all conduct requirements when on the Client’s Premises or in attendance at an Event.

### The facilitation of three charities attending each Contract term’s events free of charge, for the purposes of:

### a free of charge exhibition stand at large scale event locations (e.g. Edinburgh and London for 2026)

### a free of charge workshop at two locations

### visibility as a partner for CS Live on the event website, including their logo on the event website with a blurb (up to 150 words) on their organisation

### Lead retrieval link to be provided for use on exhibition stand

### Post-event attendee report from lead retrieval link of delegates who have opted in to share data

### running a workshop, either individually or jointly with another entity, at two locations where Events are held in each Contract Term.

### Event Reporting, including but not limited to;

      - Monthly budget reports and ad hoc reports if any potential overspend is identified, (to include income from exhibitor fees);

### Daily updates and weekly reports on registration figures, specific requests and individual sessions booked, as well as post-event attendance reports to the Authority;

### Delegate tracking (attendance) for all events and all sessions;

### Load testing reports on website and digital platforms,

      - Monthly analytics reports from the content library for the duration of the hosting period;

      - Provision of post event attendance analytics;

      - Website analytics;

      - Data on staff insight surveys to inform the programme build.;

### Provision of information regarding access to the venues (including public transport);

### Liaison with venues and the Authority to organise specific requirements including accessibility, dietary etc;

### Production of event badges or e-badges (circa 19,000 badges);

### On-site registration at all venues including digital passes - this will need to be fast paced to allow high volume in peak periods;

### Event & Technical Production Management, including:

## An electronic file storage system to

## allow speakers/presenters to upload materials pre-event, and

## ensuring presentations can be opened and played on AV equipment (noting that some may include video clips/ sound/ internet content etc).

## manage the transfer of large presentation files pre/post-event and on the day.

### Liaison with all venues/suppliers to obtain value for money for AV production to help mitigate cost.

### AV production and delivery in all rooms for each venue including:

### audience interaction via audience engagement tools such as Slido and associated licences;

### Stage, set and dressing (minimal) where required;

### Internet access (both hardwired and WiFi) is an essential element of the events and it must be able to cope with the number of sessions and activity taking place in the exhibition area,

### IT & Broadband support to include web streaming/remote participation;

### Accessibility equipment e.g. induction loops etc.

### Auxiliary equipment e.g. cabling, radio handset etc.

### All technicians, sub-contractors, operators and crew;

### Evaluation technology and support and associated licences and equipment hire (eg ipads);

### Registration technology and support;

### Install and de-rig;

      - Transport to and from venues;

      - Travel and subsistence costs for the AV supplier.

## The provision of equipment may change depending on room size/style and session required, however for the purpose of the tender, the Supplier should base costs for each venue on the following:

### Each venue will require AV in:

#### a main plenary room;

#### Each syndicate room;

#### the exhibition room;

          - The registration area.

## Further details of the AV packages we anticipate needing is as follows:

| Equipment and furniture required | Room Capacity |  |  |
| --- | --- | --- | --- |
|  | Plenary Room: 500+ | Between 100-500 people | Between 30-100 people |
| PA system | 1 | 1 | 1 |
| Laptop with wireless mouse | 2 | 2 | 2 |
| Laser Pointer | 1 | 1 | 1 |
| Screen and Projector | 1 | 1 | 1 |
| Internet / WIFI | 1 | 1 | 1 |
| Lectern & Microphone | 2 | 2 | 1 |
| Top Table | 0 | 1 | 1 |
| Soft Seating on stage | 6 | 0 | 0 |
| Coffee table on stage | 2 | 0 | 0 |
| Lapel Microphone | 8 | 4 | 4 |
| Hand held/roving microphone | 4 | 4 | 4 |
| Audience engagement system (eg Sli.do) | 1 | 1 | 1 |
| Technician in room | 2 | 1 | 1 |

### Exhibition management, including, the design, supply, installation, transport, maintenance, and removal of all necessary event infrastructure and support services, including:

      - Management of an application process and portal which gathers exhibitor requirements (to include a shopping list of AV/exhibition equipment. An options list of basic AV equipment and furniture will need to be produced for teams and departments to select from, as you will need to charge them for these items. These may include display boards, high stools, poseur/low tables, power, AV equipment etc.);

      - The Provision of:

Shell Scheme
- Modular systems with white Foamex panels and aluminium frames.
- Customisation options available for exhibitors (graphics / furniture)
- Variety of stand sizes and layouts (TBC)

Fascias & Name Boards
- White nameboard design with standard font
- Upgraded fascia option to include company logo and coloured background

Plans
- CAD drawings including DWG files for venues to identify the number of stands viable within the space, taking into consideration access for wheelchairs and power
- Electrical and Mains plans

Registration Counters/desks
- Branded, powered counters/desk with storage and queuing systems

Flooring & Carpeting
- Per sqm cost for standard exhibition carpet including recycling cost and confirmation
- Per sqm cost for raised flooring options 

Charging Stations
- Branded charging tables, complete with furniture and electric  

Branding Panels
- Full sized inserted and seamless graphics for shell scheme
- Directional signage
- Hanging exhibition banners

Floor Vinyl’s
- Thematic and directional floor stickers

Exhibition Hubs
- Non-AV 6mx6m Hub
- AV theatre style 6mx6m Hub

Stand Electrics
- Shell scheme electrical packages

Mains Power Distribution
- Mains ordering, installation and distribution

Transportation
- Timely delivery, setup, and breakdown of all equipment.

Storage
- Built in storage solutions (shell scheme)

Material Handling
- Material transfer services (between venues / to + from holding warehouse). A small charge can be made to the stand-holders for the safe transport of these items. (Teams and departments will be responsible for packing up their exhibition stand/materials to transfer between events and will arrange collection of their materials following the London event.)

Subsistence & Accommodation
- Provision for labour, travel, accommodation and subsistence

Parking
- Contractor vehicle permits and loading bay schedules.

Site Visits
- Pre-event inspections and post-event review.

      - Entering into a contract with each exhibitor attending the events within the contract term, which sets out:

        - the total cost payable by that exhibitor to the supplier and the specified payment terms (each an "Exhibitor Payment");

        - That you, as the supplier, will use best endeavours to ensure that each Exhibitor Payment is paid by the relevant exhibitor to you;

        - That you, as the supplier, will transfer an amount equal to the sum of all Exhibitor Payments paid by exhibitors to you (net of any contractual repayments to exhibitors on account of exhibitor cancellations but

        - otherwise without deduction), in one block payment to CO by no later than 60 days after each event to the bank account nominated by CO; and

        - You will not offset any Exhibitor Payment against any amount which CO is, or may become, due to pay in connection with delivery of the events.

### Repayment of exhibitor fees to the Authority by the agreed deadline.

## The event website

## The event website will need to be configured and hosted by the supplier and incorporate:

## CS Live branding and design, approved by the Authority and

## comply with the HMG service standard (including submitting the site for service assessments), at alpha and (private) beta stages. We would require sight of the platform at bid stage, ahead of contract award.

      - meet UK Gov Cyber and Information Security standards including Secure by Design https://www.security.gov.uk/policy-and-guidance/secure-by-design/about/#section_2_how-assurance-works.

## The website URL will be supplied by the Authority.

## The website or associated registration portals will need to:

### be designed and tested no later than 13 February 2026;

### meet best practice in terms of usability and accessibility;

### be able to cope with spikes in visitors (e.g., over 50,000 visitors on registration launch day) (and the supplier will be required to submit load test reports for approval during the build before the site is signed off);

### incorporate (but not be limited to) the following:

#### An introduction to the event;

#### Registration pages (meeting all data protection rules and best practice);

### Venue information, accessibility information and travel details;

### A page to explain how to apply for exhibition stands/sessions/to volunteer at the events and linked application forms;

### Event programmes;

### Exhibitors’ page;

### The ability to host live stream and on demand sessions and session collateral (PowerPoint presentations, handouts and transcripts and recordings.);

### Host social media/videos;

        - A web-based event app to allow delegates to receive live updates, to include:

          - Home Page

          - Agenda

          - Your e-ticket/QR code

          - Messages

          - Polling and Questions

          - Venue Map

          - Exhibitor information and floor plan

          - Getting to the venue

          - App user guide

          - Venue information

          - Get in touch

          - Session feedback

          - How to install app

          - Contact details;

### FAQs.

### Meet UK Government security guidelines including Third Party Personnel Security Guidance);

### Meet UK Government guidelines on data processing arrangements;

        - Accessibility reports both for the website/registration portal/content library and for each of the venues and live streaming platforms;

### Reporting functionality including analytics reports which can be scheduled on a weekly basis, or on request, which can be downloaded as needed;

        - Support for the maintenance of the website; Making any and all updates to the website as requested by the client;

### Suppliers will be assessed on their ability to use new and innovative technology to deliver the outcome, including, but not limited to the use of event apps and the use of AI.

# OUR APPROACH: FURTHER BACKGROUND TO THE TENDER

## The day-to-day project management will be with the CO Event Programme Manager in the CO Communications Team. The appointed Supplier must be able to provide a fast and flexible approach with stringent attention to detail and initiative that maintains the success of the CS Live series. There will also be a wider planning group, devising and developing the content.

## The Supplier will be required to work closely with the CO Communications Team, wider planning group, venues and stakeholders to design and construct the event programmes and provide all materials and key staff necessary to run this programme of work.

### The format of the events will comprise parallel plenary, syndicate sessions and exhibition. The exact number of sessions for each event is still to be confirmed, so this specification is indicative of what will be required.  There will be a full programme of presentations running throughout the day for delegates to choose and book. Polling of registrants’ interest in sessions will be monitored by the Supplier.

## The provision of services will involve the set-up of the plenary room, production and design of exhibition areas as well as syndicate rooms. Internet and accessibility are key requirements for these events. The Supplier will be able to outsource aspects of delivery but will be held responsible for ensuring the quality, timing and overall service provision.

## Sustainability should be factored into your proposal in terms of how the Supplier would aim to reduce the carbon footprint of the event, and whether its chosen sub-contracted suppliers have sustainability accreditation.

## Core services including strategic planning, account management and reporting must not be subcontracted.

### The Agency will be required to work collaboratively and effectively with multiple stakeholders, partners and other agencies of the Client to ensure smooth delivery of the events, achieve best value and drive best outcomes.

### Venues will be secured and paid for by the Authority. We will work with the the Supplier to ensure the Supplier is content they can deliver the AV and exhibition build required, and they are fit for purpose. In cases where issues are identified by either party, we will make reasonable efforts to select an alternative venue;

### Large scale-events in June and July will be in person (face-to-face) events will include:

#### One main plenary room for 400-800 theatre;

#### 10-20 syndicates for between 40 and 600;

#### 1 x exhibition space circa 2,000 sqm;

#### A small number of back of house rooms, to include volunteer room, organisers’ office, prayer room, medical room, VIP speaker rooms x 2)

#### Cash catering;

#### Water available for all delegates through the day;

#### Cloakroom and toilets; and

#### Venue to be compliant with DDA best practices.

### Smaller scale events running from September to May will be in hybrid events will include:

#### One main plenary room for c350 - 500 theatre;

#### 1-2 syndicates for between 150 - 250 theatre;

#### A smaller session room for c30 - 50 theatre, running regional content only

#### A small number of back of house rooms, to include volunteer room, organisers’ office, prayer room, medical room, VIP speaker rooms x 2)

#### 1 x exhibition space to accommodate c 30 table top stands;

#### Cash catering;

#### Water available for all delegates through the day;

#### Cloakroom and toilets; and

#### Venue to be compliant with DDA best practices.

### Events programmes will run from 8:30am until 5:00pm, with tickets available for morning or afternoon sessions;

## One build day will be secured for the large scale events and a day or evening for the small scale events where possible.

## We wish to avoid the use of producing delegate materials. Delegates should be able to print off their own delegate badges and personalised agendas for the day, however many of the event materials need to be replicated on the website so the Supplier should include costs for:

### Production of delegate badges (should include mechanism for scanning delegates for syndicate sessions and should list the delegates’ booked sessions);

### Exhibitor confirmation and information pack applicable to each venue;

### Speaker/presenter confirmation and information pack applicable to each venue;

### Signage: must be flexible to work across all venues but not excessive;

## We also require cost effective, creative ideas on how we can monitor the number of delegates for each session to help obtain feedback post event.

## HMG expects the very highest standards of accessibility. Disabled access in set, staging, signage, print and all pre-event communication MUST be exemplary.

## The successful Supplier will be required to provide creative ideas for a system of gathering feedback from attendees. Please include this as a separate line item within your costs to include production of a post event report.

## The Supplier with be expected to work with the Authority to input into a number of briefing/communication products including:

### Session owners’ brief;

### Speakers’ brief;

### Accessibility reports;

### Exhibitors’ brief (to include a shopping list of AV/exhibition equipment);

### Email correspondence from the Supplier to include, but not limited to:

#### Delegate joining instructions (c 3 emails) including delegate badges and personalised agendas;

#### Delegate/speaker/exhibitor evaluation communications (c2 emails);

#### Updates on changes to the programme (c10 per event).

## Civil servants cannot be charged to attend this event.

## Central Government Bodies and Private sector bodies can be charged a nominal amount, agreed by the Client, for exhibition space at the Events, for stand space and furniture and power which would be collected to directly offset event costs. The Supplier would be responsible for:

## raising the contract with the exhibitors for each event,

## agreeing payment terms and collecting all payments from exhibitors,

## then returning the income to the Authority within 60 days of each event.)

## Should the Supplier wish to engage sub–contractor(s) for this project, these will need to be identified in its proposal and agreed in advance by the Authority.

# KEY MILESTONES AND DELIVERABLES

- REDACTED TEXT under FOIA Section 43 Commercial Interests.

# MANAGEMENT INFORMATION/reporting

## The Supplier will be expected to work to the reporting procedures as stated below:

### Provision of a comprehensive project management plan, detailing milestones to be delivered within two weeks of the inception meeting;

### Provision of detailed risk register to be produced for every aspect of the event, along with contingency plans for all high impact and high likelihood risks. This register should be:

#### Produced as part of the initial planning for the event, in consultation with CO planning team and should be monitored and updated as required throughout the planning process;

#### Delivered within two weeks of the inception meeting, which will be scheduled following contract award.

### The Supplier’s senior project staff must be available to attend an agreed schedule of regular update meetings pre-and post-event, please state in your proposal how many meetings are included. The schedule of meetings should be agreed within two weeks of the inception meeting and reviewed regularly. These may be held virtually or face-to-face.

### The registration figures for event and sessions booked, once these items have been published (dates of publication will be agreed as part of the project plan).

### Monthly budget updates to CO Event Manager (with any anomalies flagged in real time).

### Registration reports for each event as well as each session both prior to and following each event.

### Uploading of presentation materials to the event content library

### Analytics for the website and registration and content library pages once these items have been published (dates of publication will be agreed as part of the project plan).

### Database management in line with all data protection rules and regulations.

### The provision of privacy policies in line with GDPR to cover the data handling of all attendees at the events, including speakers and exhibitors. The policy should be agreed within two weeks of the initial meeting and refreshed if anything substantive alters.

### Exhibitor evaluation reports and full event evaluation report, the schedule for which will be agreed as part of the project plan.

### Summary of exhibitors secured at each of the regular meetings, the schedule for which will be agreed as part of the project plan.

# VOLUMES

## For CS Live 2026 delivery, and the initial contract term, we anticipate:

### 9 or more regional events;

### 34,000+ registrations across the full event series;

# CONTINUOUS IMPROVEMENT

## The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## The Supplier should present new ways of working to the Buyer during quarterly Contract review meetings.

## Changes to the way in which the Services are to be delivered must be brought to the Buyer’s attention and agreed prior to any changes being implemented.

# SUSTAINABILITY / SOCIAL VALUE

## The Supplier must ensure best practice in terms of sustainability is adhered to and demonstrated in their response. Whilst not essential, the Supplier’s adherence with ISO2012 and other relevant policies should be included as evidence where applicable.

## There are no specific sustainability requirements applied to this contract, due to its overarching nature, however the Contracting Authority expects the Supplier to comply with all current legislation regarding sustainability and legislation introduced or amended during the period of the contract pertaining to this.

## This must include compliance with the Modern Slavery Act 2015 and Climate Change Act 2008 and that any chosen sub-contracted suppliers have sustainability accreditation.

## The Supplier must consider their carbon footprint in allocating and deploying resources to undertake requirement.

## Procurement Policy Note (PPN) 6/20 – Taking Account of Social Value in the Award of Central Government Contracts. ‘Social value should be explicitly evaluated in all central government procurement, where the requirements are related and proportionate to the subject-matter of the contract, rather than just ‘considered’.

## PPN 06/20 guidance documents can be found at: https://www.gov.uk/government/publications/procurement-policy-note-0620-taking-account-of-social-value-in-the-award-of-central-government-contracts .

  - ‘Social Value for Commercial Success’ - an e-learning course accessed through the Government Commercial College that can be found via the ‘Social Value Mandatory eLearning’ link. It takes less than one hour to complete and will help you to better understand what social value is, why it is important and how to implement it.

# QUALITY

## The Supplier is required to hold or be working towards ISO 9001, with a view to being accredited no later than January 2027.

## The Supplier is required to hold or be working towards ISO 2012 - Event sustainability management systems, with a view to being accredited no later than January 2027.

# PRICE

## Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

## Should the Authority cancel the planned event or any part of the Services due to unforeseen circumstances, at its convenience, or for reasons which are not caused by any fault of the Supplier the  Authority will, subject to the Supplier using all reasonable endeavours to mitigate any such costs and subject to providing the Authority with written evidence of the incurred costs, reimburse the Supplier for all reasonable and unavoidable costs incurred in providing the contracted services, up until the date of the confirmed cancellation.

## The appointed Supplier’s Price Schedule (Attachment 4) may be used by the Authority at its discretion to determine the agreed maximum limit the Authority would be liable for, per month, if it were to take the decision to cancel the event for the reasons above. The Authority’s maximum liability for cancellation will not exceed the agreed sums set out in this Price Schedule unless agreed in writing by both parties.

## The Price Schedule (Attachment 4) must clearly show the individual roles involved in delivery and the number of days against these roles. Any/all invoices and receipts may be requested for auditing and FOI purposes and should be provided when requested; this will include any third party suppliers you contract. The contract will be published on the Contracts Finder website as part of HMG transparency agenda.

## A full breakdown for travel and subsistence should be included in the Price Schedule (standard rates of public transport should be used and the use of taxis avoided).  Any travel and subsistence claimed should be within the limits set in Cabinet Office policy. A copy of the policy can be provided on request. Payment terms will be in accordance with the Framework Agreement.

# STAFF AND CUSTOMER SERVICE

## The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

## The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

## The Supplier shall ensure that staff understand the Buyer’s vision and objectives and will provide excellent customer service to the Buyer throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

- REDACTED TEXT under FOIA Section 43 Commercial Interests.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

## Security checks for both delegates, the Supplier and its sub-contractors should be completed in line with the Metropolitan Police Service’s advice and the threat level operating at that time in the UK.

## It is anticipated that all delegates will be expected to show their Civil Service pass or photo ID on arrival to be permitted entry to the events. The appointed Supplier should have successfully completed a BPSS for all staff working on behalf of the Supplier or the Supplier’s subcontractors, as per the HMG policy guide and standard for all staff, at the link here -  https://www.gov.uk/government/publications/government-baseline-personnel-security-standard

# PAYMENT AND INVOICING

## Supplier Invoicing schedule should also be detailed on Attachment 4 -the price schedule. Invoices should be sent to the CO Events Manager in the first instance for approval. Cabinet Office, PO Box 405, SSCL, Phoenix House, Celtic Springs Business Park, Newport, NP10 8FZ

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

# CONTRACT MANAGEMENT

## Attendance at Contract Review meetings shall be at the Supplier’s own expense.

# LOCATION

## All meetings will take place virtually or at 70 Whitehall or 1 Horseguard’s Road, London or a location close to Westminster. It may be possible for the Supplier to join some, but not all, meetings remotely. This can be agreed on a meeting-by-meeting basis.