INVITATION TO TENDER (ITT) for What Works Centre for Children’s Social Care – Incubator Contract

1	Your organisation along with others is invited to offer a tender for provision of the above, to the specification outlined in the attached documents.  Enclosed are:

Document 1	Instructions and information on the tendering procedures.

Document 2	Specification of the Requirement.

Document 3	List of attachments.

Document 4	Declaration and information to be provided by tenderer.

2	Please read the instructions on the tendering procedures carefully.  Failure to comply with them may invalidate your tender which must be returned by the date and time given below using the address label provided.

3	One electronic copy of your tender must be received by CSC.WHATWORKSCENTRE@education.gov.uk no later than 5th June 2017.  Late tenders will not be considered.

4	Please contact the above email address if you have any questions about the tendering procedure.  The enclosed Document 1 also contains details for providing you with further information or clarification of the Department’s requirement.

DOCUMENT 1

INSTRUCTIONS AND INFORMATION ON TENDERING PROCEDURES

1	These instructions are designed to ensure that all tenders are given equal and fair consideration.  It is important therefore that you provide all the information asked for in the format and order specified.  Please contact CSC.WHATWORKSCENTRE@education.gov.uk if you have any doubts as to what is required or you have difficulty in providing the information requested.  Pre-tender negotiations are not allowed.

2	Please note that references to the 'Department' throughout these documents mean The Secretary of State for Education acting through her representatives in the Department for Education.

Contract Period

3	The contract is to be for a period from July 2017 to March 2020 (2 years, 9 months).

Incomplete Tender

4	Tenders may be rejected if the information asked for in the ITT and Specification is not given at the time of tendering.

Returning Tenders

5	Envelopes and packages must bear no reference to the tenderer by name; franking machines which automatically print the company’s name should not be used.  Tenders must be delivered by 5pm on 5th June 2017.

Receipt of Tenders

6	Tenders will be received up to the time and date stated.  Those received before the due date will be retained unopened until then.  It is the responsibility of the tenderer to ensure that their tender is delivered not later than the appointed time.

Acceptance of Tenders

7	By issuing this invitation the Department is not bound in any way and does not have to accept the lowest or any tender, and reserves the right to accept a portion of any tender, unless the tenderer expressly stipulates otherwise in their tender.

Inducements

8	Offering an inducement of any kind in relation to obtaining this or any other contract with the Department will disqualify your tender from being considered and may constitute a criminal offence.

Confidentiality of Tenders

9	Please note the following requirements, you must not:

- Tell anyone else what your tender price is or will be, before the time limit for delivery of tenders.

- Try to obtain any information about anyone else's tender or proposed tender before the time limit for delivery of tenders.

- Make any arrangements with another organisation about whether or not they should tender, or about their or your tender price.

Failure to comply with these conditions may disqualify your tender.

Costs and Expenses

10	You will not be entitled to claim from the Department any costs or expenses which you may incur in preparing your tender whether or not your tender is successful.

Debriefing

11	Following the award of contract, debriefing will be available to unsuccessful tenderers on request.

Evaluation Criteria

12	The tender process will be conducted in a manner that ensures tenders are evaluated fairly to ascertain the economically most advantageous tender. The award criteria will include 90% of the score for quality, and 10% for cost.

Purchasing Strategy

14	The Department’s purchasing strategy is designed to promote fair and open competition, and constructive co-operation between the Department and suppliers.

Freedom Of Information

15	The Department is committed to open government and to meeting their responsibilities under the Freedom of Information Act 2000. Accordingly, all information submitted to the department may need to be disclosed in response to a request under the Act.  If you consider that any of the information included in your tender is commercially sensitive, please identify it and explain (in broad terms) what harm may result from disclosure if a request is received, and the time period applicable to that sensitivity. You should be aware that, even where you have indicated that information is commercially sensitive, we may still be required to disclose it under the Act if a request is received. Please also note that the receipt of any material marked ‘confidential’ or equivalent by the department should not be taken to mean that we accept any duty of confidence by virtue of that marking. If a request is received, we may also be required to disclose details of unsuccessful tenders.

Publication of Contract

16	Under the Government’s Transparency requirements we are obliged to publish the contract between the Department and the successful tenderer(s) in full.  The successful tenderer(s) should identify any information regarded as commercially sensitive and explain (in broad terms) what harm may result from disclosure and the time period applicable to that sensitivity.  You should be aware that, even where you have indicated that information is commercially sensitive, we may still be required to disclose it if the public interest in disclosure outweighs withholding the information.  Please see Procurement Policy Note 13/15 which contains further information on the general transparency principles that require public procurers proactively to disclose contract and related information that may previously have been withheld on grounds of commercial confidentiality

Information Sharing Across Government

17	All Central Government Departments and their Executive Agencies and Non Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further, the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement - including ensuring value for money and related aspects of good procurement practice.

18	For these purposes, the Department may disclose within Government any of the Contractor's documentation/information (including any that the Contractor considers to be confidential and/or commercially sensitive such as specific bid information) submitted by the Contractor to the Department during this Procurement. The information will not be disclosed outside Government. Contractors taking part in this competition consent to these terms as part of the competition process.”

Cyber Essentials Scheme

19	The Government has introduced its new Cyber Essentials Scheme in consultation with industry to mitigate the risk from common internet based threats.

20	From 1st October 2014, it is mandatory for new Central Government contracts, which feature characteristics involving the handling of personal data and ICT systems designed to store or process data at the OFFICIAL level of the Government Security Classifications scheme  to comply with Cyber Essentials requirements.

21	All potential tenderers for Central Government contracts, featuring the above characteristics, should make themselves aware of Cyber Essentials and the requirements for the appropriate level of certification “or equivalent”.

22	As this requirement features the above characteristics, you are required to demonstrate in your tender response that:

- Your organisation has [Cyber Essentials] or [Cyber Essentials Plus] certification; [select the relevant level] or

- Your organisation will be able to secure [Cyber Essentials] or [Cyber Essentials Plus] certification [select the relevant level] prior to contract award; or

- Your organisation has equivalent evidence to support that you have appropriate technical and organisational measures to mitigate the risk from common internet based threats in respect to the following five technical areas:

- Boundary firewalls and internet gateways - these are devices designed to prevent unauthorised access to or from private networks, but good setup of these devices either in hardware or software form is important for them to be fully effective.

- Secure configuration – ensuring that systems are configured in the most secure way for the needs of the organisation

- Access control – Ensuring only those who should have access to systems to have access and at the appropriate level.

- Malware protection – ensuring that virus and malware protection is installed and is up to date

- Patch management – ensuring the latest supported version of applications is used and all the necessary patches supplied by the vendor have been applied.

Any equivalent evidence must be verified by a technically competent and independent third party.

23	The successful tenderer will be required to provide evidence of [Cyber Essentials] or [Cyber Essentials Plus] certification [select the relevant level] “or equivalent” (i.e. demonstrate they meet the five technical areas the Cyber Essentials Scheme covers) prior to contract award.

24	The successful tenderer will be required to secure and provide evidence of [Cyber Essentials] or [Cyber Essentials Plus] re-certification [select the relevant level] “or equivalent” (i.e. demonstrate they meet the five technical areas) on an annual basis.

25	Details of certification bodies are available at: https://www.cyberstreetwise.com/cyberessentials

Data Security Standards

26	For contracts which require the holding or processing of either personal data and/or OFFICIAL data the successful contractor will need to assure the Department that they can comply with the Department’s security standards.

27	Departmental security standards are listed as contract clauses in an annex to this letter (see Document 3 – List of Attachments). [Ensure that you select the relevant clauses prior to sending out the ITT letter.  See Data Security guidance]

Government Security Classifications

28	On 2nd April 2014 the Government introduced a Government Security Classifications (GSC) classification scheme to replace the previous Protective Marking System (GPMS). A key aspect of this is the reduction in the number of security classifications used. All potential suppliers are encouraged to make themselves aware of the changes and identify any potential impacts in their Tender, as the protective marking and applicable protection of any material passed to, or generated by, you during the tender process or pursuant to any Contract awarded to you as a result of this tender process will be subject to the new GSC. The link below to the Gov.uk website provides information on the GSC:

https://www.gov.uk/government/publications/government-security-classifications

The Department reserves the right to amend any security related term or condition of the draft contract accompanying this ITT to reflect any changes introduced by the GSC.

Prompt Payment Policy

28	Government’s aim is to pay all correctly submitted invoices within 5 days of receipt and we are 100% committed to paying correctly submitted invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.

29	The payment period will be deemed to have started when a correctly submitted invoice reaches the nominated address.  Contractors can assume receipt to be two days after mailing (by first class post). The thirty day “clock” therefore commences two days after mailing first class.

30	A correct invoice is one that is:

- delivered in timing in accordance with the contract;

- that is for the correct sum;

- In respect of goods / services supplied or delivered to the required quality (or are expected to be at the required quality);

- include the date, supplier name, contact details and bank details;

- which quote the relevant purchase order / contract reference;

- which has been delivered to the nominated address.

31	Any correctly submitted invoices that are not paid within 30 days will be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.

Sub-contracting to Small and Medium Enterprises (SMEs)

32	DfE is committed to removing barriers to SME participation in its contracts, and would like to also actively encourage its larger suppliers to make their sub-contacts accessible to smaller companies and implement SME-friendly policies in their supply-chains.  This can be achieved by advertising subcontracting opportunities on Contracts Finder and implementing the principles of the SME and Growth Agenda in your own organisation.

33	To help us measure the volume of business we do with SMEs, we will be asking DFE suppliers to provide us with information about the size of your own organisation and those in your supply chain.   We will ask about volumes of business that will flow from this contract down your supply chains, and ask you to quantify that for us.   This data will help us contribute towards Government targets on the use of SMEs. We may also publish success stories and examples of good practice on our website

Armed Forces Covenant

34	The Armed Forces Covenant is a public sector pledge from Government, businesses, charities and organisations to demonstrate their support for the armed forces community. The Covenant was brought in under the Armed Forces Act 2011 to recognise that the whole nation has a moral obligation to redress the disadvantages the armed forces community face in comparison to other citizens, and recognise sacrifices made.

35	The Covenant’s 2 principles are that:

• the armed forces community should not face disadvantages when compared to other citizens in the provision of public and commercial services

• special consideration is appropriate in some cases, especially for those who have given most such as the injured and the bereaved.

36	The Department encourages all Tenderers, and their suppliers, to sign the Corporate Covenant, declaring their support for the Armed Forces community by displaying the values and behaviours set out therein.

37	Guidance on the various ways you can demonstrate your support through the Corporate Covenant is at The Corporate Covenant.

38	If you wish to register your support you can provide a point of contact for your company on this issue to the Armed Forces Covenant Team at the address below, so that the MOD can alert you to any events or initiatives in which you may wish to participate. The Covenant Team can also provide any information you require in addition to that included on the website.

Email address: covenant-mailbox@mod.uk

Address: Armed Forces Covenant Team

Zone D, 6th Floor, Ministry of Defence,

Main Building, Whitehall, London, SW1A 2HB

39	Paragraphs 34-38 above are not a condition of working with the Department now or in the future, nor will this issue form any part of the tender evaluation, contract award procedure or any resulting contract. However, the Department very much hopes you will want to provide your support.

[Include the following paragraph on Prime Contractor Obligations only when the contract value is likely to exceed £5m.  See Library of Special Clauses for the relevant contractual clauses to include in the contract.  Remember to remove the italics and renumber the subsequent paragraphs]

Prime Contractor Obligations

40	For any contract with a value exceeding £5m, the contractor shall be obliged to advertise any sub-contracting opportunities on Contracts Finder which is a website provided by the Cabinet Office to advertise contract opportunities available at www.contractsfinder.co.uk

Apprentices

41	For any contract with an estimated value of over £10m and a contract length of over 12 months please contact the Commercial Helpline.

Tender Period

42	Due to the intensive evaluation process the Department requires tenders to remain valid for a period specified in Document 4.

Basis of the Contract

43	The specification in Document 2, and the terms and conditions in Document 3, together with any special requirements, will form the basis of the contract between the successful tenderer and the Secretary of State for Education.

Format of Bids

44	Tenderers should present their proposals in the following format:

Section 1	Table of Contents

Section 2	Management Summary

Section 3	Meeting the Specification (Please respond to the 4 Quality based questions identified Document 2 Section 8)

Section 4	Cost and Charging Arrangements (Please provide your proposed contract price responding to Document 2 Section 4)

Section 5	References and Experience

Section 6	Declarations, Undertakings and Attachments (see Document 4)

Conclusions

45	Whilst every endeavour has been made to give tenderers an accurate description of the Department's requirement, tenderers should make their own assessment about the methods and resources needed to meet those requirements.

DOCUMENT 2

SPECIFICATION

1	Background

The What Works Centre (WWC) for Children’s Social Care will foster a culture of evidence-based practice in the sector. It will be an ambitious project, independent of government, that will develop a strong evidence base around effective interventions and practice systems in children’s social care, and support their implementation by practitioners and decision makers. Its goal will be to improve outcomes for children and their families by supporting translation of evidence into better practice on the ground.

The WWC forms part of the Department’s wider agenda to develop a culture of learning across children’s social care. This includes driving a strong evidence base through the Innovation Programme and Partners in Practice, along with recommendations identified through the new Child Safeguarding Practice Review Panel and other key partners.

The WWC’s aims and scope

The WWC will become a central mechanism and driving force for evidence-based practice in children’s social care. Its activities will include:

- Collating, synthesising and reviewing existing research, evidence and data to identify what is known across the sector and bring it together into a central repository - including the learning from the Children’s Social Care Innovation Programme projects; this would include identifying gaps in knowledge around evidence;

- Identifying appropriate standards of evidence in children’s social care; exploring where methods such as RCTs can and should be used; and supporting the use of robust standards of evidence in children’s social care research;

- Developing the evidence base by conducting new high quality trials and evaluations to improve the sector’s knowledge around effective practice;

- Translating existing and new evidence into easily accessible guidance and resources for practitioners;

- Driving and supporting the dissemination and implementation of findings into practice, especially at organisational level;

- Supporting practitioners and decision-makers to understand the importance and utility of research in order to create a culture for evidence-based practice;

- Support the development of a coherent learning infrastructure across children’s social care that will enable and foster learning.

It is envisaged that the WWC’s primary target audience will be children’s social work practitioners (including frontline social workers, practice managers and practice leaders). Its broader audience will include all practitioners and decision-makers working within children’s social care, including those in residential homes (including the private sector), healthcare, policing and policy-makers. The Department is keen for the agenda of the WWC to be driven directly by the needs of frontline practitioners, and therefore envisages that the WWC will have a large degree of independence from government.

The WWC’s broad scope will include support for children from the point of referral through to permanence, including adoption, care-leaver support and targeted early help. Its focus will be on children’s social care practice in England, but we are keen to draw on and share learning from other countries and at the international level.

The initial research areas will be agreed in partnership with the successful bidders. However, the Department is keen that the WWC will have a strong focus on social work practice in its initial years.

The WWC network

The new WWC will join the What Works Network of 7 existing independent WWCs and 2 affiliate members, promoted and supported by Cabinet Office. The network is underpinned by the principle that good decision-making should be informed by the best available evidence.

Existing WWCs include the National Institute for Health and Care Excellence (NICE), which has gained a worldwide reputation for its pioneering use of clinical and cost-effective methodologies to produce authoritative advice and guidelines. The Education Endowment Foundation (EEF), since its launch in 2011, has commissioned 100 evaluations and is working with 7,500 schools and reaching 750,000 pupils across England. Other WWCs include the Early Intervention Foundation, What Works Centre for Crime Reduction and the Centre for Ageing Better.

The new WWC’s scope is envisaged to complement the work of the Early Intervention Foundation, which focuses largely on interventions in families at an earlier stage than referral. The Department also funds the Education Endowment Foundation’s work in identifying effective practice in teaching and learning amongst school children.

This procurement exercise

Over the last year, the Department has engaged extensively with the sector, other WWCs and an independent advisor to develop options for set-up of the new WWC. It is envisaged that the WWC will require a range of capabilities to tackle the challenge of bringing research to time and resource-pressured practitioners operating in a high-risk environment. These include innovation, communication, strong leadership, and the ability to build and drive an agenda for change. The WWC will also need to adopt a dynamic model, with flexibility to test and trial a variety of approaches.

The Department has therefore decided to take an incubation approach to WWC set-up, with two contracts running in parallel up to March 2020:

- The first contract from July 2017 to March 2020 (2 years, 9 months) for an ‘incubator’ to develop and test the initial WWC model internally, including the setting of the strategic direction and leadership and development of a dissemination and engagement strategy; and

- The second contract from September 2017 to March 2020 (2 years, 7 months) for a research partner to start the initial synthesis and development of the evidence base. Sifting and interviewing for the research partner contract has been staggered so that the successful incubator bidder/s can feed into the selection process.

This approach is intended to develop and test an initial model  and provide the WWC with flexibility and innovation in its early stage up to March 2020. An emphasis on dissemination and engagement is key, and the two contracts have been split to enable the initial research work to take place separately whilst the leadership, strategic direction and dissemination and engagement functions are developed. It is envisaged in the longer term that the research partner will become part of the core WWC, once a suitable model has been established.

The Department will consider the case for further funding after March 2020. It is anticipated that the WWC should be positioned so as to attract at least a proportion of its funding from non-government sources, to cement its position in the sector and its independence from government. Experience from other WWCs indicates that further government funding may be required after this point.

Bidders are able to submit proposals for both contracts but can only be awarded one contract, to ensure an equal focus on both research and dissemination/engagement activities. The successful incubator bidder/s would have to withdraw their application for the research partner contract, if they had applied.

The split of responsibilities between the incubator and research partner is expected to be as follows (note that some of the activities envisaged will be interdependent).

Incubator

- Establishing an initial model for the WWC (to be housed internally up to 2020) to be tested, and trialing a suitable relationship with government and the sector to secure appropriate positioning for the WWC. The Department envisages that this may include:

  - a leadership team (including potentially a Chair, CEO and Board) with strong frontline experience of children’s social care and strong leadership and engagement skills;

  - strong engagement and communications capabilities – to build the credibility and status of the WWC and develop and trial and test a dissemination strategy (in partnership with the Research Partner);

  - a set of governance or user panels to provide accountability and challenge – including both academic robustness and user-representation to ensure that the end-products are user-friendly and accessible;

  - innovative thinking, including potentially from outside of children’s social care, to inform methods of influence and communication; and

  - an operational core, such as administrative support, HR, IT, legal, and other capabilities.

- Provision of mentoring, guidance, sharing of experience, expertise and networks to develop and test the WWC’s frontline activities. This should include:

  - establishing and positioning the WWC with a strong status, brand and credibility in the sector as a central authority for evidence-based practice across a range of audiences and stakeholders, including social workers, practice leaders, Directors of Children’s Services, other local authority decision-makers and practitioners, policy-makers etc.;

  - developing a strong ongoing stakeholder engagement strategy across a wide range of audiences;

  - supporting the Research Partner (with input from the Department) to identify a strong research programme for the WWC that is driven by the needs of frontline practitioners and influences organisational practice;

  - testing and trialling, alongside the Research Partner, a suitable dissemination strategy, amongst a range of audiences and stakeholders – including creating accessible tools and resources suitable for practitioners operating in a resource and time-pressured environment;

  - supporting the development of a coherent learning infrastructure across children’s social care – this should include the building of relationships with the Children’s Social Care Innovation Programme, the Child Safeguarding Practice Review Panel and the wider social policy research work (other What Works Centre Network, research centres operating in related areas, and international research partners);

  - driving a wider culture of learning and evidence-based practice in the children’s social care sector by engaging practitioners in a constructive dialogue and encouraging them to promote the importance of learning;

  - developing a long-term, financially sustainable business model which aims to source funding from a range of non-government sources; and

  - developing and implementing a methodology for robust impact measurement of the WWC’s activities.

Research Partner

The Research Partner will develop the strategic research programme for the WWC (in partnership with the incubator) and start the initial review of the literature, developing evidence base and dissemination strategy. This will include:

- establishing, with input from the Incubator and Department, a strong strategic research programme for the WWC that is driven by the needs of practitioners and influences organisational practice;

- developing a robust methodology for reviewing evidence, e.g. a set of evidence standards and outcome measures;

- conducting evidence synthesis by analysing and bringing together the existing research and evidence, e.g. producing reviews, scrutinising and collating existing data sets;

- identifying evidence gaps and running and/or commissioning evaluations and trials to strengthen the evidence base (this might include  c. 4-6 new evaluations or trials in the contract period);

- testing and trialing, alongside the Research Partner, a suitable dissemination strategy, amongst a range of audiences and stakeholders – including creating accessible tools and resources suitable for practitioners operating in a resource and time-pressured environment;

- supporting the development of a coherent learning infrastructure across children’s social care – this should include the building of relationships with the Children’s Social Care Innovation Programme, the Child Safeguarding Practice Review Panel and the wider social policy research work (other What Works Centre Network, research centres operating in related areas, and international research partners);

- driving a wider culture of learning and evidence-based practice in the children’s social care sector by engaging practitioners in a constructive dialogue and encouraging them to promote the importance of learning; and

- developing and implementing a methodology for robust impact measurement of the WWC’s activities.

Please note that both procurement exercises are subject to the views of new Ministers, following the General Election on 8 June.

Expectation of outputs/outcomes up to March 2020:

| By March 2018 | Incubator Establish initial WWC model internally Establish core mission and values and strategic direction for WWC Initial development of dissemination tools Research Partner Establish initial research priorities Establish standards of evidence Initiate evidence syntheses (estimated 4-8 across 3 year period) Initiate new trials and evaluations (estimated 4-8 across 3 year period) Develop online ‘toolkit’ identifying effective interventions/programmes |
| --- | --- |
| By March 2019 | Incubator Continue testing and start rolling out dissemination tools Run engagement activities with the sector Research Partner Continue running of new trials and evaluations Establish initial outcome measures Establish proposals for flagship research programmes Continue development of online ‘toolkit’ identifying effective interventions/programmes |
| By March 2020 | Incubator Results from testing initial WWC model Results from initial testing of dissemination tools Recommendations for WWC model for future Evaluate engagement activities undertaken Research Partner Complete trials, evaluations and reports Present recommendations for future WWC research priorities |

The Department would welcome ideas and suggestions from bidders on additional or alternative outputs and activities that can help us to realise the full value of the programme.

Budget

The overall budget for the WWC contracts is up to £9.81m including VAT, including:

- Incubator - £4.96m (of which part is for set-up/trialing/mentoring and part is for frontline delivery functions eg. dissemination)

- Research Partner - £4.85m

The breakdown of figures is as follows:

|  | 2017-18 | 2018-19 | 2019-20 | Total |
| --- | --- | --- | --- | --- |
| Incubator total of which: | £1,340,000 | £1,940,000 | £1,680,000 | £4,960,000 |
| WWC set-up, trial and testing and mentoring | £440,000 | £190,000 | £130,000 | £760,000 |
| WWC frontline activities eg. dissemination | £900,000 | £1,750,000 | £1,550,000 | £4,200,000 |
| Research Partner total | £900,000 | £1,800,000 | £2,150,000 | £4,850,000 |
| Total | £2,240,000 | £3,740,000 | £3,830,000 | £9,810,000 |

These figures all include VAT, where applicable.

Indicative Timescales

| 21st April 2017 | Bids open for incubator and research contracts |
| --- | --- |
| 5th June 2017 | Bids close for incubator and research contracts |
| June | Evaluate incubator bids |
| Late June | Expected incubator interview dates |
| Mid-July | Incubator to start work |
| August | Assessment of bids for research contract |
| Mid-September | Research partner to start work |

Document 2 – Specification continued

3	Security of Data

Ask the tenderer to submit a security plan that explains how they will ensure that departmental or personal data will be protected.

4	Contract Price

4.1	Please give a detailed breakdown of costs (including VAT).  You must calculate the full costs of providing the service, works or goods for which you are Tendering, including both the direct and non-direct costs. Please also include the split between set-up/trialling/mentoring costs and frontline delivery costs.

Funding has been committed and will be made available by Department for Education.  The total contract value will be in the region of £4.96m for the Incubator and £4.85m for the Research Partner, inclusive of all costs.

The Contract Price element of the award criteria will be evaluated in respect of the contract using the following methodology:

- The lowest price (excluding ‘Abnormally Low Bids’) will attract full marks i.e. the Tenderer that submits the lowest price will be awarded 100% of the available marks for price.

- All other Tender submissions will be awarded a mark on price calculated relative to the lowest (acceptable) price received.  To provide some worked examples, three bids are received:  Bid 1 totals £100,000; Bid 2 totals £108,000 and Bid 3 totals £125,000.  In this worked example only, price equates to 40 marks.

  - Bid 1 in being the lowest (acceptable) price shall receive 100% of the marks available for price i.e. 40 marks

  - Bid 2 shall receive 92% of the marks available for price i.e. 36.8 marks

  - Bid 3 shall receive 75% of the marks available for price i.e. 30 marks

- Any submission that is equal to or greater than twice the lowest (acceptable) price will attracted a score of zero points on price

4.2	Payments will be made by BACS transfer following receipt of a valid invoice.

4.3	The successful tenderer should provide details of discounts for prompt payment.

5	VAT

5.1	Please state clearly when submitting prices whether or not VAT will be charged.

5.2	Where the contract price agreed between the Department and contractor is inclusive of any VAT, further amounts will not be paid by the Department should a vatable supply claim be made at any later stage.

5.3	Where the overall contract price is exclusive of VAT, the Department will pay any VAT incurred at the prevailing rate (currently 20%).  If the VAT rate changes the Department will pay any VAT incurred at the new rate.

5.4	It is the responsibility of tenderers to check the VAT position with HMRC before submitting a bid.

6	Child Sex Abuse

6.1	The Internet Watch Foundation (IWF) was established in 1996 by the UK internet industry to provide the UK internet Hotline for public and IT professionals to report potentially illegal online content and to be the 'notice and take-down' body for this content. IWF works in partnership with the online industry, law enforcement, Government, the education sector, charities, international partners and the public to minimise the availability of this content, specifically, child sexual abuse content hosted anywhere in the world.

6.2	Access to the IWF URL list is available to ISPs, mobile operators, search providers and filtering companies only. All organisations that require access must sign a licence which sets out how the data can be used.

6.3	It is a contract conditions that the successful supplier must block access to those Uniform Resource Locators (URLs) specified on the IWF’s list.

7. 	Evaluation Criteria

7.1	Detailed below is the Departments evaluation criteria and scoring matrix.  There are 4 questions that you are required to respond to as part of your tender submission.  Your responses to the Departments specification should set out how you will meet all of the requirements set out in the Specification.  Your Method Statements are the formal offer to the DfE and will form part of the contract between us.

  - The purpose of the Questions and your Responses is to allow us to evaluate your understanding of our requirements and the quality of your proposals for meeting them.  To help us evaluate responses, we ask that you present the information as requested in the Specification.

  - Group of potential suppliers - If the potential supplier is bidding on behalf of a group, for example, a consortium, or intends to use sub-contractors, then the consortium lead should complete all of the questions on behalf of the consortium and/or any sub-contractors. The consortium lead should make it clear who the lead member of the group is, and who will be contractually responsible for delivery of the contract.

All members of the group are required to provide the information required in the procurement documents, as part of a single composite response (unless the question specifically directs otherwise). You may require members of the group to assume a specific legal form if awarded the contract, if considered necessary for the satisfactory performance of the contract. Where the group is proposing to create a separate legal entity, such as a Special Purpose Vehicle (SPV) or consortium, they should provide details of the actual or proposed percentage shareholding of the constituent members within the new legal entity. They should also provide the name for the new entity and details of its legal and operational structure. An SPV is a legal entity that is formed to perform a specific contract.

Technical & Professional ability – Past Performance

Consortia bids should provide relevant examples of where the consortium has delivered similar requirements. If this is not possible (e.g. the consortium is newly formed or a Special Purpose Vehicle is to be created for this contract) then three separate examples should be provided between the principal member(s) of the proposed consortium or Special Purpose Vehicle (three examples are not required from each member).

8. Quality-based Questions

| IMPORTANT INFORMATION: The Authority may seek independent advice to validate information declared, or to assist in the evaluation. |  |  | Section Weighting: 90% |
| --- | --- | --- | --- |
| Evaluation Section : Technical |  |  |  |
| IMPORTANT INFORMATION: Please provide an answer for each question explicitly. References to answers in other questions/sections may not be considered, and could result in a lower score being applied. Evaluators cannot take into account previous knowledge of your delivery unless it is included in the bid, therefore please be explicit about outcomes you have delivered and provide clear evidence and examples of your skills and experience. Please only provide the information requested and where directed to do so. Any additional documentation will not be evaluated. Minimum Standard - Please note that the Authority may at its absolute discretion refuse to consider your bid further if the score achieved in any one of the Technical Requirements sections is less than 60% in total across all of the Technical Requirements sections following evaluation. |  |  |  |
| Ref | Questions – Delivery | Look Fors | Question Weighting |
| 1 | Ability to develop and test an innovative and flexible model for the WWC for children’s social care – bringing together the right sets of capabilities to improve outcomes and capacity and drive evidence-based practice in the sector. Max word count: 700 | - Experience of establishing and/or providing mentoring or support to develop innovate and flexible delivery models, including strong leadership, governance systems and stakeholder engagement/communications capabilities; - An outline of how the bidder would establish and test an effective WWC model, including potential sources for required skills and capabilities and particularly, strong leadership and innovative and creative thinking. | 40% |
| 2 | Ability to support the WWC to develop a strong strategic brand, status and work programme, including innovative practices, that responds to the needs of frontline practitioners and provides the WWC with credibility. Max word count: 700 | - Experience of establishing strategic direction and a programme of work that responds to the needs of stakeholders; - An outline of how the bidder would support the WWC to develop strong strategic direction and leadership, including: drawing on the needs of stakeholders and actively engaging them in a wider conversation about sector learning; working closely with the Research Partner; identifying work programme priorities in the set-up phase; and alignment with the DfE’s wider social work reform priorities. The bidder should set out how they would drive improvement in learning across the sector with real organisational-level impact. | 25% |
| 3 | Ability to support the WWC to disseminate research and evidence and support practitioners to implement evidence-based practice in a complex, resource-constrained and high-risk environment. Max word count: 700 | - Experience of disseminating complex messages to a diverse range of stakeholders with demonstrable impact; - An outline of how the bidder would support the WWC to inspire a culture of learning and development, including: disseminating evidence and research via innovative and creative channels and resources, supporting practitioners to implement evidence-based practice at organisational level, and measuring the impact of this dissemination and engagement. | 20% |
| 4 | Ability to deliver efficiently, provide good value for money for the taxpayer and manage risks effectively Max word count: 500 | - A detailed breakdown of costs, including separately by financial year, and split between set-up and frontline delivery costs, and including VAT; - Evidence of how value for money will be delivered and effective governance arrangements; - A realistic approach to delivery and expenditure - Identification of the key risks and proposals to mitigate. | 15% |

| Evaluation sections and questions The method of scoring the evaluation sections will be a 5-point scale (0-4), evaluators will use this to assign a score to each evaluation question response which will then be multiplied by the respective question weighting to produce the final score for each evaluation question: |  |  |
| --- | --- | --- |
| Evaluation | Score | Interpretation |
| Excellent | 4 | An excellent comprehensive response that meets the requirements, with detailed supporting evidence and no weaknesses resulting in a high level of confidence. |
| Good | 3 | A good response that meets the requirements with good supporting evidence. Demonstrates good understanding. |
| Acceptable | 2 | Meets the requirements – the response generally meets the requirements, but lacks sufficient detail to warrant a higher mark. |
| Poor | 1 | A poor response with reservations. The response lacks convincing detail with risk that the proposal will not be successful in meeting all the requirements. |
| Unacceptable | 0 | Failed to provide confidence that the proposal will meet the requirements. An unacceptable response with serious reservations. |

DOCUMENT 3

LIST OF ATTACHMENTS

1	STANDARD CONTRACT OF CONDITIONS FOR PURCHASE

2	DEPARTMENTAL SECURITY REQUIREMENTS [see end of this document.]

DOCUMENT 4

Standard Selection Questionnaire

Dear Bidder There are a number of mandatory requirements in this invitation to tender which must be completed if your bid is to be considered compliant. Every question must be answered. Please note that the Authority may at its absolute discretion refuse to consider your bid further dependent on the answers given to these questions. Unless otherwise directed, please complete all questions below and include this within your tender submission.

Summary

| Section Number | Section Requirement | Scoring/Weighting |
| --- | --- | --- |
| 1 | Part 1: Supplier Information | Mandatory – Not scored |
| 2 | Part 2: Grounds for Mandatory Rejection | Mandatory – Pass/Fail |
| 3 | Part 2 : Grounds for Discretionary Rejection | Mandatory – Pass/Fail |
| 4 | Part 3: Economic and Financial Standing | Mandatory – Not scored |
| 5 | Part 3: Consortium/ Group Details |  |
| 6 | Part 3: Technical and Professional Ability | Mandatory – Not scored |
| 7 | Part 3: Modern Slavery Act 2015 |  |
| 8 | Part 3: Additional questions | Mandatory – Pass/Fail |
| 9 | Declaration | Mandatory – Pass/Fail |

Potential Supplier Information and Exclusion Grounds: Part 1 and Part 2.

The standard Selection Questionnaire is a self-declaration, made by you (the potential supplier), that you do not meet any of the grounds for exclusion. If there are grounds for exclusion, there is an opportunity to explain the background and any measures you have taken to rectify the situation (we call this self-cleaning).

A completed declaration of Part 1 and Part 2 provides a formal statement that the organisation making the declaration has not breached any of the exclusions grounds. Consequently we require all the organisations that you will rely on to meet the selection criteria to provide a completed Part 1 and Part 2. For example these could be parent companies, affiliates, associates, or essential sub-contractors, if they are relied upon to meet the selection criteria. This means that where you are joining in a group of organisations, including joint ventures and partnerships, each organisation in that group must complete one of these self-declarations. Sub-contractors that you rely on to meet the selection criteria must also complete a self-declaration (although sub-contractors that are not relied upon do not need to complete the self-declaration).

Supplier Selection Questions: Part 3

The procurement document will provide instructions on the selection questions you need to respond to and how to submit those responses. If you are bidding on behalf of a group (consortium) or you intend to use sub-contractors, you should complete all of the selection questions on behalf of the consortium and/or any sub-contractors.

If the relevant documentary evidence referred to in the Selection Questionnaire is not provided upon request and without delay we reserve the right to amend the contract award decision and award to the next compliant bidder.

Consequences of misrepresentation

If you seriously misrepresent any factual information in filling in the Selection Questionnaire, and so induce an authority to enter into a contract, there may be significant consequences.  You may be excluded from the procurement procedure, and from bidding for other contracts for three years. If a contract has been entered into you may be sued for damages and the contract may be rescinded. If fraud, or fraudulent intent, can be proved, you or your responsible officers may be prosecuted and convicted of the offence of fraud by false representation, and you must be excluded from further procurements for five years.

Notes for completion

- The “authority” means the Department for Education or anyone acting on behalf of the DFE, that is seeking to invite suitable candidates to participate in this procurement process.

- “ITT” means this Invitation to Tender.

- “You” / “Your” refers to the potential supplier completing this standard Selection Questionnaire i.e. the legal entity responsible for the information provided. The term “potential supplier” is intended to cover any economic operator as defined by the Public Contracts Regulations 2015 (referred to as the “regulations”) and could be a registered company; the lead contact for a group of economic operators; charitable organisation; Voluntary Community and Social Enterprise (VCSE); Special Purpose Vehicle; or other form of entity.

- Please ensure that all questions are completed in full, and in the format requested. If the question does not apply to you, please state ‘N/A’. Should you need to provide additional information in response to the questions, please submit a clearly identified annex.

- The authority recognises that arrangements set out in section 1.2 of the standard Selection Questionnaire, in relation to a group of economic operators (for example, a consortium) and/or use of sub-contractors, may be subject to change and will, therefore, not be finalised until a later date.  The lead contact should notify the authority immediately of any change in the proposed arrangements and ensure a completed Part 1 and Part 2 is submitted for any new organisation relied on to meet the selection criteria. The authority will make a revised assessment of the submission based on the updated information.

- For Part 1 and Part 2 every organisation that is being relied on to meet the selection must complete and submit the self-declaration.

- All sub-contractors are required to complete Part 1 and Part 2.

- For answers to Part 3 - If you are bidding on behalf of a group, for example, a consortium, or you intend to use sub-contractors, you should complete all of the questions on behalf of the consortium and/ or any sub-contractors, providing one composite response and declaration.

The authority confirms that it will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the regulations, or pursuant to an order of the court or demand made by any competent authority or body where the authority is under a legal or regulatory obligation to make such a disclosure.

Part 1: Potential Supplier information

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

| Section 1 | Potential supplier information |  |
| --- | --- | --- |
| Question number | Question | Response |
| 1.01 | Full name of the potential supplier submitting the information |  |
| 1.02 | Registered office address |  |
| 1.03 | Registered website address (if applicable) |  |
| 1.04 | Trading status - public limited company - limited company - limited liability partnership - other partnership - sole trader - third sector - other () | Multiple choice |
| 1.05 | If selected 'other' in response to 1.04, please specify your trading status: |  |
| 1.06 | Date of registration in country of origin |  |
| 1.07 | Company registration number |  |
| 1.08 | Charity registration number (if applicable) |  |
| 1.09 | Head office DUNS number (if applicable) |  |
| 1.10 | Registered VAT number |  |
| 1.11 | If applicable, is your organisation registered with the appropriate professional or trade register(s) in the member state where it is established? | Yes ☐ No ☐ N/A ☐ |
| 1.12 | If you responded yes to 1.11, please provide the relevant details, including the registration number(s). |  |
| 1.13 | Is it a legal requirement in the state where you are established for you to possess a particular authorisation, or be a member of a particular organisation in order to provide the services specified in this procurement? If you responded yes, please provide additional details of what is required and confirmation that you have complied with this. | Tick box and text |
| 1.14 | Trading name(s) that will be used if successful in this procurement |  |
| 1.15 | Relevant classifications Are you a Voluntary Community Social Enterprise (VCSE) | Tick box |
| 1.16 | Are you a Sheltered Workshop | Tick box |
| 1.17 | Are you a Public service mutual? | Tick box |
| 1.18 | Are you a Small, Medium or Micro Enterprise (SME)? | Yes ☐ No ☐ |
| 1.19 | Details of Persons of Significant Control (PSC), where appropriate: - Name; - Date of birth; - Nationality; - Country, state or part of the UK where the PSC usually lives; - Service address; - The date he or she became a PSC in relation to the company (for existing companies the 6 April 2016 should be used); - Which conditions for being a PSC are met; - Over 25% up to (and including) 50%, - More than 50% and less than 75%, - 75% or more. (Please enter N/A if not applicable) | Text |
| 1.20 | Details of ultimate parent company: - Full name of the ultimate parent company - Registered office address (if applicable) - Registration number (if applicable) - Head office DUNS number (if applicable) - Head office VAT number (if applicable) (Please enter N/A if not applicable) | text |

Please note: A criminal record check for relevant convictions may be undertaken for the preferred suppliers and the persons of significant in control of them.

Please provide the following information about your approach to this procurement:

| Section 1 | Bidding model |  |
| --- | --- | --- |
| Question number | Question | Response |
| 1.21 | Are you bidding as the lead contact for a group of economic operators? If yes, please provide details at questions 1.22, 1.23 and to 1.24, 1.25,1.26 to 1.33, Section 2 and 3 If no, and you are a supporting bidder please provide the name of your group at 1.22, for reference purposes and complete 1.26 to 1.33, Section 2 and 3 | Yes ☐ No ☐ |
| 1.22 | Name of group of economic operators (if applicable) |  |
| 1.23 | Proposed legal structure if the group of economic operators intends to form a named single legal entity prior to signing a contract, if awarded. If you do not propose to form a single legal entity, please explain the legal structure. |  |
| 1.24 | Are you or, if applicable, the group of economic operators proposing to use sub-contractors? | Yes ☐ No ☐ |
| 1.25 | Bidding Model - If you responded yes to 1.24 please provide a completed attachment detailing the following information for each sub-contractor Name - Registered address - Trading status - Company registration number - Head office DUNS number (if applicable) - Registered VAT number - Type of organisation - SME (yes/no) - The role each subcontractor will take in providing the works and / or supplies eg key deliverables - The approximate % of contractual obligations assigned to each sub contractor |  |

Contact details and declaration

I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

I declare that, upon request and without delay I will provide the certificates or documentary evidence referred to in this document.

I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

I understand that the authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

I am aware of the consequences of serious misrepresentation.

| Section 1 | Contact details and declaration |  |
| --- | --- | --- |
| Question number | Question | Response |
| 1.26 | Contact name |  |
| 1.27 | Name of organisation |  |
| 1.28 | Role in organisation |  |
| 1.29 | Phone number |  |
| 1.30 | E-mail address |  |
| 1.31 | Postal address |  |
| 1.32 | Signature (electronic is acceptable) |  |
| 1.33 | Date |  |

Part 2: Exclusion Grounds

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

| Section 2 | Grounds for mandatory exclusion |  |
| --- | --- | --- |
| Question number | Question | Response |
|  | Regulations 57(1) and (2) The detailed grounds for mandatory exclusion of an organisation are set out on this web page, which should be referred to before completing these questions. Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below and listed on the webpage. |  |
| 2.01 | Participation in a criminal organisation. | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.02 | Corruption. | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.03 | Fraud. | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.04 | Terrorist offences or offences linked to terrorist activities | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.05 | Money laundering or terrorist financing | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.06 | Child labour and other forms of trafficking in human beings | Yes ☐ No ☐ If Yes please provide details at 2.07 |
| 2.07 | If you have answered yes to questions 2.01- 2.06, please provide further details. Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction, Identity of who has been convicted If the relevant documentation is available electronically please provide the web address, issuing authority, precise reference of the documents. | TEXT |
| 2.08 | If you have answered Yes to any of the points above have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion ? (Self Cleaning) | Yes ☐ No ☐ |
| 2.09 | Regulation 57(3) Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | Yes ☐ No ☐ |
| 2.10 | If you have answered yes to question 2.09 please provide further details. Please also confirm you have paid, or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

Please Note: The authority reserves the right to use its discretion to exclude a potential supplier where it can demonstrate by any appropriate means that the potential supplier is in breach of its obligations relating to the non-payment of taxes or social security contributions.

| Section 3 | Grounds for discretionary exclusion |  |
| --- | --- | --- |
|  | Question | Response |
|  | Regulation 57 (8) The detailed grounds for discretionary exclusion of an organisation are set out on this web page, which should be referred to before completing these questions. Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation. |  |
| 3.01 | Breach of environmental obligations? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.02 | Breach of social obligations? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.03 | Breach of labour law obligations? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.04 | Bankrupt or is the subject of insolvency or winding-up proceedings, where the organisation’s assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.05 | Guilty of grave professional misconduct? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.06 | Entered into agreements with other economic operators aimed at distorting competition? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.07 | Aware of any conflict of interest within the meaning of regulation 24 due to the participation in the procurement procedure? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.08 | Been involved in the preparation of the procurement procedure? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.09 | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.10 | The organisation is guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria. | Yes ☐ No ☐ If yes please provide details at 3.14 |
| 3.11 | The organisation has withheld such information. | Yes ☐ No ☐ If yes please provide details at 3.15 |
| 3.12 | The organisation is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015. | Yes ☐ No ☐ If Yes please provide details at 3.14 |
| 3.13 | The organisation has influenced the decision-making process of the contracting authority to obtain confidential information that may confer upon the organisation undue advantages in the procurement procedure, or to negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award. | Yes ☐ No ☐ If Yes please provide details at 3.14 |
| 3.14 | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self Cleaning) | TEXT |

Part 3: Selection Questions

| Section 4 | Economic and Financial Standing |  |  |
| --- | --- | --- | --- |
|  | Question | Response |  |
| 4.01 | Are you able to provide a copy of your audited accounts for the last two years, if requested? | Yes ☐ No ☐ |  |
| 4.02 | If responded ‘No’ to 4.01 Can you provide: A statement of the turnover, Profit and Loss Account/Income Statement, Balance Sheet/Statement of Financial Position and Statement of Cash Flow for the most recent year of trading for this organisation. | Yes ☐ No ☐ |  |
| 4.03 | If responded ‘No’ to 4.01 and 4.02 Can you provide: A statement of the cash flow forecast for the current year and a bank letter outlining the current cash and credit position. |  | Yes ☐ No ☐ |
| 4.04 | If responded ‘No’ to 4.01, 4.02 and 4.03 Can you provide: Alternative means of demonstrating financial status if any of the above are not available (e.g. forecast of turnover for the current year and a statement of funding provided by the owners and/or the bank, charity accruals accounts or an alternative means of demonstrating financial status). |  | Yes ☐ No ☐ |
| 4.05 | Where we have specified a minimum level of economic and financial standing and/ or a minimum financial threshold within the evaluation criteria for this procurement, please self-certify by answering ‘Yes’ or ‘No’ that you meet the requirements set out. |  | Yes ☐ No ☐ |

| Section 5 |  | If you have indicated in the Selection Questionnaire that you are part of a wider group, please provide further details |  |
| --- | --- | --- | --- |
| 5.01 | Name of organisation |  |  |
| 5.02 | Relationship to the Supplier completing these questions |  |  |

| 5.03 | Are you able to provide parent company accounts if requested to at a later stage? | Yes ☐ No ☐ |
| --- | --- | --- |
| 5.04 | If yes, would the parent company be willing to provide a guarantee if necessary? | Yes ☐ No ☐ |
| 5.05 | If no, would you be able to obtain a guarantee elsewhere (e.g. from a bank)? | Yes ☐ No ☐ |

| Section 6 | Technical and Professional Ability |
| --- | --- |
| 6.01 | Relevant experience and contract examples Please provide details of up to three contracts, in any combination from either the public or private sector; voluntary, charity or social enterprise (VCSE) that are relevant to our requirement. VCSEs may include samples of grant-funded work. Contracts for supplies or services should have been performed during the past three years. Works contracts may be from the past five years. The named contact provided should be able to provide written evidence to confirm the accuracy of the information provided below. Consortia bids should provide relevant examples of where the consortium has delivered similar requirements. If this is not possible (e.g. the consortium is newly formed or a Special Purpose Vehicle is to be created for this contract) then three separate examples should be provided between the principal member(s) of the proposed consortium or Special Purpose Vehicle (three examples are not required from each member). Where the Supplier is a Special Purpose Vehicle, or a managing agent not intending to be the main provider of the supplies or services, the information requested should be provided in respect of the main intended provider(s) or sub-contractor(s) who will deliver the contract. If you cannot provide examples see question 6.05 |

|  | 6.01 Contract 1 | 6.02 Contract 2 | 6.03 Contract 3 |
| --- | --- | --- | --- |
| Name of customer organisation |  |  |  |
| Point of contact in the organisation |  |  |  |
| Position in the organisation |  |  |  |
| E-mail address |  |  |  |
| Description of contract |  |  |  |
| Contract Start date |  |  |  |
| Contract completion date |  |  |  |
| Estimated contract value |  |  |  |

| 6.04 | Where you intend to sub-contract a proportion of the contract, please demonstrate how you have previously maintained healthy supply chains with your sub-contractor(s) Evidence should include, but is not limited to, details of your supply chain management tracking systems to ensure performance of the contract and including prompt payment or membership of the UK Prompt Payment Code (or equivalent schemes in other countries) |
| --- | --- |

| 6.05 | If you cannot provide at least one example for questions 6.01, in no more than 500 words please provide an explanation for this e.g. your organisation is a new start-up or you have provided services in the past but not under a contract. |
| --- | --- |

| Section 7 | Modern Slavery Act 2015: Requirements under Modern Slavery Act 2015 |  |
| --- | --- | --- |
| 7.01 | Are you a relevant commercial organisation as defined by section 54 ("Transparency in supply chains etc.") of the Modern Slavery Act 2015 ("the Act")? | Yes ☐ N/A ☐ |
| 7.02 | If you have answered yes to question 7.01 are you compliant with the annual reporting requirements contained within Section 54 of the Act 2015? | Yes ☐ No ☐ |
| 7.03 | If Yes, Please provide the relevant url to view the statement | Text |
| 7.04 | If No, please provide an explanation | Text |

8. Additional Questions

Suppliers who self-certify that they meet the requirements to these additional questions will be required to provide evidence of this if they are successful at contract award stage.

| Section 8 | Additional Questions |  |
| --- | --- | --- |
|  | Insurance |  |
| 8.01 | Please self-certify whether you already have, or can commit to obtain, prior to the commencement of the contract, the levels of insurance cover indicated below: Employer’s (Compulsory) Liability Insurance = £x Public Liability Insurance = £x Professional Indemnity Insurance = £x Product Liability Insurance = £x | I Certify / I do not Certify *It is a legal requirement that all companies hold Employer’s (Compulsory) Liability Insurance of £5 million as a minimum. Please note this requirement is not applicable to Sole Traders. |

|  | Skills and Apprentices – (please refer to supplier selection guidance) |  |
| --- | --- | --- |
| 8.02 | Public procurement of contracts with a full life value of £10 million and above and duration of 12 months and above should be used to support skills development and delivery of the apprenticeship commitment. This policy is set out in detail in Procurement Policy Note 14/15. Please confirm if you will be supporting apprenticeships and skills development through this contract. | Yes ☐ No ☐ |
| 8.03 | If yes, can you provide at a later stage documentary evidence to support your commitment to developing and investing in skills, development and apprenticeships to build a more skilled and productive workforce and reducing the risks of supply constraints and increasing labour cost inflation? | Yes ☐ No ☐ |
| 8.04 | Do you have a process in place to ensure that your supply chain supports skills, development and apprenticeships in line with PPN 14/15 (see guidance) and can provide evidence if requested? | Yes ☐ No ☐ |

|  |  | Suppliers’ Past Performance - (please refer to supplier selection guidance - this question should only be included by central government contracting authorities) |  |  |
| --- | --- | --- | --- | --- |
| 8.05 |  | Can you supply a list of your relevant principal contracts for goods and/or services provided in the last three years? |  | Yes ☐ No ☐ |
| 8.06 |  | On request can you provide a certificate from those customers on the list? |  | Yes ☐ No ☐ |
| 8.07 |  | If you cannot obtain a certificate from a customer can you explain the reasons why? |  | Yes ☐ No ☐ |
| 8.08 |  | If the certificate states that goods and/or services supplied were not satisfactory are you able to supply information which shows why this will not recur in this contract if you are awarded it? |  | Yes ☐ No ☐ |
| 8.09 |  | Can you supply the information in questions a. to d. above for any sub-contractors [or consortium members] who you are relying upon to perform this contract? |  | Yes ☐ No ☐ |
| 8.10 |  | Can you certify that your organisation meet the Cyber Essential Scheme as required by DfE? On request? |  | Yes ☐ No ☐ |
|  | Steel – (please refer to supplier selection guidance) |  |  |  |
| 8.11 | Please describe the supply chain management systems, policies, standards and procedures you currently have in place to ensure robust supply chain management |  | Text box |  |
| 8.12 | Please provide details of previous similar projects where you have demonstrated a high level of competency and effectiveness in managing of all supply chain members involved in steel supply or production so that there was a sustainable and safe supply of steel. |  | Text box |  |
| 8.13 | Please provide all the relevant details of previous breaches of health and safety legislation in the last 5 years, applicable to the country in which you operate, on comparable projects, for both: (i) Your company (ii) All your supply chain members involved in the production or supply of steel. |  | Attachment |  |

| Section 9 | Declaration |  |
| --- | --- | --- |
| 9.01 | Please complete the following Declaration statement DECLARATIONS 1. ........................................……………………………. (Name of tenderer) declares that we accept the Department’s standard terms and conditions as the basis of the contract; and 2. agree that the Department may disclose the Contractor's information/documentation (submitted to the Department during this Procurement) more widely within Government for the purpose of ensuring effective cross-Government procurement processes, including value for money and related purposes. 3. declare that we have not communicated to any other party the amount or approximate amount of the tender price other than in confidence and for the express purpose of obtaining insurances or a bond in connection with this tender. The tender price has not been fixed nor adjusted in collusion with any third party, and 4. declare that the tender will remain valid until 11 August 2017 and that we are not entitled to claim from the Department any costs or expenses incurred in preparing the tender or subsequent negotiations whether or not the tender is successful. signed on behalf of the Tenderer .................................................................................. |  |

Attachment 1

Terms and Conditions

CONTRACT FOR...***Insert the Contract Title Here***

THIS CONTRACT IS DATED ..***Insert Date, in manuscript, the Department Signed the Contract Here***

Parties

1)	The Secretary of State for Education whose Head Office is at Sanctuary Buildings, Great Smith Street, London, SW1P 3BT acting as part of the Crown (“the Department”); and

***Choose the appropriate paragraph 2 from those below, then delete the others.***

2)	***enter company name and registered number*** whose registered office is at ***enter the full address*** (“the Contractor”)

2)	***enter full local authority name*** of ***enter the full address*** (“the Contractor”).

2)	***enter the name of the university or further education college*** of ***enter the full address*** (“the Contractor”).

2)	***enter individual's name*** (a partner in the partnership of ***enter the name of the partnership*** of ***enter the full address*** (“the Contractor”)

2)	***enter individual's name***  (trading as ***enter the trading name***) of ***enter the full address*** (“the Contractor”)

Recitals

The Contractor has agreed to ***briefly state the nature of the services*** on the terms and conditions set out in this Contract.

The Department's reference number for this Contract is ***enter a unique reference no.***.

1	Interpretation

1.1	In this Contract the following words shall mean:-

| “the Services”" | the services to be performed by the Contractor as described in Schedule 1; |
| --- | --- |
| "Affiliate" | in relation to a body corporate, any other entity which directly or indirectly Controls, is Controlled by, or is under direct or indirect common Control with, that body corporate from time to time; |
| “Central Government Body” “the Contract Manager” | means a body listed in one of the following sub-categories of the Central Government classification of the Public Sector Classification Guide, as published and amended from time to time by the Office for National Statistics: (a) Government Department; (b) Non-Departmental Public Body or Assembly Sponsored Public Body (advisory, executive, or tribunal); (c) Non-Ministerial Department; or (d) Executive Agency; ***name and full address of the Department's Contract manager*** |
| "Contractor Personnel" | all employees, agents, Contractors and contractors of the Contractor and/or of any Sub-contractor; |
| “the Contractors Contract Manager | *** name of the Contractors Contract Manager*** |
| “Confidential Information” | the Department's Confidential Information and/or the Contractor's Confidential Information; |
| "Contracting Department" | any contracting Department as defined in Regulation 5(2) of the Public Contracts (Works, Services and Supply) (Amendment) Regulations 2000 other than the Department; |
| "Contractor Personnel" | all employees, agents, consultants and contractors of the Contractor and/or of any Sub-contractor; |
| "Control" | means that a person possesses, directly or indirectly, the power to direct or cause the direction of the management and policies of the other person (whether through the ownership of voting shares, by contract or otherwise) and "Controls" and "Controlled" shall be interpreted accordingly; |
| “Crown” | means Queen Elizabeth II and any successor |
| "Crown Body" | any department, office or agency of the Crown; |
| "Department’s Confidential Information" | all Personal Data and any information, however it is conveyed, that relates to the business, affairs, developments, trade secrets, know-how, personnel, and suppliers of the Department, including all IPRs, together with all information derived from any of the above, and any other information clearly designated as being confidential (whether or not it is marked "confidential") or which ought reasonably be considered to be confidential; |
| "Environmental Information Regulations" | the Environmental Information Regulations 2004 together with any guidance and/or codes of practice issues by the Information Commissioner or relevant Government Department in relation to such regulations; |
| "FOIA" | the Freedom of Information Act 2000 and any subordinate legislation made under this Act from time to time together with any guidance and/or codes of practice issued by the Information Commissioner or relevant Government Department in relation to such legislation; |
| “Her Majesty's Government” | means the duly elected Government for the time being during the reign of Her Majesty and/or any department, committee, office, servant or officer of such Government |
| "Information" | has the meaning given under section 84 of the Freedom of Information Act 2000; |
| "Personal Data" | shall have the same meaning as set out in the Data Protection Act 1998; |
| “Property” | means the property, other than real property, issued or made available to the Contractor by the Client in connection with the Contract. |
| “Regulatory Bodies” | those government departments and regulatory, statutory and other entities, committees and bodies which, whether under statute, rules, regulations, codes of practice or otherwise, are entitled to regulate, investigate, or influence the matters dealt with in this Contract or any other affairs of the Department and "Regulatory Body" shall be construed accordingly. |
| "Request for Information" | a request for information or an apparent request under the Code of Practice on Access to Government Information, FOIA or the Environmental Information Regulations; |
| "SME" | means a micro, small or medium-sized enterprise defined in accordance with the European Commission Recommendation 2003/361/EC and any subsequent revisions. |
| "Sub-contractor" | the third party with whom the Contractor enters into a Sub-contract or its servants or agents and any third party with whom that third party enters into a Sub-contract or its servants or agents; |
| "Working Day" | any day other than a Saturday, Sunday or public holiday in England and Wales. |

1.2 	References to “Contract” mean this contract (and include the Schedules).  References to “Clauses” and “Schedules” mean clauses of and schedules to this Contract.  The provisions of the Schedules shall be binding on the parties as if set out in full in this Contract.

1.3	Reference to the singular include the plural and vice versa and references to any gender include both genders.  References to a person include any individual, firm, unincorporated association or body corporate.

2	Commencement and Continuation

The Contractor shall commence the Services on ***enter start date*** and, subject to Clause 10.1 shall complete the Services on or before ***enter end date***

***Add the following line if the contract will be signed  late after the start date of the contract***

This Contract shall be deemed to have been effective from ***enter same start date as above***.

3	Contractor's Obligations

3.1	The Contractor shall promptly and efficiently complete the Services in accordance with the provisions set out in Schedule 1,***Include the following lines if you will have a schedule 3.*** and the special conditions set out in Schedule 3.  Where there is any conflict between the terms of this Contract and the special conditions set out in Schedule 3, the special conditions shall prevail.

3.2	The Contractor shall comply with the accounting and information provisions of Schedule 2.

3.3	The Contractor shall comply with all statutory provisions including all prior and subsequent enactments, amendments and substitutions relating to that provision and to any regulations made under it.

4	Departments Obligations

The Department will comply with the payment provisions of Schedule 2 provided that the Department has received full and accurate information and documentation as required by Schedule 2 to be submitted by the Contractor for work completed to the satisfaction of the Department.

5	Changes to the Department's Requirements

5.1	The Department shall notify the Contractor of any material change to the Department's requirement under this Contract.

5.2	The Contractor shall use its best endeavours to accommodate any changes to the needs and requirements of the Department provided that it shall be entitled to payment for any additional costs it incurs as a result of any such changes.  The amount of such additional costs to be agreed between the parties in writing.

6	Management

6.1	The Contractor shall promptly comply with all reasonable requests or directions of the Contract Manager in respect of the Services.

6.2	The Contractor shall address any enquiries about procedural or contractual matters in writing to the Contract Manager.  Any correspondence relating to this Contract shall quote the reference number set out in the Recitals to this Contract.

7	Contractor's Employees and Sub-Contractors

7.1	Where the Contractor enters into a contract with a supplier or contractor for the purpose of performing its obligations under the Contract (the “Sub-contractor”) it shall ensure prompt payment in accordance with this clause 7.1. Unless otherwise agreed by the Department in writing, the Contractor shall ensure that any contract requiring payment to a Sub-contractor shall provide for undisputed sums due to the Sub-contractor to be made within a specified period from the receipt of a valid invoice not exceeding:

7.1.1	10 days, where the Sub-contractor is an SME; or

7.1.2	30 days either, where the sub-contractor is not an SME, or both the Contractor and the Sub-contractor are SMEs,

The Contractor shall comply with such terms and shall provide, at the Department’s request, sufficient evidence to demonstrate compliance.

7.2	The Department shall be entitled to withhold payment due under clause 7.1 for so long as the Contractor, in the Department’s reasonable opinion, has failed to comply with its obligations to pay any Sub-contractors promptly in accordance with clause 7.1.  For the avoidance of doubt the Department shall not be liable to pay any interest or penalty in withholding such payment.  .

7.3	The Contractor shall take all reasonable steps to satisfy itself that its employees or sub-contractors (or their employees) are suitable in all respects to perform the Services.

7.4	The Contractor shall immediately notify the Department if they have any concerns regarding the propriety of any of its sub-contractors in respect of work/services rendered in connection with this Contract.

7.5	The Contractor, its employees and sub-contractors (or their employees), whilst on Departmental premises, shall comply with such rules, regulations and requirements (including those relating to security arrangements) as may be in force from time to time.

7.6 	The Contractor shall ensure the security of all the Property whilst in its possession, during the supply of the Services, in accordance with the Department’s reasonable security requirements as required from time to time.

8	Copyright

***include the following if Copyright will be an issue in this Contract otherwise delete.  Note that if this Contract involves copyright in IT based developments then the more formal copyright/intellectual property rights clause contained in the Library should be used.***

Copyright in all reports and other documents and materials arising out of the performance by the Contractor of their duties under this Contract are to be assigned to and shall vest in the Crown absolutely.  This condition shall apply during the continuance of this Contract and after its termination howsoever arising.

9	Warranty and Indemnity

9.1	The Contractor warrants to the Department that the obligations of the Contractor under this Contract will be performed by appropriately qualified and trained personnel with reasonable skill, care and diligence and to such high standards of quality as it is reasonable for the Department to expect in all the circumstances.  The Department will be relying upon the Contractor's skill, expertise and experience in the performance of the Services and also upon the accuracy of all representations or statements made and the advice given by the Contractor in connection with the performance of the Services and the accuracy of any documents conceived, originated, made or developed by the Contractor as part of this Contract.  The Contractor warrants that any goods supplied by the Contractor forming a part of the Services will be of satisfactory quality and fit for their purpose and will be free from defects in design, material and workmanship.

9.2	Without prejudice to any other remedy, if any part of the Services is not performed in accordance with this Contract then the Department shall be entitled, where appropriate to:

9.2.1	require the Contractor promptly to re-perform or replace the relevant part of the Services without additional charge to the Department; or

9.2.2	assess the cost of remedying the failure (“the assessed cost”) and to deduct from any sums due to the Contractor the Assessed Cost for the period that such failure continues.

9.3	The Contractor shall be liable for and shall indemnify the Department in full against any expense, liability, loss, claim or proceedings arising under statute or at common law in respect of personal injury to or death of any person whomsoever or loss of or damage to property whether belonging to the Department or otherwise arising out of or in the course of or caused by the provision of the Services.

9.4	The Contractor shall be liable for and shall indemnify the Department against any expense, liability, loss, claim or proceedings arising as a result of or in connection with any breach of the terms of this Contract or otherwise through the default of the Contractor

9.5	All property of the Contractor whilst on the Department's premises shall be there at the risk of the Contractor and the Department shall accept no liability for any loss or damage howsoever occurring to it.

9.6	The Contractor shall ensure that it has adequate insurance cover with an insurer of good repute to cover claims under this Contract or any other claims or demands which may be brought or made against it by any person suffering any injury damage or loss in connection with this Contract.  The Contractor shall upon request produce to the Department, its policy or policies of insurance, together with the receipt for the payment of the last premium in respect of each policy or produce documentary evidence that the policy or policies are properly maintained.

10	Termination

10.1	This Contract may be terminated by either party giving to the other party at least ***enter notice period e.g. 7days, 30 days. 3 months etc.*** notice in writing.

10.2	In the event of any breach of this Contract by either party, the other party may serve a notice on the party in breach requiring the breach to be remedied within a period specified in the notice which shall be reasonable in all the circumstances.  If the breach has not been remedied by the expiry of the specified period, the party not in breach may terminate this Contract with immediate effect by notice in writing.

10.3	In the event of a material breach of this Contract by either party, the other party may terminate this Contract with immediate effect by notice in writing.

10.4	This Contract may be terminated by the Department with immediate effect by notice in writing if at any time:-

***Use this set of termination clauses if the Contractor is a Company.***

10.4.1	the Contractor passes a resolution that it be wound-up or that an application be made for an administration order or the Contractor applies to enter into a voluntary arrangement with its creditors; or

10.4.2	a receiver, liquidator, administrator, supervisor or administrative receiver be appointed in respect of the Contractor's property, assets or any part thereof; or

10.4.3	the court orders that the Contractor be wound-up or a receiver of all or any part of the Contractor's assets be appointed; or

10.4.4	the Contractor is unable to pay its debts in accordance with Section 123 of the Insolvency Act 1986.

10.4.5	there is a change in the legal or beneficial ownership of 50% or more of the Contractor's share capital issued at the date of this Contract or there is a change in the control of the Contractor, unless the Contractor has previously notified the Department in writing.  For the purpose of this Sub-Clause 10.4.5 “control” means the power of a person to secure that the affairs of the Contractor are conducted in accordance with the wishes of that person by means of the holding of shares or the possession of voting power.

10.4.6		the Contractor is convicted (or being a company, any officers or representatives of the Contractor are convicted) of a criminal offence related to the business or professional conduct

10.4.7		the Contractor commits (or being a company, any officers or representatives of the Contractor commit) an act of grave misconduct in the course of the business;

10.4.8		the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to the payment of Social Security contributions;

10.4.9	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to payment of taxes;

10.4.10	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to disclose any serious misrepresentation in supplying information required by the Department in or pursuant to this Contract.

10.5	Nothing in this Clause 10 shall affect the coming into, or continuance in force of any provision of this Contract which is expressly or by implication intended to come into force or continue in force upon termination of this Contract.

***Use this set of termination clauses if the Contractor is an individual or a partnership.***

10.4.1 	in England and Wales, a petition is presented for the Contractor's bankruptcy or a criminal bankruptcy order is made against the Contractor or he or she makes any composition or arrangement with or for the benefit of creditors or makes any conveyance or assignment for the benefit of creditors; or

10.4.2	in Scotland, if the Contractor becomes apparently insolvent within the meaning of Section 7 of the Bankruptcy (Scotland) act 1985; or

10.4.3	where the Contractor is a firm or a number of persons acting together in any capacity (including as trustees), any event referred to in Sub-Clauses 10.4.1 or 10.4.2 occurs in respect of any partner in the firm or any of those persons (including any trustees);

10.4.4		the Contractor is convicted (or being a company, any officers or representatives of the Contractor are convicted) of a criminal offence related to the business or professional conduct;

10.4.5		the Contractor commits (or being a company, any officers or representatives of the Contractor commit) an act of grave misconduct in the course of the business;

10.4.6		the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to the payment of Social Security contributions;

10.4.7		the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to payment of taxes;

10.4.8		the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to disclose any serious misrepresentation in supplying information required by the Department in or pursuant to this Contract.

10.5	Nothing in this Clause 10 shall affect the coming into, or continuance in force of any provision of this Contract which is expressly or by implication intended to come into force or continue in force upon termination of this Contract.

11	Status of Contractor

11.1	In carrying out its obligations under this Contract the Contractor agrees that it will be acting as principal and not as the agent of the Department.

11.2	The Contractor shall not say or do anything that may lead any other person to believe that the Contractor is acting as the agent of the Department.

12	Confidentiality

12.1	Except to the extent set out in this clause or where disclosure is expressly permitted elsewhere in this Contract, each party shall:

12.1.1	treat the other party's Confidential Information as confidential and safeguard it accordingly; and

12.1.2	not disclose the other party's Confidential Information to any other person without the owner's prior written consent.

12.2	Clause 12 shall not apply to the extent that:

12.2.1	such disclosure is a requirement of Law placed upon the party making the disclosure, including any requirements for disclosure under the FOIA, Code of Practice on Access to Government Information or the Environmental Information Regulations pursuant to Clause 13 (Freedom of Information);

12.2.2	such information was in the possession of the party making the disclosure without obligation of confidentiality prior to its disclosure by the information owner;

12.2.3	such information was obtained from a third party without obligation of confidentiality;

12.2.4	such information was already in the public domain at the time of disclosure otherwise than by a breach of this Contract; or

12.2.5	it is independently developed without access to the other party's Confidential Information.

12.3	The Contractor may only disclose the Department's Confidential Information to the Contractor Personnel who are directly involved in the provision of the Project and who need to know the information, and shall ensure that such Contractor Personnel are aware of and shall comply with these obligations as to confidentiality.

12.4	The Contractor shall not, and shall procure that the Contractor Personnel do not, use any of the Department's Confidential Information received otherwise than for the purposes of this Contract.

[12.5	***Include one of these options and then delete this drafting note.***

The Contractor shall ensure that their employees, servants or such professional advisors or consultants sign a confidentiality undertaking before commencing work in connection with the Contract.

12.6	Nothing in this Contract shall prevent the Department from disclosing the Contractor's Confidential Information:

12.6.1	on a confidential basis to any Central Government Body for any proper purpose of the Department or of the relevant Central Government Body;

12.6.2	to Parliament and Parliamentary Committees or if required by any Parliamentary reporting requirement;

12.6.3	to the extent that the Department (acting reasonably) deems disclosure necessary or appropriate in the course of carrying out its public functions;

12.6.4	on a confidential basis to a professional adviser, consultant, supplier or other person engaged by any of the entities described in Clause 12.6.1 (including any benchmarking organisation) for any purpose relating to or connected with this Contract;

12.6.5	on a confidential basis for the purpose of the exercise of its rights under this Contract, including audit rights, step-in rights and exit management rights; or

12.6.6	on a confidential basis to a proposed successor body in connection with any assignment, novation or disposal of any of its rights, obligations or liabilities under this Contract.

12.7	The Department shall use all reasonable endeavours to ensure that any Central Government Body, Contracting Department, employee, third party or Sub-contractor to whom the Contractor's Confidential Information is disclosed pursuant to clause 12 is made aware of the Department's obligations of confidentiality.

12.8	Nothing in this clause 12 shall prevent either party from using any techniques, ideas or know-how gained during the performance of the Contract in the course of its normal business to the extent that this use does not result in a disclosure of the other party's Confidential Information or an infringement of Intellectual Property Rights.

12.9	The parties acknowledge that, except for any information which is exempt from disclosure in accordance with the provisions of the FOIA, the content of this Contract is not Confidential Information.  The Department shall be responsible for determining in its absolute discretion whether any of the content of the Contract is exempt from disclosure in accordance with the provisions of the FOIA.

12.10	Subject to Clause 12.9, the Contractor hereby gives its consent for the Department to publish the Contract in its entirety, including from time to time agreed changes to the Contract, to the general public.

12.11	The Department may consult with the Contractor to inform its decision regarding any redactions but the Department shall have the final decision in its absolute discretion.

12.12	The Contractor shall assist and cooperate with the Department to enable the Department to publish this Contract.

13	Freedom of Information

13.1	The Contractor acknowledges that the Department is subject to the requirements of the FOIA and the Environmental Information Regulations and shall assist and cooperate with the Department to enable the Department to comply with its information disclosure obligations.

13.2	The Contractor shall and shall procure that its Sub-contractors shall:

13.2.1	transfer to the Department all Requests for Information that it receives as soon as practicable and in any event within two Working Days of receiving a Request for Information;

13.2.2	provide the Department with a copy of all Information in its possession, or power in the form that the Department requires within five Working Days (or such other period as the Department may specify) of the Department's request; and

13.2.3	provide all necessary assistance as reasonably requested by the Department to enable the Department to respond to the Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations.

13.3	The Department shall be responsible for determining in its absolute discretion and notwithstanding any other provision in this Contract or any other agreement whether any Information is exempt from disclosure in accordance with the provisions of the FOIA or the Environmental Information Regulations.

13.4	In no event shall the Contractor respond directly to a Request for Information unless expressly authorised to do so by the Department.

13.5	The Contractor acknowledges that (notwithstanding the provisions of Clause 13) the Department may, acting in accordance with the Ministry of Justice’s Code of Practice on the Discharge of the Functions of Public Authorities under Part 1 of the Freedom of Information Act 2000 (“the Code”), be obliged under the FOIA, or the Environmental Information Regulations to disclose information concerning the Contractor or the Project:

13.5.1	in certain circumstances without consulting the Contractor; or

13.5.2	following consultation with the Contractor and having taken their views into account;

provided always that where 13.5.1 applies the Department shall, in accordance with any recommendations of the Code, take reasonable steps, where appropriate, to give the Contractor advanced notice, or failing that, to draw the disclosure to the Contractor’s attention after any such disclosure.

13.6	The Contractor shall ensure that all Information is retained for disclosure and shall permit the Department to inspect such records as requested from time to time.

14	Access and Information

The Contractor shall provide access at all reasonable times to the Department's internal auditors or other duly authorised staff or agents to inspect such documents as the Department considers necessary in connection with this Contract and where appropriate speak to the Contractors employees.

15	Transfer of Responsibility on Expiry or Termination

15.1	The Contractor shall, at no cost to the Department, promptly provide such assistance and comply with such timetable as the Department may reasonably require for the purpose of ensuring an orderly transfer of responsibility upon the expiry or other termination of this Contract.  The Department shall be entitled to require the provision of such assistance both prior to and, for a reasonable period of time after the expiry or other termination of this Contract.

15.2	Such assistance may include (without limitation) the delivery of documents and data in the possession or control of the Contractor which relate to this Contract, including the documents and data, if any, referred to in the Schedule.

15.3	The Contractor undertakes that it shall not knowingly do or omit to do anything which may adversely affect the ability of the Department to ensure an orderly transfer of responsibility.

16	Tax Indemnity

- 16.1	Where the Contractor is liable to be taxed in the UK in respect of consideration received under this contract, it shall at all times comply with the Income Tax (Earnings and Pensions) Act 2003 (ITEPA) and all other statutes and regulations relating to income tax in respect of that consideration.

- 16.2	Where the Contractor is liable to National Insurance Contributions (NICs) in respect of consideration received under this contract, it shall at all times comply with the Social Security Contributions and Benefits Act 1992 (SSCBA) and all other statutes and regulations relating to NICs in respect of that consideration.

- 16.3	The Department may, at any time during the term of this contract, ask the Contractor to provide information which demonstrates how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it.

- 16.4	A request under Clause 16.3 above may specify the information which the Contractor must provide and the period within which that information must be provided.

- 16.5	The Department may terminate this contract if-

- (a)	in the case of a request mentioned in Clause 16.3 above if the Contractor:

- (i)	fails to provide information in response to the request within a reasonable time, or

- (ii)	provides information which is inadequate to demonstrate either how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it;

- (b)	in the case of a request mentioned in Clause 16.4 above, the Contractor fails to provide the specified information within the specified period, or

- (c)	it receives information which demonstrates that, at any time when Clauses 16.1 and 16.2 apply, the Contractor is not complying with those Clauses.

- 16.6	The Department may supply any information which it receives under Clause 16.3 to the Commissioners of Her Majesty’s Revenue and Customs for the purpose of the collection and management of revenue for which they are responsible.

***Use this set of tax clauses if the Contractor is a Company.***

- 16.7	The Contractor warrants and represents to the Department that it is an independent contractor and, as such, bears sole responsibility for the payment of tax and national insurance contributions which may be found due from it in relation to any payments or arrangements made under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

- 16.8	The Contractor will account to the appropriate authorities for any income tax, national insurance, VAT and all other taxes, liabilities, charges and duties relating to any payments made to the Contractor under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

- 16.9	The Contractor shall indemnify Department against any liability, assessment or claim made by the HM Revenue and Customs or any other relevant authority arising out of the performance by the parties of their obligations under this Contract (other than in respect of employer's secondary national insurance contributions) and any costs, expenses, penalty fine or interest incurred or payable by Department in connection with any such assessment or claim.

- 16.10	The Contractor authorises the Department to provide the HM Revenue and Customs and all other departments or agencies of the Government with any information which they may request as to fees and/or expenses paid or due to be paid under this Contract whether or not Department is obliged as a matter of law to comply with such request.

***Use this set of tax clauses if the Contractor is an individual or a partnership.***

- 16.7	The  Contractor warrants and represents to the Department that he is an independent contractor and, as such, bears sole responsibility for the payment of tax and national insurance contributions which may be found due from it in relation to any payments or arrangements made under this Contract. The Contractor shall promptly and regularly pay all National Insurance Contributions due from it as a self-employed person and shall account to the HM Revenue and Customs for all taxes due from it in respect of the payments made to it under this Contract.

- 16.8	If, notwithstanding Clause Error: Reference source not found7, the HM Revenue and Customs and/or any other appropriate agency consider that the Contractor is an employee of the Department for the purposes of tax and/or national insurance contributions; then the Department shall be entitled to terminate this Contract immediately and deduct from the payments payable to the Contractor under the terms of this Contract, such sums as the HM Revenue and Customs and/or other agencies require in respect of income tax and employee national insurance contributions.  The deduction of such tax and national insurance contributions will not affect the status of the Contractor as self-employed for all other purposes.

- 16.9	Without prejudice to the provisions of Clause 16.8 above, the Contractor shall indemnify the Department against any liability, assessment or claim made by the HM Revenue and Customs or any other relevant authority arising out of the performance by the parties of their obligations under this Contract (other than in respect of employer's secondary national insurance contributions) and any costs, expenses, penalty fine or interest incurred or payable by the Department in connection with any such assessment or claim.

- 16.10	The Contractor authorises the Department to provide the HM Revenue and Customs and all other departments or agencies of the Government with any information which they may request as to fees and/or expenses paid or due to be paid under this Contract whether or not the Department is obliged as a matter of law to comply with such request.

- 16.11	The Contractor shall register for value added tax if and when required by law and shall promptly notify the Department for Work and Pensions of its liability for Class 2 and, where appropriate, Class 4 national insurance contributions.

17	Data Protection Act

17.1	With respect to the parties' rights and obligations under this Contract, the parties agree that the Department is the Data Controller and that the Contractor is the Data Processor.  For the purposes of this Clause 17, the terms “Data Controller”, “Data Processor”, “Data Subject”, “Personal Data”, “Process” and “Processing shall have the meaning prescribed under the DPA.

17.2	The Contractor shall:

17.2.1	Process the Personal Data only in accordance with instructions from the Department (which may be specific instructions or instructions of a general nature as set out in this Contract or as otherwise notified by the Department to the Contractor during the period of the Contract);

17.2.2	Process the Personal Data only to the extent, and in such manner, as is necessary for the provision of the Services or as is required by law or any Regulatory Body;

17.2.3	Implement appropriate technical and organisational measures to protect the Personal Data against unauthorised or unlawful processing and against accidental loss, destruction, damage, alteration or disclosure. These measures shall be appropriate to the harm which might result from any unauthorised or unlawful Processing, accidental loss, destruction or damage to the Personal Data and having regard to the nature of the Personal Data which is to be protected;

17.2.4	Take reasonable steps to ensure the reliability of any Contractor Personnel who have access to the Personal Data;

17.2.5	Obtain prior written consent from the Department in order to transfer the Personal Data to any Sub-contractors or Affiliates for the provision of the Services;

17.2.6	Ensure that all Contractor Personnel required to access the Personal Data are informed of the confidential nature of the Personal Data and comply with the obligations set out in this Clause17;

17.2.7	Ensure that none of Contractor Personnel publish, disclose or divulge any of the Personal Data to any third party unless directed in writing to do so by the Department;

17.2.8	Notify the Department within five Working Days if it receives:

17.2.8.1	a request from a Data Subject to have access to that person's Personal Data; or

17.2.8.2	a complaint or request relating to the Department's obligations under the Data Protection Legislation;

17.2.9	Provide the Department with full cooperation and assistance in relation to any complaint or request made, including by:

17.2.9.1	 providing the Department with full details of the complaint or request;

17.2.9.2	complying with a data access request within the relevant timescales set out in the Data Protection Legislation and in accordance with the Department's instructions;

17.2.9.3	providing the Department with any Personal Data it holds in relation to a Data Subject (within the timescales required by the Department); and

17.2.9.4	providing the Department with any information requested by the Department;

17.2.10 Permit the Department or the Department’s Representative (subject to reasonable and appropriate confidentiality undertakings), to inspect and audit the Contractor's data processing activities (and/or those of its agents, subsidiaries and Sub-contractors) and comply with all reasonable requests or directions by the Department to enable the Department to verify and/or procure that the Contractor is in full compliance with its obligations under this Contract;

17.2.11 Provide a written description of the technical and organisational methods employed by the Contractor for processing Personal Data (within the timescales required by the Department); and

17.2.12 Not Process or otherwise transfer any Personal Data outside the European

Economic Area. If, after the Commencement Date, the Contractor (or any

Sub-contractor) wishes to Process and/or transfer any Personal Data

outside the European Economic Area, the following provisions shall apply:

17.2.12.1	the Contractor shall submit a request for change to the Department which shall be dealt with in accordance with any  Change Control Procedure

17.2.12.2	the Contractor shall set out in its request for change details of the following:

(a) 	the Personal Data which will be Processed and/or transferred outside the European Economic Area;

(b)	the country or countries in which the Personal Data will be Processed and/or to which the Personal Data will be transferred outside the European Economic Area;

(c) 	any Sub-contractors or other third parties who will be Processing and/or transferring Personal Data outside the European Economic Area; and

(d)	how the Contractor will ensure an adequate level of protection and adequate safeguards (in accordance with the Data Protection Legislation and in particular so as to ensure the Department’s compliance with the Data Protection Legislation) in respect of the Personal Data that will be Processed and/or transferred outside the European Economic Area;

17.2.12.3	in providing and evaluating the request for change, the parties shall ensure that they have regard to and comply with then-current Department, Government and Information Commissioner Office policies, procedures, guidance and codes of practice on, and any approvals processes in connection with, the Processing and/or transfers of Personal Data outside the European Economic Area and/or overseas generally; and

17.2.12.4	the Contractor shall comply with such other instructions and shall carry out such other actions as the Department may notify in writing, including:

(a)	incorporating standard and/or model clauses (which are approved by the European Commission as offering adequate safeguards under the Data Protection Legislation) in this Contract or a separate data processing agreement between the parties; and

(b)	procuring that any Sub-contractor or other third party who will be Processing and/or transferring the Personal Data outside the European Economic Area enters into a direct data processing agreement with the Authority on such terms as may be required by the Department, which the Contractor acknowledges may include the incorporation of standard and/or model clauses (which are approved by the European Commission as offering adequate safeguards under the Data Protection Legislation).”

17.3	The Contractor shall comply at all times with the Data Protection Legislation and shall not perform its obligations under this Contract in such a way as to cause the Department to breach any of its applicable obligations under the Data Protection Legislation.

18	Amendment and variation

No amendment or variation to this Contract shall be effective unless it is in writing and signed by or on behalf of each of the parties hereto.  The Contractor shall comply with any formal procedures for amending or varying contracts which the Department may have in place from time to time.

19	Assignment and Sub-contracting

The benefit and burden of this Contract may not be assigned or sub-contracted in whole or in part by the Contractor without the prior written consent of the Department.  Such consent may be given subject to any conditions which the Department considers necessary.  The Department may withdraw its consent to any sub-contractor where it no longer has reasonable grounds to approve of the sub-contractor or the sub-contracting arrangement and where these grounds have been presented in writing to the Contractor.

20	The Contract (Rights of Third Parties) Act 1999

This Contract is not intended to create any benefit, claim or rights of any kind whatsoever enforceable by any person not a party to the Contract.

21	Waiver

No delay by or omission by either Party in exercising any right, power, privilege or remedy under this Contract shall operate to impair such right, power, privilege or remedy or be construed as a waiver thereof.  Any single or partial exercise of any such right, power, privilege or remedy shall not preclude any other or further exercise thereof or the exercise of any other right, power, privilege or remedy.

22	Notices

Any notices to be given under this Contract shall be delivered personally or sent by post or by facsimile transmission to the Contract Manager (in the case of the Department) or to the address set out in this Contract (in the case of the Contractor).  Any such notice shall be deemed to be served, if delivered personally, at the time of delivery, if sent by post, 48 hours after posting or, if sent by facsimile transmission, 12 hours after proper transmission.

23	Dispute resolution

23.1	The Parties shall use all reasonable endeavours to negotiate in good faith and settle amicably any dispute that arises during the continuance of this Contract.

23.2	Any dispute not capable of resolution by the parties in accordance with the terms of Clause 23 shall be settled as far as possible by mediation in accordance with the Centre for Dispute Resolution (CEDR) Model Mediation Procedure.

23.3	No party may commence any court proceedings/arbitration in relation to any dispute arising out of this Contract until they have attempted to settle it by mediation, but any such mediation may be terminated by either party at any time of such party wishing to commence court proceedings/arbitration.

24	Discrimination

24.1	The Contractor shall not unlawfully discriminate within the meaning and scope of any law, enactment, order, or regulation relating to discrimination (whether in race, gender, religion, disability, sexual orientation or otherwise) in employment.

24.2	The Contractor shall take all reasonable steps to secure the observance of Clause 24.1 by all servants, employees or agents of the Contractor and all suppliers and sub-contractors employed in the execution of the Contract.

25	Law and Jurisdiction

This Contract shall be governed by and interpreted in accordance with English Law and the parties submit to the jurisdiction of the English courts.

As witness the hands of the parties

Authorised to sign for and on	Authorised to sign for and on

behalf of the Secretary of	behalf of ***insert full name

State for Education	of Contractor***

Signature	Signature

Name in CAPITALS	Name in CAPITALS

Position in Organisation	Position in Organisation

Address in full	Address in full

Date	Date

Schedule 1

[The agreed specification and/or work schedule will be included here]

Schedule 2

1	Table

***Example Table***

| Task | Cost | Total | Invoice date |
| --- | --- | --- | --- |
| Attendance at management/editorial meeting. | 1 day @ £200 p.d. | £200 | 31/03/0X |
| Attendance at meeting with Departmental staff | 1 day @ £200 p.d. | £200 | 31/03/0X |
| Preparation of timetable showing all key stages. | 1.5 days @ £175 p.d. | £262.50 | 31 25/03/0X |
| Issuing an introductory letter to all agreed contributors outlining aims, objectives and copy deadlines. | 0.5 days @ £175 p.d. | £87.50 | 31/03/0X |
| Step1. To research and write the first 8 page A4 newsletter (500 words per page approx). To chase and collate and edit material from agreed contributors. | 9 days @ £200 p.d. Articles @ £1000 per issue Photos and Drgs. £1000 per issue Travel per issue. | £1800 £1000 £1000 £100 | First Edition 31/04/0X |
| Step 2. Submission of draft newsletter for Departmental approval (on 3.5" disk). | 0.5 days @ £175 p.d. | £87.50 | First Edition 31/04/0X |
| Step 3. To respond to the Department's comments and send disk to Information Branch. | 2 days @ £200 p.d. | £400 | First Edition 31/05/0X |
| Step 4. To undertake final proofreading and checking. | 1 day @ £175 p.d. | £175 | First Edition 31/05/0X |
| Step 5. To deliver a half day workshop on newsletter production | 1 day @ £175 p.d. | £175 | First Edition 31/05/0X |
| For Issue 2 repeat task steps 1 to 4. |  | £4562.5 | As agreed in the timetable |
| For Issue 3 repeat task steps 1 to 4 |  | £4562.5 | As agreed in the timetable |
| For Issue 4 repeat task steps 1 to 4 |  | £4562.5 | As agreed in the timetable |
| To invite and monitor reader's comments on the newsletter. | 1 day @ £200 p.d. | £200 | As agreed in the timetable |
| To evaluate the Service to ascertain its benefit to Service promoters. | 4 days @ £200 p.d. | £800 | In the final Invoice. |
| Grand Total (excluding VAT) |  | £20,175 | . |

***'VAT will be payable at the prevailing rate' or 'the above prices are inclusive of VAT' delete as appropriate***

***end of example***

2	Funds allocated to a particular expenditure heading in the table at paragraph 1 ("the Table") are available for that expenditure heading only.  Funds allocated to a particular accounting year are available for that accounting year only.  The allocation of funds in the Table may not be altered except with the prior written consent of the Department.

3	The Contractor shall maintain full and accurate accounts for the Service against the expenditure headings in the Table.  Such accounts shall be retained for at least 6 years after the end of the financial year in which the last payment was made under this Contract.  Input and output VAT shall be included as separate items in such accounts.

4  	The Contractor shall permit duly authorised staff or agents of the Department or the National Audit Office to examine the accounts at any reasonable time and shall furnish oral or written explanations of the account if required.  The Department reserves the right to have such staff or agents carry out examinations into the economy, efficiency and effectiveness with which the Contractor has used the Department's resources in the performance of this Contract.

*** Where funding does not include a contribution from the European Social Fund delete paragraph 4.1***

4.1	The Contractor shall also permit persons duly authorised by the European Court of Auditors and the European Commission to examine the accounts at any reasonable time and shall furnish oral or written explanation of the accounts if required.

***Choose the appropriate Clause 5 for when you are making either a single payment or several payments***

5	One invoice shall be prepared by the Contractor on completion of the Service and shall be detailed against the expenditure headings set out in the Table.  The Contractor or his or her nominated representative or accountant shall certify on the invoice that the amounts claimed were expended wholly and necessarily by the Contractor on the Service in accordance with the Contract and that the invoice does not include any costs being claimed from any other body or individual or from the Department within the terms of another contract.

5	Invoices shall be prepared by the Contractor ***either state a period of time (e.g. monthly) or insert the term 'on the invoice dates specified in the Table' *** in arrears and shall be detailed against the expenditure headings set out in the Table.  The Contractor or his or her nominated representative or accountant shall certify on the invoice that the amounts claimed were expended wholly and necessarily by the Contractor on the Service in accordance with the Contract and that the invoice does not include any costs being claimed from any other body or individual or from the Department within the terms of another contract.

***Choose the appropriate Clause 6 for when you are making either a single payment or several payments***

6	The invoice shall be sent, within 30 days of the end of the Project to SSCL Accounts Payable Team, Room 6124, Tomlinson House, Norcross, Blackpool FY5 3TA, quoting the Contract reference number.   The Department undertakes to pay correctly submitted invoices within 5 days of receipt. The Department is obliged to pay invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.  Any correctly submitted invoices that are not paid within 30 days will be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.  A correct invoice is one that: is delivered in timing in accordance with the contract; is for the correct sum; in respect of goods/services supplied or delivered to the required quality (or are expected to be at the required quality); includes the date, supplier name, contact details and bank details; quotes the relevant purchase order/contract reference and has been delivered to the nominated address.   If any problems arise contact the Department's Contract Manager.  The Department aims to reply to complaints within 10 working days.  The Department shall not be responsible for any delay in payment caused by an incomplete or illegible invoice.

6	Invoices shall be sent, within ***enter period of time (e.g. within 30 days)*** of the end of the relevant ***enter period (e.g. month)*** to SSCL Accounts Payable Team, Room 6124, Tomlinson House, Norcross, Blackpool FY5 3TA, quoting the Contract reference number.   The Department undertakes to pay correctly submitted invoices within 5 days of receipt. The Department is obliged to pay invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.  Any correctly submitted invoices that are not paid within 30 days will be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.  A correct invoice is one that: is delivered in timing in accordance with the contract; is for the correct sum; in respect of goods/services supplied or delivered to the required quality (or are expected to be at the required quality); includes the date, supplier name, contact details and bank details; quotes the relevant purchase order/contract reference and has been delivered to the nominated address..  If any problems arise, contact the Department's Contract Manager.  The Department aims to reply to complaints within 10 working days.  The Department shall not be responsible for any delay in payment caused by incomplete or illegible invoices.

7	The Contractor shall have regard to the need for economy in all expenditure.  Where any expenditure in an invoice, in the Department's reasonable opinion, is excessive having due regard to the purpose for which it was incurred, the Department shall only be liable to reimburse so much (if any) of the expenditure disallowed as, in the Department's reasonable opinion after consultation with the Contractor, would reasonably have been required for that purpose.

8 	If this Contract is terminated by the Department due to the Contractors insolvency or default at any time before completion of the Service, the Department shall only be liable under paragraph 1 to reimburse eligible payments made by, or due to, the Contractor before the date of termination.

***Use the following Clauses 9 and 10 when you are making a single payment***

9 	The Department shall not be obliged to pay the invoice until the Contractor has carried out all the elements of the Service specified as in Schedule 1.

10	It shall be the responsibility of the Contractor to ensure that the invoice covers all outstanding expenditure for which reimbursement may be claimed.  On payment of the invoice by the Department all amounts due to be reimbursed under this Contract shall be deemed to have been paid and the Department shall have no further liability to make reimbursement of any kind.

***Use the following Clauses 9, 10 and 11 when you are making several payments***

9	On completion of the Service or on termination of this Contract, the Contractor shall promptly draw-up a final invoice, which shall cover all outstanding expenditure incurred for the Service.  The final invoice shall be submitted not later than 30 days after the date of completion of the Service.

10	The Department shall not be obliged to pay the final invoice until the Contractor has carried out all the elements of the Service specified as in Schedule 1.

11	It shall be the responsibility of the Contractor to ensure that the final invoice covers all outstanding expenditure for which reimbursement may be claimed.  Provided that all previous invoices have been duly paid, on due payment of the final invoice by the Department all amounts due to be reimbursed under this Contract shall be deemed to have been paid and the Department shall have no further liability to make reimbursement of any kind.

- End of Schedule 2

Attachment 2

Departmental Security Standards

Notes for use of this clause – NB Remove the guidance text in italics below!

The clauses, guidance and interpretation of terms provided below can be used to form the basis of an Invitation to Tender (ITT) or appropriate clauses in a Business Services or ICT contract where the information involved is classified no higher than OFFICIAL, including OFFICIAL-SENSITIVE, as described in the Government Security Classification Policy. The ‘OFFICIAL–SENSITIVE’ caveat is used to identify a limited subset of OFFICIAL information that could have more damaging consequences (for individuals, an organisation or government generally) if it were lost, stolen or published in the media, and might include sensitive business information and data of a personal or sensitive personal nature, as defined by the Data Protection Act 1998.

Please Note:

When this document is used to inform an ITT to deliver an ICT solution then all 24 security clauses should be incorporated within the ITT, however, for a Business Service ITT the final two (2) clauses numbered 12.23 and 12.24 should be removed.

When this document is used to inform clauses for an ICT solution contract then all 24 security clauses, subject to any exceptions, such as that contained in the guidance at clause 12.1, or resulting from the guidance contained within any of the other clauses detailed below, should be incorporated within the contract. Additionally where these clauses are used fto inform a Business Service contract the final two (2) clauses numbered 12.23 and 12.24 may also be removed.

Further advice and guidance on Data Security is available on the Commercial Policy Intranet page.

It is important that the project’s Senior Responsible Owner (SRO), understands that the security requirements included in the contract are both appropriate and proportionate to the risks involved. Where necessary, the project should acquire the services of a CESG Certified Professional Security & Information Risk Advisor (CCP SIRA) contractor to assist them in assessing the risks and specifying the appropriate security in response to that assessment. To facilitate access to CCP SIRA assistance, if required, projects may procure it via the existing framework contract detailed on the Information Assurance pages of the DSU Intranet.

Most requirements are the same for all business services contracts.  However, for contracts involving equivalent certifications or the processing of particularly sensitive data, alternatives are suggested in the (italicised) commentary text. For clause 12.3, there are two alternatives, as follows:

- Clause 12.3 requires “certification” to ISO 27001 for contracts involving the processing of particularly sensitive data. Otherwise, “conformance” is sufficient.

The Departmental Security pages on the DSU Intranet provide further information to help you assess the sensitivity of the information. However, the risk assessment by a CCP SIRA will be able to more fully inform the security requirements.

- Departmental Security Standards for Business Services and ICT Contracts

| “BPSS” “Baseline Personnel Security Standard” | a level of security clearance described as pre-employment checks in the National Vetting Policy. |
| --- | --- |
| “CESG” | is the UK government’s National Technical Authority for Information Assurance. The website is http://www.cesg.gov.uk/Pages/homepage.aspx |
| “CESG IAP” “CESG Information Assurance Policy Portfolio” | means the CESG Information Assurance policy Portfolio containing HMG policy and guidance on the application of ‘security assurance’ for HMG systems. |
| “CTAS” ”CESG Tailored Assurance” | is an ‘information assurance scheme’ which provides assurance for a wide range of HMG, MOD, Critical National Infrastructure (CNI) and public sector customers procuring IT systems, products and services, ranging from simple software components to national infrastructure networks. |
| “CPA” “CESG Product Assurance” | is an ‘information assurance scheme’ which evaluates commercial off the shelf (COTS) products and their developers against published security and development standards. These CPA certified products can be used by government, the wider public sector and industry. |
| “CCSC” “CESG Certified Cyber Security Consultancy” | is CESG's approach to assessing the services provided by consultancies and confirming that they meet CESG's standards. This approach builds on the strength of CLAS and certifies the competence of suppliers to deliver a wide and complex range of cyber security consultancy services to both the public and private sectors. |
| “CCP” “CESG Certified Professional” | is a CESG scheme in consultation with government, industry and academia to address the growing need for specialists in the cyber security profession and are building a community of recognised professionals in both the UK public and private sectors. |
| “CC” “Common Criteria” | the Common Criteria scheme provides assurance that a developer’s claims about the security features of their product are valid and have been independently tested against recognised criteria. |
| “Cyber Essentials” “Cyber Essentials Plus” | Cyber Essentials is the government backed, industry supported scheme to help organisations protect themselves against common cyber-attacks. Cyber Essentials and Cyber Essentials Plus are levels within the scheme. |
| “Data” “Data Controller” “Data Processor” “Personal Data” “Sensitive Personal Data” “Data Subject”, “Process” and “Processing” | shall have the meanings given to those terms by the Data Protection Act 1998 |
| "Department’s Data" “Department’s Information” | is any data or information owned or retained in order to meet departmental business objectives and tasks, including: (a) any data, text, drawings, diagrams, images or sounds (together with any repository or database made up of any of these components) which are embodied in any electronic, magnetic, optical or tangible media, and which are: (i) supplied to the Contractor by or on behalf of the Department; or (ii) which the Contractor is required to generate, process, store or transmit pursuant to this Contract; or (b) any Personal Data for which the Department is the Data Controller; |
| “DfE” “Department” | means the Department for Education |
| “Departmental Security Standards” | means the Department’s security policy or any standards, procedures, process or specification for security that the Contractor is required to deliver. |
| “Digital Marketplace / GCloud” | the Digital Marketplace is the online framework for identifying and procuring cloud technology and people for digital projects. Cloud services (e.g. web hosting or IT health checks) are on the G-Cloud framework. |
| “FIPS 140-2” | this is the Federal Information Processing Standard (FIPS) Publication 140-2, (FIPS PUB 140-2), entitled ‘Security Requirements for Cryptographic Modules’. This document is the de facto security standard used for the accreditation of cryptographic modules. |
| “Good Industry Practice” “Industry Good Practice” | means the exercise of that degree of skill, care, prudence, efficiency, foresight and timeliness as would be expected from a leading company within the relevant industry or business sector. |
| “Good Industry Standard” “Industry Good Standard” | means the implementation of products and solutions, and the exercise of that degree of skill, care, prudence, efficiency, foresight and timeliness as would be expected from a leading company within the relevant industry or business sector. |
| “GSC” “GSCP” | means the Government Security Classification Policy which establishes the rules for classifying HMG information. The policy is available at: https://www.gov.uk/government/publications/government-security-classifications |
| “HMG” | means Her Majesty’s Government |
| “SPF” “HMG Security Policy Framework” | This is the definitive HMG Security Policy which describes the expectations of the Cabinet Secretary and Government’s Official Committee on Security on how HMG organisations and third parties handling HMG information and other assets will apply protective security to ensure HMG can function effectively, efficiently and securely. |
| “ICT” | means Information and communications technology (ICT) is used as an extended synonym for information technology (IT), used to describe the bringing together of enabling technologies used to deliver the end-to-end solution |
| IS5 | this is HMG Information Assurance Standard No. 5 - Secure Sanitisation issued by CESG |
| “ISO/IEC 27001” “ISO 27001” | is the International Standard for Information Security Management Systems Requirements |
| “ISO/IEC 27002” “ISO 27002” | is the International Standard describing the Code of Practice for Information Security Controls. |
| “ISO 22301” | is the International Standard describing for Business Continuity |
| “IT Security Health Check” “Penetration Testing” | means an assessment to identify risks and vulnerabilities in systems, applications and networks which may compromise the confidentiality, integrity or availability of information held on that IT system. |
| “Need-to-Know” | the Need-to-Know principle is employed within HMG to limit the distribution of classified information to those people with a clear ‘need to know’ in order to carry out their duties. |
| “OFFICIAL” “OFFICIAL-SENSITIVE” | - the term ‘OFFICIAL’ is used to describe the baseline level of ‘security classification’ described within the Government Security Classification Policy (GSCP) which details the level of protection to be afforded to information by HMG, for all routine public sector business, operations and services. the ‘OFFICIAL–SENSITIVE’ caveat is used to identify a limited subset of OFFICIAL information that could have more damaging consequences (for individuals, an organisation or government generally) if it were lost, stolen or published in the media, as described in the Government Security Classification Policy. |
| “Security and Information Risk Advisor” “CCP SIRA” “SIRA” | the Security and Information Risk Advisor (SIRA) is a role defined under the CESG CESG Certified Professional Scheme |

  - The Contractor shall comply with Departmental Security Standards for Contractors which include but are not constrained to the following clauses.

- (Guidance: Providers on the HMG Digital Marketplace / GCloud or Public Service Network (PSN) that have demonstrated compliance, as part of their scheme application, to the relevant scheme’s security framework, such as the HMG Cloud Security Principles for the HMG Digital Marketplace / GCloud, may on presentation of suitable evidence of compliance be excused from compliance to similar clauses within the DfE Security Clauses detailed in this section (Section 12).)

  - Where the Contractor will provide ICT products or Services or otherwise handle information at OFFICIAL on behalf of the Department, the requirements under Cabinet Office Procurement Policy Note – Use of Cyber Essentials Scheme certification - Action Note 09/14 25 September 2014, or any subsequent updated document, are mandated; that “contractors supplying products or services to HMG shall have achieved, and retain certification at the appropriate level, under the HMG Cyber Essentials Scheme”. The certification scope must be relevant to the services supplied to, or on behalf of, the Department.

- (Guidance: The Department’s expectation is that the certification scope will be relevant to the services supplied to, or on behalf of, the Department. However, where a contractor or (sub) contractor is able to evidence a valid exception or certification to an equivalent recognised scheme or standard, such as ISO 27001, then certification under the Cyber Essentials scheme could be waived and this clause may be removed. Changes to the Cabinet Office Procurement Policy Note – Use of Cyber Essentials Scheme certification - Action Note 09/14 25 September 2014 will be tracked by the DSU)

- (Guidance: The terms OFFICIAL and OFFICIAL-SENSITIVE are taken from the Government Security Classification Policy (GSCP). The Department’s expectations are that all contractors shall handle the Department’s information in a manner compliant with the GSCP – see 12.4 below. Details of the GSCP can be found on the GOV.UK website at: https://www.gov.uk/government/publications/government-security-classifications.)

[Use the appropriate Clause 12.3]

  - [Either]

- The Contractor shall be able to demonstrate conformance to, and show evidence of such conformance to the ISO/IEC 27001 (Information Security Management Systems Requirements) standard, including the application of controls from ISO/IEC 27002 (Code of Practice for Information Security Controls).

(Guidance: The Department’s expectation is that suppliers demonstrating conformance to ISO/IEC 27001 will be able to provide the Department with copies of their Scope of Conformance and Statement of Applicability.)

[Or, for contracts involving the processing of particularly sensitive data]

12.3	The Contractor shall have achieved, and be able to maintain, independent certification to ISO/IEC 27001 (Information Security Management Systems Requirements). The ISO/IEC 27001 certification must have a scope relevant to the services supplied to, or on behalf of, the Department. The scope of certification and the statement of applicability must be acceptable, following review, to the Department, including the application of controls from ISO/IEC 27002 (Code of Practice for Information Security Controls).

- (Guidance: The Department’s expectation is that suppliers claiming certification to ISO/IEC 27001 shall provide the Department with copies of their Scope of Certification, Statement of Applicability and a valid ISO/IEC 27001 Certificate issued by an authorised certification body. Where the provider is an SME that has a valid Cyber Essentials certification then certification under the ISO/IEC 27001 scheme could be waived and this clause may be removed.)

  - The Contractor shall follow the UK Government Security Classification Policy (GSCP) in respect of any Departmental Data being handled in the course of providing this service, and will handle this data in accordance with its security classification. (In the event where the Contractor has an existing Protective Marking Scheme then the Contractor may continue to use this but must map the HMG security classifications against it to ensure the correct controls are applied to the Departmental Data).

- (Guidance: The Department’s expectations are that all contractors shall handle the Department’s information in a manner compliant with the GSCP. Details of the GSCP can be found on the GOV.UK website at: https://www.gov.uk/government/publications/government-security-classifications.)

  - Departmental Data being handled in the course of providing the ICT solution or service must be segregated from other data on the Contractor’s or sub-contractor’s own IT equipment to both protect the Departmental Data and enable it to be identified and securely deleted when required. In the event that it is not possible to segregate any Departmental Data then the Contractor and any sub-contractor shall be required to ensure that it is stored in such a way that it is possible to securely delete the data in line with Clause 12.14.

- (Guidance: Advice on HMG secure sanitisation policy and approved methods are described in HMG IS5.)

  - The Contractor shall have in place and maintain physical security and entry control mechanisms (e.g. door access) to premises and sensitive areas and separate logical access controls (e.g. identification and authentication) to ICT systems to ensure only authorised personnel have access to Departmental Data.

- (Guidance: Where the contractor’s and sub-contractor services are wholly carried out within Departmental premises and all access to buildings or ICT systems is managed directly by the Department as part of the service, the Department shall be responsible for meeting the requirements of this clause and it need not be included.)

  - The Contractor shall have in place and shall maintain procedural, personnel, physical and technical safeguards to protect Departmental Data, including but not limited to: physical security controls; good industry standard policies and process; anti-virus and firewalls; security updates and up-to-date patching regimes for anti-virus solutions; operating systems, network devices, and application software, user access controls and the creation and retention of audit logs of system use.

- (Guidance: Where the contractor’s and sub-contractor services are wholly carried out using Departmental ICT resources or locations managed directly by the Department as part of the service, the Department shall be responsible for meeting the requirements of this clause and it need not be included.)

  - Any electronic transfer methods across public space or cyberspace, including third party provider networks must be protected via encryption which has been certified to a minimum of FIPS 140-2 standard or a similar method approved by the Department prior to being used for the transfer of any Departmental Data.

- (Guidance: The terms “public space” and “cyberspace” are used to describe the internet and any commercially provided third party network used to transmit Departmental information. Even where the contractor’s and sub-contractor services are wholly carried out using Departmental ICT resources managed directly by the Department as part of the service, if there is still the possibility of emails being sent to external addresses, this clause should be included.)

  - Storage of Departmental Data on any portable devices or media shall be limited to the absolute minimum required to deliver the stated business requirement and shall be subject to Clause 12.10 and 12.11 below.

  - Any portable removable media (including but not constrained to pen drives, flash drives, memory sticks, CDs, DVDs, or other devices) which handle, store or process Departmental Data to deliver and support the service, shall be under the control and configuration management of the contractor or (sub-)contractors providing the service, shall be both necessary to deliver the service and shall be encrypted using a product which has been certified to a minimum of FIPS140-2 standard or use another encryption standard that is acceptable to the Department.

- (Guidance: Where the use of removable media as described at Clause 12.9 above is either prohibited or not required in order to deliver the service this clause shall be revised as follows: - ‘The use of removable media in any form is not permitted’.)

  - All portable ICT devices, including but not limited to laptops, tablets, smartphones or other devices, such as smart watches, which handle, store or process Departmental Data to deliver and support the service, shall be under the control and configuration management of the contractor or sub-contractors providing the service, and shall be necessary to deliver the service. These devices shall be full-disk encrypted using a product which has been certified to a minimum of FIPS140-2 standard or use another encryption standard that is acceptable to the Department.

- (Guidance: Where there is no suitable FIPS140-2 encryption product available to provide the necessary full-disk encryption, the Department shall agree a suitable alternative product that meets ‘industry good practice’ in this area with the contractor or sub-contractor. Where the contractor’s and sub-contractor services are wholly carried out using Departmental ICT resources managed directly by the Department as part of the service, the Department shall be responsible for meeting the requirements of this clause and it need not be included.)

  - Whilst in the Contractor’s care all removable media and hardcopy paper documents containing Departmental Data must be handled securely and secured under lock and key when not in use and shall be securely destroyed when no longer required, using either a cross-cut shredder or a professional secure waste paper organisation.

- (Guidance: The term ‘lock and key’ is defined as: “securing information in a lockable desk drawer, cupboard or filing cabinet which is under the user’s sole control and to which they hold the keys”.)

  - When necessary to hand carry removable media and/or hardcopy paper documents containing Departmental Data, the media or documents being carried shall be kept under cover and transported in such a way as to ensure that no unauthorised person has access to the material being carried. This clause shall apply equally regardless of whether the material is being carried inside or outside of company premises.

- (Guidance: The term ‘under cover’ means that the information is carried within an opaque folder or envelope within official premises and buildings and within a closed briefcase or other similar bag or container when travelling outside of official premises or buildings).

  - At the end of the contract or in the event of equipment failure or obsolescence, all Departmental information and data, in either hardcopy or electronic format, that is physically held or logically stored on the Contractor’s ICT infrastructure must be securely sanitised or destroyed in accordance with the current HMG policy (HMG IS5) using a CESG approved product or method. Where sanitisation or destruction is not possible for legal, regulatory or technical reasons, such as a Storage Area Network (SAN) or shared backup tapes, then the Contractor or sub-contractor shall protect the Department’s information and data until the time, which may be long after the end of the contract, when it can be securely cleansed or destroyed.

- (Guidance: Where no departmental information or data shall be held by the Contractor or sub-contractor, in either physical or logical form this clause may be removed.)

- (Guidance: Where there is no acceptable secure sanitisation method available for a piece of equipment, or it is not possible to sanitise the equipment due to an irrecoverable technical defect, the storage media involved shall be destroyed using an approved method described in HMG IS5.)

  - Access by Contractor or sub-contractor staff to Departmental Data shall be confined to those individuals who have a “need-to-know” and the appropriate level of security clearance, as required by the Department for those individuals whose access is essential for the purpose of their duties. All employees with direct or indirect access to Departmental Data must be subject to pre-employment checks equivalent to or higher than the Baseline Personnel Security Standard (BPSS)

- (Guidance: Further details of the requirements for BPSS clearance are available on the website at: https://www.gov.uk/government/publications/security-policy-framework)

  - All Contractor or sub-contractor employees who handle Departmental Data must have annual awareness training in protecting information.

  - The Contractor shall, as a minimum, have in place robust and ISO 22301 conformant Business Continuity arrangements and processes including IT disaster recovery plans and procedures to ensure that the delivery of the contract is not adversely affected in the event of an incident. An incident shall be defined as any situation that might be, or could lead to, a disruption, loss, emergency or crisis. When a certificate is not available it shall be necessary to verify the ongoing effectiveness of the ISO 22301 conformant Business Continuity arrangements and processes including IT disaster recovery plans and procedures, to the extent that the Contractor must have tested/exercised these plans within the last 12 months and produced a written report of the test/exercise, outcome and feedback, including required actions.

- (Guidance: The creation of robust business continuity and disaster recovery plans are aligned with industry good practice and it is the Department’s expectation that all vendors providing services or infrastructure to the Department will have plans that are aligned to the ISO 22301 standard in place. Further information on the requirements of ISO 22301 may be found in the standard.)

  - Any non-compliance with these Departmental Security Standards for Contractors, or other Security Standards pertaining to the solution, or any suspected or actual breach of the confidentiality, integrity or availability of Departmental Data being handled in the course of providing this service, shall be investigated immediately and escalated to the Department by a method agreed by both parties.

- (Guidance: The Department’s expectation is that non-compliances, or any suspected or actual breach of the confidentiality, integrity or availability of the Department’s Data shall be reported as incidents and investigated by the vendor with outcomes being notified to the Department.)

  - The Contractor shall ensure that any IT systems and hosting environments that are used to hold Departmental Data being handled, stored or processed in the course of providing this service shall be subject to an independent IT Health Check (ITHC) using a CESG approved ITHC provider before go-live and periodically (at least annually) thereafter. The findings of the ITHC relevant to the service being provided are to be shared with the Department and all necessary remedial work carried out. In the event of significant security issues being identified, a follow up remediation test may be required.

- (Guidance: Further information on IT Health Checks and the CESG CHECK Scheme which enables penetration testing by CESG approved companies can be found on the CESG website at: https://www.cesg.gov.uk/scheme/penetration-testing.)

  - The Contractor or sub-contractors providing the service will provide the Department with full details of any actual storage outside of the UK or any future intention to host Departmental Data outside the UK or to perform any form of ICT management or support function from outside the UK. The Contractor or sub-contractor will not go ahead with any such proposal without the prior written agreement from the Department.

- (Guidance: The offshoring of HMG information outside of the UK is subject to approval by the Departmental SIRO and, in some cases, also by the Office of the Government Senior Information Risk Owner (OGSIRO). Further information on this process can be found at: https://ogsirooffshoring.zendesk.com/hc/en-us/articles/203107991-HMG-s-Offshoring-Policy)

  - The Department reserves the right to audit the Contractor or sub-contractors providing the service within a mutually agreed timeframe but always within seven days of notice of a request to audit being given. The audit shall cover the overall scope of the service being supplied and the Contractor’s, and any sub-contractors, compliance with the clauses contained in this Section.

  - The Contractor shall contractually enforce all these Departmental Security Standards for Contractors onto any third-party suppliers, sub-contractors or partners who could potentially access Departmental Data in the course of providing this service.

*** ICT-SPECIFIC CLAUSES ONLY ***

(These ICT-specific clauses should be removed for Business Service Contracts)

  - The Contractor shall deliver ICT solutions and services that are compliant with the HMG Security Policy Framework in conjunction with current CESG Information Assurance Policy Portfolio and Departmental Policy. The Contractor will provide the Department with evidence of compliance for the solutions and services to be delivered. The Department’s expectation is that the Contractor shall provide written evidence of:

- Existing security assurance for the services to be delivered, such as: PSN Compliance as a PSN Customer and/or as a PSN Service; CESG Tailored Assurance (CTAS); inclusion in the Common Criteria (CC) or CESG Product Assurance Schemes (CPA); ISO 27001 / 27002 or an equivalent industry level certification. Documented evidence of any existing security assurance or certification shall be required.

- Existing HMG security accreditations that are still valid including: details of the body awarding the accreditation; the scope of the accreditation; any caveats or restrictions to the accreditation; the date awarded, plus a copy of the residual risk statement. Documented evidence of any existing security accreditation shall be required.

- Documented progress in achieving any security assurance or accreditation activities including whether documentation has been produced and submitted. The Contractor shall provide details of who the awarding body or organisation will be and date expected.

  - If no current security accreditation or assurance is held the Contractor and sub-contractors shall undergo appropriate security assurance activities as determined by the Department. Contractor and sub-contractors shall support the provision of appropriate evidence of assurance and the production of the necessary security documentation. This will include obtaining any necessary professional security resources required to support the Contractor’s and sub-contractor’s security assurance activities such as: a CESG Certified Cyber Security Consultancy (CCSC) or CESG Certified Professional (CCP) Security and Information Risk Advisor (SIRA)

- (Guidance: It is Departmental policy that all systems used to store or process Departmental information and data shall achieve an acceptable level of security assurance. Further advice and guidance on the Department’s Security Assurance Model can be supplied on request.)

- (Guidance: Further information on the CCSC and CCP roles described above can be found on the CESG Website at: http://www.cesg.gov.uk/awarenesstraining/certified-professionals/Pages/index.aspx)

For the list of exclusion please see https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/551130/List_of_Mandatory_and_Discretionary_Exclusions.pdf

See EU definition of SME: http://ec.europa.eu/enterprise/policies/sme/facts-figures-analysis/sme-definition/

UK companies, Societates European (SEs) and limited liability partnerships (LLPs) will be required to identify and record the people who own or control their company. Companies, SEs and LLPs will need to keep a PSC register, and must file the PSC information with the central public register at Companies House. See PSC guidance.

Central Government contracting authorities should use this information to have the PSC information for the preferred supplier checked before award.

See Action Note 8/16 Updated Standard Selection Questionnaire

Procurement Policy Note 9/16 Modern Slavery Act 2015

Procurement Policy Note 14/15– Supporting Apprenticeships and Skills Through Public Procurement

Procurement Policy Note 04/15 Taking Account of Suppliers’ Past Performance

Procurement Policy Note 16/15– Procuring steel in major projects