Schedule 1

to CT/COMM1/0095

NEC 3

STRICTLY PRIVATE and CONFIDENTIAL

PROFESSIONAL SERVICES CONTRACT

MAIN OPTION A

June 2005

This document is NEC3 PSC with adoption of relevant Options and then amended to suit the requirements of MOD pursuant to the MOD’s license to use NEC3.

CONTENTS

| Core clauses | 1 | General |  |
| --- | --- | --- | --- |
|  | 2 | The Parties main responsibilities |  |
|  | 3 | Time |  |
|  | 4 | Quality |  |
|  | 5 | Payment |  |
|  | 6 | Compensation events |  |
|  | 7 | Rights to material |  |
|  | 8 | Indemnity, insurance and liability |  |
|  | 9 | Termination |  |
| Dispute resolution | W1 | Option W1 |  |
| Secondary Option clauses |  |  |  |
|  | X2 | Changes in the law |  |
|  | X4 | Parent company guarantee |  |
|  | X13 | Performance bond |  |
|  | X19 | Task Orders |  |
|  | X20 | Key Performance Indicators |  |
|  | Y(UK)2 | The Housing Grants, Construction and Regeneration Act 1996 |  |
|  | Y(UK)3 | The Contracts (Rights of Third Parties) Act 1999 |  |
| Contract Data |  |  |  |

CORE CLAUSES

1 General

| Actions |  |  |  |  | 10 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 10.1 |  |  | The Employer, the Service Manager and the Consultant shall act as stated in this contract and in a spirit of mutual trust and co-operation. |  |  |  |
| Identified and defined |  |  |  |  | 11 |  |  |  |  |  |  |
| terms |  |  |  |  | 11.1 |  |  | In this Contract, terms identified in the Contract Data are in italics and defined terms set out in this clause and/or the Framework Agreement have capital initials. |  |  |  |
|  |  |  |  |  | 11.2 |  |  | - The Accepted Plan is the Consultant’s plan (as detailed in clause 31) identified in the Contract Data or is the latest plan accepted by the Service Manager. The latest plan accepted by the Service Manager supersedes previous Accepted Plans. |  |  |  |
|  |  |  |  |  |  |  |  | - Affected Property is the property of the Employer or Others which is affected by the services or used by the Consultant To Provide the Services and which is identified in the Contract Data. |  |  |  |
|  |  |  |  |  |  |  |  | - Background IPR means any IPR not created, or developed by or on behalf of the Consultant under or for the purpose of this Contract. |  |  |  |
|  |  |  |  |  |  |  |  | - NOT USED |  |  |  |
|  |  |  |  |  |  |  |  | - Change Management Process means the process outlined in clause 19L. |  |  |  |
|  |  |  |  |  |  |  |  | - Change of Control in respect of clause 19A.1 means: |  |  |  |
|  |  |  |  |  |  |  |  | (a) any sale, transfer, or disposal of any legal, beneficial or equitable interest in any or all of the shares in the Consultant including control over the exercise of voting rights conferred on those shares or the control over the right to appoint or remove directors or the right to dividends) and/or; |  |  |  |
|  |  |  |  |  |  |  |  | (b) any other arrangements that have or may have or which result in the same effect as (6)(a) above. |  |  |  |
|  |  |  |  |  |  |  |  | - Completion is when the Consultant has |  |  |  |
|  |  |  |  |  |  |  |  | - done all the work which the Scope states he is to do by the Completion Date and |  |  |  |
|  |  |  |  |  |  |  |  | - corrected Defects which would have prevented the Employer from using the services and Others from doing their work. |  |  |  |
|  |  |  |  |  |  |  |  | If the work which the Consultant is to do by the Completion Date is not stated in the Scope, Completion is when the Consultant has done all the work necessary for the Employer to use the services and for Others to do their work. |  |  |  |
|  |  |  |  |  |  |  |  | - The Completion Date is the completion date set out in the Contract Data Part 1 unless later changed in accordance with this contract. |  |  |  |
|  |  |  |  |  |  |  |  | - Confidential Information means: |  |  |  |
|  |  |  |  |  |  |  |  | - any information which has been designated as confidential by either Party in writing or that ought to be considered as confidential (however it is conveyed or on whatever media it is stored) including information which would or would be likely to prejudice the commercial interests of any person, trade secrets, Intellectual Property Rights, know-how of either Party and all personal data and sensitive data within the meaning of the Data Protection Act 1998; and |  |  |  |
|  |  |  |  |  |  |  |  | - the Commercially Sensitive Information - but excluding any information - which was public knowledge at the time of disclosure (otherwise than by breach of Clause 13B (Confidential Information); - which was in the possession of the receiving Party, without restriction as to its disclosure, before receiving it from the disclosing Party; - which is received from a third party (who lawfully acquired it) without restriction as to its disclosure; or - is independently developed without access to the Confidential Information. |  |  |  |
|  |  |  |  |  |  |  |  | - The Contract Date is the date when this Contract came into existence being the date of the relevant Demand Order duly executed by the Parties in accordance with the Framework Agreement. |  |  |  |
|  |  |  |  |  |  |  |  | - Commercially Sensitive Information is the information listed in the Consultant Commercially Sensitive Information [DIO DOC 12] to this Contract being information notified by the Consultant to the Employer which is acknowledged by the Employer as being commercially sensitive information. |  |  |  |
|  |  |  |  |  |  |  |  | - Contract Records means all records, agreements, specifications, drawings, manufacturing data, information and documents that are produced in connection with the services. |  |  |  |
|  |  |  |  |  |  |  |  | - Consultant’s Task Order means the notification from the Consultant pursuant to the Change Management Process. |  |  |  |
|  |  |  |  |  |  |  |  | - Crown means the government of the United Kingdom (including the Northern Ireland Executive Committee and the Northern Ireland Departments, the Scottish Executive and the National Assembly for Wales), including, but not limited to, government ministers, government departments, government and particular bodies and government agencies. |  |  |  |
|  |  |  |  |  |  |  |  | - A Defect is: - a part of the services which is not provided in accordance with the Contract or the Scope; or - a part of the services which is not in accordance with the applicable law or the Accepted Plan; or - a part of the services the design of which is the responsibility of the Consultant, if that design has not been prepared in accordance with the standard required by the Contract. |  |  |  |
|  |  |  |  |  |  |  | - Environmental Information Regulations means the Environmental Information Regulations 2004 as the same may be revised and updated from time to time and any guidance and/or codes of practice issued by the Information Commissioner or relevant government department in relation to such regulations. |  |  |  |  |
|  |  |  |  |  |  |  | - Equipment is items provided by the Consultant and used by him to Provide the Services and which the Scope does not require him to include in the Affected Property. |  |  |  |  |
|  |  |  |  |  |  |  | - Establishment is either a land parcel or collection of land parcels that function as an administrative whole to provide military capability. Occasionally these may be stand alone level 2 assets which may form part of a larger collective such as a garrison. |  |  |  |  |
|  |  |  |  |  |  |  | - [not used] |  |  |  |  |
|  |  |  |  |  |  |  | - Firm Price means a price/rate agreed for the services or any part of the services which is not subject to variation at any time during the Contract or such other period as the Contract states the Firm Price is to apply as the same are set out in the Price List. |  |  |  |  |
|  |  |  |  |  |  |  | - Fixed Price means a price/rate agreed for the services or any part of the services which is subject to variation only in accordance with the variation of price provisions contained in the Contract. |  |  |  |  |
|  |  |  |  |  |  |  | - FOIA means the Freedom of Information Act 2000 and any subordinate legislation made under this Act as the same may be revised and replaced from time to time together with any guidance and/or codes of practice issued by the Information Commissioner or relevant government department in relation to such legislation. |  |  |  |  |
|  |  |  |  |  |  |  | - Foreground IPR means any IPR created, or developed by or on behalf of the Consultant under or for the purpose of this Contract. |  |  |  |  |
|  |  |  |  |  |  |  | - Fraud means any offence under the law creating offences in respect of fraudulent acts. |  |  |  |  |
|  |  |  |  |  |  |  | - Head of Establishment means the Employer nominated individual responsible for an Establishment. |  |  |  |  |
|  |  |  |  |  |  |  | - Information means any information in any written or other tangible form disclosed to one Party by or on behalf of the other Party under or in connection with this Contract. |  |  |  |  |
|  |  |  |  |  |  |  | - Insurance Table means the table at clause 81. |  |  |  |  |
|  |  |  |  |  |  |  | - Intellectual Property Rights (“IPRs”) means patents, inventions, design rights (whether registrable or otherwise), applications for any of the foregoing, copyright, database rights, domain names, trade or business names, moral rights and other similar rights or obligations whether registrable or not in any country (including but not limited to the United Kingdom) and the right to sue for passing off. |  |  |  |  |
|  |  |  |  |  |  |  | - IP Materials means any guidance, specifications, instructions, toolkits, plans, data, drawings, databases, patents, patterns, models, designs or other material. |  |  |  |  |
|  |  |  |  |  |  |  | - Issued Property means any Plant, Material or Materiel or equipment provided by the Employer to the Contractor under this Contract. |  |  |  |  |
|  |  |  |  |  |  |  | - Joint Venture (JV) company is two or more companies engaged in a solitary business enterprise for profit without actual partnership or incorporation. |  |  |  |  |
|  |  |  |  |  |  |  | - A Key Date is the date by which work is to meet the Condition stated. The Key Date is the key date stated in the Contract Data and the Condition is the condition stated in the Contract Data unless later changed in accordance with this contract. |  |  |  |  |
|  |  |  |  |  |  |  | - [not used] |  |  |  |  |
|  |  |  |  |  |  |  | - List X means the grant of the necessary Facility Security Clearance under the national security requirements in accordance with the Cabinet Office Security Policy Framework which a contractor, consultant or sub-contractor is required to hold where a contract involves protectively marked aspects at the level of Confidential (within the meaning of the UK Government’s Protective Marking Scheme) or above. |  |  |  |  |
|  |  |  |  |  |  |  | - Materiel is derived from property owned by the Employer and issued to the Consultant for the sole performance of this Contract. |  |  |  |  |
|  |  |  |  |  |  | - Others are people or organisations who are not the Employer, the Consultant, the Adjudicator or any employee, Subconsultant or supplier of the Consultant. |  |  |  |  |  |
|  |  |  |  |  |  | - The Parties are the Employer and the Consultant. |  |  |  |  |  |
|  |  |  |  |  |  | - Personnel means all employees, agents, consultants and Subconsultants (including Sub-contractors in the case of the Consultant) of either Party as the case may be. |  |  |  |  |  |
|  |  |  |  |  |  | - PLC means Public Limited Company which is registered as such under the s4 of the Companies Act 2006. |  |  |  |  |  |
|  |  |  |  |  |  | - The Prices mean the Firm Prices and the Fixed Prices for the services as referred to in the Demand Order or as otherwise calculated in accordance with this Contract. |  |  |  |  |  |
|  |  |  |  |  |  | - The Price for Services Provided to Date is: - the total of the Prices for the services which have been completed to date. |  |  |  |  |  |
|  |  |  |  |  |  | - The Price List is the price list unless later changed in accordance with this Contract as detailed in [ DIO DOC 26]. |  |  |  |  |  |
|  |  |  |  |  |  | - The Project Bank Account (should the parties chose to operate one) is the bank account opened by the Consultant and held jointly with the Employer in accordance with the terms set out in Trust Deed and Bank Account Agreement. |  |  |  |  |  |
|  |  |  |  |  |  | - To Provide the Services means to do the work necessary to complete the services in accordance with this Contract and all incidental work, services and actions which this Contract requires. |  |  |  |  |  |
|  |  |  |  |  |  | - Relevant Day means the day which is thirty (30) days after the relevant assessment date as detailed in clause 50.1. |  |  |  |  |  |
|  |  |  |  |  |  | - The Risk Register is a register of the risks which are listed in the Contract Data and the risks which the Service Manager or the Consultant has notified as an early warning matter. It includes a description of the risk and a description of the actions which are to be taken to avoid or reduce the risk. |  |  |  |  |  |
|  |  |  |  |  |  | - Secret Matter is any matter connected with this Contract, or its performance which is designated in writing by the Employer as 'Top Secret', 'Secret', or 'Confidential', and will include any information concerning the content of such matter and anything which contains or may reveal that matter. |  |  |  |  |  |
|  |  |  |  |  |  | - The Scope is information which either |  |  |  |  |  |
|  |  |  |  |  |  | - specifies and describes the services or |  |  |  |  |  |
|  |  |  |  |  |  | - states any constraints on how the Consultant Provides the Services |  |  |  |  |  |
|  |  |  |  |  |  | and is either |  |  |  |  |  |
|  |  |  |  |  |  | - in the documents which the Contract Data states it is in or |  |  |  |  |  |
|  |  |  |  |  |  | - in an instruction given in accordance with this Contract. |  |  |  |  |  |
|  |  |  |  |  |  | - or any other document forming part of this Contract. |  |  |  |  |  |
|  |  |  |  |  |  | - The Service Manager means the individual appointed by the Employer (or his nominated representative) as the responsible official for the purposes of this Contract. |  |  |  |  |  |
|  |  |  |  |  |  | - A Subconsultant is a person or organisation who has a contract with the Consultant or with a sub-consultant (of any tier) to the Consultant to provide part of the services. |  |  |  |  |  |
|  |  |  |  |  |  | - Task Order is the notification from the Employer pursuant to Clause X19. |  |  |  |  |  |
|  |  |  |  |  |  | - Theft means the Criminal Offence of Theft within the meaning of the: Theft Act 1968; the Theft Act (Northern Ireland) 1969; the Theft Act 1978; the Theft (Northern Ireland) Order 1978; and the Fraud Act 2006; or any other relevant superseding legislation which comes into force and/or within the meaning of any other applicable statutory provision or common law having application in England, Wales, Scotland or Northern Ireland. |  |  |  |  |  |
|  |  |  |  |  |  | - Transparency Information is the content of this Contract in its entirety, including from time to time agreed changes to the Contract, and details of any payments made by the Employer to the Consultant under this Contract. |  |  |  |  |  |
|  |  |  |  |  |  | - Trust Deed means the trust deed (if any) established for the operation of the Project Bank Account. |  |  |  |  |  |
|  |  |  |  |  |  | - Unsuitable Third Party means any person: - whose activities do, in the reasonable opinion of the Employer, pose or could pose a threat to national security, incompatible with any operations or activities carried out by the Employer for the purposes contemplated by this Contract or any other of the Employer’s legal duties or other functions; or - who is, in the reasonable opinion of the Employer, inappropriate because the Employer has received specific information from the Crown, the Serious Fraud Office or the Crown Prosecution Service about the suitability of the proposed new third party to act in relation to the service; or - if the service includes, or will involve the disclosure of information about a Secret Matter, who is not a List X organisation. |  |  |  |  |  |
|  |  |  |  |  |  | - Working Day means Monday to Friday excluding bank holidays. |  |  |  |  |  |
| Interpretation and |  |  | 12 |  |  |  |  |  |  |  |  |
| the law |  |  | 12.1 |  |  | In this Contract, except where the context shows otherwise, words in the singular also mean in the plural and the other way round and words in the masculine also mean in the feminine and neuter. |  |  |  |  |  |
|  |  |  | 12.2 |  |  | The Contract will be considered as a contract made in England and subject to English Law. |  |  |  |  |  |
|  |  |  | 12.3 |  |  | Without prejudice to the dispute resolution process set out in clause W1, each party hereby irrevocably submits and agrees to the exclusive jurisdiction of the Courts of England to resolve, and the laws of England to govern, any actions, proceedings, controversy or claim of whatever nature arising out of or relating to this Contract or breach thereof. |  |  |  |  |  |
|  |  |  | 12.4 |  |  | Other jurisdictions may apply solely for the purpose of giving effect to this clause and for the enforcement of any judgement, order or award given under English jurisdiction. |  |  |  |  |  |
|  |  |  | 12.5 |  |  | This Contract constitutes the entire agreement between the Parties and supersedes any previous agreement between the Parties for the services. Any services undertaken by the Consultant prior to the date of this Contract will be deemed to have been undertaken pursuant to the terms of this Contract. |  |  |  |  |  |
|  |  |  | 12.6 |  |  | References to any statutes or statutory provisions will be construed as references to the same as they may be amended from time to time amended, modified or re-enacted. |  |  |  |  |  |
|  |  |  | 12.7 |  |  | Headings or clauses and sub-clauses are for convenience only and do not affect the interpretation of this Contract. |  |  |  |  |  |
|  |  |  | 12.8 12.9 |  |  | Save as otherwise provided in this Contract the Consultant shall not be or be deemed to be an agent of the Employer and the Consultant shall not hold itself out as having authority or power to bind the Employer in any way. This Contract shall not create a partnership between the Employer and the Consultant within the meaning of the Partnership Act 1890 or any landlord and tenant relationship other than where specifically contemplated by the terms of this Contract. In this Contract: - References to ‘Framework Agreement’ mean the Framework Agreement entered into between the Employer and the Consultant dated 10th June 2014. - Words/phrases defined in the Framework Agreement shall have the same meaning in this Contract - References to ‘this Contract’ shall mean ‘Contract’ as defined in the Framework Agreement |  |  |  |  |  |
| Communications |  |  | 13 |  |  |  |  |  |  |  |  |
|  |  |  | 13.1 |  |  | Each instruction, certificate, submission, proposal, record, acceptance, notification, reply and other communication which this Contract requires is communicated in a form which can be read, copied and recorded. Writing is in the language of this Contract. |  |  |  |  |  |
|  |  |  | 13.2 |  |  | A communication (as described in clause 13.1 above) has effect when it is received at the last address notified by the recipient for receiving communications or, if none is notified, at the address of the recipient stated in the Contract Data. |  |  |  |  |  |
|  |  |  | 13.3 |  |  | Any notice or other communication whatsoever which the Employer is required or authorised by this Contract to give or make to the Consultant will, without prejudice to any other method of giving or making it, be sufficiently given or made if it is sent by post in a prepaid letter addressed to the Consultant by name at the last known place of abode or business of the Consultant and if that letter is not returned through the post undelivered, that notice or communication will be deemed for the purposes of this Contract to have been given or made at the time at which the letter would in the ordinary course of post be delivered. |  |  |  |  |  |
|  |  |  | 13.4 |  |  | The Service Manager replies to a communication submitted or resubmitted to him by the Consultant for acceptance. If his reply is not acceptance, the Service Manager states his reasons and the Consultant resubmits the communication within the period for reply taking account of these reasons. A reason for withholding acceptance may include that more information is needed in order to assess the Consultant’s submission fully. |  |  |  |  |  |
|  |  |  | 13.5 |  |  | The Service Manager may extend the period for reply to a communication if the Service Manager and the Consultant agree to the extension before the reply is due. The Service Manager notifies the Consultant of the extension which has been agreed. |  |  |  |  |  |
|  |  |  | 13.6 |  |  | The Consultant retains copies of drawings, specifications, reports and other documents which record the services for the period for retention. The copies are retained in the form stated in the Scope. |  |  |  |  |  |
|  |  |  | 13.7 |  |  | A notification which this Contract requires is communicated separately from other communications. |  |  |  |  |  |
|  |  |  | 13.8 |  |  | The Service Manager may withhold acceptance of a submission by the Consultant. Withholding acceptance for a reason stated in this Contract is not a compensation event. |  |  |  |  |  |
| Freedom of Information Act (“FOIA”) |  |  | 13A |  |  | For the purposes of this clause 13A: “Information" has the meaning given under section 84 of the (FOIA); and "Requests for Information" has the meaning set out in the FOIA or the Environmental Information Regulations as relevant (where the meaning set out for the term "request" applies). |  |  |  |  |  |
|  |  |  | 13A.1 |  |  | The Consultant acknowledges that the Employer is subject to the requirements of the code of practice on government information, the FOIA and the Environmental Information Regulations and assists and co-operates with the Employer to enable the Employer to comply with its Information disclosure obligations. |  |  |  |  |  |
|  |  |  | 13A.2 |  |  | The Consultant: - transfers to the Service Manager all Requests for Information that it receives as soon as practicable and in any event within one week of receiving a Request for Information; - provides the Service Manager with a copy of all Information in its possession, or power in the form that the Service Manager requires within five (5) Working Days (or such other period as the Service Manager may specify) of the Service Manager's request; and - provides all necessary assistance as reasonably requested by the Service Manager to enable the Employer to respond to the Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations. |  |  |  |  |  |
|  |  |  | 13A.3 |  |  | The Employer is responsible for determining in its absolute discretion (and procures that its sub-contractors do likewise) whether the Commercially Sensitive Information and/or any other Information is exempt from disclosure in accordance with the provisions of the Code of Practice on Government Information, the FOIA or the Environmental Information Regulations. |  |  |  |  |  |
|  |  |  | 13A.4 |  |  | The Consultant does not respond directly to a Request for Information unless expressly authorised to do so by the Employer. |  |  |  |  |  |
|  |  |  | 13A.5 |  |  | The Consultant acknowledges that the Employer may be obliged under the FOIA, or the Environmental Information Regulations to disclose information concerning the Consultant or the service without consulting the Consultant or having taken their views into account. Where the Employer does not consult with the Consultant, the Employer takes reasonable steps, where appropriate, to give the Consultant advanced notice or draws the disclosure to the Consultant’s attention after any such disclosure. |  |  |  |  |  |
|  |  |  | 13A.6 |  |  | The Consultant ensures that all Information is retained for disclosure in accordance with DIO DOC 12 (Commercially Sensitive Information) and permits the Service Manager and/or the Employer to inspect such records as requested from time to time. |  |  |  |  |  |
|  |  |  | 13A.7 |  |  | The Consultant acknowledges that the Commercially Sensitive Information listed in DIO DOC 12 (Commercially Sensitive Information) is of indicative value only and that the Employer may be obliged to disclose Information, with or without consultation. |  |  |  |  |  |
| Disclosure of Information |  |  |  | 13B |  |  |  |  |  |  |  |
|  |  |  |  | 13B.1 |  | Subject to clauses 13B.4, 13B.5 and 13B.6 each Party: |  |  |  |  |  |
|  |  |  |  |  |  | - will treat in confidence all Information it receives from the other; - will not disclose any of that Information to any third party without the prior written consent of the other Party, which consent will not unreasonably be withheld, except that the Consultant may disclose Information in confidence, without prior consent, to such persons and to such extent as may be necessary for the performance of this Contract; - will not use any of that Information otherwise than for the purpose of the Contract; and - will not copy any of that Information except to the extent necessary for the purpose of exercising its rights of use and disclosure under this Contract provided that: the Consultant hereby gives irrevocable consent for the Employer to disclose any Information it receives from the Consultant (including Confidential Information) and the details of this Contract: - to any party which has been invited by the Employer to submit a tender for appointment as the Employer’s SBP as described in Clause 19 so far as necessary for the purpose of preparing the tender; - to any party appointed as the Employer’s SBP as described in Clause 19 so far as necessary for the purpose of enabling that party to act as the SBP; - to the Incorporated Entity as described in Clause 19 so far as necessary for the purpose of enabling the Incorporated Entity to manage this Contract; - to any party appointed as Service Manager in respect of this Contract so far as necessary for the purpose of enabling the Service Manager to carry out the activities and tasks to be undertaken by the Service Manager under this Contract and provided further that the Consultant hereby agrees upon receipt of notice from the Employer to disclose any Information (including Confidential Information) which the Contractor is required to disclose to the Employer under the terms of this Contract: - to any party which has been invited by the Employer to submit a tender for appointment as the Employer’s SBP as described in Clause 19 so far as necessary for the purpose of preparing the tender; - to any party appointed as the Employer’s SBP as described in Clause 19 so far as necessary for the purpose of enabling that party to act as the SBP; - to the Incorporated Entity as described in Clause 19 so far as necessary for the purpose of enabling the Incorporated Entity to manage this Contract; - to any party appointed as Service Manager in respect of this Contract so far as necessary for the purpose of enabling the Service Manager to carry out the activities and tasks to be undertaken by the Service Manager under this Contract |  |  |  |  |  |
|  |  |  |  | 13B.2 |  | The Consultant will take all reasonable precautions necessary to ensure that all Information disclosed to the Consultant by or on behalf of the Employer under or in connection with this Contract: |  |  |  |  |  |
|  |  |  |  |  |  | a) is disclosed to Personnel only to the extent necessary for the performance of this Contract; and b) is treated in confidence by them and not disclosed except with prior written consent or used otherwise than for the purpose of performing the services or having work performed for the Employer under this Contract or any sub-contract under it. |  |  |  |  |  |
|  |  |  |  | 13B.3 |  | The Consultant will ensure that his Personnel are aware of his arrangements for discharging the obligations at clauses 13B.1 and 13B.2 before they receive Information and will take such steps as may be reasonably practical to enforce such arrangements. |  |  |  |  |  |
|  |  |  |  | 13B.4 |  | The restrictions contained in Clauses 13B.1 and 13B.2 will not apply to any Information to the extent that either Party: |  |  |  |  |  |
|  |  |  |  |  |  | - exercises rights of use or disclosure granted otherwise than in consequence of, or under, this Contract; - has the right to use or disclose the Information in accordance with other conditions of the Contract; or - can show: - that the Information was or has become published or publicly available for use otherwise than in breach of any provision of this Contract or any other agreement between the Parties; - that the Information was already known to it (without restrictions on disclosure or use) prior to it receiving it under or in connection with this Contract; - that the Information was received without restriction on further disclosure from a third party who lawfully acquired it and who is himself under no obligation restricting its disclosure; or - from its records that the same information was derived independently of that received under or in connection with this Contract; provided the relationship to any other Information is not revealed. |  |  |  |  |  |
|  |  |  |  | 13B.5 |  | Neither Party will be in breach of this clause where it can show that any disclosure of Information was made solely and to the extent necessary to comply with a statutory, judicial or parliamentary obligation. Where such a disclosure is made, the Party making the disclosure will ensure that the recipient of the Information is made aware of and asked to respect its confidentiality. Such disclosure will in no way diminish the obligations of the Parties under this clause. |  |  |  |  |  |
|  |  |  |  | 13B.6 |  | The Employer will not be in breach of this Contract where it can show that any disclosure of Information is made solely and to the extent necessary to comply with the FOIA or the Environmental Information Regulations. To the extent permitted by the time for compliance under the FOIA or the Environmental Information Regulations, the Employer will consult the Consultant where the Employer is considering the disclosure of Information under the FOIA or the Environmental Information Regulations and, in any event, will provide prior notification to the Consultant of any decision to disclose the Information. The Consultant acknowledges and accepts that its representations on disclosure during consultation may not be determinative and that the decision whether to disclose Information in order to comply with the FOIA or the Environmental Information Regulations is a matter in which the Employer will exercise its own discretion, subject always to the provisions of the FOIA or the Environmental Information Regulations. For the avoidance of doubt, nothing in this clause will affect the Consultant’s rights at law. |  |  |  |  |  |
|  |  |  |  | 13B.7 |  | Nothing in this clause will affect the Parties' obligations of confidentiality where information is disclosed orally in confidence. |  |  |  |  |  |
|  |  |  |  | 13B.8 |  | The Consultant will take every precaution to ensure that information about the Contract, or arising from or connected with this Contract, is divulged only to the minimum number of employees and then only to the extent essential to each person's action in carrying out this Contract. The Consultant will not in any circumstances allow access by employees to general information not relating to the Establishment with which such employee is personally concerned. No information regarding the services being provided under the Contract or facilities to photograph or film will be given or permitted by the Consultant except with prior written permission of the Employer. |  |  |  |  |  |
|  |  |  |  | 13B.9 |  | The Consultant will not communicate with representatives of the general and technical press, radio, television or other communications media unless specifically granted permission to do so in writing by the Employer. |  |  |  |  |  |
|  |  |  |  | 13B.10 |  | The Consultant will fully indemnify the Employer, his servants or agents against the costs of dealing with any claims made in respect of information subject to the Data Protection Act 1998 which claims would not have arisen but for some act, omission or negligence on the part of the Consultant, his servants, agents, suppliers or any other person under his control. |  |  |  |  |  |
| The Service Manager |  |  | 14 |  |  |  |  |  |  |  |  |
|  |  |  | 14.1 |  |  | The Service Manager’s acceptance of a communication from the Consultant or of his work does not change the Consultant’s responsibility to Provide the Services or his liability for compliance with the terms of this Contract. |  |  |  |  |  |
|  |  |  | 14.2 |  |  | The Service Manager, after notifying the Consultant, may delegate any of his actions and may cancel any delegation. A reference to an action of the Service Manager in this Contract includes an action by his delegate. In the event of any misunderstanding and/or clarification as regards the authority or areas of responsibility of a delegate, the Consultant may serve a written notice of clarification upon the Service Manager. Within 14 Working Days thereafter the Service Manager shall answer in writing the Consultant’s notice of clarification. |  |  |  |  |  |
|  |  |  | 14.3 |  |  | The Service Manager may give an instruction, in accordance with the Change Management Process, to the Consultant which changes the Scope (including, but not limited to, ordering additional services). This does not constitute a compensation event in accordance with clause 60.1 but the effect on the Prices (if any) will be determined in accordance with Clause 19L (Change Management Process) and if the Employer wishes to proceed with the change the Service Manager shall issue a Task Order in accordance with clause X19. |  |  |  |  |  |
|  |  |  | 14.4 |  |  | The Employer may replace the Service Manager after he has notified the Consultant in writing of the name of the replacement. |  |  |  |  |  |
| Early warning |  |  | 15 |  |  |  |  |  |  |  |  |
|  |  |  | 15.1 |  |  | The Employer and the Consultant give an early warning by notifying the other as soon as either becomes aware of any matter which could |  |  |  |  |  |
|  |  |  |  |  |  | - Impact the total of the Prices, |  |  |  |  |  |
|  |  |  |  |  |  | - delay Completion, |  |  |  |  |  |
|  |  |  |  |  |  | - change the Accepted Programme, |  |  |  |  |  |
|  |  |  |  |  |  | - delay meeting a Key Date, |  |  |  |  |  |
|  |  |  |  |  |  | - impair the effectiveness of the services or |  |  |  |  |  |
|  |  |  |  |  |  | - affect the work of the Employer, an Employer’s contractor or another consultant. |  |  |  |  |  |
|  |  |  |  |  |  | The Consultant may give an early warning by notifying the Service Manager of any other matter which could increase the total of the Prices. The Consultant enters early warning matters in the Risk Register. Early warning of a matter for which a compensation event has previously been notified is not required. |  |  |  |  |  |
|  |  |  | 15.2 |  |  | In general, early warnings notified in accordance with clause 15.1 will be considered on a monthly basis at risk reduction meetings as detailed in DIO DOC 55. Notwithstanding any monthly meetings, either the Service Manager or the Consultant may instruct, given at least two (2) Working Days notice has been provided, the other to attend a risk reduction meeting. Each may instruct other people to attend if the Service Manager agrees but for the avoidance of doubt the Consultant will be deemed to have agreed to the attendance of the Employer at any such risk reduction meetings. |  |  |  |  |  |
|  |  |  | 15.3 |  |  | At a risk reduction meeting, those who attend co-operate in |  |  |  |  |  |
|  |  |  |  |  |  | - making and considering proposals for how the effect of the registered risks can be avoided or reduced, |  |  |  |  |  |
|  |  |  |  |  |  | - seeking solutions that will bring advantage to all those who will be affected, |  |  |  |  |  |
|  |  |  |  |  |  | - deciding on the actions which will be taken and who, in accordance with this Contract, will take them and |  |  |  |  |  |
|  |  |  |  |  |  | - deciding which risks have now been avoided or have passed and can be removed from the Risk Register. |  |  |  |  |  |
|  |  |  | 15.4 |  |  | The Consultantrevises the Risk Register to record the decisions made at each risk reduction meeting and issues the revised Risk Register for the approval of the Service Manager. If a decision needs a change to the Scope, the Service Manager instructs the change as soon as reasonably possible in accordance with the Change Management Process. No decision taken at a risk reduction meeting and/or change to the Risk Register will operate to change the contractual allocation of risk hereunder or the obligations of the Employer or the Service Manager or a Head of Establishment, unless specifically instructed otherwise in writing by the Service Manager. |  |  |  |  |  |
| Ambiguities and |  |  | 16 |  |  |  |  |  |  |  |  |
| inconsistencies |  |  | 16.1 |  |  | The Service Manager or the Consultant notifies the other as soon as either becomes aware of any mistake, inaccuracy, discrepancy or omission in the design of the services or in the Scope or any other document forming part of this Contract. The Service Manager gives an instruction as to how the mistake, inaccuracy, discrepancy or omission is to be dealt with. Compliance with such an instruction by the Consultant shall not constitute a compensation event where the instruction relates to any mistake, inaccuracy, discrepancy or omission in the design of the services or in any part of the Scope or any other document forming part of this Contract which was provided by the Consultant. |  |  |  |  |  |
| Illegal and impossible |  |  | 17 |  |  |  |  |  |  |  |  |
| requirements |  |  | 17.1 |  |  | The Consultant notifies the Service Manager as soon as he considers that the Scope requires him to do anything which is illegal or impossible. If the Service Manager agrees, he gives an instruction to change the Scope appropriately. |  |  |  |  |  |
| Assignment |  |  | 18 |  |  |  |  |  |  |  |  |
|  |  |  | 18.1 |  |  | The Consultant will not give, bargain, sell assign, or otherwise dispose of the Contract or any part thereof, or the benefit or advantage of the Contract or any part thereof, without the previous consent in writing of the Employer. The Employer may assign the benefit of the whole or any part of the Contract at any time without the prior consent of the Consultant. |  |  |  |  |  |
| Transformation |  |  | 19 |  |  |  |  |  |  |  |  |
|  |  |  | 19.1 |  |  | The Employer is currently carrying out a transformation programme, as part of which it intends to appoint a strategic business partner (“SBP”) to manage the delivery function of the current Defence Infrastructure Organisation. As part of this transformation programme the delivery function may be transferred into a separate legal entity (the “Incorporated Entity”), which will be managed by the SBP, and which may be granted responsibility by the Employer for managing this Contract. The Employer reserves the right at any time to: - appoint a third party to act as the Employer’s SBP, which role shall include managing the delivery function of the Employer; and - transfer the Employer’s delivery function to the Incorporated Entity, in which case the Incorporated Entity may be made responsible for managing this Contract. In the event of any of the above circumstances, the Employer will notify the Consultant of the identity of the SBP or Incorporated Entity and the scope of the SBP or Incorporated Entity’s authority to act. |  |  |  |  |  |
| Change of Control |  |  |  | 19A |  |  |  |  |  |  |  |
|  |  |  |  | 19A.1 |  | The Consultant will inform the Employer, as soon as practicable, in writing of any material Change in Control of the Consultant. The Consultant will not be required to submit any advice which is unlawful or is in breach of either any pre-existing non-disclosure agreement or any regulations governing the conduct of the Consultant in the UK or other jurisdictions where the Consultant may be subject to legal sanction arising from issue of such advice. |  |  |  |  |  |
|  |  |  |  | 19A.2 |  | For the purposes of this clause ‘control’ means the power of a person to secure that the affairs of the Consultant are conducted in accordance with the wishes of that person: - by means of the holding of shares, or the possession of voting powers in, or in relation to, the Consultant; or - by virtue of any powers conferred by the constitutional or corporate documents, or any other document, regulating the Consultant and a material Change of Control occurs if a person who controls the Consultant ceases to do so or if another person acquires control of the Consultant. |  |  |  |  |  |
|  |  |  |  | 19A.3 |  | The Consultant will inform the Employer on each occurrence of a material change in control. Each advice will be taken to be in respect of all contracts with the Employer. The advice should be submitted to: Mergers and Acquisitions Section Directorate of Supplier Relations Ash 1 #3103 Ministry of Defence Abbey Wood Bristol BS34 8JH |  |  |  |  |  |
|  |  |  |  | 19A.4 |  | Where the material Change of Control is to an Unsuitable Third Party or where the Consultant is in breach of the provisions of this clause 19A, the Employer may terminate the Consultant’s employment under clause 90 of this Contract at any time. |  |  |  |  |  |
|  |  |  |  | 19A.5 |  | Advice by the Consultant of any material change of control will not prejudice the existing rights of the Employer or the Consultant under the Contract nor create or imply any rights of either the Consultant or the Employer additional to the Employer’s right to receive that information. |  |  |  |  |  |
| Waiver |  |  |  | 19B |  |  |  |  |  |  |  |
|  |  |  |  | 19B.1 |  | No act or omission of either Party will by itself amount to a waiver of any right or remedy unless expressly stated by that Party in writing. In particular, no reasonable delay in exercising any right or remedy, will by itself constitute a waiver of that right or remedy. |  |  |  |  |  |
|  |  |  |  | 19B.2 |  | No waiver in respect of any right of remedy will operate as a waiver in respect of any other right or remedy. |  |  |  |  |  |
| Severability |  |  |  | 19C |  |  |  |  |  |  |  |
|  |  |  |  | 19C.1 |  | If any provision of this Contract is held to be invalid, illegal or unenforceable to any extent then: - such provision will (to the extent it is invalid, illegal or unenforceable) be given no effect and will be deemed not to be included in the Contract but without invalidating any of the remaining provisions of the Contract; and - the Parties will use all reasonable endeavours to replace the invalid, illegal or unenforceable provision by a valid, legal and enforceable substitute provision the effect of which is as close as possible to the intended effect of the invalid, illegal or unenforceable provision. |  |  |  |  |  |
| Third Party Rights |  |  |  | 19D |  |  |  |  |  |  |  |
|  |  |  |  | 19D.1 |  | Except as provided in clause 19D.2 and notwithstanding anything to the contrary elsewhere in the Contract, no right is granted to any person who is not a party to the Contract to enforce any term of the Contract in his own right and the Parties to the Contract declare that they have no intention to grant any such right. |  |  |  |  |  |
|  |  |  |  | 19D.2 |  | Where, and only where, a clause in this Contract expressly states that a third party will be entitled to enforce a term of this Contract: - the said third party will be entitled to enforce that term in his own right; - the Consultant will inform the said third party as soon as is reasonably practicable of the existence of the relevant right together with any other terms (including the terms of this clause) relevant to the exercise of that right; and - the third party's rights will be subject to any provision in the Contract that provides for the submission of disputes under the Contract generally or the said rights in particular to arbitration (such as in Secondary Option W). The Parties’ rights to rescind or agree any variation under this Contract are not subject to the consent of any other party. |  |  |  |  |  |
| Recovery of Sums Due |  |  |  | 19E |  |  |  |  |  |  |  |
|  |  |  |  | 19E.1 |  | Whenever under the Contract any sum of money will be recoverable from or payable by the Consultant, the same may be deducted from any sum then due or which at any time thereafter may become due to the Consultant under the Contract, or under any other contract with the Employer or with the Crown and/or such sum may be recoverable by the Employer from the Consultant as a debt. |  |  |  |  |  |
| Decoupling clause |  |  |  | 19F |  |  |  |  |  |  |  |
|  |  |  |  | 19F.1 |  | If the Consultant will enter into any other contract with the Crown relating in any way to the subject matter of the Contract, then, no breach by the Crown of that other contract nor any other act or omission nor any written or oral statement nor any representation whatsoever of or by the Crown its servants or agents or other consultants relating to or connected with any other contracts as aforesaid will, regardless of any negligence on its part or their part: - give the Consultant any right under the Contract to a compensation event or any other relief or remedy whatsoever against the Employer; or - affect, modify, reduce or extinguish either the obligations of the Consultant or the rights or remedies of the Employer or - be taken to amend, add to, delete or waive any term or condition of the Contract. |  |  |  |  |  |
| Publicity |  |  |  | 19G |  |  |  |  |  |  |  |
|  |  |  |  | 19G.1 |  | The Consultant may publicise the services only with the Employer’s written agreement. |  |  |  |  |  |
|  |  |  |  | 19G.2 |  | The Consultant will take all reasonable steps to ensure that the Consultant’s Personnel do not publicise the services other than in accordance with clause 19G.1. |  |  |  |  |  |
| Audit |  |  |  | 19H |  | In addition to any other rights under the Contract, the Employer and its agents may at any time and without notice audit the books and records being maintained by the Consultant whilst undertaking this Contract, including those books and records relating to any costs and expenses incurred by the Consultant or charged to the Employer and including those books and records being maintained by the Consultant's subconsultants. |  |  |  |  |  |
| Fraud and prevention of corruption |  |  |  | 19I |  |  |  |  |  |  |  |
|  |  |  |  | 19I.1 |  | Further to the requirements of DIO DOCs 33-38, Fraud sections, the Consultant will maintain a robust Fraud Prevention and Ethics policy, which concurs with the Employer’s zero tolerance regimes with regard to Fraud and Theft. |  |  |  |  |  |
|  |  |  |  | 19I.2 |  | The Consultant will produce and maintain a fraud risk register of potential fraud and theft risks to this Contract and show what controls they propose to address the risks identified. This is to be reviewed and updated annually from the date of this Contract until the completion date. |  |  |  |  |  |
|  |  |  |  | 19I.3 |  | The Consultant will provide the Service Manager with a programme and details of fraud awareness training which is to be provided to the Consultant’s Personnel or any other persons under his control at regular intervals. Training is to clearly show what is expected from them to fulfil the Fraud prevention measures under this Contract. |  |  |  |  |  |
|  |  |  |  | 19I.4 |  | The Consultant warrants that in entering this Contract he has not committed any Fraud and will have a robust Fraud prevention and ethics policy which concurs with the Employer’s zero tolerance regime with regard to Fraud and Theft. |  |  |  |  |  |
|  |  |  |  | 19I.5 |  | The Consultant will procure that his Subconsultants are under equivalent contractual obligations as are set out in this clause 19I and will take all practicable steps to prevent Fraud or the risk of Fraud arising and will disclose the relevant provisions within the sub-contracts upon request by the Employer. |  |  |  |  |  |
|  |  |  |  | 19I.6 |  | The Consultant warrants that he has read, and that his Personnel will comply with the detailed anti-fraud measures and recommendations set out within the Fraud Prevention Manual (DIO DOC 33), MOD Fraud, Theft, Corruption, Bribery and Irregularity Policy(DIO DOC 36) and the MOD Fraud Response Procedure(DIO DOC 38) hereto and upon entering into this Contract will circulate copies of the said Manual/Policies to each and every member of his Personnel at any time engaged in relation to this Contract. |  |  |  |  |  |
|  |  |  |  | 19I.7 |  | The Consultant will, in complying with the measures and recommendations contained within The Fraud Prevention Manual(DIO DOC 33), keep and maintain all relevant records, invoices, approvals, notes, minutes of meetings and all such other original Contract documents as may be required to verify work carried out by the Consultant and his Subconsultants so that they may be provided to the Employer upon request. |  |  |  |  |  |
|  |  |  |  | 19I.8 |  | The Consultant will, in accordance with MOD Fraud Prevention Manual (DIO DOC 33), carry out an internal audit on a period not greater than 6 monthly basis in respect of this Contract. Where the Consultant or its parent is a PLC the audit committee of the Consultant or PLC Company will manage and be responsible for such audit. Where the Consultant is a Joint Venture company, or a non-PLC, that company or Joint Venture Company will be set an audit committee to manage and be responsible for such audit. The audit committee will: - Report to the Employer in respect of the standards achieved in the audit; - Notify the Employer of any fraud identified in any internal or external audit; and - Make recommendations to the Employer as to what measures should be taken to improve fraud prevention and forward an action plan to show recommendations are put in place and ensure that these are acted upon. |  |  |  |  |  |
|  |  |  |  | 19I.9 |  | Without prejudice to clause 13B (Disclosure of Information) and clause 26G (Security Measures), the Consultant will immediately report to the Employer any circumstances giving rise to Fraud within his own organisation, that of his Subconsultants or the Employer or otherwise in relation to this Contract and will provide all such relevant information which may assist the Employer in dealing with such report efficiently and effectively. |  |  |  |  |  |
|  |  |  |  | 19I.10 |  | The Consultant will immediately report to the Employer any act or omission, whether fraudulent, inadvertent or accidental which has resulted or could result in the Employer being charged for work and/or services which have not been carried out. |  |  |  |  |  |
|  |  |  |  | 19I.11 |  | The Employer shall be entitled to terminate all or part of the Consultant’s employment under this Contract in accordance with clause 90 (Termination) in the event that the Consultant, any of its Subconsultants, any of its Personnel or any other party for whom it is responsible commits an act of Fraud or Theft. |  |  |  |  |  |
|  |  |  |  | 19I.12 |  | The Consultant will fully co-operate and comply with any investigations and enquiries initiated by the Employer, the Defence Fraud Unit, the National Audit Office, the Police, or any other organisation identified by the Employer and/or any organisation acting on behalf of them. The Consultant will procure that his sub-contracts contain the same provisions, extracts of which are to be provided upon request by the Employer. |  |  |  |  |  |
|  |  |  |  | 19I.13 |  | The Employer will be entitled to set-off, deduct, abate or recover as a debt against the Consultant all monies and losses howsoever arising in connection with or sustained as a consequence of Fraud including all associated investigation costs. |  |  |  |  |  |
|  |  |  |  | 19I.14 |  | Any Fraud related actions under this clause 19l may be brought by the Employer or such other appropriate body by civil or criminal proceedings. Such proceedings will be brought in the English courts unless the Parties otherwise agree. |  |  |  |  |  |
| Timescales |  |  |  | 19J |  | The Parties act within such timescales as may be reasonable in all the circumstances where this Contract does not provide for a specific timescale |  |  |  |  |  |
| Amendments to Contract |  |  |  | 19K |  |  |  |  |  |  |  |
|  |  |  |  | 19K.1 |  | The terms and conditions of this Contract may not be amended except by the written agreement of the duly authorised representatives of the Parties. |  |  |  |  |  |
|  |  |  |  | 19K.2 |  | The written agreement of the Parties will be obtained only by: - serially numbered amendment being issued to the Consultant by the Employer. The amendment will come into force only when the Consultant has despatched to the Employer on a DEFFORM 10B an unqualified acceptance of the Employer's offer; or - the despatch by the Employer of a serially numbered amendment letter as an unqualified acceptance of an offer from the Consultant. |  |  |  |  |  |
|  |  |  |  | 19K.3 |  | Any purported amendment to the terms and conditions of this Contract which does not satisfy the terms of this Condition will be of no effect. |  |  |  |  |  |
|  |  |  |  | 19K.4 |  | Any changes of the Scope may only be made in accordance with the Change Management Process and the issue of a Task Order in accordance with clause X19. |  |  |  |  |  |
|  |  |  |  | 19K.5 |  | If the scope of the services are reduced the Employer shall be free to appoint another consultant to carry out any part of the services that has been so removed. |  |  |  |  |  |
| Change Management Process |  |  |  | 19L |  |  |  |  |  |  |  |
|  |  |  |  | 19L.1 |  | Either the Employer or the Consultant may propose changes to the Scope on the change proposal/demand order form at DIO DOC 25. If the Consultant proposes a change he shall also provide the Service Manager with a statement containing the following supporting information: - the reason for the proposed change; |  |  |  |  |  |
|  |  |  |  | 19L.2 |  | Where changes to the Scope are proposed by either the Employer or the Consultant, the Consultant shall provide: - the effect and/or impact, if any, which the change might have on the Consultant’s performance of this Contract; - estimates of the costs and/or the time involved in, or required for effecting the change; - confirmation and clarification where appropriate of how the Consultant proposed change would be of significant benefit to the Employer; - any other data or information whether financial or otherwise that the Service Manager may reasonably require in order to decide whether or not to authorise the Consultant to proceed with the change; - (where relevant) confirmation as to how the proposed change will affect any interface contracts (in particular any Defcon 2000, Standalone Prime or Regional Prime Contracts), operating simultaneously during the course of the services. |  |  |  |  |  |
|  |  |  |  | 19L.3 |  | Before a change to the Scope proposed by either the Employer or Consultant can be approved, the Consultant shall submit a Consultant’s Task Order containing a quotation of the changes to the Prices and an estimate of the delay to any Completion Date. |  |  |  |  |  |
|  |  |  |  | 19L.4 |  | In the quotation the Consultant shall use the rates and prices contained in the Price List to calculate the changes to the Prices. The format of the Task Order shall be as detailed on the change proposal/demand order form at DIO DOC 25. |  |  |  |  |  |
|  |  |  |  | 19L.5 |  | Exceptionally, where the Consultant can demonstrate to the entire satisfaction of the Employer that the rates and prices contained in the Price List are not appropriate for pricing the proposed change, the Consultant shall submit his proposed revision to the Prices and the Price List on an alternative basis. In such exceptional circumstances, the Consultant must demonstrate to the complete satisfaction of the Employer that the rates and prices quoted are the most advantageous available and represent value for money for the Employer. |  |  |  |  |  |
|  |  |  |  | 19L.6 |  | It shall be a condition precedent that for the Consultant to recover rates and prices different to those contained in the Price List he shall have fully complied with clause 19L.5 above and that the Employer shall have accepted in writing any such alternative rates or prices, prior to any further services and/or any consequent adjustments for the change being carried out under such alternative rates or prices. |  |  |  |  |  |
|  |  |  |  | 19L.7 |  | Upon receiving the Consultant’s Task Order, the Employer shall be entitled to reject, accept the same or negotiate with the Consultant with a view to reaching an agreement on any adjustment to the Contract. |  |  |  |  |  |
|  |  |  |  | 19L.8 |  | If the rates or prices cannot be agreed the Consultant or Employer shall be entitled to resolve the matter in accordance with clause W1 within 10 Working Days of a dispute arising after which time no challenge to the adjustments proposed by the Employer shall be capable of being made. The Employer shall have discretion whether or not to proceed with and approve the change following any determination in accordance with the dispute procedure. |  |  |  |  |  |
|  |  |  |  | 19L.9 |  | The Employer may call a meeting with the Consultant to discuss any changes proposed by the Consultant. |  |  |  |  |  |
| Negative Covenants |  |  |  | 19M |  |  |  |  |  |  |  |
|  |  |  |  |  |  | - Unless the Consultant shall have obtained the prior written consent of the Employer, the Consultant shall not (or, to the extent the same is within his control, shall not permit any person to): - Create, incur, assume or permit to exist any lien upon the Establishment or any other Affected Property or any part thereof, or upon any property of the Employer; - Sell, lease, assign, transfer or otherwise dispose of any of the Employer 's property (including all property owned, hired or used by the Employer); - Cause the Employer to be, or to become, responsible or liable for obligations of any other person; - Settle or compromise any action or claim or institute any proceedings, suits or litigation for or on behalf of the Employer. |  |  |  |  |  |
| The Employer’s |  |  |  | 20 |  |  |  |  |  |  |  |
| obligations |  |  |  | 20.1 |  | The Employer does not give an instruction to the Consultant which would require him to act in a way that was outside his professional code of conduct. |  |  |  |  |  |
|  |  |  |  | 20.2 |  | Subject to clause 21.6 the Service Manager shall provide copies of any relevant documents, or relevant portions of documents, as well as technical, operational and other information to the extent reasonably available to the Employer and to the extent necessary, in the opinion of the Service Manager, for the performance by the Consultant of his obligations under this Contract. |  |  |  |  |  |
| Providing the Services |  |  |  | 21 |  |  |  |  |  |  |  |
|  |  |  |  | 21.1 |  | The Consultant Provides the Services in accordance with the Scope and the other applicable clauses of this Contract (including but not limited to, complying with the Accepted Plan and (where applicable) the ESTS for each Establishment). |  |  |  |  |  |
|  |  |  |  | 21.2 |  | In Providing the Services, the Consultant minimises the interference caused to the Affected Property and the activities taking place in it. |  |  |  |  |  |
|  |  |  |  | 21.3 |  | - Without prejudice to any obligation of the Consultant contained anywhere in any document forming part of this Contract (including the Scope) the Consultant warrants and undertakes that: - the services have been or will be carried out and completed exercising the reasonable skill care and diligence to be expected of a properly qualified and competent consultant of the relevant discipline experienced in the provision of like services to the services for projects of an equivalent type, size, scope and complexity to the project to which the services relate; - he shall comply and shall ensure that his Personnel and Subconsultants comply with any general or local Act of Parliament, any instrument rule or order made under any Act of Parliament, regulations and bylaws of any local or other statutory authority and any European Directive and/or regulation (referred to in the Contract documents as the "Statutory Requirements") throughout the duration of this Contract. In the event of the Consultant failing to comply with any Statutory Requirements, he shall keep the Employer indemnified against all penalties and liabilities of every kind. For the avoidance of doubt, the Employer may set off any such liabilities against payments. |  |  |  |  |  |
|  |  |  |  | 21.4 |  | The Consultant warrants that he has and his Personnel and Subconsultants have the experience and resources To Provide the Services (including where relevant the design of the services) and has/have experience of, and has/have provided services of a similar in size, scope, duration and complexity as the services. |  |  |  |  |  |
|  |  |  |  | 21.5 |  | The Consultant will be deemed to have fully acquainted himself with the Affected Property and to have obtained all the same information as to risks, contingencies and all other circumstances which may influence or affect the services and no failure on the part of the Consultant to discover or foresee any such condition, risk, contingency or circumstances (whether the same ought reasonably to have been discovered or foreseen or not) will entitle the Consultant to an addition to the Prices or to claim indemnities or otherwise any additional sum. |  |  |  |  |  |
|  |  |  |  | 21.6 |  | - The Consultant will not be entitled to rely upon any survey, report or other document prepared by or on behalf of the Employer (including the Scope) regarding any such matter as is referred to in this clause and the Employer makes no representation or warranty as to the accuracy or completeness of any such survey, report or document (including the Scope) or any representation or statement whether negligently or otherwise made therein. |  |  |  |  |  |
|  |  |  |  | 21.7 |  | [not used] |  |  |  |  |  |
|  |  |  |  | 21.8 |  | - The Consultant will provide continual supervision of the services and perform and provide everything necessary for the organisation and co-ordination of the services between its Personnel and Others. |  |  |  |  |  |
|  |  |  |  | 21.9 |  | - The Consultant designs the parts of the services that the Scope states he is to design. |  |  |  |  |  |
|  |  |  |  | 21.10 |  | The Consultant shall submit the particulars of his design to the Service Manager within the period or periods stated in the Scope or (if no such period or periods are stated) within a period which will reasonably allow the Service Manager to raise queries. |  |  |  |  |  |
|  |  |  |  | 21.11 |  | The Service Manager may raise such questions as it requires for the purpose of considering whether the design submitted to the Service Manager in accordance with clause 21.10 is in accordance with the Scope or any other requirement of this Contract. |  |  |  |  |  |
|  |  |  |  | 21.12 |  | The Consultant shall respond promptly to any comments made or questions raised by the Service Manager in relation to any design particulars submitted by the Consultant. |  |  |  |  |  |
|  |  |  |  | 21.13 |  | Notwithstanding any queries raised or comments made by the Service Manager under clause 21.11 or any other provision to the contrary in this Contract, the Consultant accepts entire responsibility for the design of the services (including all design work prepared before or after the date hereof (and whether carried out by or on behalf of the Employer or the Consultant)), all designs contained in the Scope and/or contained in any other document forming part of this Contract and for any mistake, inaccuracy, omission or discrepancy in such design or such documents. |  |  |  |  |  |
|  |  |  |  | 21.14 |  | Nothing in this clause 21 or any other provision of this Contract shall relieve the Consultant of any liability under this Contract for any defect in the services or for any inconsistency between any design documents and no design shall be deemed to satisfy the requirements of this Contract by virtue of having been submitted to and/or considered by the Service Manager (or Employer) pursuant to the terms of this clause 21. |  |  |  |  |  |
| People |  |  |  | 22 |  |  |  |  |  |  |  |
|  |  |  |  | 22.1 |  | The Head of Establishment will provide such available administrative and technical facilities for the Consultant's Personnel employed at an Establishment for the purpose of the Contract as may in his/her opinion be necessary for the effective and economical discharge of work under the Contract. These facilities will be provided free of charge unless otherwise stated in the Contract. The status to be accorded to the Consultant's Personnel for messing purposes will be at the discretion of the Head of Establishment. |  |  |  |  |  |
|  |  |  |  | 22.2 |  | Any land or premises (including compound and temporary buildings) made available to the Consultant by the Employer in connection with the Contract will be made available to the Consultant free of charge, unless otherwise stated in the Contract, and will be used by the Consultant solely for the purposes of performing the Contract. The Consultant will have the use of such land or premises as licensee and will vacate the same upon completion of the Contract. Any utilities required by the Consultant will be subject to the charges set out in this Contract. |  |  |  |  |  |
|  |  |  |  | 22.3 |  | All fittings, equipment and consumables provided free of charge by the Employer to the Consultant or for use by the Consultant will be solely for the purposes of performing this Contract and will remain vested in the name of the Employer. |  |  |  |  |  |
|  |  |  |  | 22.4 |  | The Consultant will have no claim against the Employer for any additional cost or delay occasioned by the closure for holidays of Establishments, where this is made known to him prior to entering into this Contract. |  |  |  |  |  |
|  |  |  |  | 22.5 |  | Without prejudice to the provisions of Section 8 the Consultant will, except as otherwise provided for in this Contract, make good or, at the option of the Employer, pay compensation for all damage occurring to government property, which includes land and buildings, occasioned by the Consultant or the Consultant’s Personnel, arising from his or their presence on a an Establishment in connection with the Contract. |  |  |  |  |  |
|  |  |  |  | 22.6 |  | The Consultant will submit in writing to the Employer for approval, initially and as necessary from time to time, a list of those of his Personnel who may need to enter an Establishment for the purpose of, or in connection with, work under the Contract, giving such particulars as the Employer may require, including full details of birthplace and parentage of any such Personnel who: a) was not born in the United Kingdom; or b) if he was born in the United Kingdom, was born of parents either or both of whom were not born in the United Kingdom. |  |  |  |  |  |
|  |  |  |  | 22.7 |  | The Employer will issue passes for those Personnel who are approved by it in accordance with this clause 22.7 for admission to a Government Establishment and Personnel will not be admitted unless in possession of such a pass. Passes will remain the property of the Employer and will be surrendered on demand or on completion of the work. |  |  |  |  |  |
|  |  |  |  | 22.8 |  | Notwithstanding the provisions of clauses 22.6 and 22.7 if, in the opinion of the Employer, any of the Consultant’s Personnel will misconduct himself, or it will not be in the public interest for any person to be employed or engaged by the Consultant, the Consultant will remove such person without delay on being required to do so and will cause the work to be performed by such other person as may be necessary (provided always that any such removal or replacement of any of the Consultant’s Personnel will not constitute a compensation event and the cost of compliance with any instruction in relation to the same will be borne by the Consultant). |  |  |  |  |  |
|  |  |  |  | 22.9 |  | The decision of the Employer upon any matter arising under clauses 22.7, 22.8 or 22.11 will be final and conclusive and without any liability to the Employer. |  |  |  |  |  |
|  |  |  |  |  | 22.10 | The Consultant either employs each key person named to do the job for him stated in the Contract Data or employs a replacement person who has been accepted by the Employer. The Consultant submits the name, relevant qualifications and experience of a proposed replacement person to the Employer for acceptance. A reason for not accepting the person is that his relevant qualifications and experience are not as good as those of the person who is to be replaced. |  |  |  |  |  |
|  |  |  |  |  | 22.11 | The Employer may, having stated his reasons, instruct the Consultant to remove a person employed by the Consultant. The Consultant then arranges that, after one day, the person has no further connection with the work included in this contract. |  |  |  |  |  |
| Working with the |  |  |  |  | 23 |  |  |  |  |  |  |
| Employer and Others |  |  |  |  | 23.1 | The Consultant co-operates with Others in obtaining and providing information which they need in connection with the services. The Consultant co-operates with Others and shares the Affected Property with them as stated in the Scope. |  |  |  |  |  |
|  |  |  |  |  | 23.2 | Where necessary to Provide the Services, the Consultant holds or attends meetings with Others. The Consultant informs the Employer of these meetings beforehand and the Employer may attend them. |  |  |  |  |  |
|  |  |  |  |  | 23.3 | If the Employer decides that the work does not meet the Condition stated for a Key Date by the date stated and, as a result, the Employer incurs additional cost either |  |  |  |  |  |
|  |  |  |  |  |  | - in carrying out work or |  |  |  |  |  |
|  |  |  |  |  |  | - by paying an additional amount to Others in carrying out work |  |  |  |  |  |
|  |  |  |  |  |  | on the same project, the additional cost the Employer has paid or will incur is paid by the Consultant. The Employer assesses the additional cost within four weeks of the date when the Condition stated for that Key Date is met. |  |  |  |  |  |
|  |  |  |  |  | 23.4 | The Employer and the Consultant provide facilities and other things as stated in the Scope. Any cost incurred by the Employer as a result of the Consultant not providing the facilities and other things he is to provide is assessed by the Service Manager and paid by the Consultant. |  |  |  |  |  |

| Subconsulting |  |  |  |  |  | 24 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 24.1 |  |  | If the Consultant subcontracts work, he is responsible for Providing the Services as if he had not subcontracted. This Contract applies as if a Subconsultant’s employees were the Consultant’s. |
|  |  |  |  |  |  | 24.2 |  |  | The Consultant will ensure to the extent that they are applicable that the conditions of this Contract are included in any subcontracts placed by him for any part of the work under the Contract and the Consultant will not place subcontracts with any party unless that party agrees to assume the same obligations corresponding to those imposed on the Consultant in the conditions of this Contract. The Consultant will nevertheless remain liable for the due observance of these conditions of contract by his Personnel. |
|  |  |  |  |  |  | 24.3 |  |  | The Consultant submits the name of each proposed Subconsultant to the Employer for acceptance. A reason for not accepting the Subconsultant is that his appointment will not allow the Consultant to Provide the Services. The Consultant does not appoint a proposed Subconsultant until the Employer has accepted him. |
|  |  |  |  |  |  | 24.4 |  |  | The Consultant submits the proposed conditions of contract for each subcontract to the Service Manager for acceptance unless the Service Manager has agreed that no submission is required. The Consultant does not appoint a Subconsultant on the proposed sub-contract conditions submitted without prior written consent from the Service Manager. A non-exclusive reason for not accepting them is that |
|  |  |  |  |  |  |  |  |  | - they will not allow the Consultant to Provide the Service or - they do not include a statement that the parties to the subcontract will act in a spirit of mutual trust and co-operation; or - they do not operate so as to allow the Employer step-in rights as set out in clause 24A below; - they do not include a term which requires payment to be made to the Subconsultant within a specified period not exceeding 30 days from receipt of a valid invoice as defined by the subcontract requirements. |
|  |  |  |  |  |  | 24.5 |  |  | The Consultant will in relation to any subletting of any portion of the services (or the design thereof): - procure that the relevant subcontract will, in all respects be compatible with the terms of this Contract and that all applicable obligations are contained within the terms and conditions of the relevant subcontract; - procure that all relevant subcontracts will be executed and delivered as a deed; and - provide to the Employer on demand certified copies of any subcontract. |
|  |  |  |  |  |  | 24.6 |  |  | When placing subcontracts the Consultant gives consideration, as far as possible, to the placing of work on a competitive basis with supported employment enterprises registered with the Department for Work and Pensions under the Special Contracts Arrangement. Details of the capabilities of these enterprises are available from Job Centre Plus, Disability and Rehabilitation Division, Level 3 West Wing, Rockingham House, 123 West Street, Sheffield S1 4ER (Tel: 0114 259 6964). |
| Step-In Rights |  |  |  |  |  |  | 24A |  |  |
|  |  |  |  |  |  |  | 24A.1 |  | The Consultant procures (by way of inclusion of relevant provisions in the subcontracts/the warranties to be given to the Employer by the Subconsultants) that in the event of determination of this Contract then its Subconsultants will, if so required by notice in writing given by the Employer, accept the instructions of the Employer or his appointee to the exclusion of the Consultant in respect of the services upon the terms and conditions of the relevant subcontracts. The Consultant acknowledges that the Subconsultants will be entitled to rely on a notice from the Employer as conclusive evidence for the purposes of this Contract of the determination of the Consultant’s employment under this Contract – and further acknowledges that such acceptance of the instructions of the Employer to the exclusion of the Consultant will not constitute any breach of a Subcontractor’s obligations to the Consultant under its subcontract. |
|  |  |  |  |  |  |  | 24A.2 |  | The Consultant ensures that it is a term of his subcontracts that his Subconsultants do not exercise any right of determination of their employment under the subcontract without having first: - copied to the Employer any written notices required to be sent prior to there being an entitlement to give notice that such employment is to be determined; and - given to the Employer two weeks’ prior written notice that it has the right under its subcontract to determine its employment thereunder. |
|  |  |  |  |  |  |  | 24A.3 |  | The Employer may, not later than the expiry of the notice period set out in clause 24A.2 above, require the Subconsultants by notice in writing to accept the instructions of the Employer or his appointee to the exclusion of the Consultant in respect of the service on the terms and conditions of the subcontract. |
|  |  |  |  |  |  |  | 24A.4 |  | It will be a condition of any notice given by the Employer under this clause 24A that the Employer or its appointee accepts liability for payment of the sums certified as due/properly due to the Subconsultants under the subcontract and for the performance of the Consultant’s obligations thereunder, including for the avoidance of doubt, payment for any sums outstanding at the date of such notice. Upon the issue of any step-in notice by the Employer, the subcontracts will continue in full force and effect as if they had been made between the Employer and the Subconsultants ab initio and no right of determination had arisen. The Consultant will procure that the subcontracts provide that, where the Employer steps in to the subcontracts, the Subconsultants will be liable to the Employer in lieu of the Consultant. |
|  | Other responsibilities |  |  |  |  | 25 |  |  |  |
|  |  |  |  |  |  | 25.1 |  |  | The Consultant obtains approval from Others where necessary to Provide the Services. |
|  |  |  |  |  |  | 25.2 |  |  | The Employer provides access to a person, place or thing to the Consultant as stated in the Contract Data on or before the later of its access date and the access date for it shown on the Accepted Plan. |
|  |  |  |  |  |  | 25.3 |  |  | The Consultant obeys an instruction which is in accordance with this Contract and is given to him by the Service Manager. |
|  |  |  |  |  |  | 25.4 |  |  | The Consultant acts in accordance with Statutory health and safety requirements |
|  |  |  |  |  |  | 25.5 |  |  | The Consultant will at all times ensure that there is no trespass by the Consultant or its Personnel on or over any adjoining or neighbouring property arising out of, or in the course of, or caused by the carrying out of the services and the Consultant will prevent damage or injury to any persons including (but without limitation) the occupiers of adjoining or neighbouring property and members of the public. |
|  |  |  |  |  |  | 25.6 |  |  | The Consultant will be responsible for and will indemnify the Employer from and against any and all expenses, liabilities, losses, claims and proceedings resulting from any failure or default by the Consultant in performing his obligations under clause 25.5. |
|  | Conflicts of Interest |  |  |  |  | 26A |  |  |  |
|  |  |  |  |  |  | 26A.1 |  |  | The Consultant takes appropriate steps to ensure that neither the Consultant nor any of the Consultant’s Personnel is placed in a position where, in the reasonable opinion of the Employer - there is or may be an actual conflict or potential conflict, between the pecuniary or personal interests of the Consultant and the duties owed to the Employer under the provisions of the Contract; or - the behaviour of the Consultant or the Consultant’s Personnel is not in the Employer’s best interest or might adversely affect the Employer’s reputation. |
|  |  |  |  |  |  | 26A.2 |  |  | The Consultant as soon as reasonably practicable discloses to the Employer full particulars of any behaviour which might give rise to an actual or potential conflict. |
|  |  |  |  |  |  | 26A.3 |  |  | The Employer may, in accordance with clause 90 (Termination), terminate all or part of the Contractor’s employment under the Contract and/or take such other steps it deems necessary where, in the reasonable opinion of the Employer, there is or may be an actual conflict or potential conflict, between the financial or personal interests of the Consultant or the Consultant’s Personnel and the duties owed to the Employer under the provisions of the Contract. The actions of the Employer pursuant to this clause do not prejudice or affect any right of action or remedy which has accrued or will accrue to the Employer. |
|  | Corrupt Gifts and Payments of Commission |  |  |  |  | 26B |  |  |  |
|  |  |  |  |  |  | 26B.1 |  |  | In addition to clause 19I, the Consultant will not do, and warrants that in entering the Contract he has not done any of the following (hereafter referred to as “Prohibited Acts”): a) offer, promise, give or agree to give to any Crown servant any gift or financial advantage of any kind as an inducement or reward; - for doing or not doing (or for having done or not having done) any act in relation to the obtaining or execution of this or any other contract with the Crown; or - for showing or not showing favour or disfavour to any person in relation to this or any other contract with the Crown. b) enter into this or any other contract with the Crown in connection with which commission has been paid or has been agreed to be paid by him or on his behalf, or to his knowledge, unless before the Contract is made particulars of any such commission and of the terms and conditions of any such agreement for the payment thereof have been disclosed in writing to the Employer. |
|  |  |  |  |  |  | 26B.2 |  |  | If the Consultant or his Personnel does any of the Prohibited Acts or commits any offence under the Bribery Act 2010 with or without the knowledge or authority of the Consultant in relation to this Contract or any other contract with the Crown, the Employer will be entitled: a) to terminate all or part of the Consultant’s employment under the Contract in accordance with clause 90 (Termination) and recover from the Consultant the amount of any loss resulting from the termination; b) to recover from the Consultant the amount or value of any such gift, consideration or commission; and c) to recover from the Consultant any other loss sustained in consequence of any breach of this clause 26B, where the Contract has not been terminated. |
|  |  |  |  |  |  | 26B.3 |  |  | In exercising its rights or remedies under this clause 26B, the Employer will: a) act in a reasonable and proportionate manner having regard to such matters as the gravity of, and the identity of the person performing, the Prohibited Act; b) give all due consideration, where appropriate, to action other than termination of the Contract, including (without being limited to); - requiring the Consultant to procure the termination of a subcontract where the Prohibited Act is that of a Subconsultant or anyone acting on its or their behalf; - requiring the Consultant to procure the dismissal of an employee (whether its own or that of a Subconsultant or anyone acting on its behalf) where the Prohibited Act is that of such employee. |
|  |  |  |  |  |  | 26B.4 |  |  | Recovery action taken against any person in Her Majesty’s service will be without prejudice to any recovery action taken against the Consultant pursuant to this clause. |
|  | Intellectual Property Rights |  |  |  |  | 26C |  |  |  |
|  |  |  |  |  |  | 26C.1 |  |  | Subject to the retention by the Consultant, or the third party owner (as the case may be) of the Consultant’s Background IPR, and where appropriate a license back to the Consultant to use the IP Materials for all purposes connected with this Contract, the Consultant assigns (or ensures that the third party owner assigns) to the Employer, with full title guarantee, all Intellectual Property Rights which may subsist in the IP Materials specific to Contract. These assignments takes effect on the date of this Contract or as a present assignment of future rights that will take effect immediately on the coming into existence of the Intellectual Property Rights produced by the Consultant or the third party owner (as the case may be). The Consultant executes (or ensures that the third party owner executes) all documentation necessary to execute these assignments. |
|  |  |  |  |  |  | 26C.2 |  |  | The Consultant does not, and procures that the Consultant’s Personnel do not, (except when necessary for the performance of this Contract) without prior written consent of the Employer, use or disclose any such Intellectual Property Rights in the Foreground IPR. |
|  |  |  |  |  |  | 26C.3 |  |  | All Foreground IPR whether created by the Consultant or any of his Personnel or a third party belongs to the Employer and all Background IPR furnished or made available to the Consultant by or on behalf of the Employer remains the property of the Employer. |
|  |  |  |  |  |  | 26C.4 |  |  | The Consultant waives or procures a waiver of any moral rights subsisting in copyright produced for this Contract. |
|  |  |  |  |  |  | 26C.5 |  |  | The Consultant ensures that the third party owner of any Background Intellectual Property Rights in IP Materials that are delivered by or on behalf of the Consultant in relation to the performance by the Contractor of its obligations under this Contract grants to the Employer a non-exclusive licence or, if itself a licensee of those rights, grants to the Employer an authorised sub-licence, to use, reproduce, modify, develop and maintain the Intellectual Property Rights in the same. Such licence or sub-licence is non-exclusive, perpetual, royalty free and irrevocable and includes the right for the Employer to sub-licence, transfer, novate or assign to other Government Departments, any replacement Consultant or to any other third party. |
|  |  |  |  |  | 26C.6 |  |  |  | The Consultant does not infringe any Intellectual Property Rights of any third party in providing the services and the Consultant, from the date of this Contract indemnifies and keeps indemnified and holds the Employer harmless from and against all actions, suits, claims, demands, losses, charges, damages, costs and expenses and other liabilities which the Employer may suffer or incur as a result of or in connection with any breach of this clause, except where such claim arises from the use of data supplied by the Employer which is not required to be verified by the Consultant under any provision of this Contract. |
|  |  |  |  |  | 26C.7 |  |  |  | The Employer notifies the Consultant in writing of any claim or demand brought against the Employer for infringement or alleged infringement of any Intellectual Property Right in materials supplied or licensed by the Contractor. |
|  |  |  |  |  | 26C.8 |  |  |  | The Consultant at its own expense conducts all negotiations and any litigation arising in connection with any claim for breach of Intellectual Property Rights in materials supplied or licensed by the Consultant, provided always that the Consultant: (a) consults the Employer on all substantive issues which arise during the conduct of such litigation and negotiations; (b) takes due and proper account of the interests of the Employer; and (c) does not settle or compromise any claim without the Employer’s prior written consent (not to be unreasonably withheld or delayed). |
|  |  |  |  |  | 26C.9 |  |  |  | The Employer at the Consultant’s request affords to the Consultant all reasonable assistance for the purpose of contesting any claim or demand made or action brought against the Employer or the Consultant by a third party for infringement or alleged infringement of any third party Intellectual Property Rights in connection with the performance of the Consultant’s obligations under this Contract and the Consultant indemnifies the Employer for all reasonable costs and expenses (including, but not limited to, legal costs and disbursements) incurred in doing so. |
|  |  |  |  |  | 26C.10 |  |  |  | The Employer does not make any admissions which may be prejudicial to the defence or settlement of any claim, demand or action for infringement or alleged infringement of any Intellectual Property Right by the Employer or the Consultant in connection with the performance of its obligations under this Contract. |
|  |  |  |  |  | 26C.11 |  |  |  | If a claim, demand or action for infringement or alleged infringement of any Intellectual Property Right by the Contractor is made in connection with this Contract or in the reasonable opinion of the Consultant is likely to be made, the Consultant notifies the Employer as soon as reasonably practicable and, at its own expense and subject to the consent of the Employer (not to be unreasonably withheld or delayed), uses its best endeavours to: - modify any services without reducing the performance or functionality of the same, or substitute alternative works of equivalent performance and functionality, in order to avoid the infringement or the alleged infringement, provided that the provisions herein apply mutatis mutandis to such modified service or to the substitute works; or - procure a licence to use and provide any part of the services which is the subject of the alleged infringement, on terms which are acceptable to the Employer; and in the event that the Consultant is unable to comply with these requirements within twenty-eight (28) days of receipt of the Consultant’s notification the Employer may terminate this Contract by written notice. |
|  |  |  |  |  | 26C.12 |  |  |  | The Consultant grants to the Employer a royalty-free, irrevocable and non-exclusive licence (with a right to sub-licence) (and where appropriate worldwide) in perpetuity to use any Background IPR or other IPR that the Consultant owns and which the Employer reasonably requires in order to exercise its rights and take the benefit of this Contract. |
|  |  |  |  |  | 26C.13 |  |  |  | Where the Consultant secures a licence from a third party in any software for the provision of part of the service it will do so in the name of the Employer in perpetuity with the right to sublicense to any third party nominated by the Employer for the purposes of performing any part of the service which is provided at any time pursuant to this Contract. |
|  |  |  |  |  | 26C.14 |  |  |  | Where the Consultant uses any of its own software for the provision of any Works it will grant a free irrevocable licence to the Employer in perpetuity with the right to sublicense to any third party nominated by the Employer to use the software for the purposes of continuing to operate any part of the services provided at any time under this Contract. |
|  |  |  |  |  | 26C.15 |  |  |  | The Consultant shall mark any copyright work on the title page or in the title box with the legend: “Prepared by (print Consultant’s name) for the Ministry of Defence, Defence Estates, under Contract Number (insert this contract number) on (date/month/year)” on any specification, plan, drawing, or any of the other deliverable document prepared by the Contractor under this Contract. The Consultant shall also identify any confidential information contained in the copyright work, which was provided by a third party not employed in the performance of services under the Contract. |
|  | [Not used |  |  |  | 26D] |  |  |  |  |
|  | Access and Facilities Provided by the Contractor |  |  |  | 26E |  |  |  |  |
|  |  |  |  |  | 26E.1 |  |  |  | The Consultant's progress and quality standards in performing the services under the Contract will be monitored by the Employer. The Consultant will provide to the Service Manager all reasonable access to his premises for these purposes and those in connection with audit in accordance with clause 19H. |
|  |  |  |  |  | 26E.2 |  |  |  | The Consultant will provide, at no additional cost to the Employer, such accommodation and facilities for representatives of the Employer as the Employer may reasonably require. All accommodation provided will be adequately furnished, lit, heated and ventilated and will include suitable cloakroom and communication facilities. |
|  |  |  |  |  | 26E.3 |  |  |  | As far as is reasonably practical the Consultant will ensure that the provisions in clauses 26E.1 and 26E.2 are included in his subcontracts. Access to such Subconsultant’s premises will be arranged by the Employer through the Consultant. |
|  | Retention and Supply of Records and Data |  |  |  | 26F |  |  |  |  |
|  |  |  |  |  | 26F.1 |  |  |  | The Consultant will store and maintain all Contract Records and will make them available to the Employer as the Employer may reasonably require when requested upon reasonable notice. |
|  |  |  |  |  | 26F.2 |  |  |  | Subject to clause 13B (Disclosure of Information), the Consultant will permit all Contract Records to be examined and if necessary copied, by or on behalf of the Employer or will provide copies to the Employer at the Employer’s reasonable cost. |
|  |  |  |  |  | 26F.3 |  |  |  | Unless the Scope specifies otherwise the Contract Records will be retained for a period of at least six (6) years after completion of the services PROVIDED ALWAYS THAT notwithstanding the generality of this clause 26F.3 all Contract Records executed under seal or expressed to be executed as deeds will be retained by the Consultant for a minimum period of twelve (12) years following completion of the services. |
|  |  |  |  |  | 26F.4 |  |  |  | The Employer will be entitled at any time to make copies of Contract Records supplied under this clause, as the Employer may think fit and to use such Contract Records (or copies of them) in any UK Government Department and such use will not, unless otherwise provided for in the Contract, extend to the use for tendering or manufacturing purposes. |
|  |  |  |  |  | 26F.5 |  |  |  | Control Copies will be maintained by the Consultant in such media and formats as the Employer may agree. Control Copies will not be altered by the Consultant in any way which changes the build standard except as authorised in writing by the Employer. Control Copies will be deemed to be the Property of the Employer, and the Employer may take possession of any or all Control Copies notwithstanding any administration, receivership, winding-up or liquidation of the Consultant or any transfer of its assets to any third party. |
|  | Security Measures |  |  |  | 26G |  |  |  |  |
|  |  |  |  |  | 26G.1 |  |  |  | The Consultant will: a) take all reasonable steps to ensure that all Personnel engaged on any work in connection with the Contract have notice that the Official Secrets Acts 1911-1989 apply to them and will continue so to apply after the completion or termination of the Contract; and b) if directed by the Employer, ensure that any Personnel will sign a statement acknowledging that, both during the term of the Contract and after its completion or termination, he is bound by the Official Secrets Acts 1911-1989 (and where applicable by any other legislation). |
|  |  |  |  |  | 26G.2 |  |  |  | Unless he has the written authorisation of the Employer to do otherwise, neither the Consultant nor any of his Personnel will, either before or after the completion or termination of the Contract, do or permit to be done anything which they know or ought reasonably to know may result in Secret Matter being disclosed to or acquired by a person in any of the following categories: a) who is not a British citizen; b) who does not hold the appropriate authority for access to the protected matter; c) in respect of whom the Employer has notified the Consultant in writing that the Secret Matter will not be disclosed to or acquired by that person; d) who is not one of the Consultant’s Personnel; e) who is one of the Consultant’s Personnel and has no need to know the information for the proper performance of the Contract. |
|  |  |  |  |  | 26G.3 |  |  |  | Unless he has the written permission of the Employer to do otherwise, the Consultant and his Personnel will, both before and after the completion or termination of the Contract, take all reasonable steps to ensure that: a) no photograph of, or pertaining to, any Secret Matter will be taken and no copy of or extract from any Secret Matter will be made except to the extent necessary for the proper performance of the Contract; b) any Secret Matter is at all times strictly safeguarded in accordance with the Security Policy Framework and upon request, is delivered up to the Employer who will be entitled to retain it. A decision of the Employer on the question of whether the Consultant has taken or is taking reasonable steps as required by this clause, will be final and conclusive. |
|  |  |  |  |  | 26G.4 |  |  |  | The Consultant will: a) provide to the Employer: - upon request, such records giving particulars of all Personnel who have had at any time, access to any Secret Matter that is required to be kept in accordance with clause 26G.3(b); - upon request, such information as the Employer may from time to time require so as to be satisfied that the Consultant and his Personnel are complying with his obligations under this clause, including the measures taken or proposed by the Consultant so as to comply with his obligations and to prevent any breach of them; - full particulars of any failure by the Consultant and his Personnel to comply with any obligations relating to Secret Matter arising under this clause immediately upon such failure becoming apparent; b) ensure that, for the purpose of checking the Consultant's compliance with the obligation in clause 26G.3(b), a representative of the Employer will be entitled at any time to enter and inspect any premises used by the Consultant which are in any way connected with the Contract and inspect any document or thing in any such premises, which is being used or made for the purposes of the Contract. Such representative will be entitled to all such information as he may reasonably require. |
|  |  |  |  |  | 26G.5 |  |  |  | If at any time either before or after the completion or termination of the Contract, the Consultant or any of his Personnel discovers or suspects that an unauthorised person is seeking or has sought to obtain information directly or indirectly concerning any Secret Matter, the Consultant will forthwith inform the Employer of the matter with full particulars thereof. |
|  |  |  |  |  | 26G.6 |  |  |  | If the Consultant proposes to make a subcontract which will involve the disclosure of Secret Matter to the Subcontractor, the Consultant will: a) submit for approval of the Employer the name of the proposed Subcontractor, a statement of the work to be carried out and any other details known to the Consultant which the Employer will reasonably require; b) incorporate into the subcontract the terms of DIO DOC 39 and such secrecy and security obligations as the Employer will direct. In the Annex 'Agreement' will mean the 'Subcontract', 'First Party' will mean the 'Consultant' and 'Second Party' will mean the 'Subcontractor'; c) inform the Employer immediately he becomes aware of any breach by the Subcontractor of any secrecy or security obligation and, if requested to do so by the Employer, terminate the subcontract. |
|  |  |  |  |  | 26G.7 |  |  |  | The Employer will in accordance with clause 90 (Termination) be entitled to terminate all or part of the Consultant’s employment under the Contract immediately if: a) the Consultant is in breach of any obligation under this clause; or b) the Consultant is in breach of any secrecy or security obligation imposed by any other contract with the Crown; where the Employer considers the circumstances of the breach jeopardise the secrecy or security of the Secret Matter. |
|  | Discrimination |  |  |  | 26H |  |  |  |  |
|  |  |  |  |  | 26H.1 |  |  |  | The Consultant will not unlawfully discriminate within the meaning and scope of the provisions of the Equality Act 2010 or any statutory modification or re-enactment thereof relating to discrimination in employment. |
|  |  |  |  |  | 26H.2 |  |  |  | The Consultant will take all reasonable steps to secure the observance of the provisions of clause 26H.1 hereof by all his Personnel and Consultant and all other persons under his control employed in the execution of the Contract. |
|  |  |  |  |  | 26H.3 |  |  |  | The Consultant will immediately notify the Employer, of any prosecution or proceedings, brought under the legislation detailed in clause 26H.1, against the Consultant, his Personnel and all other persons under his control employed in the execution of the Contract. |
|  |  |  |  |  | 26H.4 |  |  |  | Notification by the Consultant of such information will not prejudice any rights of the Employer or the Consultant under the Contract. |
|  | Transparency |  |  |  | 26I |  |  |  |  |
|  |  |  |  |  | 26I.1 |  |  |  | Notwithstanding any other term of this Contract the Consultant understands that the Employer may publish the Transparency Information to the general public. The Consultant will assist and co-operate with the Employer to enable the Employer to publish the Transparency Information. |
|  |  |  |  |  | 26I.2 |  |  |  | Before publishing the Transparency Information to the general public in accordance with clause 26I.1 above, the Employer will redact any information that would be exempt from disclosure if it was the subject of a request for information under the FOIA or the Environmental Information Regulations 2004, including the Consultant Commercially Sensitive Information. |
|  |  |  |  |  | 26I.3 |  |  |  | The Employer may consult with the Consultant before redacting any information from the Transparency Information in accordance with clause 26I.2. The Consultant acknowledges and accepts that its representations on redactions during consultations may not be determinative and that the decision whether to redact information is a matter in which the Employer will exercise its own discretion, subject always to the FOIA or the Environmental Information Regulations. |
|  | Accounting for the Property of the Employer |  |  |  | 26J |  |  |  |  |
|  |  |  |  |  | 26J.1 |  |  |  | The Consultant will: a) maintain a Public Store Account (“PSA”), as defined in DEFSTAN 05-99, which will include a complete list of all property of the Employer, as defined in clause 26J.2, and record for that property all transactions or other accounting information specified in the Scope; b) supply to the Employer quarterly reports on the current PSA holdings. At least one report in any twelve-month accounting period or part thereof will be a reconciled report. This will be submitted with the Annual Certificate Form AAC 32 as required in DEFSTAN 05-99. The other three reports submitted in the period may be un-reconciled advisory reports. The submission by the Consultant and receipt by the Employer of these reports will not prejudice any rights or obligations of the Employer or the Consultant under the Contract; c) ensure that the PSA is available for inspection by the Employer at any reasonable time; d) on being given eight weeks’ notice or any other period as has been stated in the Contract permit, and co-operate with, the Employer to conduct audits of the PSA in a manner to be determined by the Employer; where the Employer has reasonable grounds to doubt the integrity of the PSA to the extent that the Employer is not satisfied of the proper use of property of the Employer, an audit may be conducted without notice; e) retain the PSA for a period of three years after disposal of the last item of the property of the Employer, or for any other period as may be specified in the Contract; f) if the Employer agrees that a Subconsultant at whatever level of subcontracting will have responsibility in the Subconsultant’s PSA for property of the Employer issued in aid of the Contract, the Consultant will include in any subcontract with those Subconsultants only the provisions corresponding to those set out in this clause that apply to property of the Employer issued in aid of the subcontract, in particular clauses 26J.1, 26J.2, 26J.4 and 26J.7; and g) manage the Government Furnished Assets (“GFA”) component of the PSA in accordance with the provisions of DEFSTAN 05-99; and implement any new edition of or amendment to DEFSTAN 05-99 within twelve weeks of the publication date of the new edition. These amendments will not have retrospective effect. |
|  |  |  |  |  | 26J.2 |  |  |  | For the purposes of this clause 'property of the Employer' means GFA and fixed assets, including property issued under clause 70.4 and property of the Employer issued to the Consultant under any other authorising document [except for property vested in the Employer under clause 71.1. |
|  |  |  |  |  | 26J.3 |  |  |  | For the avoidance of doubt, it is a condition of this Contract that this clause will apply to all property issued to the Consultant from the date of this Contract, whether in aid of the Contract, any other contract or other agreement with the Employer. Property of the Employer issued prior to the date of this Contract may be subject to separate contractual arrangements. |
|  |  |  |  |  | 26J.4 |  |  |  | The o Obligations of the Consultant arising under this clause in respect of property of the Employer issued in aid of the Contract will survive completion of the Contract and will not be completed until all such obligations are fulfilled including the provisions of clause 26J.1(e). |
|  |  |  |  |  | 26J.5 |  |  |  | The obligations of the Consultant arising under this clause in respect of property of the Employer unconnected with the Contract will survive completion of the Contract and will not be completed until all those obligations are fulfilled including the provisions of clause 26J.1(e) unless and until a subsequent contract containing clause 26J is placed with the Consultant at which time obligations in respect of any remaining property of the Employer unconnected with the Contract will be subsumed in the subsequent contract. |
|  |  |  |  |  | 26J.6 |  |  |  | If, after completion of the Contract, no subsequent contract is placed containing clause 26J within the period detailed at clause 26J.1(e), then the obligations of the Consultant arising under this clause in respect of property of the Employer unconnected with the Contract will cease on expiry of the period detailed at clause 26J.1(e). |
|  |  |  |  |  | 26J.7 |  |  |  | The Employer reserves the right to amend PSA without further consultation where the amendments arise from the Employer’s proper and reasonable accounting requirements. For the purposes of this clause, PSA will be regarded as part of the services and subject to the terms of this Contract. If the Employer exercises this right: a) the Consultant will implement the amendment to PSA at the commencement of the Employer’s next accounting year provided that a notice of six months or such other period as may expressly be agreed between the Employer and Consultant is given to the Consultant. These amendments will not have retrospective effect; and - the Consultant will inform the Employer as soon as practicable, but in any event within three months of notice having been given, if the Consultant cannot comply with the amendment to PSA; but any amendment made pursuant to this clause 26J.7 will not constitute a change to the Scope and will not constitute a compensation event for the purpose of this Contract. |
|  | Environment and Carbon Management |  |  |  | 26K |  |  |  |  |
|  |  |  |  |  | 26K.1 |  |  |  | ## The Consultant will use its best endeavours to improve the environmental efficiency of the provision of the services and at all times demonstrate to the Employer a commitment to compliance with environment legislation in force from time to time. |
|  |  |  |  |  | 26K.2 |  |  |  | ## In particular the Consultant will where possible use energy efficient vehicles, reduce, reuse and recycle waste generated, use energy for buildings and equipment in an efficient manner, and use and reuse water and other resources in an efficient manner. |
|  | Health & Safety and the Environment |  |  |  | 26L |  |  |  |  |
|  |  |  |  |  | 26L.1 |  |  |  | ## The Consultant will Provide the Services in accordance with the Employer’s health and safety and sustainable development and environmental management requirements and in compliance with DIO DOC 57 Section 3.3. The Consultant will indemnify and keep the Employer indemnified from and against any direct claims, actions, liabilities, losses, costs, expenses and damages arising as a result of the Consultant’s negligence in complying with its obligations under this clause 26L. The Consultant may be required to attend safety training at any Establishment, which may be arranged from time to time by the Employer. |
|  |  |  |  |  | 26L.2 |  |  |  | ## Prior to commencing the services the Consultant will provide the Service Manager with full details of all known hazardous materials and substances used or stored on the Affected Property and of any such materials which are not clearly labelled or appropriately stored, and will inform the Service Manager whether the Affected Property contains any toxic, hazardous or carcinogenic substances along with its procedures for dealing with and carrying out the disposal of any hazardous or toxic waste as required within DIO DOC 57 Section 3.3. |
|  |  |  |  |  | 26L.3 |  |  |  | ## The Consultant notifies the Service Manager of any health and safety hazards of which it is aware or ought reasonably to be aware, which may arise in connection with the performance of this Contract. The Consultant will also draw these hazards to the attention of the Employer and Others any other persons engaged by the Consultant in the performance of the services at any Affected Property, or any other person who may be affected by these hazards. |
|  |  |  |  |  | 26L.4 |  |  |  | ## The Consultant will procure that all Personnel will familiarise themselves with the emergency procedures laid down by the Service Manager and the Consultant and any other relevant Health and Safety policies and procedures adopted by the Consultant in accordance with DIO DOC 57 SECTION 3.3 |
|  |  |  |  |  | 26L.5 |  |  |  | ## The Consultant must and will procure that the Personnel at all times comply with all legal requirements including but not limited to the "Duty of Care" provisions contained in part II of the Environmental Protection Act 1990 and any relevant regulations made under that Act and must ensure that all Personnel, perform their duties in accordance with the Health and Safety Acts. |
|  |  |  |  |  | 26L.6 |  |  |  | All property of the Consultant and his Personnel will be at the risk of the Consultant whilst it is on any Government Establishment, and the Employer will accept no liability for any loss or damage howsoever occurring thereto or caused thereby, except as follows: a) where any such loss or damage was caused or contributed to by any act, neglect or default of any of the Employer’s Personnel then the Employer will accept liability therefore to the extent to which such loss or damage is so caused or contributed to as aforesaid; and ## b) where any property of the Consultant has been taken on charge by the Head of Establishment, and a proper receipt has been given therefore, then the Employer will be liable for any loss or damage occurring to that property while held on such charge as aforesaid, save to any extent such loss or damage is caused or contributed by any act neglect or default of the Contractor or any of the Contractor Personnel. |
|  |  |  |  |  | 26L.7 |  |  |  | The Consultant will report any injury, disease or dangerous occurrence at any Government Establishment arising out of the performance of this Contract, which is required to be reported under the Reporting of Injuries, Diseases and Dangerous Occurrences Regulations 1995 (“RIDDOR”) to the Head of Establishment in accordance with DIO DOC 57 SECTION 3.3. This would be in addition to any report, which the Consultant may be required to submit under RIDDOR to the relevant enforcing authority (e.g. Health and Safety Executive or Local Authority). |
|  |  |  |  |  |  |  |  | 26L.8 | Where the Consultant enters a Government Establishment for the purpose of performing work under the Contract: a) The Consultant will notify the Head of Establishment and the Service Manager of: - any health and safety hazards associated with the work to be performed by him or any of his Personnel; - any foreseeable risks to the health and safety of all persons associated with such hazards; and - any precautions to be taken by him as well as any precautions which, in his opinion, ought to be taken by the Employer, in order to control such risks. b) The Employer will notify the Consultant of: - any material health and safety hazards of which it is aware and which may be encountered by the Consultant or any of his Personnel on the Government Establishment and which a competent consultant could not be expected to have known about or have foreseen ; and - any precautions (but without being responsible for the same) which, in its opinion, ought to be taken by the Consultant, in order to control such risks. c) The Consultant will notify his Personnel of and, where appropriate, provide adequate instruction in relation to: - the hazards, risks and precautions notified by him to the Employer under clause 26L.8(a); - the hazards, risks and precautions notified by the Employer to the Consultant under clause 26L.8(b); and - the precautions which, in his opinion, ought to be taken by his Personnel in order to control those risks. d) The Consultant will provide the Head of Establishment and the Service Manager with: - copies of those sections of his own and, where appropriate, his Personnel’s safety policies which are relevant to the risks notified under clause 26L.8(a); - copies of any related risk assessments; and - copies of any notifications and instructions issued by him to his Personnel under clause 26L.8(c). e) The Employer will provide the Consultant with: - copies of those sections of its own safety policies which are relevant to the risks notified under clause 26L.8(b); - copies of any related risk assessments; and - copies of any notifications and instructions issued by it to its employees similar to those called for from the Consultant under clause 26L.8(c), and the Consultant will comply with the safety policies and the Employer Policies. |
|  | Consultant’s Warranties |  |  |  |  |  |  | 26M | - The Consultant hereby represents and warrants for the benefit of the Employer that: - The Consultant is a company validly existing and is authorised to conduct its business under the laws of England. The Consultant has the power and authority to enter into this Contract, and to perform his obligations hereunder. - The Consultant shall immediately notify the Employer if it becomes insolvent (as defined in clause 113 of the Housing Grants, Construction and Regeneration Act 1996 (as amended) and/or if any claim, litigation, arbitration or administrative proceeding is in progress or pending or threatened against him or any of his assets or any party which has given the Employer a guarantee or indemnity in respect of the Consultant’s obligations and liabilities under the Contract which will or might have a materially adverse effect on the ability of the Consultant to perform his obligations under this Contract; - The Consultant has and will maintain the necessary training, experience and capability to perform all of his obligations under this Contract; - The Consultant based his tender on his own inspection and own independent verification of any information made available to him by the Employer with the Scope. The Consultant acknowledges that no entitlements to changes, extensions of time or hardship claims on the basis that the Consultant has failed to carry out his own due diligence on all aspects of the documents will be accepted by the Employer. - The Consultant shall immediately notify the Employer if there is any change in its key Subconsultants. - The Consultant shall immediately notify the Service Manager of any change in his credit rating (for example, Dun & Bradstreet (D&B), Moody's, Standard & Poor (S&P) or Fitch IBCA) from that existing at the time of Contract award. Notification by the Consultant of such information shall not prejudice any rights of the Employer or the Consultant under the Contract. |
|  | Fair Employment (Northern Ireland) Act 1989 |  |  |  |  |  |  | 26N |  |
|  |  |  |  |  |  |  |  | 26N.1 | The Consultant shall not sub-contract the carrying out of the services under this Contract to an “unqualified person” within the meaning of section 38(2) of the Fair Employment and Treatment (Northern Ireland) Act 1988 as amended by the Fair Employment and Treatment Order (Amendment) Regulations (Northern Ireland) 2003. |
|  | Employee Transfer ARRANGEMENTS on entry/Staff Transfer on exit |  |  |  |  |  |  | 28A |  |
|  |  |  |  |  |  |  |  | 28A.1 | The Parties shall comply with their respective employment pensions and associated obligations set out in [insert cross reference to TUPE schedule] for the purposes of which references therein to “the Authority” shall mean “the Employer” as defined in the Contract Data. |

3 Time

| Starting, Completion and |  | 30 |  |  |
| --- | --- | --- | --- | --- |
| Key Dates |  | 30.1 | The Consultant does not start work until the starting date and does the work so that Completion is on or before the Completion Date. |  |
|  |  | 30.2 | The Employer decides the date of Completion and certifies it within one week of the date. |  |
|  |  | 30.3 | The Consultant does the work so that the Condition stated for each Key Date is met by the Key Date. |  |
| The Consultant’s Plan |  | 31 |  |  |
|  |  | 31.1 | If a plan is not identified in the Contract Data, the Consultant submits a first plan to the Service Manager for acceptance within the period stated in the Contract Data. |  |
|  |  | 31.2 | The Consultant’s plan will (unless the Service Manager agrees otherwise) include the following as a minimum and the Consultant will include additional information as necessary to demonstrate the basis of proper control. The Consultant (unless the Service Manager agrees otherwise) shows on each plan which he submits for acceptance |  |
|  |  |  | - the starting date, Key Dates and Completion Date, |  |
|  |  |  | - planned Completion, |  |
|  |  |  | - the order and timing of the operations which the Consultant plans to do in order to Provide the Services, |  |
|  |  |  | - the order and timing of the work of the Employer and Others as last agreed with them by the Consultant or, if not so agreed, as stated in the Scope, |  |
|  |  |  | - the dates when the Consultant plans to meet each Condition stated for the Key Dates and to complete other work needed to allow the Employer and Others to do their work, |  |
|  |  |  | - provisions for |  |
|  |  |  |  | - float, |
|  |  |  |  | - time risk allowances, |
|  |  |  |  | - health and safety requirements and |
|  |  |  |  | - the procedures set out in this contract, |
|  |  |  | - the dates when, in order to Provide the Services in accordance with his programme, the Consultant will need |  |
|  |  |  |  | - access to the Affected Property as stated in the Scope, |
|  |  |  |  | - acceptances, and |
|  |  |  |  | - information and approval from Others, |
|  |  |  | - for each operation, a statement of how the Consultant plans to do the work identifying the resources which he plans to use and |  |
|  |  |  | - other information which the Scope requires the Consultant to show on a plan submitted for acceptance. |  |
|  |  | 31.3 | Within two weeks of the Consultant submitting a plan to him for acceptance, the Employer either accepts the plan or notifies the Consultant of his reasons for not accepting it. A reason for not accepting a plan is that |  |
|  |  |  | - the Consultant’s plans which it shows are not practicable, |  |
|  |  |  | - it does not show the information which this Contract requires, |  |
|  |  |  | - it does not represent the Consultant’s plans realistically or |  |
|  |  |  | - it does not comply with the Scope. |  |
| Revising the programme |  | 32 |  |  |
|  |  | 32.1 | The Consultant shows on each revised programme |  |
|  |  |  | - the actual progress achieved on each operation and its effect upon the timing of the remaining work, |  |
|  |  |  | - the effects of implemented compensation events, |  |
|  |  |  | - how the Consultant plans to deal with any delays and to correct notified Defects and |  |
|  |  |  | - any other changes which the Consultant proposes to make to the Accepted Programme. |  |
|  |  | 32.2 | The Consultant submits a revised programme to the Employer for acceptance |  |
|  |  |  | - within the period for reply after the Employer has instructed him to, |  |
|  |  |  | - when the Consultant chooses to and, in any case, |  |
|  |  |  | - at no longer interval than the interval stated in the Contract Data from the starting date until Completion of the whole of the services. |  |
|  |  | 32.3 | The Consultant shall attend a progress meetings with the Employer in accordance with the requirements of the Scope to assess progress on the Contract. |  |
| Reporting Obligations |  | 32A |  |  |
|  |  | 32A.1 | The Consultant shall provide the Service Manager with a monthly written report within 3 Working Days from the end of each month. Such report shall include: - the matters referred to in the Scope . - such other matters, including any other adhoc reports, as the Service Manager may reasonably direct; - written confirmation from the Consultant that he has complied with all of his obligations under this Contract. - information as agreed and requested from time to time by the Service Manager. |  |
|  |  | 32A.2 | The Consultant, when employed within the boundaries of an Establishment, shall comply with such rules, regulations and requirements (including those relating to security arrangements) as may be in force for the conduct of personnel at the Establishment. Details of such rules, regulations and requirements shall be provided, on request, by the Head of Establishment concerned. |  |
| Access |  | 32B |  |  |
|  |  | 32B.1 | The Employer grants to the Consultant a right of access to the Affected Property as shown on the Accepted Plan or as otherwise agreed by the Employer (acting reasonably) but the Consultant will obtain the necessary consents in order to Provide the Services and any failure to gain access, otherwise than by the Employer removing the Consultant’s right of access, will not be a compensation event. |  |
| Instructions to stop or |  | 33 |  |  |
| not to start work |  | 33.1 | The Service Manager may instruct the Consultant to stop or not to start any work and may at any time within the next six (6) months instruct him that he may re-start or start it. |  |
|  |  | 33.2 | If within 6 months from the date of postponement the Employer instructs the Consultant to resume work, then any payments made shall be considered as payments on account towards the total of the Prices. |  |
|  |  | 33.3 | If the Employer has not instructed the Consultant to resume work which has been postponed at a date six months from the date of postponement, the Service Manager will be deemed to have given an instruction under clause 14.3 changing the Scope to remove the postponed work from the services. |  |
| Acceleration |  | 34 |  |  |
|  |  | 34.1 | The Employer may instruct the Consultant to submit a quotation for acceleration to achieve Completion before the Completion Date. The Employer states changes to the Key Dates to be included in the quotation. A quotation for an acceleration comprises proposed changes to the Prices and a revised programme showing the earlier Completion Date and the changed Key Dates. The Consultant submits details of his assessment with each quotation. |  |
|  |  | 34.2 | The Consultant submits a quotation within the period for reply. |  |
|  |  | 34.3 | Any instruction to accelerate to achieve Completion before the Completion Date (or achieve a Condition before the relevant Key Date) does not constitute a compensation event in accordance with clause 60.1 but the effect on the Prices (if any) will be determined in accordance with Clause 19L (Change Management Process) and if the Employer wishes to proceed with the acceleration the Service Manager shall issue a Task Order in accordance with clause X19. |  |

4 Quality

| Quality management |  | 40 |  |
| --- | --- | --- | --- |
| system |  | 40.1 | The Consultant operates a quality management system for Providing the Services as stated in the Scope. The quality management system complies with the requirements stated in the Scope. |
|  |  | 40.2 | The Consultant provides the Service Manager, within the period stated in the Contract Data, with a quality policy statement and a quality plan for acceptance. The quality policy statement and quality plan comply with the requirements stated in the Scope. |
|  |  | 40.3 | The Consultant complies with an instruction from the Service Manager to the Consultant to correct a failure to comply with the quality plan. |
|  |  | 40A |  |
|  |  | 40A.1 | The Consultant shall provide a management organisation to co-ordinate and deliver the services as set out in DIO DOC 22 based upon the management regime approved at Contract award. The Consultant’s management organisation is as set out in DIO DOC 51. |
|  |  | 40A.2 | If the Consultant wishes at any time to change the management regime he shall notify the Service Manager of the proposed change together with reasons and with an assessment of the effects of the proposed change on delivery of the services. If the Service Manager is satisfied that the proposed change would not adversely affect the delivery of the services the Service Manager shall approve the change to the management regime. The Service Manager shall be further entitled following a proposal from the Consultant or at any other time to make alternative recommendations as to the management regime and/or require changes to be made to the management regime so that the services are capable of being delivered in accordance with the other provisions of the Contract. |
| Correcting Defects |  | 41 |  |
|  |  | 41.1 | Until the defects date, the Employer notifies the Consultant of each Defect as soon as he finds it and the Consultant notifies the Employer of each Defect as soon as he finds it. At Completion the Consultant notifies the Employer of the Defects which have not been corrected. After Completion and until the defects date, the Consultant notifies the Employer of each Defect as soon as he finds it. The Employer’s rights in respect of a Defect which the Employer has not found or notified by the defects date are not affected. |
|  |  | 41.2 | The Consultant corrects a Defect whether or not the Employer notifies him of it. The Consultant corrects Defects within a time which minimises the adverse effect on the Employer or Others. In addition to other remedies available to the Employer, if the Consultant does not correct a Defect within the time required by this Contract, or agreed with the Service Manager, the Service Manager assesses the cost to the Employer of having the Defect corrected by other people and the Consultant pays this amount. |
| Accepting Defects |  | 43 |  |
|  |  | 43.1 | The Consultant and the Service Manager may each propose to the other (via the Change Management Process) that the Scope should be changed so that a Defect does not have to be corrected. The Employer has complete discretion as to whether or not the Employer will agree to any change but if he does so and accepts the Consultant’s quotation, the Service Manager issues a Task Order to change the Scope and the Prices accordingly. |
| Delayed delivery of service |  | 44 |  |
|  |  | 44.1 | The Consultant will notify the Service Manager when delivery of any part of the Services is delayed beyond the date required under this Contract. In the event that any Services are not delivered, the Service Manager will determine if the Consultant has already received payment for those services. If payment has been received the Service Manager will instruct the Consultant to calculate the value of the undelivered services using the pricing information in the Price List and the next payment application will be abated by a corresponding amount or (if the Service Manager does not agree with the Consultant’s calculation) such other amount as the Service Manager shall certify together with any additional amounts incurred by the Employer by reason of the undelivered services being delivered by another Consultant. If and when the Consultant delivers the outstanding services, he will be entitled to recover the sum abated in the next interim payment. |
|  |  | 44.2 | In the event that the Consultant has failed to deliver any part of the services by the time required under this Contract, the Service Manager may determine that the Services should not be delivered or may be delivered by another Consultant. The Service Manager will instruct the Consultant to calculate the value of the undelivered services using the pricing information in the Price List and the next payment application will be reduced by a corresponding amount or (if the Service Manager does not agree with the Consultant’s calculation) such other amount as the Service Manager shall certify together with any additional amounts incurred by the Employer by reason of the undelivered Services being delivered by another Consultant. |

5 Payment

| Pricing Provisions |  | 50A |  |  |
| --- | --- | --- | --- | --- |
|  |  | 50A.1 |  | All Prices are inclusive of overheads, travel and subsistence and profit, but are exclusive of VAT. In exceptional circumstances, travel and subsistence may be payable in addition to the Fixed Prices but only with prior approval in the Task Order issued by the Service Manager. In such circumstances, the Employer and the Consultant will agree the most cost effective option for travel. Where Employer transport is available this shall be used unless an alternative is more cost effective. Travel and subsistence costs shall be agreed based on Civil Service Class II rates current at the date of the relevant Task Order. |
|  |  | 50A.2 |  | For Enabling Services and in exceptional circumstances the Employer and Consultant may agree a price based on a limit of liability using the applicable Prices set out in the Price List. The limit of liability shall be the maximum value the Employer will pay. The Consultant shall be paid for the actual service provided based on the Prices. The Consultant shall provide the Employer with regular reports of expenditure against the limit of liability, including any request for a change in accordance with the Change Management Process. Should the Consultant exceed the limit of liability such expense shall be entirely at the Consultant’s own risk. |
|  |  | 50A.3 |  | The Employer reserves the right to inspect the records of the Consultant or his Subconsultant to substantiate any claim for payment. |
| Milestone Payments |  | 50B 50B.1 |  | Where the Consultant is providing services in support of Defcon 2000, Standalone Prime Contracts or other long term requirements the Consultant shall be entitled to request milestone payments. Such arrangements shall be in accordance with the terms of the applicable agreement. In the event that no such terms are provided, the Consultant shall be entitled to apply for and to be paid milestone payments for services delivered provided that: - all services to which the milestone payment relates have been properly carried out to the reasonable satisfaction of the Service Manager; - the milestones are completed by the Consultant in the sequence shown in the agreed milestone payment schedule attached to the relevant Demand Order; and - the Consultant has complied with all of his contractual obligations at the date of the milestone. |
|  |  | 50B.2 |  | The Consultant shall comply with the following procedure before being entitled to any milestone payment ; - the Consultant shall provide the Service Manager with written notice of the date on which he expects to reach a milestone not less than 2 weeks before that date; - subject to the Service Manager’s confirmation of completion of a milestone in accordance with Clause 50B.3, the Consultant shall provide to the Service Manager an application for payment with: - written confirmation that the milestone has been completed; - all necessary documentation reasonably required by the Service Manager to demonstrate that the milestone has been reached; and - written confirmation as evidence that the Consultant has complied with the requirements of Clause 19I. |
|  |  | 50B.3 |  | Not later than 2 weeks after the Consultant has complied with Clause 50B.2 the Service Manager shall send to the Consultant either: - a written notice confirming that the milestone has been achieved by the Consultant; or - a written notice that the milestone has not been achieved, setting out the reasons for this conclusion |
| Assessing the amount due |  | 50 |  |  |
|  |  | 50.1 |  | The Service Manager assesses the amount due at each assessment date (being the relevant assessment date set out in the relevant Demand Order or in relation to milestone payments the date of the Service Manager’s notice under clause 50B.3 |
|  |  |  | 50.2 | The amount due is: - the Price for Services Provided to Date, - plus other amounts to be paid to the Consultant, - less amounts to be paid by or retained from the Consultant. |
|  |  |  | 50.3 | If no plan is identified in the Contract Data and/or the Employer and the Consultant have not agreed a suitable performance assessment criteria framework (“PACF”), then without prejudice to any other remedy the Employer may have one quarter of the Price for Services Provided to Date is retained in assessments of the amount due until the Consultant has submitted a first plan to the Service Manager for acceptance showing the information which this Contract requires and has agreed a PACF with the Employer. |
|  |  |  | 50.4 | In assessing the amount due, the Service Manager considers any application for payment the Consultant has submitted on or before the assessment date. The Consultant’s application is the notice of payment to the Employer specifying the amount due at the payment date and stating the basis on which the amount was calculated. If no application is received on or before the assessment date (or no valid invoice has been received by the Employer in accordance with clause 51.1) the amount due (and therefore the notified sum) shall be nil. |
|  |  |  | 50.5 | The Service Manager corrects any wrongly assessed amount due in a later payment certificate. |
|  |  |  | 50.6 | The Service Manager certifies a payment within one week of each assessment date. The Service Manager’s certificate is the notice of payment to the Consultant specifying the amount due at the payment due date. |
|  |  |  | 50.7 | The date on which payment becomes due is ten (10) days after the assessment date. The final date for payment is the Relevant Day. |
|  |  |  | 50.8 | In respect of each payment instalment the Employer shall pay to the Consultant by the Relevant Day (subject to any pay less notice issued in accordance with clause 50.9) the amount certified by the Service Manager under clause 50.6 (notified sum), or where an amount has not been so certified by the Service Manager the sum stated in the Contractor’s application for payment as referred to in clause 50.4 (notified sum). |
|  |  |  | 50.8A | The Employer shall be entitled to set off against any amount due to the Consultant under any payment or otherwise, such sums as represent its actual losses or a reasonable estimate of the same arising out of the Consultant’s failure to carry out his obligations under this Contract or under any other contract between the Employer and the Consultant and such sums as the Employer considers it is entitled to from the Consultant pursuant to this Contract or any other contract the Employer has with the Consultant. |
|  |  |  | 50.8B | Whenever under the Contract any sum of money shall be recoverable from or payable by the Consultant the same may be deducted from any sum then due, or which at any time thereafter may become due, to the Consultant under the Contract, or under any other contract with the Employer, or with the Crown. |
|  |  |  | 50.9 | If either Party intends to pay less than the notified sum, he notifies the other Party not later than fifteen (15) days before the final date for payment by stating the amount considered to be due and the basis on which that sum is calculated. A Party does not withhold payment of an amount due under this Contact unless he has notified his intention to pay less than the notified sum as required by the Contract. |
|  |  |  | 50.10 | In relation to giving notices under this clause 50 it is immaterial that the amount then considered to be due may be zero. |
|  |  |  | 50.11 | A pay less notice given by the Employer under this clause 50 may be given on its behalf by the Service Manager or any other person who the Employer notifies the Consultant as being authorised to do so |
|  |  |  | 50.12 | Where the Consultant enters into a sub-contract with a Subconsultant for the purpose of performing this Contract, he will cause a term to be included in such sub-contract which requires payment to be made to the Subconsultant within a specified period not exceeding thirty (30) days from receipt of a valid claim as defined by the sub-contract requirements. In the event that the duration of the service to be carried out under such sub-contract is agreed by the Consultant and Subconsultant as being more than forty-five (45) days, the Consultant and his Subconsultant may agree a timetable of one or more interim payments to be made upon satisfactory completion of previously agreed milestones. |
| Payment Under P2P |  |  | 51 |  |
|  |  |  | 51.1 | The Consultant will no later than ten (10) days before the Relevant Day submit an invoice for the notified sum (less any amount stated in a pay less notice issued under clause 50.9) (“P2P invoice”), using a properly prepared message structure and format for an invoice in accordance with the arrangements in Defform 30 Agreement. Once an invoice is certified and signed by the Service Manager it will be retained for audit purposes. |
|  |  |  | 51.2 | Upon submission of the P2P invoice the Employer will within five (5) Working Days receipt the request on the P2P invoice system for the notified sum (less any amount stated in a pay less notice issued under clause 50.9). |
|  |  |  | 51.3 | The receipting by the Employer of the request for the notified sum in clause 51.2 (“Payment Approval”) will enable payment to be made by the Bill Paying Branch. |
|  |  |  | 51.4 | NOT USED |
|  |  |  | 51.5 | Notwithstanding any statement to the contrary any documentation received from the Consultant, the Payment Approval will not be construed as acceptance by the Employer of the performance of the Consultant’s obligations nor as a waiver of his rights and remedies under this Contract or otherwise. |
| Unique Order Identifier |  |  | 51.6 | For the purposes of this clause, Unique Order Identifier (“UOI”) are generated by P2P. This Contract will reference UOIs. The application of UOIs is at the line item level. The Consultant must quote the applicable UOI in any communication concerning a line item. |
|  |  |  | 51.7 | Confirmation of receipt of deliveries by UOIs will not be construed as an acceptance for the purposes of DEFCON 525 or any other term of this Contract relating to acceptance by the Employer. |
| Payment & Interest |  |  | 52 |  |
|  |  |  | 52.1 | All valid, properly prepared invoices submitted to the Employer in accordance with this clause will be paid by the Employer on or before the Relevant Day. |
|  |  |  | 52.2 | Where and to the extent that the debt would otherwise be a 'qualifying debt' under the Late Payment of Commercial Debts (Interest) Act 1998 (“the Debts Act”): a) the interest provided for by this clause 52.2 is a contractual remedy and is not a statutory interest. Therefore, to the extent permissible by law, the provisions of the Debts Act relating to statutory interest will not apply to this Contract; b) from the day after the Relevant Day and thereafter until payment is made, simple interest at a rate calculated in accordance with clause 52.2 (c) of this clause, may be claimed by the Consultant on the value of all valid claims for payment (or unpaid parts thereof); c) without prejudice to clause 52.2(a), the rate of interest referred to in clause 52.2(b) will be the prevailing rate of statutory interest (as defined in the Debts Act) on the Relevant Day; d) no interest will be payable for any period of delay attributable to the conduct of the Consultant; e) all claims for interest made pursuant to this clause 52.2 will be notified in writing to the commercial officer; and f) any interest pursuant to this clause 52.2 will not form a part of the Prices and, as a remedy for late payment, will not be subject to VAT. |
|  |  |  | 52.3 | If the Employer corrects the amount due in a later payment approval, then the Employer will pay interest on the corrected amount. Interest will be calculated from the date when the correct amount was certified until the date when the corrected amount is included in a later payment approval. |
|  |  |  | 53 | NOT USED |
| Banking & Financial Dealings Act 1971 |  |  | 54 |  |
|  |  |  | 54.1 | Where any act is required to be done within a specified period after or from a specified date: - the period begins immediately after that date; and - where the specified period would include Christmas Day, Good Friday or a day which under the Banking and Financial Dealings Act 1971 is a Bank Holiday in England and Wales, or, as the case may be, in Scotland or in Northern Ireland, that day will be excluded. |
| Value Added Tax |  |  | 55 |  |
|  |  |  | 55.1 | The Prices exclude any UK output Value Added Tax (“VAT”) and any similar EU (or non-EU) taxes chargeable on the supply of the services by the Consultant to the Employer. |
|  |  |  | 55.2 | If the Consultant is required by UK VAT law to be registered for UK VAT (or has registered voluntarily) in respect of his business activities at the time of any supply, and the circumstances of any supply are such that the Consultant is liable to pay the tax due to HM Revenue and Customs (“HMRC”), the Employer will pay to the Consultant in addition to any sum due under clause 50.8 (or any other sum due to the Consultant) a sum equal to the output VAT chargeable on the tax value of the supply of the services, and all other payments under this Contract according to the law at the relevant tax point. In the event of any doubt about the applicability of the tax in such cases, the Employer may require the Consultant to obtain and pass to the Employer a formal ruling from HMRC. |
|  |  |  | 55.3 | The Consultant is responsible for the determination of VAT liability. The Consultant is to consult his local VAT office in cases of doubt. The Consultant will notify the Service Manager of the Employer’s VAT liability under this Contract, and any changes to it, when the liability is other than at the standard rate of VAT. |
|  |  |  | 55.4 | Where a supply of the services comes within the scope of UK VAT, but the Consultant is not required by UK VAT law to be registered for UK VAT (and has not registered voluntarily), the Employer will be responsible for assessing and paying over directly to HMRC any UK output VAT due in respect of the services. |
|  |  |  | 55.5 | Where the services are deemed to be supplied to the Employer outside the UK, the Consultant may be required by the laws of the country where the supply takes place to register there for EU (or non- EU) turnover or similar tax. In that event, the Employer will pay to the Consultant in addition to any sum due under clause 50.8 (and any other sum due to the Consultant under this Contract) sum equal to the tax the Consultant is liable to pay to the tax authorities of the country in question in relation to services. |
|  |  |  | 55.6 | For the avoidance of doubt, the Employer will not be required to pay any sum in respect of the Consultant’s input VAT (and / or similar EU and non-EU input taxes) in relation to the service supplied under this Contract. |
| Customs Duty Drawback |  |  | 57 |  |
|  |  |  | 57.1 | The Prices will be inclusive of any UK Customs and Excise or other duty payable. The Consultant will not be entitled to make, nor will the Consultant make any claim for drawback of UK import duty on any Plant, Materials or Equipment supplied for use for or in connection with the provision of the services which may be for shipment overseas. |

6 Compensation events

| Compensation events |  | 60 |  |
| --- | --- | --- | --- |
|  |  | 60.1 | The following are compensation events. |
|  |  |  | (1) The Employer gives an instruction under clause 17.1 changing the Scope. |
|  |  |  | (2) The Employer does not provide the right of access to the Affected Property in accordance with the Accepted Plan. |
|  |  |  | (3) The Employer does not provide something which he is to provide as stated in the Scope in accordance with on the Accepted Plan. |
|  |  |  | (4) The Service Manager gives an instruction to stop or not to start any work or to change a Key Date where that instruction is not due to the default, act or omission of the Contractor or any of his Personnel. |
|  |  |  | (5) The Employer does not work in accordance with the Accepted Plan or within the conditions stated in the Scope. |
|  |  |  | (6) NOT USED |
|  |  |  | (7) The Service Manager changes a decision which he has previously communicated to the Consultant. |
|  |  |  | (8) The Service Manager unreasonably withholds an acceptance (other than acceptance of a quotation for acceleration) for a reason not stated in this contract. |
|  |  |  | (9) A breach of contract by the Employer which is not one of the other compensation events in this contract and which after all reasonable mitigation by the Consultant causes a material increase in the Consultant’s costs of providing the services. |
| Notifying compensation |  | 61 |  |
| events |  | 61.1 | For compensation events which arise from the Service Manager giving an instruction or changing an earlier decision, the Service Manager notifies the Consultant of the compensation event at the time of giving the instruction or changing the earlier decision. He also instructs the Consultant to submit quotations in accordance with the Change Management Process, unless the event arises from a fault of the Consultant or quotations have already been submitted. The Consultant puts the instruction or changed decision into effect. |
|  |  | 61.2 | The Service Manager may instruct the Consultant to submit quotations for a proposed instruction or a proposed changed decision. The Consultant does not put a proposed instruction or a proposed changed decision into effect. |
|  |  | 61.3 | The Consultant notifies the Service Manager of an event which has happened or which he expects to happen as a compensation event if |
|  |  |  | - the Consultant believes that the event is a compensation event and |
|  |  |  | - the Service Manager has not notified the event to the Consultant. |
|  |  |  | If the Consultant does not notify a compensation event within three weeks of becoming aware of the event, he is not entitled to a change in Prices, the Completion Date or a Key Date unless the Service Manager should have notified the event to the Consultant but did not. |
|  |  | 61.4 | If the Service Manager decides that an event notified by the Consultant |
|  |  |  | - arises by reason of any act, omission, breach or default by the Consultant or his Personnel, |
|  |  |  | - has not happened and is not expected to happen, |
|  |  |  | - has no effect upon the Price, Completion or meeting a Key Date |
|  |  |  | - is not one of the compensation events stated in this contract, or |
|  |  |  | - has not been duly mitigated by the Consultant. |
|  |  |  | he notifies the Consultant of his decision that the Prices, the Completion Date and the Key Date are not to be changed. |
|  |  |  | If the Service Manager decides otherwise, he notifies the Consultant accordingly and instructs him to submit quotations in accordance with the Change Management Process. |
|  |  |  | If the Service Manager does not notify his decision to the Consultant within either |
|  |  |  | - two weeks of the Consultant’s notification or |
|  |  |  | - a longer period to which the Consultant has agreed, or |
|  |  |  | - a longer period specified by the Service Manager (being not more than 4 weeks), |
|  |  |  | the Consultant may notify the Service Manager to this effect. If the Service Manager fails to reply within two weeks of this notification, the Consultant will be entitled to issue a further notification to the Service Manager with a copy to the commercial manager. A failure by the Employer to reply within two weeks of this further notification is treated as acceptance by the Service Manager that the event is a compensation event and an instruction to submit quotations in accordance with the Change Management Process. |
|  |  | 61.5 | If the Service Manager decides that the Consultant did not give an early warning of the event which an experienced consultant could have given, he notifies this decision to the Consultant when he instructs him to submit quotations. |
|  |  | 61.6 | If the Service Manager decides that the effects of a compensation event are too uncertain to be forecast reasonably, he states assumptions about the event in his instruction to the Consultant to submit quotations. Assessment of the event is based on these assumptions. If any of them is later found to have been wrong, the Service Manager notifies a correction. |
|  |  | 61.7 | A compensation event is not notified after the defects date. |
|  |  | 61.8 | A compensation event is not be notified where the reason for the event arises from any act, omission or other default of the Consultant or his Personnel. |
| Quotations for |  | 62 |  |
| compensation events |  | 62.1 | After discussing with the Consultant different ways of dealing with the compensation event which are practicable, the Service Manager may instruct the Consultant to submit alternative quotations. The Consultant submits the required quotations to the Service Manager and may submit quotations for other methods of dealing with the compensation event which he considers practicable. |
|  |  | 62.2 | Quotations for compensation events comprise proposed changes to the Prices and any delay to the Completion Date and Key Dates assessed by the Consultant. The Consultant submits details of his assessment with each quotation. If the plan for remaining work is altered by the compensation event, the Consultant includes the alterations to the Accepted Plan in his quotation. |
|  |  | 62.3 | The Consultant submits quotations as soon as possible, but in any event, within three weeks of being instructed to do so by the Service Manager. The Service Manager replies within four weeks of the submission. His reply is |
|  |  |  | - an instruction to submit a revised quotation, |
|  |  |  | - an acceptance of a quotation, |
|  |  |  | - a notification that a proposed instruction will not be given or a proposed changed decision will not be made or |
|  |  |  | - a notification that he will be making his own assessment. |
|  |  | 62.4 | The Service Manager instructs the Consultant to submit a revised quotation only after explaining his reasons for doing so to the Consultant. The Consultant submits the revised quotation as soon as possible, but in any event within three weeks of being instructed to do so. |
|  |  | 62.5 | The Service Manager extends the time allowed for |
|  |  |  | - the Consultant to submit quotations for a compensation event and |
|  |  |  | - the Service Manager to reply to a quotation |
|  |  |  | if the Service Manager and the Consultant agree to the extension before the submission or reply is due. The Service Manager notifies the extension that has been agreed to the Consultant. |
|  |  | 62.6 | If the Service Manager does not reply to a quotation within the time allowed, the Consultant may notify the Service Manager to this effect. If the Consultant submitted more than one quotation for the compensation event, he states in his notification which quotation he proposes is to be accepted. If the Service Manager fails to reply within two weeks of this notification the Consultant will be entitled to issue a further notification to the Service Manager with a copy to the commercial officer. A failure by the Service Manager to reply within two weeks of this further notification is treated as acceptance by the Service Manager that the event is a compensation event and an instruction to submit quotations in accordance with the Change Management Process. |
| Assessing compensation |  | 63 |  |
| events |  | 63.1 | The changes to the Prices are assessed as the effect of the compensation event upon the Prices, using : |
|  |  |  | - the rates and prices contained in the Price List; or |
|  |  |  | - exceptionally, where the Consultant can demonstrate to the entire satisfaction of the Service Manager that the rates and prices contained in the Price List are not appropriate for pricing the effect of the compensation event on the Prices, the Consultant shall submit his proposed revision to the Fixed Prices. In such circumstances the Consultant must demonstrate to the complete satisfaction of the Service Manager that the rates and prices are the most advantageous and represent value for money for the Employer. |
|  |  | 63.2 | The effect of a compensation event may reduce as well as increase the Prices. |
|  |  | 63.3 | A delay to the Completion Date is assessed as the length of time that, due to the compensation event, planned Completion is later than planned Completion as shown on the Accepted Plan. A delay to a Key Date is assessed as the length of time that, due to the compensation event, the planned date when the Condition stated for a Key Date will be met is later than the date shown on the Accepted Plan. |
|  |  | 63.4 | The rights of the Employer and the Consultant to changes to the Prices, the Completion Date and the Key Dates are their only rights in respect of a compensation event provided that a compensation event under the grounds of clause 60.1(2), 60.1(3) and/or 60.1(5) shall not entitle the Consultant to any rights or remedies otherwise than as set out in clause 63.3 and so that the provisions of clauses 62 and 63 allowing for any changes increasing the Prices shall not apply in the case of these compensation events. |
|  |  | 63.5 | If the Service Manager has notified the Consultant of his decision that the Consultant did not give an early warning of a compensation event in accordance with clause 15 which an experienced consultant could have given, the event is assessed as if the Consultant had given early warning and had taken such actions as the Service Manager (acting reasonably) decided should have been taken to mitigate, avoid or reduce any increase to the total of the Prices or any impairment of the performance of the services.. |
|  |  | 63.6 | Assessment of the effect of a compensation event includes risk allowances for cost and time for matters which have a significant chance of occurring and are at the Consultant’s risk under this contract. |
|  |  | 63.7 | Assessments are based upon the assumptions that the Consultant reacts competently and promptly to the compensation event that any costs due to the event are reasonably incurred and that the Accepted Plan can be changed. |
|  |  | 63.8 | Where the Price List has been changed consequent upon a compensation event than these Prices may be used for subsequent assessments of the Prices for Services Performed to Date. |
|  |  | 63.9 | The following are deducted from the assessment of compensation events |
|  |  |  | - the cost of events for which this Contract requires the Consultant to insure and |
|  |  |  | - other costs paid to the Consultant by insurers. |
| The Employer’s |  | 64 |  |
| assessments |  | 64.1 | The Service Manager assesses a compensation event via his own Task Order. |
|  |  |  | - if the Consultant has not submitted a quotation and details of his assessment within the time allowed, |
|  |  |  | - if the Service Manager decides that the Consultant has not assessed the compensation event in accordance with this Contract in a quotation and he does not instruct the Consultant to submit a revised quotation, |
|  |  |  | - if, when the Consultant submits quotations for a compensation event, he has not submitted a plan or alterations to a plan which this Contract requires him to submit or |
|  |  |  | - if, when the Consultant submits quotations for a compensation event, the Service Manager has not accepted the Consultant’s latest plan for one of the reasons stated in this Contract. |
|  |  | 64.2 | The Service Manager assesses a compensation event using his own assessment of the plan for the remaining work if |
|  |  |  | - there is no Accepted Plan or |
|  |  |  | - the Consultant has not submitted a programme or alterations to a plan for acceptance as required by this Contract. |
|  |  | 64.3 | The Service Manager notifies the Consultant of his assessment of a compensation event and gives him details of it within the period allowed for the Consultant’s submission of his quotation for the same event. This period starts when the need for the Service Manager’s assessment becomes apparent. |
|  |  | 64.4 | If the Service Manager does not assess a compensation event within the time allowed, the Consultant may notify the Service Manager to this effect. If the Consultant submitted more than one quotation for the compensation event, he states in his notification which quotation he proposes is to be accepted. If the Service Manager fails to reply within two weeks of this notification the Consultant will be entitled to issue a further notification to the Service Manager with a copy to the commercial officer. A failure by the Service Manager to reply within three weeks of this further notification is treated as acceptance of the Consultant’s quotation by the Service Manager. |
| Implementing |  | 65 |  |
| compensation events |  | 65.1 | A compensation event is implemented when |
|  |  |  | - the Service Manager notifies his acceptance of the Consultant’s Task Order and in accordance with the Change Management Process, |
|  |  |  | - the Service Manager notifies the Consultant of his own assessment via a Task Order or |
|  |  |  | - a Consultant’s quotation is treated as having been accepted by the Service Manager in accordance with clause 64.4. |
|  |  | 65.2 | The assessment of a compensation event is not revised if a forecast upon which it is based is shown by later recorded information to have been wrong. |
|  |  | 65.3 | The changes to the Price List are included in the Task Order (or the Consultant’s Task Order which the Service Manager has accepted) implementing a compensation event. |

7 Rights to material

| The Parties’ use of |  | 70 |  |
| --- | --- | --- | --- |
| material |  | 70.1 | The Employer has the right to use the material provided by the Consultant for the purpose stated in the Scope. The Consultant obtains from a Subconsultant, equivalent rights for the Employer to use material prepared by the Subconsultant. |
|  |  | 70.2 | On Completion of the whole of the services, the Consultant: |
|  |  |  | - returns to the Employer, materials and Materiel provided by the Employer; and |
|  |  |  | - provides information and other things as stated in the Scope. |
|  |  | 70.3 | The Consultant has full responsibility and liability for all materials and Materiel during the carrying out of the services and compensates the Employer for any loss or damage occurring to the same. |
|  |  | 70.4 | The Consultant may use the material provided by him under this Contract for other work unless stated otherwise in the Scope. |
| Issued Property |  | 71 | For the purpose of this clause 71 the term “Issued Property” will mean any materials and Materiel provided by the Employer to the Consultant under this Contract. |
|  |  | 71.1 | Subject to clauses 71.2 and 71.5 below, within 14 days of receipt of any Issued Property provided by the Employer, or such other longer period as may be specified in this Contract, the Consultant will: a) check the Issued Property to verify that it corresponds with the Issued Property specified in this Contract; b) conduct a reasonable visual inspection; and c) conduct any additional inspection and testing as may be necessary and practicable to check that the Issued Property is not defective or deficient for the purpose for which it has been provided; and notify the Employer of any defects, deficiencies or discrepancies discovered. |
|  |  | 71.2 | Where Issued Property is packaged it will not be unpacked earlier than is necessary. The period identified at clause 71.1 above will count from the date on which packages are opened. |
|  |  | 71.3 | The Employer will within a reasonable time after receipt of any notice under clause 71.1 replace, re-issue or authorise repair of Issued Property agreed to be defective or deficient and, if appropriate, the Service Manager will revise the delivery schedule. If appropriate, the Service Manager will also issue written instructions for the return or disposal of the defective or deficient Issued Property. |
|  |  | 71.4 | In the event that the Employer fails to provide, replace, or authorise repair of defective or deficient Issued Property within a reasonable time of receipt of a notice in accordance with clause 71.1, if appropriate a fair and reasonable revision will be made to the delivery schedule provided that the Consultant has taken all reasonable measures to mitigate the consequences of any such delay. |
|  |  | 71.5 | Clauses 71.1 – 71.4 do not apply in the following circumstances: a) where Issued Property is issued for the purpose of repair, overhaul, conversion or other work to be performed on the Issued Property, inspection of such property will be as specified in this Contract; b) where the Consultant can show that the Issued Property cannot be fully tested until it has been integrated with other items, inspection of such property will be as specified in this Contract. |
|  |  | 71.6 | Subject to clause 71.9 below and any limitation or exclusion of liability as may be specified in this Contract, the Consultant will be responsible for the safe custody and due return of Issued Property, whether or not incorporated into the Affected Property, and will be responsible for all loss or damage thereto, until re-delivered in accordance with the Employer's instructions or until the expiry of the period specified in clause 71.10. |
|  |  | 71.7 | The Consultant will be responsible for such calibration and maintenance of the Issued Property as is specified in the Scope. |
|  |  | 71.8 | If requested, the Employer, within a reasonable time, and where practicable before delivery of the Issued Property, will notify the Consultant of the value of the Issued Property. |
|  |  | 71.9 | The Consultant will not be liable in respect of: a) defects or deficiencies notified to the Employer in accordance with clause 71.1 or latent defects which the Consultant can show could not reasonably have been discovered by means of the activities described at clause 71.1; b) fair wear and tear in Issued Property resulting from its normal and proper use in the execution of this Contract (except insofar as the deterioration is contributed to by any misuse, lack of care or want of maintenance by the Consultant); c) Issued Property rendered unserviceable as a direct result of ordinary performance of this Contract; d) any loss or damage to Issued Property arising from: - aircraft or other aerial devices or objects dropped from them, including pressure waves caused by aircraft or such devices whether travelling at sonic or supersonic speeds; - ionising radiation or contamination by radioactivity from any nuclear fuel or from nuclear waste from the combustion of nuclear fuel; - the radioactive, toxic, explosive or other hazardous properties of any nuclear assembly or nuclear component thereof; - riot, civil commotion, civil war, rebellion, revolution, insurrection, military or usurped power or acts of the Queen’s enemies. |
|  |  | 71.10 | On Completion of the whole of the services the Consultant will forward a list of Issued Property still held to the Service Manager. Return or disposal of such Issued Property will be as specified in the Scope, or as instructed by the Employer or Service Manager at Contract completion. If no disposal instructions are specified in this Contract the Service Manager will provide such instructions within two months of the Consultant's written request to do so. |
| Publicity |  | 72 |  |
|  |  | 72.1 | The Consultant may publicise the services only with the Employer’s written agreement. |
|  |  | 72.2 | The Consultant does not disclose information obtained in connection with the services except when necessary to carry out his duties under this Contract. |

8 Indemnity, insurance and liability

| Indemnity |  | 80 |  |  |
| --- | --- | --- | --- | --- |
|  |  | 80.1 | The Consultant indemnifies the Employer against losses, damages, expenses, claims, proceedings, compensation and costs payable arising out of a breach by the Consultant of its obligations under this contract or an infringement by the Consultant of the rights of Others, except an infringement which arose out of the use by the Consultant of things provided by the Employer. |  |
| Insurance cover |  | 81 |  |  |
|  |  | 81.1 | The Consultant provides the insurances stated in the Insurance Table except any insurance which the Employer is to provide as stated in the Contract Data. The insurances provide cover from the Contract Date until the end of the periods stated in the Contract Data. |  |
|  |  |  | INSURANCE TABLE |  |
|  |  |  | Insurance against | Minimum amount of cover |
|  |  |  | Liability of the Consultant for claims made against him arising out of his failure to use the skill and care normally used by professionals providing services similar to the services | £30,000,000 |
|  |  |  | Liability for death of or bodily injury to a person (not an employee of the Consultant) or loss of or damage to property resulting from an action or failure to take action by the Consultant | £10,000,000 |
|  |  |  | Liability for death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with this contract | £10,000,000 |
|  |  | 81.2 | When requested by a Party the other Party provides certificates from his insurer or broker stating that the insurances required by this contract are in force. |  |
|  |  | 81.3 | The Consultant shall not be entitled to recover from the Employer any sum paid by way of excess or deductible under the insurances whether under the Prices in the Contract; through any other terms of this Contract; or otherwise. |  |
|  |  | 81.4 | Neither failure to comply nor full compliance with the insurance provisions of this Contract shall limit or relieve the Consultant of its liabilities and obligations under this Contract and in particular the Consultant’s obligations in compliance with any indemnity provisions contained in this Contract. |  |
|  |  | 81.5 | The supply to the Employer of any evidence of insurance cover shall not imply acceptance by the Employer that the extent of insurance cover is sufficient or that the terms and conditions thereof are satisfactory, in either case, for the purposes of this Contract. |  |

| Nuclear Indemnity |  | 82 |  |
| --- | --- | --- | --- |
|  |  | 82.1 | Definitions In this clause:- - "Beneficiaries" means the Consultant and any sub-consultant of the Consultant, or any sub-consultant of such sub-consultant, provided that in the case of a sub-consultant (or sub-consultant of a sub-consultant), the Employer has agreed in writing that such person shall be a Beneficiary for the purposes of this definition; - "Nuclear Accident" shall have the meaning ascribed to it in BR3019(1) Part 1, namely, "an unexpected event which is likely to lead to, or has resulted in, a release of fission products external to the fuel"; - “Naval Base” means Her Majesty’s Naval Base Clyde, including Faslane Naval base & RNAD Coulport - "Nuclear Matter" shall have the meaning ascribed to it under section 26 of the Nuclear Installations Act 1965 and shall also include any nuclear fuel and any explosive nuclear assembly or nuclear component thereof; - "Nuclear Reactor" means any plant (including any machinery, equipment or appliance) designed or adapted for the production of atomic energy by a fission process in which a controlled chain reaction can be maintained without an additional source of neutrons; - “Paris/Brussels Conventions” means the Paris Convention on Third Party Liability in the Field of Nuclear Energy of 1960, as supplemented by the Brussels Supplementary Convention of 1963 and as amended by the Joint Protocol Relating to the Application of the Vienna Convention and the Paris Convention of 1988, each as amended, supplemented and/or substituted from time to time and all matters agreed pursuant to their terms; - "Radioactive Material" shall have the meaning ascribed to it under section 1 of the Radioactive Substances Act 1993; - "Radioactive Waste" shall have the meaning ascribed to it under section 2 of the Radioactive Substances Act 1993 and shall include any other nuclear waste and nuclear waste from combustion or any nuclear fuel and nuclear waste from any explosive nuclear assembly or nuclear component thereof; and References in this Contract to any legislation (including without limitation the Nuclear Installations Act 1965 and the Radioactive Substances Act 1993) shall be such legislation as supplemented, amended or replaced from time to time (including in particular the implementation into domestic law of any past or future changes to the Paris/Brussels Conventions). |
|  |  | 82.2 82.2 | Indemnity The Employer shall indemnify and keep the Beneficiaries indemnified from and against:- 1.9 any loss or contamination of, or damage to, any property of, leased or on hire or on loan to the Beneficiaries (other than property so leased, on hire or on loan which is owned by the Employer) and any loss of use thereof thereby suffered by the Beneficiaries and any reasonable expenses (but not loss of profit) properly incurred as a direct result of such loss, contamination or damage; or - 1.10 any action, claim (including for the avoidance of doubt any claim which arises out of or results from the acts or omissions of the Beneficiaries or which is made under the Radiation Workers Compensation Scheme) or proceedings brought by a third party (including for the avoidance of doubt employees, officers, agents or sub-contractors of any tier of the Beneficiaries and employees, officers, agents or sub-contractors of any tier of the Employer); insofar as such loss, damage, contamination, loss of use, action, claim or proceedings as aforesaid ("Liability") shall arise out of or result from:- (a) the radioactive properties, or a combination of those and any toxic, explosive or other hazardous properties of any Nuclear Matter, Radioactive Material or Radioactive Waste which: (i) is at the Naval Base, or is in the course of carriage between one part of the Naval Base and another; (ii) is discharged on or from the Naval Base, or in the course of carriage between one part of the Naval Base and another; or - is intended to be used, is being used or has been used in connection with the operation of a Nuclear Reactor in any nuclear powered warship which is, or was, the property of the Employer or which is or was at the Naval Base during the Contract Period of the Framework Agreement or any Contract made under or pursuant to it with the agreement of the Employer; or - the emission of ionising radiations on or from the Naval Base; and - 1.11 any action, claim or proceedings brought by a third party in respect of any matter for which the Employer is liable pursuant to the Nuclear Installations Act 1965 by virtue of its responsibility under a licence under that Act as authorisee in respect of the Naval Base, to the extent of that liability. Exclusions - 1.11 The indemnity in paragraph 82.2 shall not apply to the extent:- - 1.11.1 of the first £50,000 of any such Liability, except where the Liability arises out of or results from a Nuclear Accident, in which case the figure shall be £100,000; or - 1.11.2 to which the Beneficiaries are indemnified under and successfully indemnified by any other provision of this Contract or any contract made under or pursuant to it ; or - 1.11.3 to which the Beneficiaries are insured in respect of and successfully insured against such Liability. |
|  |  | 82.3 | - Conduct of Claims - 1.12 The Beneficiaries shall:- - 1.12.1 forthwith upon sustaining any loss or damage or being notified of any claim or demand by a third party to which, in each case, paragraph 82.2 applies, furnish in writing to the Employer particulars thereof and thereafter afford to the Employer such assistance and furnish such particulars and information as the Employer may from time to time reasonably require; - 1.12.2 allow the Employer after receiving a request in writing from the Employer to have control of all actions, claims or proceedings under paragraph 1.10 above and the exclusive right to determine the conduct of such actions, claims or proceedings, including the right to appoint counsel and solicitors; and - 1.12.3 not without the prior written consent of the Employer, pay, compound or settle any action, claim or proceeding within the scope of this indemnity nor knowingly do nor knowingly permit anything to be done which may prejudice or adversely affect the defence or disposal thereof. |
|  |  | 82.4 | - The indemnity hereby given shall extend to any Liability which the Beneficiaries may, with the prior consent in writing of the Employer, assume or incur (whether or not legally required so to do), by reason of any indemnity given by the Beneficiaries. |
|  |  | 82.5 | - Waiver - The Employer hereby waives any claim against the Beneficiaries arising out of or resulting from any of the circumstances referred to in paragraph 82.2 above, provided always that this paragraph 82.5 shall not have effect in relation to the first £50,000 of any such claim except where the claim arises out of or results from a Nuclear Accident, in which case the figure shall be £100,000. - Where, in terms of paragraphs 3.1 and 6 above, the liability of the Employer is expressed to exist only above a particular monetary threshold, then that threshold shall apply separately to each and every Beneficiary. |

9. Termination

| Termination |  |  |  |  | 90 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 90A.1 |  |  | If either Party wishes to terminate the Consultant’s obligation to Provide the Service, he notifies the Service Manager and the other Party giving details of his reason for terminating. The Services Manager issues a termination certificate to both Parties promptly if the reason complies with this Contract. |  |
|  |  |  |  |  | 90.1 |  |  | The Employer may terminate the Consultant’s obligation to Provide the Services by notifying the Consultant if the Consultant has done one of the following or its equivalent. |  |
|  |  |  |  |  |  |  | - If the Consultant is an individual and has |  |  |
|  |  |  |  |  |  | - presented his petition for bankruptcy, |  |  |  |
|  |  |  |  |  |  | - had a bankruptcy order made against him, |  |  |  |
|  |  |  |  |  |  | - had a receiver appointed over his assets or |  |  |  |
|  |  |  |  |  |  | - made an arrangement with his creditors. |  |  |  |
|  |  |  |  |  |  | - If the Consultant is a company or partnership and has |  |  |  |
|  |  |  |  |  |  | - had a winding-up order made against it, |  |  |  |
|  |  |  |  |  |  | - had a provisional liquidator appointed to it, |  |  |  |
|  |  |  |  |  |  | - passed a resolution for winding-up (other than in order to amalgamate or reconstruct), |  |  |  |
|  |  |  |  |  |  | - had an administration order made against it, |  |  |  |
|  |  |  |  |  |  | - had a receiver, receiver and manager, or administrative receiver appointed over the whole or a substantial part of its undertaking or assets or |  |  |  |
|  |  |  |  |  |  | - made an arrangement with its creditors. |  |  |  |
|  |  |  | 90.2 |  |  | The Consultant may terminate his obligation to Provide the Services by notifying the Employer if the Employer has not paid an amount certified by the Service Manager as properly due and payable (and no valid pay less notice has been given) within thirteen weeks of the issue of a notice by the Consultant to the Employer that payment is overdue. |  |  |  |
|  |  |  | 90.3 |  |  | The Employer may terminate the Consultant’s obligation to Provide the Services by notifying the Consultant if |  |  |  |
|  |  |  |  |  |  | - the Employer no longer requires the Consultant to carry out the services, |  |  |  |
|  |  |  |  |  |  | - the Consultant has failed to comply with his obligations and has not put the default right within two weeks of a notification by the Employer, |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 19A.4 apply, |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 19I.11apply, |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 26A.3 apply, |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 26B.2 apply, |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 26C.11 apply, or |  |  |  |
|  |  |  |  |  |  | - the provisions of clause 26G.7 apply. |  |  |  |
|  |  |  | 90.4 |  |  | The Employer may terminate the Consultant’s obligation to Provide the Services by notifying the Consultant if an event occurs which |  |  |  |
|  |  |  |  |  |  | - stops the Consultant completing the services or |  |  |  |
|  |  |  |  |  |  | - stops the Consultant completing the services by the date shown on the Accepted Plan and is forecast to delay Completion by more than 13 weeks, |  |  |  |
|  |  |  |  |  |  | and which |  |  |  |
|  |  |  |  |  |  | - neither Party could prevent and |  |  |  |
|  |  |  |  |  |  | - an experienced consultant would have judged at the Contract Date to have such a small chance of occurring that it would have been unreasonable for him to have allowed for it. |  |  |  |
| Procedures on termination |  |  |  |  | 91 |  |  |  |  |
|  |  |  |  |  | 91.1 |  |  |  | On termination |
|  |  |  |  |  |  |  |  |  | - the Consultant does no further work necessary to Provide the Services, |
|  |  |  |  |  |  |  |  |  | - the Employer may complete the services (and employ other consultants for that purpose) and may use any material to which he has title and may instruct the Consultant to remove any Equipment and materials, |
|  |  |  |  |  |  |  |  |  | - the Employer may require the Consultant to assign the benefit of any subconsultancy or other contract related to performance of this contract to the Employer, |
|  |  |  |  |  |  |  |  |  | - The Employer may, at his discretion take over from the Consultant at a fair and reasonable price, if payment has not already been made, all used and undamaged materials, in the possession of the Consultant and properly provided by or supplied to the Contractor for the performance of this Contract. |
|  |  |  |  |  |  |  |  |  | - The Consultant will prepare and deliver to the Employer within an agreed period, or in default of agreement within such period as the Employer may specify, a list of all such unused and undamaged materials, in addition to materials vested in the Employer, liable to be taken over by or previously belonging to the Employer and will deliver these in accordance with the directions of the Employer. |
|  |  |  |  |  |  |  |  |  | - the Parties continue to comply with the constraints and obligations in this contract on, |
|  |  |  |  |  |  |  |  |  | - the use of material prepared or obtained by the Consultant, |
|  |  |  |  |  |  |  |  |  | - publicising the services, |
|  |  |  |  |  |  |  |  |  | - the Consultant gives to the Employer information resulting from work carried out to date and information the Consultant has obtained which he has a responsibility to provide under this contract, |
|  |  |  |  |  |  |  |  |  | - the Consultant shall provide to the Employer details of all additional costs including his profit that the Consultant has reasonably incurred in carrying out his obligations up to the date of the termination certificate but excluding all other losses including future losses and any other loss of profit arising by reason of the termination, - the Consultant shall as soon as reasonably possible, but in any event not more than 1 week after the notice of termination certificate, provide the Employer all financial documents to substantiate a final payment to the Consultant, - the Consultant shall soon as reasonably possible, but in any event not more than 2 weeks after the termination certificate, forward all accumulated records to the Employer for retention, |
|  |  |  |  |  |  |  |  |  | - the Consultant shall forthwith deliver to the Employer all records and documentation held in connection with the services. Furthermore, the Employer shall have the right to take possession of all results of services done by or on behalf of the Consultant under this Contract, - the Employer may complete any outstanding services itself, and - the Employer may employ any other consultant to complete any outstanding services and in either case may use such data, database, reports, drawings, computer software object code, source code and associated documentation, specifications, designs or other material generated, or inventions made, under this Contract which shall have vested in so as to become the property of the Employer. |
|  |  |  |  |  | 91.2 |  |  |  | Upon expiry or termination of all or any part of the Contract, the Consultant provides all reasonable co-operation, assistance and information to the Employer (and to any replacement contractor appointed by the Employer) for a period of up to six (6) months from the date of expiry of the Contract Period or termination if requested, to the extent necessary to effect an orderly assumption of the services by the Employer or the replacement consultant. |
|  |  |  |  |  | 91.3 |  |  |  | Save as otherwise expressly provided in the Contract: - termination or expiry of this Contract is without prejudice to any rights, remedies or obligations accrued under the Contract prior to termination or expiration and nothing in the Contract prejudices the right of either Party to recover any amount outstanding at such termination or expiry and termination of this Contract does not affect the continuing rights, remedies or obligations of the Employer or the Consultant under clause 8 (Indemnity, Insurance and Liability) and clause 92 (Procedures on Termination) and Clause 26C(IPR); 26 G (security measures) and/or clause 28 A (Employee transfers) and/or under any other provision of this Contract which is expressed to survive termination or which is required to give effect to such termination and the consequences of such termination. |
|  |  |  |  |  | 91.4 |  |  |  | On the termination of the Contract for any reason, the Consultant: - immediately returns to the Employer all Confidential Information, Personal Data and IP Materials relating to the Contract in its possession or in the possession or under the control of any Personnel which was obtained or produced in the course of providing the services; - immediately delivers to the Employer all property (including materials, documents, information and access keys) provided to the Consultant for the purposes of the Contract. Such property is to be handed back in good working order (allowance to be made for reasonable wear and tear); - assists and co-operates with the Employer to ensure an orderly transition of the services to any replacement contractor and/or the completion of any work in progress; promptly provides all information concerning the services which may reasonably be requested by the Employer for the purposes of adequately understanding the provision of the services or for the purpose of allowing the Employer or any replacement contractor to conduct due diligence. |
|  |  |  |  |  | 91.5 |  |  |  | If the Consultant does not immediately return all Confidential Information, IP Materials relating to the Contract and property, the Employer may recover possession thereof and the Consultant grants a licence to the Employer or its appointed agents to enter (for the purposes of such recovery) any premises of the Consultant or its Personnel. |
|  |  |  |  |  | 91.6 |  |  |  | Where the Contract is terminated the Consultant shall provide all reasonable assistance to assist with the orderly transition of the services to a replacement consultant and the provision of information concerning the services which the Employer may request free of charge. |
| Payment on termination |  |  |  |  | 92 |  |  |  |  |
|  |  |  |  |  | 92.1 |  |  |  | A final payment is made as soon as possible after termination. The amount due on termination includes |
|  |  |  |  |  |  |  |  |  | - an amount due assessed as for normal payments |
|  |  |  |  |  |  |  |  |  | Provided that the Employer shall not be liable to pay the Consultant any money on account of the Contract until all the costs of completion of the services, and all other loss and expense incurred by the Employer have been ascertained and the amount thereof agreed by the Employer. The Consultant shall then only be entitled to receive payment of any outstanding sum or sums (if any) as would (but for such termination) have been due to him in respect of any services which the Consultant has satisfactorily completed under this Contract prior to its termination after first deducting there from the amount of the Employer’s costs, damages, losses and expenses as aforesaid. If such amount of the Employer’s costs, damages, losses and expenses shall exceed the sum which would otherwise have been payable to the Consultant in respect of such services satisfactorily completed by the Consultant prior to termination of the Contract, then the Consultant shall upon demand pay to the Employer the amount of such excess and shall be deemed to be a debt due by the Consultant to the Employer and shall be recoverable accordingly with no deduction or set off whatsoever. In the event that either the Employer or the Consultant does not agree the sums calculated as owing, either party shall be entitled to invoke the dispute procedure in accordance with clause W1 within 1 week of being notified of sums due. In the event that no such notice is given, the amount thereof agreed by the Employer shall be final and conclusive. |

DISPUTE RESOLUTION

Option W1 (DEFCON 530)

W1.1	Subject always to the right of either Party to refer any dispute to adjudication as described in clauses W2.1 to W2.31 below, the Parties will attempt in good faith to resolve any dispute or claim arising out of or relating to this Contract through negotiations between the respective representatives of the Parties having authority to settle the matter, which attempts may include the use of any Alternative Dispute Resolution (“ADR”) procedure on which the Parties may agree.

W1.2	In the event that the dispute or claim is not resolved by negotiation, or where the Parties have agreed to use an ADR procedure, by the use of such procedure, the dispute shall be referred to arbitration.

W1.3	The Party initiating the arbitration shall give a written Notice of Arbitration to the other Party.  The Notice of Arbitration shall specifically state:

a)	that the dispute is referred to arbitration; and

b)	the particulars of the Contract out of or in relation to which the dispute arises.

W1.4	Unless otherwise agreed in writing by the Parties, the arbitration and this clause shall be governed by the provisions of the Arbitration Act 1996.

W1.5	It is agreed between the Parties that for the purposes of the arbitration, the arbitrator shall have the power to make provisional awards as provided for in Section 39 of the Arbitration Act 1996.

W1.6	For the avoidance of doubt it is agreed between the Parties that the arbitration process and anything said, done or produced in or in relation to the arbitration process (including any awards) shall be confidential as between the Parties, except as may be lawfully required in judicial proceedings relating to the arbitration or otherwise.  No report relating to anything said, done or produced in or in relation to the arbitration process may be made beyond the tribunal, the Parties, their legal representatives and any person necessary to the conduct of the proceedings, without the concurrence of all the parties to the arbitration.

W2.1	Either Party to the Contract may (insofar as the Housing Grants, Construction and Regeneration Act 1996 (as amended by the Local Democracy, Economic Development and Construction Act 2009) (“the Act”) applies) at any time refer any dispute arising under the Contract to adjudication in accordance with this clause notwithstanding that any legal proceedings have been commenced in respect of such dispute.

W2.2	Any decision of the Employer, the Service Manager’s instruction or change to the Scope which is the subject of adjudication shall remain in force until the decision of the Adjudicator.

W2.3	For the purposes of clauses W2.1 – W2.31 the term ‘dispute’ shall include any difference as defined by the Act.

W2.4	If either Party requires adjudication they shall notify the Adjudicator.  The notice shall:-

W2.4.1	specify the matter in dispute;

W2.4.2	set out the principal facts and arguments relating to the dispute; and

W2.4.3	have appended all relevant documents which the Party referring the disputes relies upon.

W2.5	A copy of the notice referred to in paragraph W2.4 and the appended relevant documents shall be sent to the other Party at the same time.

W2.6	The Adjudicator shall indicate, within four (4) days of receipt of a copy of the notice under paragraph W2.4, his willingness to act.

W2.7	Where the Adjudicator has not indicated his willingness to act in accordance with paragraph W2.6 or where no Adjudicator has been named in the Agreement, either Party may apply to the Chairman of The Technology and Construction Solicitors Association (“TeCSA”) for a nomination, in which case, the following procedure will apply:-

W2.7.1	the application shall be in writing, accompanied by a copy of the Contract (without copies of any annexed documents, unless they are relevant to the dispute), a copy of the written notice requiring adjudication, and TeCSA’s appropriate appointment fee;

W2.7.2	the Chairman of TeCSA shall endeavour to secure the appointment of an Adjudicator and the referral to him of the dispute within seven (7) days from the notice requiring adjudication; and

W2.7.3	any person so appointed, and not any person named in the Agreement whose readiness or willingness is in question, shall be the Adjudicator.

W2.8	The Chairman of TeCSA shall have the power by written notice to the Parties to replace the Adjudicator with another nominated person if and when it appears necessary to him to do so.  The Chairman of TeCSA shall consider whether to exercise such power if any party shall represent to him that the Adjudicator is not acting impartially, or that the Adjudicator is physically or mentally incapable of conducting the adjudication, or that the Adjudicator is failing with necessary dispatch to proceed with the adjudication or make his decision. In the event of a replacement under this clause, directions and decisions of the previous Adjudicator shall remain in effect unless reviewed and replaced by the new Adjudicator, and all timescales shall be recalculated from the date of the replacement.

W2.9	Where an Adjudicator has already been appointed in relation to another dispute arising out of the Contract, the Chairman of TeCSA may appoint either the same or a different person as the Adjudicator.

W2.10	Within seven (7) days of receipt of the notice referred to in clause W2.4, the other Party may submit to the Adjudicator any statement, representations or documents which that Party relies upon relating to the dispute.

W2.11	The scope of the Adjudication shall be the matters identified in the notice requiring adjudication, together with:-

W2.11.1	any further matters which all Parties agree should be within the scope of the Adjudication; and

W2.11.2	any further matters which the Adjudicator determines must be included in order that the adjudication may be effective and/or meaningful.

W2.12	The Adjudicator may rule upon his own substantive jurisdiction, and as to the scope of the adjudication.

W2.13	The underlying purpose of the adjudication is to resolve disputes between the Parties that are within the scope of the adjudication as rapidly and economically as is reasonably possible.

W2.14	Decisions of the Adjudicator shall be binding until the dispute is finally determined by arbitration pursuant to this clause W2 or by agreement.

W2.15	The Adjudicator shall have the power to review and revise any certificates or other things issued or made in accordance with the Contract.

W2.16	The Adjudicator shall act fairly and impartially, but shall not be obliged or empowered to act as though he were an arbitrator.

W2.17	The Adjudicator shall establish the procedure and timetable for the adjudication.

W2.18	Without prejudice to the generality of clause W2.17, the Adjudicator may if he thinks fit:-

W2.18.1	require the delivery of written statements of case;

W2.18.2	require any Party to produce a bundle of key documents, whether helpful or otherwise to that Party’s case, and to draw such inferences as may seem proper from any imbalance in such bundle that may become apparent;

W2.18.3	require the delivery to him and/or the other Parties of copies of any documents other than documents that would be privileged from production to a court;

W2.18.4	limit the length of any written or oral submission;

W2.18.5	require the attendance before him for questioning of any Party or employee or agent of any Party;

W2.18.6	make site visits;

W2.18.7	make use of his own specialist knowledge;

W2.18.8	obtain advice from specialist consultants, provided that at least one of the Parties so requests or consents;

W2.18.9	meet and otherwise communicate with any Party without the presence of other Parties;

W2.18.10	make directions for the conduct of the adjudication orally or in writing;

W2.18.11	review and revise any of his own previous directions;

W2.18.12	conduct the adjudication inquisitorially, and take the initiative in ascertaining the fact and the law; and

W2.18.13	reach his decision with or without holding an oral hearing, and with or without having endeavoured to facilitate an agreement between the Parties.

W2.19	The Adjudicator shall exercise such powers with a view of fairness and impartiality, giving each Party a reasonable opportunity, in light of the timetable, of putting his case and dealing with that of his opponent.

W2.20	The Adjudicator may not:-

W2.20.1	require any advance payment of, or security for, his fees;

W2.20.2	receive any written submissions from one Party that are not also made available to the other;

W2.20.3	refuse any Party the right at any hearing or meeting to be represented by any representative of that Party’s choosing who is present; or

W2.20.4	act or continue to act in the face of a conflict of interest.

W2.21	The Adjudicator shall reach a decision with twenty-eight (28) days of referral or such longer period as is agreed by the Parties after the said dispute has been referred to him. The Adjudicator shall be entitled to extend the said period of twenty-eight (28) days by up to 14 days with the consent of the Party by whom the dispute was referred.

W2.22	If a Party shall request adjudication, and it is subsequently established that he is not entitled to do so, that Party shall be solely responsible for the Adjudicator’s fees and expenses.

W2.23	Save as aforesaid, the Parties shall be jointly responsible for the Adjudicator’s fees and expenses including those of any specialist consultant appointed under clause W2.18.8. In his decision, the Adjudicator shall have the discretion to make directions with regard to those fees and expenses.  If no such directions are made, the Parties shall bear such fees and expenses in equal shares, and if any Party has paid more that such equal share, that Party shall be entitled to contribution from the other Party accordingly.

W2.24	The Adjudicator may in any decision direct the payment of such compound or simple interest as may be commercially reasonable.

W2.25	All decisions of the Adjudicator shall be in writing and shall include his reasons for his decision.

W2.26	Every decision of the Adjudicator shall be implemented without delay.  The Parties shall be entitled to such reliefs and remedies as are set out in the decision, and shall be entitled to summary enforcement of any such reliefs and remedies, regardless of whether such decision is, or is to be, the subject of any challenge or review.  No Party shall be entitled to raise any right of set-off, counterclaim or abatement in connection with any enforcement proceedings.

W2.27	Neither TeCSA, nor its Chairman, nor deputy, nor the Adjudicator nor any employee or agent of any of them shall be liable for anything done or not done in the discharge or purported discharge of his functions as Adjudicator, whether in negligence or otherwise, unless the act or omission is in bad faith.

W2.28	The adjudication and all matters arising in the course of it are and will be kept confidential by the Parties except insofar as necessary to implement or enforce any decision of the Adjudicator or as may be required for the purpose of any subsequent legal proceedings.

W2.29	In the event that any Party seeks to challenge or review any decision of the Adjudicator in any subsequent arbitration, the Adjudicator shall not be joined as a party to, nor shall he be subpoenaed or otherwise required to give evidence or provide his notes in, such arbitration.

W2.30	No Party shall, save in case of bad faith on the part of the Adjudicator, make any application to the courts whatsoever in relation to the conduct of the adjudication or the decision of the Adjudicator until such time as the Adjudicator has made his decision, or refused to make a decision, and until the Party making the application has complied with any such decision.

W2.31	In relation to any matter or thing as to which a decision of the Employer under the Contract is by the Contract expressed to be final and conclusive, the Adjudicator shall not be entitled to vary or overrule any such decision and the Consultant’s only remedy (if at all) shall be to financial compensation.

| Parent company | X4 |  |
| --- | --- | --- |
| guarantee | X4.1 | Upon the Contract Date the Consultant will execute and deliver to the Employer a parent company guarantee in the form set out in DIO DOC 11 executed as a deed and delivered by the Consultant’s parent company named in the Service Information. Notwithstanding any other provisions of this Contract no payments will become due to the Consultant under this Contract while the Consultant remains in default of this clause X4.1. |

| Task Order: | X19 |  |
| --- | --- | --- |
|  | X19.1 | (1) A Task Order is issued by the Service Manager when: - the Service Manager notifies his acceptance of the Consultant’s Task Order submitted in accordance with the Change Management Process; or - the Service Manager notifies his own Task Order in accordance with clause X19.1(2) or clause 64.1. 2) The Service Manager may issue his own Task Order if: - the Consultant has not complied with the requirements of the Change Management Process; or - the Service Manager decides that the Consultant has not properly priced any changes to the Prices in accordance with the Price List; or - the Consultant has not properly described any changes to the Scope; or - where applicable, the Consultant has not submitted a plan or alterations to a plan which this Contract requires him to submit; or - where applicable, the Service Manager has not accepted the Consultant’s latest plan for one of the reasons stated on this Contract; or - the Employer does not wish to proceed with the change to the Scope. |
| Providing the Service | X19.2 | A Task Order includes: - a detailed description of the changes to the Scope, - full details of the changes to the Prices and the Price List (assessed in accordance with the Price List).’ - details of changes to the Plan (if applicable) and the Completion Date. |
| Time | X19.3 | The Consultant does not start any services or work additional to the services until the Service Manager has issued a Task Order. Any services undertaken by the Consultant prior to such approval shall be undertaken entirely at the Consultant’s own risk. No approved change shall in any way vitiate or invalidate the Contract. No Task Order is issued after the end of the term of the Contract. |
| Introduction of Task Orders to Contract | X19.4 | Upon the issue of a Task Order by the Service Manager under clause X19.1(1) the Scope and/or the Prices and Price List and/or the Completion Date will be changed in accordance with the details set out in that Task Order (or the Consultant’s Task Order which the Service Manager has accepted). |

| Definitions | Y(UK)2 |  |
| --- | --- | --- |
|  | Y2.1 | (1) The Act is The Housing Grants, Construction and Regeneration Act 1996 as amended by the Local Democracy, Economic Development and Construction Act 2009. |
|  |  | (2) A period of time stated in days is a period calculated in accordance with Section 116 of the Act. |
| Dates for payment | Y2.2 | The date on which a payment becomes due is ten days after the assessment date. |
|  |  | The final date for payment is the Relevant Day. |
|  |  | The Service Manager’s certificate is the notice of payment to the Consultant specifying the amount of the payment due at the payment due date (the notified sum) and stating the basis on which the amount was calculated. |
| Notice of intention to withhold payment | Y2.3 | If either Party intends to pay less than the notified sum, he notifies the other Party not later than fifteen days (the prescribed period) before the final date for payment by stating the amount considered to be due and the basis on which that sum is calculated. A Party does not withhold payment of an amount due under this Contract unless he has notified his intention to pay less than the notified sum as required by this Contract. |
| Suspension of performance | Y2.4 | If the Consultant exercises his right under the Act to suspend performance it is a compensation event. |

# CONTRACT DATA

## Part one – Data provided by the Employer

|  | Completion of the data in full, according to the Options chosen, is essential to create a complete contract. |
| --- | --- |
| Statements given in all contracts |  |
| 1 General | - The conditions of contract are the conditions attached at [schedule 1] to the Framework Agreement. - The Employer is Name: The Secretary of State for Defence - Address: whose address for the purposes of the Contract shall be Defence Infrastructure Organisation, Commercial Team, Kentigern House, 65 Brown Street, Glasgow G2 8EX - The Adjudicator is Name TBC Address - The Service Manager is Name TBC - The services are as ordered under the relevant Demand Order in accordance with clause 3 or 4 of the Framework Agreement - The Scope is as described in the Framework Agreement - The language of this contract is English………………………………………………………. - The law of the contract is the law of England………………………………………………….. - The period for reply is ………4………………………… weeks. - The period for retention is ………………..…… years following Completion or earlier termination. - The Adjudicator nominating body is TBC. - The tribunal is TBC - The following matters will be included in the Risk Register |

| 2 The Parties' main responsibilities | The Affected Properties are identified in the attached documents as the same may vary from time-to-time, such changes will be introduced through the Change Management Process |  |  |
| --- | --- | --- | --- |
| 3 Time | - The starting date is to be confirmed. |  |  |
| 4 Quality | - The defects date is ……………………….. weeks after Completion of the whole of the services. |  |  |
| 5 Payment | - The currency of this contract is pounds sterling - The interest rate shall be the prevailing rate of statutory interest as defined in the Late Payment of Commercial Debts (Interest) Act 1998 as amended |  |  |
|  | - The Bill Paying Branch is DBS Finance, Walker House, Exchange Flags, Liverpool L2 3YL |  |  |
|  | - The commercial officer is Gillian Wallis………..…………………………… |  |  |
| 8 Indemnity, insurance and liability | - The amounts of insurance and the periods for which the Consultant maintains insurance are |  |  |
|  | - event | - cover | - period following Completion of the whole of the services or earlier termination |
|  | - failure of the Consultant to use the skill and care normally used by professionals providing services similar to the services | - [TENDERER TO INSERT AMOUNT AGREED UNDER FRAMEWORK AGREEMENT] - ……………………………. - in respect of each claim, without limit to the number of claims | - …………………................ |
|  | - death of or bodily injury to a person (not an employee of the Consultant) or loss of or damage to property resulting from an action or failure to take action by the Consultant | - [TENDERER TO INSERT AMOUNT AGREED UNDER FRAMEWORK AGREEMENT] - .............……………………. - in respect of each claim, without limit to the number of claims | - .............…………………… |
|  | - death of or bodily injury to employees of the Consultant arising out of and in the course of their employment in connection with this contract | - [TENDERER TO INSERT AMOUNT AGREED UNDER FRAMEWORK AGREEMENT] - …................................. - in respect of each claim, without limit to the number of claims | - ……………………............. |

|  | - The Employer provides the following insurances Nuclear indemnity |
| --- | --- |
| Optional statements | If the Employer has decided the completion date for the whole of the services - The completion date for the whole of the services is ………………………………. If no programme is identified in part two of the Contract Data - The Consultant is to submit a first programme for acceptance within ……………. weeks of the Contract Date. |
|  | If the Employer has identified work which is to meet a stated condition by a key date - The key dates and conditions to be met are condition to be met key date 1 LCR to be completed and issued Dec 15 2 3 |
|  | If the period in which payments are made is not three weeks and Y(UK)2 is not used - The period within which payments are made is …………………………………….. |
|  | If Y(UK)2 is used and the final date for payment is not 14 days after the date when payment is due - The period for payment is ……………………………………………………………… |
|  | If the Employer states any expenses - The expenses stated by the Employer are item amount |
|  | If the Consultant is to provide additional insurances - The Consultant provides these additional insurances 1. Insurance against Cover is Period of cover Deductibles are 2. Insurance against Cover is Period of cover Deductibles are |

|  | If the tribunal is arbitration - The arbitration procedure is - The place where arbitration is to be held is - The person or organisation who will choose an arbitrator - if the Parties cannot agree a choice or - if the arbitration procedure does not state who selects an arbitrator is If this contract is a subcontract and the main contract provides for joint adjudication of disputes - The main contract Adjudicator is ……………………………………………………… If Option X2 is used - The law of the project is ………………………………………………………………... |
| --- | --- |

|  | If Option X13 is used - The amount of the performance bond is …………………………………………….. |
| --- | --- |
|  | If Option X20 is used (but not if Option X12 is also used) - The incentive schedule for Key Performance Indicators is in …………………….. - A report of performance against each Key Performance Indicator is provided at intervals of …………………………………………………………………….. months. |
|  | If Option Z is used - The additional conditions of contract are …………………………………………….. |

| ## Part two – Data provided by the Consultant |  |
| --- | --- |
|  | Completion of the data in full, according to the Options chosen, is essential to create a complete contract. |
| Statements given in all contracts | - The Consultant is ………………………………………………………………………. Name …………………………………………………………………… Address ……………………………………………………………………… - The key persons are (1) Name Job Responsibilities Qualifications Experience (2) Name Job Responsibilities Qualifications Experience - The staff rates are name/designation rate see price file ………………………………….. ………………………………….. - The following matters will be included in the Risk Register |
| Optional statements | If the Consultant is to decide the completion date for the whole of the services - The completion date for the whole of the services is ……..……………….……….. If a programme is to be identified in the Contract Data - The programme identified in the Contract Data is ….……..……………….……….. If the Consultant states any expenses - The expenses stated by the Consultant are item amount ………………………………….. ………………………………….. |

|  | If the Consultant requires additional access - The Employer provides access to the following persons, places and things access to access date ………………………………….. ………………………………….. If Option A or C is used - The tendered total of the Prices is ……………………………………………………. |
| --- | --- |