## Sheet1
Coombe Cliff Conservatory
Date | Query | Response
2022-09-13 | During our site visit we noticed a cable from the Museum to the conservatory at high level. Do we know the reason for this cable | It used to have the power supply for the x2 external plug sockets mouted to it. The cable is now redundent and is included in the tender for removal.
| There is no work mentioned to the putty to the vertical sections of the glazing? | There has been no allowance for works to the vertical glazing at ground floor level within this package of works.
| What work is required to the "perspex" covering the low and high level fret work to the elevations. Some sections are cracked or broken and several fixings are missing. These will have to be removed to paint the fret work | No work is envisaged to the perspex. They will need to be removed and placed to one side, and then re-instated once painting completed.
| Is there a detailed paint specification? Is epoxy paint required and how many coats? Do you have a manufacturer in mind | No. Contractor can chose with approval.
| We have assumed we will only need to maintain a pedestrian access route to the end of the conservatory and then adjacent to the existing museum buildings | Fire exit routes are shown in the CDM information. These must remain accessible throughout. Access from the three white doors should b
| The temporary roof will require kentledges which will need to be positioned on the paving on one side and then through the hedge and onto the embankment the other | Noted and accepted.
| Are we to replace the last section of the RWP currently blocked and then to line this downpipe as it was not lined previously | An opening up specification from Conisbee has been provided to lalow this to be opened up and the blockage removed. The lining will happen outside of this contract.
| Are the existing fishscale glazing panes flat or curved as we could not ascertain during our site visit | From 2016 works all fishscales are flat. However at no poitn have single panes have not been removed to confirm.
| Do you have any other Program options as the time allocated is insufficient and mid winter is not the best time to carry out these works we would require around 5-6months on site As there is 7-8 weeks work in erecting and dismantling the scaffolding. | Unforutnately there is no alternative programme options. Weddings are booked in until the end of October, preventing an earlier start date, funding allocation expires on March 31st 2023. We remain in communication with DCMS (the funder of the works).