## Frequencies check (hidden)
Baseline/ILM | (empty)
B
ILM
TBC
(empty)
Total Result

## TM Recovery (hidden)
Sum of TM Recovery |  | Comments
SOR | Sub Asset Type | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised. | Not booked Major Project | (empty) | Total Result
4.8.11 | Conservation grassland / wildflower grassland
4.8.14 | Shrubs (Ornamental)
4.8.17 | Wildlife Housings / Structures
4.8.2 | Woodland
4.8.3.1 | Grass and vegetation
4.8.3.2 | Grass and vegetation
4.8.3.3 | Grass and vegetation
4.8.4.1 | Grass and vegetation
4.8.4.2 | Grass and vegetation
4.8.4.3 | Grass and vegetation
4.8.5.1 | Grass and vegetation
4.8.5.2 | Grass and vegetation
4.8.5.3 | Grass and vegetation
4.8.7 | Injurious weeds
4.8.8 | Invasive Plant Species
TBC | Grass and vegetation
Total Result

## Qts check (hidden)
SOR | - all -
Sum of Quants
When checking quats make sure exclude the multiple visit locations

## Intervention number check (hidden)
Max. of Intervention | Comments
Maintenance Route | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve. | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised. | Not booked Major Project | (empty) | Total Result
YNE1: M62 J22-23 |  |  |  | 2024-09-01 | 2024-09-01
YNE10: M62 J32-33 |  |  |  | 2024-08-01 | 2024-08-01
YNE100: A160 Brocklesby-Habrough |  |  |  | 2024-09-01 | 2024-09-01
YNE101: A160 Habrough-Manby |  |  |  | 2024-09-01 | 2024-09-01
YNE102: A162 Ferrybridge |  |  |  | 2024-08-01 | 2024-08-01
YNE103: A62 Gildersome |  |  |  | 2024-08-01 | 2024-08-01
YNE104: A631 Tinsley |  |  |  | 2024-07-01 | 2024-07-01
YNE105: A638 Redhouse |  |  |  | 2024-09-01 | 2024-09-01
YNE106: A1M J34-35 |  |  |  | 2024-09-01 | 2024-09-01
YNE107: A1M J35-36 |  |  |  | 2024-09-01 | 2024-09-01
YNE108: A1M J36-37 |  |  |  | 2024-10-01 | 2024-10-01
YNE109: A1M J37-38 |  |  |  | 2024-10-01 | 2024-10-01
YNE11: M62 J33-34 |  |  |  | 2024-09-01 | 2024-09-01
YNE110: A1 Redhouse-Barnsdale |  |  |  | 2024-09-01 | 2024-09-01
YNE111: A1 Barnsdale-Wentbridge |  |  |  | 2024-09-01 | 2024-09-01
YNE112: A1 Wentbridge-Darrington |  |  |  | 2024-08-01 | 2024-08-01
YNE113: A1 Darrington-A162 |  |  |  | 2024-09-01 | 2024-09-01
YNE114: A58 Chainbar |  |  |  | 2024-05-01 | 2024-05-01
YNE12: M62 J34-35 |  |  |  | 2024-09-01 | 2024-09-01
YNE13: M62 J35-36 |  |  |  | 2024-09-01 | 2024-09-01
YNE14: M62 J36-37 |  |  |  | 2024-09-01 | 2024-09-01
YNE15: M62 J37-38 |  |  |  | 2024-09-01 | 2024-09-01
YNE16: A63 NorthCave-SouthCave |  |  |  | 2024-08-01 | 2024-08-01
YNE17: A63 SouthCave-Welton |  |  |  | 2024-08-01 | 2024-08-01
YNE18: A63 Welton-Melton |  |  |  | 2024-08-01 | 2024-08-01
YNE19: A63 Melton-WesternInt |  |  |  | 2024-09-01 | 2024-09-01
YNE2: M62 J23-24 |  |  |  | 2024-04-01 | 2024-04-01
YNE20: A63 WesternInt-PrioryWay |  |  |  | 2025-03-01 | 2025-03-01
YNE21: A63 PrioryWay-BrightonSt |  |  |  | 2024-09-01 | 2024-09-01
YNE22: A63 BrightonSt-DaltrySt |  |  |  | 2024-09-01 | 2024-09-01
YNE23: A63 DaltrySt-Mytongate
YNE24: A63 Mytongate-Garrison
YNE25: A63 Garrison-Southcoates
YNE26: A1033 Southcoates-NorthernGate |  |  |  | 2024-09-01 | 2024-09-01
YNE27: A1033 NorthernGate-Marfleet |  |  |  | 2024-09-01 | 2024-09-01
YNE28: A1033 Marfleet-Somerden |  |  |  | 2025-02-01 | 2025-02-01
YNE29: A1033 Somerden-SaltEnd |  |  |  | 2024-09-01 | 2024-09-01
YNE3: M62 J24-25 |  |  |  | 2024-04-01 | 2024-04-01
YNE30: M606 J1-2 |  |  |  | 2024-05-01 | 2024-05-01
YNE31: M606 J2-3 |  |  |  | 2024-05-01 | 2024-05-01
YNE32: M621 Gildersome-J1 |  |  |  | 2024-08-01 | 2024-08-01
YNE33: M621 J1-2 |  |  |  | 2024-08-01 | 2024-08-01
YNE34: M621 J2-2a |  |  |  | 2024-08-01 | 2024-08-01
YNE35: M621 J2a-3 |  |  |  | 2024-08-01 | 2024-08-01
YNE36: M621 J3-4 |  |  |  | 2024-08-01 | 2024-08-01
YNE37: M621 J4-5 |  |  |  | 2024-08-01 | 2024-08-01
YNE38: M621 J5-6 |  |  |  | 2024-08-01 | 2024-08-01
YNE39: M621 J6-7 |  |  |  | 2024-08-01 | 2024-08-01
YNE4: M62 J25-26 |  |  |  | 2024-09-01 | 2024-09-01
YNE40: M621 J7-8 |  |  |  | 2024-08-01 | 2024-08-01
YNE41: A64 Bramham-Headley |  |  |  | 2024-11-01 | 2024-11-01
YNE42: A64 Headley-A162 |  |  |  | 2024-11-01 | 2024-11-01
YNE43: A64 A162-Tadcaster |  |  |  | 2024-11-01 | 2024-11-01
YNE44: A64 Tadcaster-Bilbrough |  |  |  | 2024-11-01 | 2024-11-01
YNE45: A64 Bilbrough-Askham |  |  |  | 2024-11-01 | 2024-11-01
YNE46: A64 Askham-Bondhill |  |  |  | 2024-12-01 | 2024-12-01
YNE47: A64 Bondhill-Fulford |  |  |  | 2024-12-01 | 2024-12-01
YNE48: A64 Fulford-Grimston |  |  |  | 2025-01-01 | 2025-01-01
YNE49: A64 Grimston-Hopgrove |  |  |  | 2025-01-01 | 2025-01-01
YNE5: M62 J26-27 |  |  |  | 2024-04-01 | 2024-04-01
YNE50: A64 NorthHopgroveSingle |  |  |  | 2025-01-01 | 2025-01-01
YNE51: A64 NorthHopgroveDual |  |  |  | 2025-01-01 | 2025-01-01
YNE52: A64 SouthMusleySingle |  |  |  | 2025-02-01 | 2025-02-01
YNE53: A64 Musley-PickeringInt |  |  |  | 2025-02-01 | 2025-02-01
YNE54: A64 PickeringInt-Brambling |  |  |  | 2025-02-01 | 2025-02-01
YNE55: A64 Brambling-Rillington |  |  |  | 2025-02-01 | 2025-02-01
YNE56: A64 Rillington-Sherburn |  |  |  | 2025-02-01 | 2025-02-01
YNE57: A64 Sherburn-Staxton |  |  |  | 2025-02-01 | 2025-02-01
YNE58: A64 Staxton-Seamer |  |  |  | 2025-02-01 | 2025-02-01
YNE59: A64 Seamer-Dunslow |  |  |  | 2025-02-01 | 2025-02-01
YNE6: M62 J27-28 |  |  |  | 2024-10-01 | 2024-10-01
YNE60: A64 Dunslow-Musham |  |  |  | 2025-02-01 | 2025-02-01
YNE61: M1 J30-31 |  | 2024-06-01 |  | 2024-10-01 | 2024-10-01
YNE62: M1 J31-32 |  | 2024-06-01 |  | 2024-10-01 | 2024-10-01
YNE63: M1 J32-33 |  | 2024-06-01 |  |  | 2024-06-01
YNE64: M1 J33-34South |  | 2024-06-01 |  |  | 2024-06-01
YNE65: M1 Tinsley |  | 2024-06-01 |  |  | 2024-06-01
YNE66: M1 J34North-35 |  | 2024-06-01 |  |  | 2024-06-01
YNE67: M1 J35-35a |  | 2024-06-01 |  |  | 2024-06-01
YNE68: M1 J35a-36 |  |  |  | 2024-10-01 | 2024-10-01
YNE69: M1 J36-37 |  |  |  | 2024-10-01 | 2024-10-01
YNE7: M62 J29-30 |  |  |  | 2024-10-01 | 2024-10-01
YNE70: M1 J37-38 |  |  |  | 2024-10-01 | 2024-10-01
YNE71: M1 J38-39 |  |  |  | 2024-10-01 | 2024-10-01
YNE72: M1 J39-40 |  |  |  | 2024-10-01 | 2024-10-01
YNE73: M1 J40-41 |  |  |  | 2024-05-01 | 2024-05-01
YNE74: M1 J41-42 |  |  |  | 2024-05-01 | 2024-05-01
YNE76: A628 Tintwistle-Crowden |  |  |  | 2024-09-01 | 2024-09-01
YNE77: A628 Crowden-Flouch |  |  |  | 2024-10-01 | 2024-10-01
YNE78: A616 Flouch-Deepcar |  |  |  | 2024-10-01 | 2024-10-01
YNE79: A616 Deepcar-Wortley |  |  |  | 2024-10-01 | 2024-10-01
YNE8: M62 J30-31 |  |  |  | 2024-10-01 | 2024-10-01
YNE80: A616 Wortley-Westwood |  |  |  | 2024-10-01 | 2024-10-01
YNE81: A616 Westwood-Stocksbridge |  |  |  | 2024-10-01 | 2024-10-01
YNE82: A61 |  |  |  | 2024-10-01 | 2024-10-01
YNE83: M18 Link-J1 | 2024-10-01 |  |  |  | 2024-10-01
YNE84: M18 J1-2 | 2024-09-01 |  |  | 2024-10-01 | 2024-10-01
YNE85: M18 J2-3 |  |  |  | 2024-10-01 | 2024-10-01
YNE86: M18 J3-4 |  |  |  | 2024-10-01 | 2024-10-01
YNE87: M18 J4-5 |  |  |  | 2024-10-01 | 2024-10-01
YNE88: M18 J5-6 |  |  |  | 2024-06-01 | 2024-06-01
YNE89: M18 J6-7 |  |  |  | 2024-06-01 | 2024-06-01
YNE9: M62 J31-32 |  |  |  | 2024-04-01 | 2024-04-01
YNE90: M180 Ings-J1 |  |  |  | 2025-02-01 | 2025-02-01
YNE91: M180 J1-2 |  |  |  | 2025-02-01 | 2025-02-01
YNE92: M180 J2-3 |  |  |  | 2025-02-01 | 2025-02-01
YNE93: M180 J3-4 |  |  |  | 2025-02-01 | 2025-02-01
YNE94: M180 J4-5 |  |  |  | 2025-02-01 | 2025-02-01
YNE95: M181 |  |  |  | 2025-03-01 | 2025-03-01
YNE96: A180 Barnetby-Brocklesby |  |  |  | 2025-03-01 | 2025-03-01
YNE97: A180 Brocklesby-Stallingborough |  |  |  | 2025-03-01 | 2025-03-01
YNE98: A180 Stallingborough-GreatCoates |  |  |  | 2025-03-01 | 2025-03-01
YNE99: A180 GreatCoates-Pyewipe |  |  |  | 2025-03-01 | 2025-03-01
(empty)
Total Result | 2024-10-01 | 2024-06-01 |  | 2025-03-01 | 2025-03-01

## Sheet5 (hidden)
Asset Type | - all -
Sum of Quants

## Sheet6 (hidden)
Asset Type | Sum of Quants
3000 - Landscape and Ecology
(empty)
Total Result

## Service Plan update 07.05.24
Maintenance Route | To be Maintained 2024/25? | Chart Section for ILM Sections | Location Detail for ILM Sections | Asset Type | Sub Asset Type | SOR | Activity | Quants | Baseline/ILM | Frequency | Intervention | Shift | TM Required | TM Booked? | Planned Start | Planned Completion | Jobs rasied? | Issues with Jobs/Quants | Comments
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 24488.3 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 6 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 296 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 143 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 43.53 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 23741.1 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 21040.554 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 5888.274 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main Intervention | 2024-04-01 | 2024-04-30
YNE1: M62 J22-23 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 16155.9 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 4 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 23726.7 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 186 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 232 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 120 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 76.49 | B | Annually | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 4484.8888 | ILM | 3 x per year (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31 | Yes | Quantities differ 201,846
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15332.4 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 11695.943 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 783.9403 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-04-01 | 2024-05-31
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 4484.8888 | ILM | 3 x per year (Apr-Sept) | 2 | Nights |  | No - to be booked if needed | 2024-06-01 | 2024-06-30 | Yes | Quantities differ 201,846
YNE10: M62 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 4484.8888 | ILM | 3 x per year (Apr-Sept) | 4 | Nights |  | No - to be booked if needed | 2024-08-01 | 2024-08-31 | Yes | Quantities differ 201,846
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 48847 | ILM | 5 x per year (Apr-Sept) | 1 | Days |  | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 48847 | ILM | 5 x per year (Apr-Sept) | 2 | Days |  | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 48847 | ILM | 5 x per year (Apr-Sept) | 3 | Days |  | Enhanced Maintenance 3 | 2024-06-01 | 2024-06-30 | Yes
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 827 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 54 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 5 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1902 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 48847 | ILM | 5 x per year (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31 | Yes
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3720.6 | B | Annually (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6577.6 | B | Annually (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 48847 | ILM | 5 x per year (Apr-Sept) | 5 | Days |  | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes
YNE100: A160 Brocklesby-Habrough | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 54878 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 48847 | ILM | 5 x per year (Apr-Sept) | 1 | Days |  | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 48847 | ILM | 5 x per year (Apr-Sept) | 2 | Days |  | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 48847 | ILM | 5 x per year (Apr-Sept) | 3 | Days |  | Enhanced Maintenance 3 | 2024-06-01 | 2024-06-30 | Yes
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1168 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 144 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 117 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 9 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 5979 | B | Annually | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 48847 | ILM | 5 x per year (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31 | Yes
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5709.6 | B | Annually (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 21080.1342 | B | Annually (Apr-Sept) | 4 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 48847 | ILM | 5 x per year (Apr-Sept) | 5 | Days |  | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes
YNE101: A160 Habrough-Manby | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 26649 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 923 | B | Annually | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 26 | B | Annually | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 33 | B | Annually | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 8 | B | Annually | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5742 | B | Annually (Apr-Sept) | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE102: A162 Ferrybridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 3423.23 | B | Annually (Apr-Sept) | 1 | Days |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 1 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4495.2 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 100 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 86 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 93 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2455.21 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 1854 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE103: A62 Gildersome | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 304.43 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 164 | B | Annually | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 48 | B | Annually | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 50 | B | Annually | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 4422.81 | B | Annually | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3737.7 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE104: A631 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 746.0946 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-07-01 | 2024-07-31
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 459 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 61 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 204 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 8 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1710.36 | B | Annually | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE105: A638 Redhouse | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3863.7 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main Intervention | 2024-09-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 1 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 5079 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 85 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 10 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 48 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 95.32 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 23473.8 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 9476.8 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE106: A1M J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 216629.3 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30 | Yes | Quants differ 68120
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1669 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 66 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 12 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 19 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 175.11 | B | Annually | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7745.4 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6607.889 | B | Annually (Apr-Sept) | 1 | Nights |  | Main Intervention | 2024-08-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2955.9 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE107: A1M J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 24483.8 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2825 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 88 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 12 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 29 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 161.79 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 12710.7 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 12715.273 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE108: A1M J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 147082.2 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-10-01 | 2024-10-31 | Yes | Quants differ 28799
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2113 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 78 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 27 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 40.09 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10521 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 12932 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 41.7754 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 5425.6 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE109: A1M J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 95701.5 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-10-01 | 2024-10-31 | Yes | Quants differ 44748
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2358.6 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 106 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 13 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 73 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 375.86 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15829.2 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 21274.484 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE11: M62 J33-34 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 19697 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 1103.8214 | ILM | 3 x per year (Apr-Sept) | 1 | Days |  | No - Enhanced Maintenance 1 | 2024-05-01 | 2024-05-31 | Yes
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 1103.8214 | ILM | 3 x per year (Apr-Sept) | 2 | Days |  | No - Enhanced Maintenance 2 | 2024-07-01 | 2024-07-31 | Yes
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2813 | B | Annually | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 200 | B | Annually | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 194 | B | Annually | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 18 | B | Annually | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 4731.53 | B | Annually | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 1103.8214 | ILM | 3 x per year (Apr-Sept) | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30 | Yes
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 16866.9 | B | Annually (Apr-Sept) | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 22911.439 | B | Annually (Apr-Sept) | 3 | Nights | Yes | Main intervention | 2024-08-01 | 2024-09-30
YNE110: A1 Redhouse-Barnsdale | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 402.3 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1673 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 96 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 26 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 15 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 535.78 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8708.4 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 16447.871 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE111: A1 Barnsdale-Wentbridge | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2204.3 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1812 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 114 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 7 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 8 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1916.52 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9909.9 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE112: A1 Wentbridge-Darrington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2026.019 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-09-30
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1041 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 56 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 9 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 10 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1134.36 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6167.7 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6556.023 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE113: A1 Darrington-A162 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 23642.6 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 192 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 30 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 70 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 19 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1210.27 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE114: A58 Chainbar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 862.2 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-05-01 | 2024-05-31
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 15157.5 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 230 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 12 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 119.1 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 27336.6 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 30427.286 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 5552.4976 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE12: M62 J34-35 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 7224.3 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 7139 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 106 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 24 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 101.7 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10690.2 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE13: M62 J35-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 7818.208 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3562.3 | B | Annually | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 82 | B | Annually | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 32 | B | Annually | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 19 | B | Annually | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 276.02 | B | Annually | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9905.4 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE14: M62 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4345.958 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-09-01 | 2024-09-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3448.1 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 195 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 89 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 34 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 370.78 | B | Annually | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 27218.7 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 24558.436 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 809.4404 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 160.0508 | B | Annually (Apr-Sept) | 1 | Nights | Yes | Main intervention | 2024-04-01 | 2024-04-30
YNE15: M62 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 9574.1 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 9456.3 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 262 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 80 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 16 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3705.42 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 5698.9844 | ILM | 3 x per year (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31 | Yes
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 16108.2 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 12188.94 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-05-31
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 5698.9844 | ILM | 3 x per year (Apr-Sept) | 2 | Days |  | No - Enhanced Maintenance 2 | 2024-06-01 | 2024-06-30 | Yes
YNE16: A63 NorthCave-SouthCave | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 5698.9844 | ILM | 3 x per year (Apr-Sept) | 3 | Days |  | No - Enhanced Maintenance 3 | 2024-08-01 | 2024-07-31 | Yes
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 18160.1 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 161 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 22 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 9 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 366.96 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 6422.8689 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31 | Yes
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 11846.7 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 18830.572 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 6422.8689 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-06-01 | 2024-06-30 | Yes
YNE17: A63 SouthCave-Welton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 6422.8689 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - Enhanced Maintenance 3 | 2024-08-01 | 2024-08-31 | Yes
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 14807.4 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 125 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 37 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 8 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 7537.14 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 20557.418 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31 | Yes
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7161.3 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6909.55 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 20557.418 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-06-01 | 2024-06-30 | Yes
YNE18: A63 Welton-Melton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 20557.418 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - Enhanced Maintenance 3 | 2024-08-01 | 2024-08-31 | Yes
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 12444.4 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 117 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 8 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 20 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 649.06 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 303.9865 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31 | Yes
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7845.3 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2067.1 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 303.9865 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-06-01 | 2024-06-30 | Yes
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 303.9865 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - Enhanced Maintenance 3 | 2024-08-01 | 2024-07-31 | Yes
YNE19: A63 Melton-WesternInt | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 5739.8 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 6628.6 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 26 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 56 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 941.7 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5779.8 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE2: M62 J23-24 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 5107.498 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 15348.7 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 195 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 34 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 21 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 432.31 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 960.6729 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31 | Yes
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9846 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 960.6729 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-06-01 | 2024-06-30 | Yes
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 960.6729 | ILM | 3 x per year (Apr-Sept) | 4 |  |  | No - Enhanced Maintenance 3 | 2024-08-01 | 2024-07-31 | Yes
YNE20: A63 WesternInt-PrioryWay | Yes |  |  | 3000 - Landscape and Ecology | Shrubs (Ornamental) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 7061.7375 | B | Annually (Sept-Feb) | Winter |  |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 274.3 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 99 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 32 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 10 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 181.46 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 1084.1146 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31 | Yes
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7088.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 1084.1146 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-07-01 | 2024-07-31 | Yes
YNE21: A63 PrioryWay-BrightonSt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 1084.1146 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - Enhanced Maintenance 3 | 2024-09-01 | 2024-09-30 | Yes
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 148.6 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 76 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 676.9 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 186.2105 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31 | Yes
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5568.3 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-05-31
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 186.2105 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - Enhanced Maintenance 2 | 2024-07-01 | 2024-07-31 | Yes
YNE22: A63 BrightonSt-DaltrySt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 186.2105 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - Enhanced Maintenance 3 | 2024-09-01 | 2024-09-30 | Yes
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 460.5 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 144 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 96 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 70 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 10896.43 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 8478.2237 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 8478.2237 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 8478.2237 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE23: A63 DaltrySt-Mytongate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3531.6 | B | Annually (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 460.5 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 188 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 69 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 83 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 7614.29 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 4069.3959 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 4069.3959 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 4069.3959 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE24: A63 Mytongate-Garrison | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3168.9 | B | Annually (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2079.9 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 52 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 6 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 16 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 6096.61 | B | Annually | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 33923.3632 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 33923.3632 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 33923.3632 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Not required | Major Project | Major Project | N/A |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 4345.2 | B | Annually (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE25: A63 Garrison-Southcoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 1270.63 | B | Annually (Apr-Sept) | 1 |  |  | Not required | Major Project | Major Project |  |  | Not booked Major Project
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 7862.1945 | ILM | 5 x per year (Apr-Sept) | 1 | Nights |  | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 7862.1945 | ILM | 5 x per year (Apr-Sept) | 2 | Nights |  | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 7862.1945 | ILM | 5 x per year (Apr-Sept) | 3 | Nights |  | Enhanced Maintenance 3 | 2024-07-01 | 2024-07-31 | Yes
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3790.6 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 105 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 75 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 32 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 5531.86 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 7862.1945 | ILM | 5 x per year (Apr-Sept) | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2016.9 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE26: A1033 Southcoates-NorthernGate | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 7862.1945 | ILM | 5 x per year (Apr-Sept) | 5 | Nights |  | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 1874.2924 | ILM | 5 x per year (Apr-Sept) | 1 | Nights | Yes | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 1874.2924 | ILM | 5 x per year (Apr-Sept) | 2 | Nights | Yes | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 1874.2924 | ILM | 5 x per year (Apr-Sept) | 3 | Nights | Yes | Enhanced Maintenance 3 | 2024-07-01 | 2024-07-31 | Yes
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 567.4 | B | Annually | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 81 | B | Annually | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 39 | B | Annually | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 19 | B | Annually | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 6249.48 | B | Annually | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 1874.2924 | ILM | 5 x per year (Apr-Sept) | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31 | Yes
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 1218.6 | B | Annually (Apr-Sept) | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 441.605 | B | Annually (Apr-Sept) | 4 | Nights | Yes | Main intervention | 2024-08-01 | 2024-08-31
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Shrubs (Ornamental) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 514.7267 | B | Annually (Sept-Feb) | Winter | Nights | Yes | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE27: A1033 NorthernGate-Marfleet | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 1874.2924 | ILM | 5 x per year (Apr-Sept) | 5 | Nights | Yes | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 18638.5163 | ILM | 5 x per year (Apr-Sept) | 1 | Nights |  | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes | Quants differ 16040
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 18638.5163 | ILM | 5 x per year (Apr-Sept) | 2 | Nights |  | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes | Quants differ 16040
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 18638.5163 | ILM | 5 x per year (Apr-Sept) | 3 | Nights |  | Enhanced Maintenance 3 | 2024-07-01 | 2024-07-31 | Yes | Quants differ 16040
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2981.1 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 140 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 33 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 40 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 11707.36 | B | Annually | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 18638.5163 | ILM | 5 x per year (Apr-Sept) | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes | Quants differ 16040
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2986.2 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 18638.5163 | ILM | 5 x per year (Apr-Sept) | 5 | Nights |  | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes | Quants differ 16040
YNE28: A1033 Marfleet-Somerden | Yes |  |  | 3000 - Landscape and Ecology | Shrubs (Ornamental) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 213.4193 | B | Annually (Sept-Feb) | Winter |  |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 18458.7662 | ILM | 5 x per year (Apr-Sept) | 1 | Nights |  | Enhanced Maintenance 1 | 2024-04-01 | 2024-04-30 | Yes | Quants differ 23280
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 18458.7662 | ILM | 5 x per year (Apr-Sept) | 2 | Nights |  | Enhanced Maintenance 2 | 2024-05-01 | 2024-05-31 | Yes | Quants differ 23280
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 18458.7662 | ILM | 5 x per year (Apr-Sept) | 3 | Nights |  | Enhanced Maintenance 3 | 2024-07-01 | 2024-07-31 | Yes | Quants differ 23280
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2976.1 | B | Annually | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 126 | B | Annually | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 84 | B | Annually | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 29 | B | Annually | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 5529.02 | B | Annually | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 18458.7662 | ILM | 5 x per year (Apr-Sept) | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes | Quants differ 23280
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3135.6 | B | Annually (Apr-Sept) | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 3551.2084 | B | Annually (Apr-Sept) | 4 | Nights |  | Main intervention | 2024-08-01 | 2024-08-31
YNE29: A1033 Somerden-SaltEnd | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 18458.7662 | ILM | 5 x per year (Apr-Sept) | 5 | Nights |  | Enhanced Maintenance 5 | 2024-09-01 | 2024-09-30 | Yes | Quants differ 23280
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 13549.1 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 7 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 213 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 87 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 118 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 146.26 | B | Annually | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 16448.4 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE3: M62 J24-25 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 12552.17 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-04-01 | 2024-04-30
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 7892.2 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 116 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 80 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 38 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 39.18 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9335.7 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 10931.068 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE30: M606 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 1046.865 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1554.7 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 99 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 52 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 43 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 126.94 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5076 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE31: M606 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4825.734 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-05-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 14238.8 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 182 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 46 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 65 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 676.91 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 18108 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 7150.56 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE32: M621 Gildersome-J1 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 7127.9767 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 360 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 101 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 28 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 34 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 708.37 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE33: M621 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3563.1 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 327 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 39 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 25 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 711.55 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE34: M621 J2-2a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3519 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 177 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 40 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 90 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 31 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2101.8 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE35: M621 J2a-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2329.2 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 392 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 62 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 50 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 42 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1159.38 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE36: M621 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5589.9 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 311 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 53 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 28 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 41 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 937.81 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3441.6 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE37: M621 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 381.3717 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 287 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 51 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 32 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 37 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 61.66 | B | Annually | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3103.2 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE38: M621 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 274.9273 | B | Annually (Apr-Sept) | 2 | Nights |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 277 | B | Annually | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 32 | B | Annually | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 20 | B | Annually | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 23 | B | Annually | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2871.9 | B | Annually (Apr-Sept) | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 255.996 | B | Annually (Apr-Sept) | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE39: M621 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 1206.8547 | B | Annually (Apr-Sept) | 2 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 21853.2 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 11 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 244 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 76 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 152 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1443.62 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 22694.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4242.795 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 3995.2824 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-04-30
YNE4: M62 J25-26 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 3559.5 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 0 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 39 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 66 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 18 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 68.15 | B | Annually | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2880.9 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE40: M621 J7-8 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2280.822 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-08-01 | 2024-08-31
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 7835.2 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 132 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 113 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3891.76 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8575.2 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 1860.06 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 8654.8 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE41: A64 Bramham-Headley | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 19583.4 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-11-01 | 2024-11-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4180.1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 48 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 4 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 469.03 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6606 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 5917.899 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 27708.5 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 63408.9 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-11-01 | 2024-11-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 17648.2 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 155 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 33 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 6 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3415.11 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 5321.2022 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes | Quants differ 5349
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10559.7 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4898.451 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 1711.9129 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 5321.2022 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31 | Yes | Quants differ 5349
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 5321.2022 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30 | Yes | Quants differ 5349
YNE43: A64 A162-Tadcaster | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 64519 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-11-01 | 2024-11-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 21692.5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 146 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 4 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 14301.02 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 3341.2697 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | No | 1st cut missing
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8016.3 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 8276.86 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 3341.2697 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 3341.2697 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE44: A64 Tadcaster-Bilbrough | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 7757.8 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-11-01 | 2024-11-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 17235.7 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 137 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 10985.44 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6859.8 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 5745.876 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 127.2715 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 6646 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE45: A64 Bilbrough-Askham | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 20540.8 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-11-01 | 2024-11-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 12590.9 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 155 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 8 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 4000.09 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7785.9 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6392.76 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 12.8686 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 33915.1 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE46: A64 Askham-Bondhill | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 36843.7 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-12-01 | 2024-12-31
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 8077.6 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 102 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 14 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 3 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1163.6 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8051.4 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2586.165 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 25114.7 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 56216.6 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-12-01 | 2024-12-31
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 15447.5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 225 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 70 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3343.84 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 4033.3178 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 14369.4 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 11541.648 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 4033.3178 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31 | Yes
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 57670.9 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 4033.3178 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30 | Yes
YNE48: A64 Fulford-Grimston | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 95280.8 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-01-01 | 2025-01-31
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 20804 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 169 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 98 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 16 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 4374.33 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 11013.3 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4668.478 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 18367.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 61000.3 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-01-01 | 2025-01-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 22528.5 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 62 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 131 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 72 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 89 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1311.59 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 20089.8 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 18163.84 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE5: M62 J26-27 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 1885.2441 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 25782.4 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 282 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 65 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 12 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 6937.48 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2550.7073 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 17136 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2550.7073 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31 | Yes
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2550.7073 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30 | Yes
YNE50: A64 NorthHopgroveSingle | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 33140.6 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-01-01 | 2025-01-31
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 30584.8 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 289 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 19264.12 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | No | Jobs not raised. Previous jobs remained open which were raised by previous regime. These have now been cancelled. Jobs to be re raised
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2030.2258 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9855.9 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 17511.892 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2030.2258 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31 | Yes
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 989.5 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2030.2258 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30 | Yes
YNE51: A64 NorthHopgroveDual | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 20900.6 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-01-01 | 2025-01-31
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 16500.8 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 209 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 6689.29 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 1561.6369 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 11145.6 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 67.54 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 1561.6369 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 40587.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 1561.6369 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE52: A64 SouthMusleySingle | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 32434.5 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 15142.2 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 8 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 7 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 220.79 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2252.5927 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10326.6 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 10457.336 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2252.5927 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 59814.9 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-09-01 | 2024-09-30
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2252.5927 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE53: A64 Musley-PickeringInt | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 27660.4 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 17503.7 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 111 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 23 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 346.72 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9165.6 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4171.04 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 41218.4 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 13089.5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 173 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 12 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 7450.57 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 3619.7652 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8163.9 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 3619.7652 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 3619.7652 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE55: A64 Brambling-Rillington | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 12727.7 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 33366.4 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 431 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 46 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 12 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 16218.13 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 28342.5546 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 20887.2 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 12971.5371 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 28342.5546 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 28342.5546 | ILM | 3 x per year (Apr-Sept) | 4 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 17173.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE56: A64 Rillington-Sherburn | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 20113 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 18237.1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 327 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 45 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 17 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 10274.19 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 16544.0198 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 13586.4 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 795.0283 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 16544.0198 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31 | Yes
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 16544.0198 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30 | Yes
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 222.6 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE57: A64 Sherburn-Staxton | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 22661.5 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 5 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 5957.8 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 24 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 9095.74 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 3035.7815 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 4627.8 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 1370.88 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 3035.7815 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 3035.7815 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 18619.2 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE58: A64 Staxton-Seamer | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 2558 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4098.4 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 78 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 22 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 7 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 5777.06 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 3144.5939 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 4244.4 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2192.4 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 3144.5939 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 3144.5939 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 757 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE59: A64 Seamer-Dunslow | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 12336.1 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 23381.1 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 55 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 134 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 86 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 58 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1008.47 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15425.1 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 5448.18 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 297.782 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE6: M62 J27-28 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 6330.9 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 6270 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 41 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 21 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 1 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 351.53 | B | Annually | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 5367.4548 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30 | Yes
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2635.2 | B | Annually (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 5367.4548 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | Yes
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 5367.4548 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE60: A64 Dunslow-Musham | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 4021.1 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3957 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 23 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 107 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 15 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 78 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3028.7 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 18828 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE61: M1 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2867.7 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1517 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 10 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 20 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 28 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 32 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1235.45 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6826.5 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 4492.5499 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE62: M1 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 9850.1 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2799 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 9 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 71 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 40 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 744.76 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 14687.1 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE63: M1 J32-33 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 8215.1 | TBC | TBC | TBC |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2463 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 11 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 67 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 45 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 42 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 654.01 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 13084.2 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 147.9516 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE64: M1 J33-34South | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 4302.6 | TBC | TBC | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 468 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 3 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 10 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 3 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 55.72 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2104.2 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE65: M1 Tinsley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 256.5 | TBC | TBC | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 468 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 12 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 64 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 15 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 42 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 896 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 11340.9 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 3196.2529 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 582.5956 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE66: M1 J34North-35 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 9060.5 | TBC | TBC | TBC | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2520 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 11 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 45 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 34 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 32 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 756.34 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 9084.6 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 292.7106 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE67: M1 J35-35a | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 6717 | TBC | TBC | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31 |  |  | At risk as roadspaceclashes with Andy Reddy Scheme - EW raised.
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1838 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 38 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 11 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 10 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 95.7 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 4883.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 1207.908 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE68: M1 J35a-36 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 3340.5 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3373 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 116 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 26 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 21 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 290.86 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15180.3 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 20399.094 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 575.9979 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE69: M1 J36-37 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 17111.8 | B | Annually (Sept-Oct) | Winter | Days |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 5799.9 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 21 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 165 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 67 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 23 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 646.51 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 13399.2 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 134.18 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 5331.9456 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE7: M62 J29-30 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 7189.6 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3380 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 4 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 108 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 12 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 6 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 163.96 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15208.2 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 16738.681 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE70: M1 J37-38 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 12399.7 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3531 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 120 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 21 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 767.44 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15887.7 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 21819.529 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE71: M1 J38-39 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 5550.4 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2419 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 7 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 83 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 10 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 24 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1140.76 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10886.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 5851 | TBC | TBC | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE72: M1 J39-40 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 426.5 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2250 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 8 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 93 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 46 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 33 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 9161.23 | B | Annually | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10125.9 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE73: M1 J40-41 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 6754.1 | TBC | TBC | 1 |  |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1432.3 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 5 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 104 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 104 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 39 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 58.11 | B | Annually | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 7686.9 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE74: M1 J41-42 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2752.3 | TBC | TBC | 1 | Nights |  | Main intervention | 2024-05-01 | 2024-06-30
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 404.7546 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | No - to be booked if needed | 2024-05-01 | 2024-05-31 | Yes
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1707 | B | Annually | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 186 | B | Annually | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 58 | B | Annually | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 17 | B | Annually | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 15034.48 | B | Annually | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 404.7546 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31 | Yes
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 13417.2 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE76: A628 Tintwistle-Crowden | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 404.7546 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | Yes
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2828 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 534 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 5 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 7012.5 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 25448.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 113.4546 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 3229.7 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 6877.9819 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-04-01 | 2024-04-30 | Yes
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 6877.9819 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-06-01 | 2024-06-30 | Yes
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2355 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 334 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 25 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 20 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 7170 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 6877.9819 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 21091.5 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 25.6823 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE78: A616 Flouch-Deepcar | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 20226.8 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 1606.4603 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | No - to be booked if needed | 2024-04-01 | 2024-04-30 | Yes | Quants differ 1913
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 1606.4603 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-06-01 | 2024-06-30 | Yes | Quants differ 1913
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 582 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 84 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 5 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 317.63 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 1606.4603 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes | Quants differ 1913
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5238 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE79: A616 Deepcar-Wortley | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 7180.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 1 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 11945 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 6 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 90 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 102 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 36 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 145.49 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 11901.6 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 3181.928 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 396.462 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE8: M62 J30-31 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 3347.5 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 452.8724 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-04-01 | 2024-04-30 | Yes
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 452.8724 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-06-01 | 2024-06-30 | Yes
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 753 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 136 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 120 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 31 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 566.66 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 452.8724 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6545.7 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 266.8649 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE80: A616 Wortley-Westwood | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2295.7 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2192.0802 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | No - to be booked if needed | 2024-04-01 | 2024-04-30 | Yes
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2192.0802 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-06-01 | 2024-06-30 | Yes
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 523 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 111 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 44 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 12 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 845.9 | B | Annually | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2192.0802 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31 | Yes
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 4710.6 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 937.8153 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-08-01 | 2024-08-31
YNE81: A616 Westwood-Stocksbridge | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 966.9 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 4698.2408 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | No - to be booked if needed | 2024-04-01 | 2024-04-30 | Yes
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 4698.2408 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-06-01 | 2024-06-30 | Yes
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 576 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 94 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 97 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 43 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 3734.01 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 4698.2408 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31 | Yes
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3447 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 742.03 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 701.1218 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE82: A61 | Yes |  |  | 3000 - Landscape and Ecology | Woodland | 4.8.2 | Woodland - thin / coppice | 28642.3 | B | Every 7 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3748 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 6 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 118 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 96 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 22 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 346.7 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 18055.8 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 13960.271 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2667.3 | TBC | TBC | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE83: M18 Link-J1 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 3288 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4687 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 212 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 33 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 31 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 228.15 | B | Annually | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 21987 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 19495.889 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 1000.507 | B | Annually (Apr-Sept) | 2 |  |  | Main intervention | 2024-09-01 | 2024-10-31 |  |  | 3 shifts at risk due to scheme clashes, meeting scheduled A. Reddy 21/11/2023 to resolve.
YNE84: M18 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 150550.8 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 1 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1519 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 54 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 4 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 7 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 128.85 | B | Annually | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 6834.6 | B | Annually (Apr-Sept) | 2 | Nights |  | Main intervention | 2024-09-01 | 2024-10-31
YNE85: M18 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2949.7 | B | Annually (Sept-Oct) | Winter | Nights |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 508.2991 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-05-01 | 2024-05-31 | No
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 508.2991 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | No
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4247 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 109 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 7 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 282.71 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 508.2991 | ILM | 3 x per year (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31 | No
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 19112.4 | B | Annually (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 1279.48 | B | Annually (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2902.0477 | B | Annually (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE86: M18 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 9811.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 726.4171 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-05-01 | 2024-05-31 | No
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 726.4171 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | No - to be booked if needed | 2024-07-01 | 2024-07-31 | No
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 3326 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 139 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 32 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 14 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 40.06 | B | Annually | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 726.4171 | ILM | 3 x per year (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31 | No
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 15543.9 | B | Annually (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 7469.444 | B | Annually (Apr-Sept) | 4 |  |  | Main intervention | 2024-09-01 | 2024-10-31
YNE87: M18 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 870.2 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1849 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 74 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 128 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 13 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 129.45 | B | Annually | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 8748 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE88: M18 J5-6 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 8282.38 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4714.8 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 130 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 48 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 19 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 606.45 | B | Annually | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 16558.2 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 3225.007 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE89: M18 J6-7 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 67.3353 | B | Annually (Apr-Sept) | 1 | Nights |  | Main intervention | 2024-06-01 | 2024-07-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 18708.4 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 5 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 90 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 20 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 17 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 387.72 | B | Annually | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10205.1 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6968.172 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE9: M62 J31-32 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 725.01 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-04-01 | 2024-05-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1146 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 146 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 78 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 13 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 12.1 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5441.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 3691.42 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE90: M180 Ings-J1 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 69977.5891 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 3 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4303 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 1 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 114 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 29 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 23.22 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 19364.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 13177.236 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 7912.7 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE91: M180 J1-2 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 223013.4103 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2605 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 160 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 43 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 86.35 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 16611.3 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 12820.016 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE92: M180 J2-3 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 171996.5331 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4519 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 138 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 14 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 29 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 17.34 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 20333.7 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6478.203 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 1366.729 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 256.6 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE93: M180 J3-4 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 130182.8958 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4779 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 146 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 94 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 37 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 290.16 | B | Annually | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 21506.4 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 24577.584 | B | Annually (Apr-Sept) | 1 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 1763.4 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE94: M180 J4-5 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 126790.3807 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-02-01 | 2025-02-28
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 6 | ILM | 3 x per year (Apr-Sept) | 1 | Days |  | No - to be booked if needed | 2024-05-01 | 2024-05-31 | No
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 6 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1968 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 157 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 21 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 29 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 41.71 | B | Annually | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 6 | ILM | 3 x per year (Apr-Sept) | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31 | No
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 3345.3 | B | Annually (Apr-Sept) | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 6725.375 | B | Annually (Apr-Sept) | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Injurious weeds | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 6 | B | Annually (Apr-Sept) | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Invasive Plant Species | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 6 | B | Annually (Apr-Sept) | 2 | Days |  | Main intervention | 2024-07-01 | 2024-07-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 6 | ILM | 3 x per year (Apr-Sept) | 3 | Days |  | No - to be booked if needed | 2024-09-01 | 2024-09-30 | No
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Shrubs (Ornamental) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 6 | B | Annually (Sept-Feb) | Winter | Days |  | No - to be booked if needed | 2025-03-01 | 2025-03-31
YNE95: M181 | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 39192.9431 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 4118.5325 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-04-01 | 2024-04-30 | Yes | Quants differ 9001
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 4118.5325 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-06-01 | 2024-06-30 | Yes | Quants differ 9001
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 4642 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 469 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 27 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 1583.6 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 4118.5325 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31 | Yes | Quants differ 9001
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 22785.3 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 9965.059 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 32462.6 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE96: A180 Barnetby-Brocklesby | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 224643.5395 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2836.1981 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-04-01 | 2024-04-30 | Yes | Quants differ 11741
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2836.1981 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-06-01 | 2024-06-30 | Yes | Quants differ 11741
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Wildlife Housings / Structures | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 1 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2857 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 157 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 16 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 16 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 925.15 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2836.1981 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31 | Yes | Quants differ 11741
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 13715.1 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 8425.708 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Conservation grassland / wildflower grassland | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 10095.6 | B | Annually (Sept-Oct) | Winter |  |  | No - Winter Programme | 2024-10-01 | 2024-10-31
YNE97: A180 Brocklesby-Stallingborough | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 105066.008 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-04-01 | 2024-04-30 | Yes
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-06-01 | 2024-06-30 | Yes
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2290 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 148 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 54 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 16 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 816.71 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31 | Yes
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 10431 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 10577.443 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE98: A180 Stallingborough-GreatCoates | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 63469.5125 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2458.1919 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | No - to be booked if needed | 2024-04-01 | 2024-04-30 | Yes | Quants differ 1610
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2458.1919 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | No - to be booked if needed | 2024-06-01 | 2024-06-30 | Yes | Quants differ 1610
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 1171 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 3 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 142 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 110 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 11 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 457.88 | B | Annually | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2458.1919 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31 | Yes | Quants differ 1610
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 5421.6 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 4176.14 | B | Annually (Apr-Sept) | 3 |  |  | Main intervention | 2024-07-01 | 2024-08-31
YNE99: A180 GreatCoates-Pyewipe | Yes |  |  | 3000 - Landscape and Ecology | Grassland | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 28808.1637 | B | Every 5 years (Sept-Feb) | Winter | Days |  | No - Winter Programme | 2025-03-01 | 2025-03-31
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31
YNE42: A64 Headley-A162 | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31
YNE47: A64 Bondhill-Fulford | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31
YNE49: A64 Grimston-Hopgrove | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Main Intervention | 2024-05-01 | 2024-06-30
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Amenity Visit 2 | 2024-07-01 | 2024-07-31
YNE54: A64 PickeringInt-Brambling | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 1 |  |  | Amenity Visit 1 | 2024-05-01 | 2024-05-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 2 |  |  | Main intervention | 2024-07-01 | 2024-07-31
YNE77: A628 Crowden-Flouch | Yes |  |  | 3000 - Landscape and Ecology | Grass and vegetation | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2254.6435 | ILM | 3 x per year (Apr-Sept) | 3 |  |  | Amenity Visit 3 | 2024-09-01 | 2024-09-30
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If cell is orange, no quants in Confirm but listed by consulting as done. I have kept last years quants in these cells

## 4.8.3.1 Quants 23-24 (hidden)
H.E. Asset Quantity | ScAR | Activity Progress | Excluded Y/N | CPF Comment | Area 12 Chart Section | Area 12 Maintenance Segments | Area 12 TM Reference
5276 | 4.8.3.1 | 100% | N |  |  | YNE1: M62 J22-23 | YNE1 Closure
1284 | 4.8.3.1 | 100% | N |  |  | YNE2: M62 J23-24 | YNE2 Closure
3188 | 4.8.3.1 | 100% | N |  |  | YNE3: M62 J24-25 | YNE3 Closure
3718 | 4.8.3.1 | 0% | Y |  |  | YNE5: M62 J26-27 | YNE5 Closure 1 EB NS
2848 | 4.8.3.1 | 0% | Y |  |  | YNE6: M62 J27-28 | YNE6 Closure
2621 | 4.8.3.1 | 0% | Y |  |  | YNE7: M62 J28-29 | YNE7 Closure
2645 | 4.8.3.1 | 100% | Y |  |  | YNE8: M62 J29-31 | YNE8 Closure
2268 | 4.8.3.1 | 100% | N |  |  | YNE9: M62 J31-32 | YNE9 Closure
2917 | 4.8.3.1 | 100% | N |  |  | YNE10: M62 J32-33 | YNE10 Closure
1710 | 4.8.3.1 | 100% |  |  |  | YNE30: M606 J1-2 | YNE30 Closure
1128 | 4.8.3.1 | 100% |  |  |  | YNE31: M606 J2-3 | YNE31 Closure
1553 | 4.8.3.1 | 100% | N |  |  | YNE41: A64 Bramham-Headley | YNE41 Closure
1468 | 4.8.3.1 | 100% | N |  |  | YNE42: A64 Headley-A162 | YNE42 Closure 2 EB NS
1766 | 4.8.3.1 | 100% | N |  |  | YNE43: A64 A162-Tadcaster | YNE43 Closure
1665 | 4.8.3.1 | 100% | N |  |  | YNE44: A64 Tadcaster-Bilbrough | YNE44 Closure
1277 | 4.8.3.1 | 100% | N |  |  | YNE45: A64 Bilbrough-Askham | YNE45 Closure
1616 | 4.8.3.1 | 100% | N |  |  | YNE46: A64 Askham-Bondhill | YNE46 Closure
1789 | 4.8.3.1 | 100% | N |  |  | YNE47: A64 Bondhill-Fulford | YNE47 Closure
2909 | 4.8.3.1 | 100% | N |  |  | YNE48: A64 Fulford-Grimston | YNE48 Closure
2126 | 4.8.3.1 | 100% | N |  |  | YNE49: A64 Grimston-Hopgrove | YNE49 Closure
1904 | 4.8.3.1 | 100% | N |  |  | YNE50: A64 NorthHopgroveSingle | YNE50 Closure
2355 | 4.8.3.1 | 100% | Y |  |  | YNE76: A628 Tintwistle-Crowden | YNE78 Closure
582 | 4.8.3.1 | 0% | Y |  |  | YNE77: A628 Crowden-Flouch | YNE79 Closure
753 | 4.8.3.1 | 0% | Y |  |  | YNE78: A616 Flouch-Deepcar | YNE80 Closure
523 | 4.8.3.1 | 0% | Y |  |  | YNE79: A616 Deepcar-Wortley | YNE81 Closure
576 | 4.8.3.1 | 0% | Y |  |  | YNE82: A61 | YNE82 Closure
523 | 4.8.3.1 | 100% |  |  |  | YNE103: A62 Gildersome | YNE103 Closure
5079 | 4.8.3.1 | 0% | Y |  |  | YNE106: A1M J34-35 | YNE106 Closure
1669 | 4.8.3.1 | 0% | Y |  |  | YNE107: A1M J35-36 | YNE107 Closure
2825 | 4.8.3.1 | 0% | Y |  |  | YNE108: A1M J36-37 | YNE108 Closure
2113 | 4.8.3.1 | 0% | Y |  |  | YNE109: A1M J37-38 | YNE109 Closure
1041 | 4.8.3.1 | 100% |  |  |  | YNE114: A58 Chainbar | YNE114 Closure
3518 | 4.8.3.1 | 100% |  |  |  | YNE11: M62 J33-34 | YNE11 Closure
6078 | 4.8.3.1 | 100% |  |  |  | YNE12: M62 J34-35 | YNE12 Closure
2200 | 4.8.3.1 | 100% |  |  |  | YNE13: M62 J35-36 | YNE13 Closure
2201 | 4.8.3.1 | 100% |  |  |  | YNE14: M62 J36-37 | YNE14 Closure
3957 | 4.8.3.1 | 100% |  |  |  | YNE61: M1 J30-31 | YNE61 Closure
1517 | 4.8.3.1 | 0% | Y |  |  | YNE62: M1 J31-32 | YNE62 Closure
2799 | 4.8.3.1 | 0% | Y |  |  | YNE63: M1 J32-33 | YNE63 Closure
2463 | 4.8.3.1 | 0% | Y |  |  | YNE64: M1 J33-34South | YNE64Closure
468 | 4.8.3.1 | 0% | Y |  |  | YNE65: M1 Tinsley | YNE65 Closure
468 | 4.8.3.1 | 0% | Y |  |  | YNE66: M1 J34North-35 | YNE66Closure
2520 | 4.8.3.1 | 0% | Y |  |  | YNE67: M1 J35-35a | YNE67 Closure
1838 | 4.8.3.1 | 0% | Y |  |  | YNE68: M1 J35a-36 | YNE68 Closure
3373 | 4.8.3.1 | 100% | N |  |  | YNE69: M1 J36-37 | YNE69Closure
3380 | 4.8.3.1 | 100% | N |  |  | YNE70: M1 J37-38 | YNE70Closure
3531 | 4.8.3.1 | 100% | N |  |  | YNE71: M1 J38-39 | YNE71 Closure
2419 | 4.8.3.1 | 100% | N |  |  | YNE72: M1 J39-40 | YNE72Closure
2250 | 4.8.3.1 | 0% | Y |  |  | YNE73: M1 J40-41 | YNE73 Closure
1638 | 4.8.3.1 | 0% | Y |  |  | YNE74: M1 J41-42 | YNE74 Closure
1146 | 4.8.3.1 | 0% | Y |  |  | YNE90: M180 Ings-J1 | YNE90 Closure
4303 | 4.8.3.1 | 0% | Y |  |  | YNE96: A180 Barnetby-Brocklesby | YNE91 Closure
2605 | 4.8.3.1 | 0% | N |  |  | YNE97: A180 Brocklesby-Stallingborough | YNE92 Closure
4519 | 4.8.3.1 | 0% | N |  |  | YNE98: A180 Stallingborough-GreatCoates | YNE93 Closure
4779 | 4.8.3.1 | 100% |  |  |  | YNE99: A180 GreatCoates-Pyewipe | YNE94 Closure
1968 | 4.8.3.1 | 0% | N |  |  | YNE95: M181 | YNE95 Closure
923 | 4.8.3.1 | 0% | Y |  |  | YNE102: A162 Ferrybridge | YNE102 Closure
831 | 4.8.3.1 | 0% | Y |  |  | YNE104: A631 Tinsley | YNE104 Closure
459 | 4.8.3.1 | 0% | Y |  |  | YNE105: A638 Redhouse | YNE105 Closure
2813 | 4.8.3.1 | 0% | Y |  |  | YNE110: A1 Redhouse-Barnsdale | YNE110 Closure
1041 | 4.8.3.1 | 0% | Y |  |  | YNE113: A1 Darrington-A162 | YNE113 Closure
3747 | 4.8.3.1 | 0% | N |  |  | YNE4: M62 J25-26 | YNE4 Closure
2814 | 4.8.3.1 | 100% |  |  |  | YNE16: A63 NorthCave-SouthCave | YNE16 Closure
2812 | 4.8.3.1 | 0% | Y |  |  | YNE17: A63 SouthCave-Welton | YNE17 Closure
1455 | 4.8.3.1 | 0% | Y |  |  | YNE18: A63 Welton-Melton | YNE18 Closure
1633 | 4.8.3.1 | 0% |  |  |  | YNE19: A63 Melton-WesternInt | YNE19 Closure
2057 | 4.8.3.1 | 0% | Y |  |  | YNE20: A63 WesternInt-PrioryWay | YNE20 Closure
638 | 4.8.3.1 | 0% | Y |  |  | YNE23: A63 DaltrySt-Mytongate | YNE23 Closure
659 | 4.8.3.1 | 0% | Y |  |  | YNE24: A63 Mytongate-Garrison | YNE24 Closure
842 | 4.8.3.1 | 0% | Y |  |  | YNE25: A63 Garrison-Southcoates | YNE25 Closure
448 | 4.8.3.1 | 100% |  |  |  | YNE26: A1033 Southcoates-NorthernGate | YNE26 Closure
271 | 4.8.3.1 | 100% | N |  |  | YNE27: A1033 NorthernGate-Marfleet | YNE27 Closure
664 | 4.8.3.1 | 100% |  |  |  | YNE28: A1033 Marfleet-Somerden | YNE28 Closure
697 | 4.8.3.1 | 100% |  |  |  | YNE29: A1033 Somerden-SaltEnd | YNE29 Closure
1707 | 4.8.3.1 | 100% |  |  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure
2828 | 4.8.3.1 | 100% |  |  |  | YNE77: A628 Crowden - Flouch | YNE77 Closure
3748 | 4.8.3.1 | 0% | Y |  |  | YNE83: M18 Link-J1 | YNE83NE83 M18 Closure
4687 | 4.8.3.1 | 0% | Y |  |  | YNE84: M18 J1-2 | YNE84 Closure
1519 | 4.8.3.1 | 0% | Y |  |  | YNE85: M18 J2-3 | YNE85Closure
508.2991 | 4.8.3.1 | 0% | Y |  |  | YNE86: M18 J3-4 | YNE86 Closure
3326 | 4.8.3.1 | 0% | Y |  |  | YNE87: M18 J4-5 | YNE87Closure
1849 | 4.8.3.1 | 0% | Y |  |  | YNE88: M18 J5-6 | YNE88 Closure
3680 | 4.8.3.1 | 0% | Y |  |  | YNE89: M18 J6-7 | YNE89 Closure
4642 | 4.8.3.1 | 100% | N |  |  | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure
2857 | 4.8.3.1 | 100% | N |  |  | YNE97: A180 Brocklesby - Stallingborough | YNE97 Closure
2290 | 4.8.3.1 | 100% | N |  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure
1171 | 4.8.3.1 | 100% | N |  |  | YNE99: A180 Great Coates - Pyewipe | YNE99 Closure
827 | 4.8.3.1 | 100% | N |  |  | YNE100: A160 Brocklesby-Habrough | YNE100 Closure
1168 | 4.8.3.1 | 100% |  |  |  | YNE101: A160 Habrough-Manby | YNE101 Closure
5957 | 4.8.3.1 | 100% |  |  |  | YNE15: M62 J37-38 | YNE15 Closure
830.75 | 4.8.3.1 | 0% |  |  |  | YNE32: M621 Gildersome-J1 | YNE32 Closure 1 CW OS

## Pivot - Total Qts by Month
Asset Type | - all -
Sum of Quants |  |  |  |  | Planned Completion
Maintenance Route | TM Booked? | Location Detail for ILM Sections | SOR | Activity | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | Total Result
YNE1: M62 J22-23 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 16155.9 | 16155.9
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 24488.3 | 24488.3
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-04-30: 6 | 6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 296 | 296
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 143 | 143
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 43.53 | 43.53
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 23741.1 | 23741.1
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 21040.554 | 21040.554
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-04-30: 5888.274 | 5888.274
YNE10: M62 J32-33 | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 4484.8888 | 4484.8888
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 4484.8888 | 4484.8888
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-05-31: 4 | 4
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 23726.7 | 23726.7
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 186 | 186
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 232 | 232
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 120 | 120
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 76.49 | 76.49
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 4484.8888 | 4484.8888
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 15332.4 | 15332.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 11695.943 | 11695.943
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 783.9403 | 783.9403
YNE100: A160 Brocklesby-Habrough | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 48847 | 48847
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 48847 | 48847
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-06-30: 48847 | 48847
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 48847 | 48847
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 54878 | 54878
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 827 | 827
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 54 | 54
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1902 | 1902
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 48847 | 48847
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3720.6 | 3720.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 6577.6 | 6577.6
YNE101: A160 Habrough-Manby | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 48847 | 48847
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 48847 | 48847
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-06-30: 48847 | 48847
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 48847 | 48847
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 26649 | 26649
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1168 | 1168
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 144 | 144
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 117 | 117
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 9 | 9
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5979 | 5979
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 48847 | 48847
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5709.6 | 5709.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 21080.1342 | 21080.1342
YNE102: A162 Ferrybridge | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 923 | 923
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 26 | 26
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 8 | 8
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5742 | 5742
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 3423.23 | 3423.23
YNE103: A62 Gildersome | Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 4495.2 | 4495.2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 100 | 100
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 86 | 86
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 93 | 93
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 2455.21 | 2455.21
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 1854 | 1854
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 304.43 | 304.43
YNE104: A631 Tinsley | Main intervention | (empty) | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 164 | 164
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 48 | 48
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 50 | 50
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 4422.81 | 4422.81
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 3737.7 | 3737.7
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 746.0946 | 746.0946
YNE105: A638 Redhouse | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 459 | 459
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 61 | 61
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 204 | 204
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 8 | 8
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 1710.36 | 1710.36
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 3863.7 | 3863.7
YNE106: A1M J34-35 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 9476.8 | 9476.8
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-09-30: 216629.3 | 216629.3
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [12 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 5079 | 5079
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 85 | 85
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 10 | 10
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 48 | 48
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 95.32 | 95.32
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 23473.8 | 23473.8
YNE107: A1M J35-36 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 2955.9 | 2955.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-09-30: 24483.8 | 24483.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1669 | 1669
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-09-30: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 66 | 66
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 175.11 | 175.11
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 7745.4 | 7745.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 6607.889 | 6607.889
YNE108: A1M J36-37 | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 147082.2 | 147082.2
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2825 | 2825
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 88 | 88
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 161.79 | 161.79
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 12710.7 | 12710.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 12715.273 | 12715.273
YNE109: A1M J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 5425.6 | 5425.6
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 95701.5 | 95701.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2113 | 2113
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-09-30: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 78 | 78
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 27 | 27
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 40.09 | 40.09
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 10521 | 10521
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 12932 | 12932
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-09-30: 41.7754 | 41.7754
YNE11: M62 J33-34 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 19697 | 19697
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 2358.6 | 2358.6
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-04-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 106 | 106
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 13 | 13
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 73 | 73
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 375.86 | 375.86
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 15829.2 | 15829.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 21274.484 | 21274.484
YNE110: A1 Redhouse-Barnsdale | No - Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 1103.8214 | 1103.8214
| No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 1103.8214 | 1103.8214
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 402.3 | 402.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2813 | 2813
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 200 | 200
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 194 | 194
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 18 | 18
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 4731.53 | 4731.53
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1103.8214 | 1103.8214
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 16866.9 | 16866.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 22911.439 | 22911.439
YNE111: A1 Barnsdale-Wentbridge | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 2204.3 | 2204.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1673 | 1673
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 96 | 96
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 26 | 26
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 15 | 15
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 535.78 | 535.78
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 8708.4 | 8708.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 16447.871 | 16447.871
YNE112: A1 Wentbridge-Darrington | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1812 | 1812
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 114 | 114
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 7 | 7
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 8 | 8
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 1916.52 | 1916.52
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 9909.9 | 9909.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 2026.019 | 2026.019
YNE113: A1 Darrington-A162 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 23642.6 | 23642.6
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1041 | 1041
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 56 | 56
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 9 | 9
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 10 | 10
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1134.36 | 1134.36
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 6167.7 | 6167.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 6556.023 | 6556.023
YNE114: A58 Chainbar | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 192 | 192
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 30 | 30
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 70 | 70
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 1210.27 | 1210.27
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 862.2 | 862.2
YNE12: M62 J34-35 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 7224.3 | 7224.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 15157.5 | 15157.5
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-04-30: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 230 | 230
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 12 | 12
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 119.1 | 119.1
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 27336.6 | 27336.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 30427.286 | 30427.286
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-04-30: 5552.4976 | 5552.4976
YNE13: M62 J35-36 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 7139 | 7139
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 106 | 106
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 24 | 24
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 101.7 | 101.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 10690.2 | 10690.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 7818.208 | 7818.208
YNE14: M62 J36-37 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 3562.3 | 3562.3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 82 | 82
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 276.02 | 276.02
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 9905.4 | 9905.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 4345.958 | 4345.958
YNE15: M62 J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 9574.1 | 9574.1
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 3448.1 | 3448.1
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-04-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 195 | 195
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 89 | 89
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 34 | 34
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 370.78 | 370.78
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 27218.7 | 27218.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 24558.436 | 24558.436
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-04-30: 809.4404 | 809.4404
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-04-30: 160.0508 | 160.0508
YNE16: A63 NorthCave-SouthCave | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 5698.9844 | 5698.9844
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 5698.9844 | 5698.9844
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 9456.3 | 9456.3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 262 | 262
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 80 | 80
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 3705.42 | 3705.42
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 5698.9844 | 5698.9844
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 16108.2 | 16108.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 12188.94 | 12188.94
YNE17: A63 SouthCave-Welton | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 6422.8689 | 6422.8689
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 6422.8689 | 6422.8689
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 18160.1 | 18160.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 161 | 161
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 22 | 22
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 9 | 9
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 366.96 | 366.96
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 6422.8689 | 6422.8689
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 11846.7 | 11846.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 18830.572 | 18830.572
YNE18: A63 Welton-Melton | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 20557.418 | 20557.418
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 20557.418 | 20557.418
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 14807.4 | 14807.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 125 | 125
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 37 | 37
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 8 | 8
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 7537.14 | 7537.14
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 20557.418 | 20557.418
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 7161.3 | 7161.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 6909.55 | 6909.55
YNE19: A63 Melton-WesternInt | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 303.9865 | 303.9865
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 303.9865 | 303.9865
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 5739.8 | 5739.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 12444.4 | 12444.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 117 | 117
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 8 | 8
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 20 | 20
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 649.06 | 649.06
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 303.9865 | 303.9865
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 7845.3 | 7845.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 2067.1 | 2067.1
YNE2: M62 J23-24 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 6628.6 | 6628.6
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-04-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 62 | 62
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 26 | 26
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 56 | 56
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 941.7 | 941.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 5779.8 | 5779.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 5107.498 | 5107.498
YNE20: A63 WesternInt-PrioryWay | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 960.6729 | 960.6729
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 960.6729 | 960.6729
| No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-03-31: 7061.7375 | 7061.7375
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 15348.7 | 15348.7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 195 | 195
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 34 | 34
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 21 | 21
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 432.31 | 432.31
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 960.6729 | 960.6729
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 9846 | 9846
YNE21: A63 PrioryWay-BrightonSt | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 1084.1146 | 1084.1146
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1084.1146 | 1084.1146
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 274.3 | 274.3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 99 | 99
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 10 | 10
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 181.46 | 181.46
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 1084.1146 | 1084.1146
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 7088.4 | 7088.4
YNE22: A63 BrightonSt-DaltrySt | No - Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 186.2105 | 186.2105
| No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 186.2105 | 186.2105
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 148.6 | 148.6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 76 | 76
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 65 | 65
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 676.9 | 676.9
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 186.2105 | 186.2105
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 5568.3 | 5568.3
YNE26: A1033 Southcoates-NorthernGate | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 7862.1945 | 7862.1945
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 7862.1945 | 7862.1945
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 7862.1945 | 7862.1945
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 7862.1945 | 7862.1945
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 3790.6 | 3790.6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 105 | 105
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 75 | 75
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 32 | 32
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5531.86 | 5531.86
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 7862.1945 | 7862.1945
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2016.9 | 2016.9
YNE27: A1033 NorthernGate-Marfleet | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 1874.2924 | 1874.2924
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 1874.2924 | 1874.2924
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 1874.2924 | 1874.2924
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 1874.2924 | 1874.2924
| No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2024-09-30: 514.7267 | 514.7267
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 567.4 | 567.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 81 | 81
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 39 | 39
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 6249.48 | 6249.48
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 1874.2924 | 1874.2924
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 1218.6 | 1218.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 441.605 | 441.605
YNE28: A1033 Marfleet-Somerden | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 18638.5163 | 18638.5163
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 18638.5163 | 18638.5163
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 18638.5163 | 18638.5163
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 18638.5163 | 18638.5163
| No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-02-28: 213.4193 | 213.4193
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2981.1 | 2981.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 140 | 140
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 40 | 40
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 11707.36 | 11707.36
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 18638.5163 | 18638.5163
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2986.2 | 2986.2
YNE29: A1033 Somerden-SaltEnd | Enhanced Maintenance 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 18458.7662 | 18458.7662
| Enhanced Maintenance 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-05-31: 18458.7662 | 18458.7662
| Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 18458.7662 | 18458.7662
| Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 18458.7662 | 18458.7662
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2976.1 | 2976.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 126 | 126
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 84 | 84
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5529.02 | 5529.02
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 18458.7662 | 18458.7662
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3135.6 | 3135.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 3551.2084 | 3551.2084
YNE3: M62 J24-25 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 13549.1 | 13549.1
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-04-30: 7 | 7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 213 | 213
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 87 | 87
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 118 | 118
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 146.26 | 146.26
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 16448.4 | 16448.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 12552.17 | 12552.17
YNE30: M606 J1-2 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 7892.2 | 7892.2
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 116 | 116
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 80 | 80
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 38 | 38
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 39.18 | 39.18
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 9335.7 | 9335.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 10931.068 | 10931.068
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 1046.865 | 1046.865
YNE31: M606 J2-3 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 1554.7 | 1554.7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 99 | 99
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 52 | 52
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 43 | 43
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 126.94 | 126.94
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 5076 | 5076
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 4825.734 | 4825.734
YNE32: M621 Gildersome-J1 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 14238.8 | 14238.8
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 4 | 4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 182 | 182
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 46 | 46
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 65 | 65
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 676.91 | 676.91
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 18108 | 18108
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 7150.56 | 7150.56
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 7127.9767 | 7127.9767
YNE33: M621 J1-2 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 360 | 360
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 101 | 101
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 28 | 28
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 34 | 34
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 708.37 | 708.37
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3563.1 | 3563.1
YNE34: M621 J2-2a | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 327 | 327
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 39 | 39
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 25 | 25
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 711.55 | 711.55
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3519 | 3519
YNE35: M621 J2a-3 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 177 | 177
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 40 | 40
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 90 | 90
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 2101.8 | 2101.8
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2329.2 | 2329.2
YNE36: M621 J3-4 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 392 | 392
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 62 | 62
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 50 | 50
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 42 | 42
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1159.38 | 1159.38
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5589.9 | 5589.9
YNE37: M621 J4-5 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 311 | 311
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 53 | 53
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 28 | 28
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 41 | 41
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 937.81 | 937.81
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3441.6 | 3441.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 381.3717 | 381.3717
YNE38: M621 J5-6 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 287 | 287
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 51 | 51
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 37 | 37
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 61.66 | 61.66
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3103.2 | 3103.2
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 274.9273 | 274.9273
YNE39: M621 J6-7 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 277 | 277
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 32 | 32
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 20 | 20
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 23 | 23
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2871.9 | 2871.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 255.996 | 255.996
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 1206.8547 | 1206.8547
YNE4: M62 J25-26 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 3559.5 | 3559.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-04-30: 21853.2 | 21853.2
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-04-30: 11 | 11
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-04-30: 244 | 244
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-04-30: 76 | 76
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-04-30: 152 | 152
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-04-30: 1443.62 | 1443.62
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-04-30: 22694.4 | 22694.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-04-30: 4242.795 | 4242.795
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-04-30: 3995.2824 | 3995.2824
YNE40: M621 J7-8 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 0 | 0
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 39 | 39
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 66 | 66
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 18 | 18
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 68.15 | 68.15
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2880.9 | 2880.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 2280.822 | 2280.822
YNE41: A64 Bramham-Headley | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 8654.8 | 8654.8
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 19583.4 | 19583.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 7835.2 | 7835.2
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 132 | 132
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 113 | 113
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 3891.76 | 3891.76
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 8575.2 | 8575.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 1860.06 | 1860.06
YNE42: A64 Headley-A162 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 27708.5 | 27708.5
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 63408.9 | 63408.9
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 4180.1 | 4180.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 48 | 48
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 4 | 4
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 469.03 | 469.03
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 6606 | 6606
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 5917.899 | 5917.899
YNE43: A64 A162-Tadcaster | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 64519 | 64519
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 5321.2022 | 5321.2022
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 5321.2022 | 5321.2022
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 17648.2 | 17648.2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 155 | 155
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 6 | 6
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 3415.11 | 3415.11
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 5321.2022 | 5321.2022
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 10559.7 | 10559.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 4898.451 | 4898.451
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-06-30: 1711.9129 | 1711.9129
YNE44: A64 Tadcaster-Bilbrough | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 3341.2697 | 3341.2697
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3341.2697 | 3341.2697
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 7757.8 | 7757.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 21692.5 | 21692.5
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 146 | 146
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 4 | 4
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 14301.02 | 14301.02
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 3341.2697 | 3341.2697
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 8016.3 | 8016.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 8276.86 | 8276.86
YNE45: A64 Bilbrough-Askham | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 6646 | 6646
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 20540.8 | 20540.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 17235.7 | 17235.7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 137 | 137
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 2 | 2
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 10985.44 | 10985.44
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 6859.8 | 6859.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 5745.876 | 5745.876
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-06-30: 127.2715 | 127.2715
YNE46: A64 Askham-Bondhill | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 33915.1 | 33915.1
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-12-31: 36843.7 | 36843.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 12590.9 | 12590.9
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 155 | 155
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 8 | 8
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 4000.09 | 4000.09
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 7785.9 | 7785.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 6392.76 | 6392.76
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-06-30: 12.8686 | 12.8686
YNE47: A64 Bondhill-Fulford | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 25114.7 | 25114.7
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-12-31: 56216.6 | 56216.6
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 8077.6 | 8077.6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 102 | 102
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 14 | 14
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 3 | 3
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 1163.6 | 1163.6
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 8051.4 | 8051.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 2586.165 | 2586.165
YNE48: A64 Fulford-Grimston | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 57670.9 | 57670.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 95280.8 | 95280.8
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 4033.3178 | 4033.3178
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 4033.3178 | 4033.3178
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 15447.5 | 15447.5
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 225 | 225
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 70 | 70
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 3343.84 | 3343.84
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 4033.3178 | 4033.3178
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 14369.4 | 14369.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 11541.648 | 11541.648
YNE49: A64 Grimston-Hopgrove | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 18367.4 | 18367.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 61000.3 | 61000.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 20804 | 20804
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 169 | 169
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 98 | 98
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 4374.33 | 4374.33
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 11013.3 | 11013.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 4668.478 | 4668.478
YNE5: M62 J26-27 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 22528.5 | 22528.5
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 62 | 62
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 131 | 131
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 72 | 72
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 89 | 89
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 1311.59 | 1311.59
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 20089.8 | 20089.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 18163.84 | 18163.84
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 1885.2441 | 1885.2441
YNE50: A64 NorthHopgroveSingle | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 33140.6 | 33140.6
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 2550.7073 | 2550.7073
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2550.7073 | 2550.7073
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 25782.4 | 25782.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 282 | 282
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 65 | 65
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 12 | 12
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 6937.48 | 6937.48
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 2550.7073 | 2550.7073
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 17136 | 17136
YNE51: A64 NorthHopgroveDual | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 989.5 | 989.5
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 20900.6 | 20900.6
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 2030.2258 | 2030.2258
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2030.2258 | 2030.2258
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-06-30: 5 | 5
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 30584.8 | 30584.8
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 289 | 289
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 19264.12 | 19264.12
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 2030.2258 | 2030.2258
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 9855.9 | 9855.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 17511.892 | 17511.892
YNE52: A64 SouthMusleySingle | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 1561.6369 | 1561.6369
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1561.6369 | 1561.6369
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 40587.4 | 40587.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 32434.5 | 32434.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 16500.8 | 16500.8
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 209 | 209
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 6689.29 | 6689.29
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 1561.6369 | 1561.6369
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 11145.6 | 11145.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 67.54 | 67.54
YNE53: A64 Musley-PickeringInt | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 2252.5927 | 2252.5927
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2252.5927 | 2252.5927
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 59814.9 | 59814.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 27660.4 | 27660.4
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-06-30: 2 | 2
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 15142.2 | 15142.2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 93 | 93
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 8 | 8
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 220.79 | 220.79
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 2252.5927 | 2252.5927
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 10326.6 | 10326.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 10457.336 | 10457.336
YNE54: A64 PickeringInt-Brambling | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 41218.4 | 41218.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 17503.7 | 17503.7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 111 | 111
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 23 | 23
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 346.72 | 346.72
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 9165.6 | 9165.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 4171.04 | 4171.04
YNE55: A64 Brambling-Rillington | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 3619.7652 | 3619.7652
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3619.7652 | 3619.7652
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 12727.7 | 12727.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 13089.5 | 13089.5
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 173 | 173
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 7450.57 | 7450.57
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 3619.7652 | 3619.7652
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 8163.9 | 8163.9
YNE56: A64 Rillington-Sherburn | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 28342.5546 | 28342.5546
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 28342.5546 | 28342.5546
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 17173.4 | 17173.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 20113 | 20113
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 33366.4 | 33366.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 431 | 431
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 46 | 46
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 12 | 12
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 16218.13 | 16218.13
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 28342.5546 | 28342.5546
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 20887.2 | 20887.2
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-06-30: 12971.5371 | 12971.5371
YNE57: A64 Sherburn-Staxton | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 222.6 | 222.6
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 22661.5 | 22661.5
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 16544.0198 | 16544.0198
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 16544.0198 | 16544.0198
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 18237.1 | 18237.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 327 | 327
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 45 | 45
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 17 | 17
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 10274.19 | 10274.19
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 16544.0198 | 16544.0198
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 13586.4 | 13586.4
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-06-30: 795.0283 | 795.0283
YNE58: A64 Staxton-Seamer | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 3035.7815 | 3035.7815
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3035.7815 | 3035.7815
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 18619.2 | 18619.2
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 2558 | 2558
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-06-30: 5 | 5
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 5957.8 | 5957.8
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 130 | 130
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 24 | 24
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 9095.74 | 9095.74
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 3035.7815 | 3035.7815
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 4627.8 | 4627.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 1370.88 | 1370.88
YNE59: A64 Seamer-Dunslow | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 3144.5939 | 3144.5939
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3144.5939 | 3144.5939
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 757 | 757
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 12336.1 | 12336.1
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 4098.4 | 4098.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 78 | 78
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 22 | 22
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 5777.06 | 5777.06
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 3144.5939 | 3144.5939
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 4244.4 | 4244.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 2192.4 | 2192.4
YNE6: M62 J27-28 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 6330.9 | 6330.9
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 23381.1 | 23381.1
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 55 | 55
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 134 | 134
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 86 | 86
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 58 | 58
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 1008.47 | 1008.47
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 15425.1 | 15425.1
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 5448.18 | 5448.18
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 297.782 | 297.782
YNE60: A64 Dunslow-Musham | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 5367.4548 | 5367.4548
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 5367.4548 | 5367.4548
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 4021.1 | 4021.1
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 6270 | 6270
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 41 | 41
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 21 | 21
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 351.53 | 351.53
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-06-30: 5367.4548 | 5367.4548
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 2635.2 | 2635.2
YNE61: M1 J30-31 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2867.7 | 2867.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 3957 | 3957
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 23 | 23
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 107 | 107
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 15 | 15
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 78 | 78
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 3028.7 | 3028.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 18828 | 18828
YNE62: M1 J31-32 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 9850.1 | 9850.1
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 1517 | 1517
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 10 | 10
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 20 | 20
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 28 | 28
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 32 | 32
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 1235.45 | 1235.45
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 6826.5 | 6826.5
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 4492.5499 | 4492.5499
YNE63: M1 J32-33 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 2799 | 2799
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 9 | 9
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 71 | 71
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 4 | 4
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 40 | 40
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 744.76 | 744.76
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 14687.1 | 14687.1
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-07-31: 8215.1 | 8215.1
YNE64: M1 J33-34South | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 2463 | 2463
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 11 | 11
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 67 | 67
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 45 | 45
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 42 | 42
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 654.01 | 654.01
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 13084.2 | 13084.2
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 147.9516 | 147.9516
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-07-31: 4302.6 | 4302.6
YNE65: M1 Tinsley | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 468 | 468
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 3 | 3
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 10 | 10
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 3 | 3
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 55.72 | 55.72
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 2104.2 | 2104.2
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-07-31: 256.5 | 256.5
YNE66: M1 J34North-35 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 468 | 468
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 12 | 12
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 64 | 64
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 15 | 15
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 42 | 42
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 896 | 896
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 11340.9 | 11340.9
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-07-31: 3196.2529 | 3196.2529
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 582.5956 | 582.5956
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-07-31: 9060.5 | 9060.5
YNE67: M1 J35-35a | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 2520 | 2520
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 11 | 11
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 45 | 45
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 34 | 34
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 32 | 32
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 756.34 | 756.34
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 9084.6 | 9084.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 292.7106 | 292.7106
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-07-31: 6717 | 6717
YNE68: M1 J35a-36 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3340.5 | 3340.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 1838 | 1838
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 38 | 38
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 11 | 11
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 10 | 10
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 95.7 | 95.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 4883.4 | 4883.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 1207.908 | 1207.908
YNE69: M1 J36-37 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 17111.8 | 17111.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 3373 | 3373
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-06-30: 4 | 4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 116 | 116
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 26 | 26
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 21 | 21
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 290.86 | 290.86
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 15180.3 | 15180.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 20399.094 | 20399.094
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-06-30: 575.9979 | 575.9979
YNE70: M1 J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 12399.7 | 12399.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 3380 | 3380
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-06-30: 4 | 4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 108 | 108
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 6 | 6
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 163.96 | 163.96
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 15208.2 | 15208.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 16738.681 | 16738.681
YNE71: M1 J38-39 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 5550.4 | 5550.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 3531 | 3531
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-06-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 120 | 120
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 21 | 21
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 767.44 | 767.44
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 15887.7 | 15887.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-06-30: 21819.529 | 21819.529
YNE72: M1 J39-40 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 426.5 | 426.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 2419 | 2419
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-06-30: 7 | 7
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 83 | 83
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 10 | 10
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 24 | 24
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 1140.76 | 1140.76
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 10886.4 | 10886.4
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-06-30: 5851 | 5851
YNE73: M1 J40-41 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 2250 | 2250
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-06-30: 8 | 8
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 93 | 93
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 46 | 46
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 33 | 33
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 9161.23 | 9161.23
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 10125.9 | 10125.9
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-06-30: 6754.1 | 6754.1
YNE74: M1 J41-42 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-06-30: 1432.3 | 1432.3
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-06-30: 5 | 5
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-06-30: 104 | 104
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-06-30: 104 | 104
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-06-30: 39 | 39
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-06-30: 58.11 | 58.11
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-06-30: 7686.9 | 7686.9
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-06-30: 2752.3 | 2752.3
YNE76: A628 Tintwistle-Crowden | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 404.7546 | 404.7546
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 404.7546 | 404.7546
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 1707 | 1707
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 186 | 186
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 58 | 58
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 17 | 17
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 15034.48 | 15034.48
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 404.7546 | 404.7546
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 13417.2 | 13417.2
YNE77: A628 Crowden-Flouch | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3229.7 | 3229.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 2828 | 2828
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 534 | 534
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 7012.5 | 7012.5
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 25448.4 | 25448.4
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 113.4546 | 113.4546
YNE78: A616 Flouch-Deepcar | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 20226.8 | 20226.8
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 6877.9819 | 6877.9819
| Amenity Visit 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 6877.9819 | 6877.9819
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2355 | 2355
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 334 | 334
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 25 | 25
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 20 | 20
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 7170 | 7170
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 6877.9819 | 6877.9819
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 21091.5 | 21091.5
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 25.6823 | 25.6823
YNE79: A616 Deepcar-Wortley | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 1606.4603 | 1606.4603
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 1606.4603 | 1606.4603
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7180.4 | 7180.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 582 | 582
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 84 | 84
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 2 | 2
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 317.63 | 317.63
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 1606.4603 | 1606.4603
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5238 | 5238
YNE80: A616 Wortley-Westwood | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2295.7 | 2295.7
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 452.8724 | 452.8724
| Amenity Visit 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 452.8724 | 452.8724
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 753 | 753
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 136 | 136
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 120 | 120
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 566.66 | 566.66
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 452.8724 | 452.8724
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 6545.7 | 6545.7
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 266.8649 | 266.8649
YNE81: A616 Westwood-Stocksbridge | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 2192.0802 | 2192.0802
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 2192.0802 | 2192.0802
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 966.9 | 966.9
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 523 | 523
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 111 | 111
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 44 | 44
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 12 | 12
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 845.9 | 845.9
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2192.0802 | 2192.0802
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 4710.6 | 4710.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 937.8153 | 937.8153
YNE82: A61 | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 4698.2408 | 4698.2408
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 4698.2408 | 4698.2408
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 28642.3 | 28642.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 576 | 576
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 94 | 94
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 97 | 97
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 43 | 43
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 3734.01 | 3734.01
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-07-31: 4698.2408 | 4698.2408
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 3447 | 3447
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 742.03 | 742.03
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 701.1218 | 701.1218
YNE83: M18 Link-J1 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3288 | 3288
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 3748 | 3748
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 6 | 6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 118 | 118
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 96 | 96
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 22 | 22
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 346.7 | 346.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 18055.8 | 18055.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 13960.271 | 13960.271
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-10-31: 2667.3 | 2667.3
YNE84: M18 J1-2 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 150550.8 | 150550.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 4687 | 4687
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 212 | 212
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 228.15 | 228.15
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 21987 | 21987
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 19495.889 | 19495.889
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-10-31: 1000.507 | 1000.507
YNE85: M18 J2-3 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2949.7 | 2949.7
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [12 empty] | 1 | bar: 2024-10-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 1519 | 1519
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 54 | 54
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 4 | 4
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 128.85 | 128.85
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 6834.6 | 6834.6
YNE86: M18 J3-4 | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 508.2991 | 508.2991
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 508.2991 | 508.2991
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 9811.4 | 9811.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 4247 | 4247
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 109 | 109
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 282.71 | 282.71
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-10-31: 508.2991 | 508.2991
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 19112.4 | 19112.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 1279.48 | 1279.48
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-10-31: 2902.0477 | 2902.0477
YNE87: M18 J4-5 | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 726.4171 | 726.4171
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 726.4171 | 726.4171
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 870.2 | 870.2
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 3326 | 3326
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-10-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 139 | 139
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 14 | 14
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 40.06 | 40.06
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-10-31: 726.4171 | 726.4171
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 15543.9 | 15543.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 7469.444 | 7469.444
YNE88: M18 J5-6 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 1849 | 1849
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 74 | 74
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 128 | 128
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 13 | 13
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 129.45 | 129.45
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 8748 | 8748
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 8282.38 | 8282.38
YNE89: M18 J6-7 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 4714.8 | 4714.8
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-07-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 130 | 130
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 48 | 48
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 606.45 | 606.45
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 16558.2 | 16558.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 3225.007 | 3225.007
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 67.3353 | 67.3353
YNE9: M62 J31-32 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 18708.4 | 18708.4
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 5 | 5
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 90 | 90
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 20 | 20
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 17 | 17
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 387.72 | 387.72
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 10205.1 | 10205.1
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 6968.172 | 6968.172
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 725.01 | 725.01
YNE90: M180 Ings-J1 | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 69977.5891 | 69977.5891
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 1146 | 1146
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 146 | 146
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 78 | 78
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 13 | 13
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 12.1 | 12.1
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 5441.4 | 5441.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 3691.42 | 3691.42
YNE91: M180 J1-2 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7912.7 | 7912.7
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 223013.4103 | 223013.4103
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-07-31: 3 | 3
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 4303 | 4303
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [12 empty] | 1 | bar: 2024-07-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 114 | 114
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 23.22 | 23.22
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 19364.4 | 19364.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 13177.236 | 13177.236
YNE92: M180 J2-3 | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 171996.5331 | 171996.5331
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 2605 | 2605
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 160 | 160
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 43 | 43
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 86.35 | 86.35
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 16611.3 | 16611.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 12820.016 | 12820.016
YNE93: M180 J3-4 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 256.6 | 256.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 130182.8958 | 130182.8958
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 4519 | 4519
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 138 | 138
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 14 | 14
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 17.34 | 17.34
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 20333.7 | 20333.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 6478.203 | 6478.203
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-07-31: 1366.729 | 1366.729
YNE94: M180 J4-5 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 1763.4 | 1763.4
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 126790.3807 | 126790.3807
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 4779 | 4779
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 146 | 146
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 94 | 94
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 37 | 37
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 290.16 | 290.16
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 21506.4 | 21506.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 24577.584 | 24577.584
YNE95: M181 | No - to be booked if needed | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-03-31: 6 | 6
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-05-31: 6 | 6
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 6 | 6
| No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 39192.9431 | 39192.9431
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | 2024-07-31: 6 | 6
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-07-31: 1968 | 1968
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-07-31: 157 | 157
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-07-31: 21 | 21
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-07-31: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-07-31: 41.71 | 41.71
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-07-31: 6 | 6
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-07-31: 3345.3 | 3345.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-07-31: 6725.375 | 6725.375
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-07-31: 6 | 6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-07-31: 6 | 6
YNE96: A180 Barnetby-Brocklesby | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 32462.6 | 32462.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 224643.5395 | 224643.5395
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 4118.5325 | 4118.5325
| Amenity Visit 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 4118.5325 | 4118.5325
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 4642 | 4642
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 469 | 469
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 27 | 27
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1583.6 | 1583.6
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 4118.5325 | 4118.5325
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 22785.3 | 22785.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 9965.059 | 9965.059
YNE97: A180 Brocklesby-Stallingborough | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 10095.6 | 10095.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 105066.008 | 105066.008
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 2836.1981 | 2836.1981
| Amenity Visit 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 2836.1981 | 2836.1981
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [12 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2857 | 2857
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 157 | 157
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 925.15 | 925.15
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2836.1981 | 2836.1981
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 13715.1 | 13715.1
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 8425.708 | 8425.708
YNE98: A180 Stallingborough-GreatCoates | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 63469.5125 | 63469.5125
| Amenity Visit 2 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 2254.6435 | 2254.6435
| Amenity Visit 1 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 2254.6435 | 2254.6435
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2290 | 2290
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 148 | 148
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 54 | 54
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 816.71 | 816.71
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2254.6435 | 2254.6435
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 10431 | 10431
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 10577.443 | 10577.443
YNE99: A180 GreatCoates-Pyewipe | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 1 | 2024-04-30: 2458.1919 | 2458.1919
|  |  |  | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 2 | 2024-06-30: 2458.1919 | 2458.1919
| No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 28808.1637 | 28808.1637
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1171 | 1171
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 142 | 142
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 110 | 110
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 457.88 | 457.88
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2458.1919 | 2458.1919
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5421.6 | 5421.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 4176.14 | 4176.14
YNE7: M62 J29-30 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7189.6 | 7189.6
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 5799.9 | 5799.9
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 21 | 21
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 165 | 165
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 67 | 67
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 23 | 23
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 646.51 | 646.51
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 13399.2 | 13399.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 134.18 | 134.18
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 5331.9456 | 5331.9456
YNE8: M62 J30-31 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3347.5 | 3347.5
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [12 empty] | 1 | bar: 2024-05-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-05-31: 11945 | 11945
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-05-31: 6 | 6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-05-31: 90 | 90
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-05-31: 102 | 102
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-05-31: 36 | 36
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-05-31: 145.49 | 145.49
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-05-31: 11901.6 | 11901.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-05-31: 3181.928 | 3181.928
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-05-31: 396.462 | 396.462
Total Result |  |  |  |  | 539875.1891 | 674582.1722 | 1173398.0564 | 585382.0004 | 576552.8074 | 1172566.6716 | 786886.8249 | 175809.9 | 93060.3 | 210322.3 | 897904.9283 | 468247.9043 | 7354589.0545

## Pivot - Qts by Month Remaining
Asset Type | - all -
Sum of Quants |  |  |  |  | Planned Completion
Maintenance Route | TM Booked? | Location Detail for ILM Sections | SOR | Activity | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | Total Result
YNE1: M62 J22-23 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 16155.9 | 16155.9
YNE10: M62 J32-33 | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 4484.8888 | 4484.8888
YNE100: A160 Brocklesby-Habrough | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 48847 | 48847
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 54878 | 54878
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 827 | 827
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 54 | 54
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1902 | 1902
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 48847 | 48847
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3720.6 | 3720.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 6577.6 | 6577.6
YNE101: A160 Habrough-Manby | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 48847 | 48847
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 26649 | 26649
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1168 | 1168
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 144 | 144
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 117 | 117
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 9 | 9
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5979 | 5979
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 48847 | 48847
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5709.6 | 5709.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 21080.1342 | 21080.1342
YNE102: A162 Ferrybridge | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 923 | 923
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 26 | 26
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 8 | 8
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5742 | 5742
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 3423.23 | 3423.23
YNE103: A62 Gildersome | Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 4495.2 | 4495.2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 100 | 100
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 86 | 86
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 93 | 93
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 2455.21 | 2455.21
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 1854 | 1854
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 304.43 | 304.43
YNE105: A638 Redhouse | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 459 | 459
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 61 | 61
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 204 | 204
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 8 | 8
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 1710.36 | 1710.36
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 3863.7 | 3863.7
YNE106: A1M J34-35 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 9476.8 | 9476.8
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-09-30: 216629.3 | 216629.3
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [8 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 5079 | 5079
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 85 | 85
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 10 | 10
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 48 | 48
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 95.32 | 95.32
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 23473.8 | 23473.8
YNE107: A1M J35-36 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 2955.9 | 2955.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-09-30: 24483.8 | 24483.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1669 | 1669
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-09-30: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 66 | 66
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 175.11 | 175.11
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 7745.4 | 7745.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 6607.889 | 6607.889
YNE108: A1M J36-37 | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 147082.2 | 147082.2
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2825 | 2825
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 88 | 88
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 12 | 12
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 161.79 | 161.79
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 12710.7 | 12710.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 12715.273 | 12715.273
YNE109: A1M J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 5425.6 | 5425.6
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 95701.5 | 95701.5
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2113 | 2113
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-09-30: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 78 | 78
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 27 | 27
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 40.09 | 40.09
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 10521 | 10521
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 12932 | 12932
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-09-30: 41.7754 | 41.7754
YNE11: M62 J33-34 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 19697 | 19697
YNE110: A1 Redhouse-Barnsdale | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 402.3 | 402.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 2813 | 2813
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 200 | 200
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 194 | 194
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 18 | 18
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 4731.53 | 4731.53
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1103.8214 | 1103.8214
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 16866.9 | 16866.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 22911.439 | 22911.439
YNE111: A1 Barnsdale-Wentbridge | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 2204.3 | 2204.3
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1673 | 1673
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 96 | 96
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 26 | 26
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 15 | 15
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 535.78 | 535.78
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 8708.4 | 8708.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 16447.871 | 16447.871
YNE112: A1 Wentbridge-Darrington | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 1812 | 1812
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 114 | 114
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 7 | 7
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 8 | 8
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 1916.52 | 1916.52
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 9909.9 | 9909.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 2026.019 | 2026.019
YNE113: A1 Darrington-A162 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 23642.6 | 23642.6
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1041 | 1041
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 56 | 56
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 9 | 9
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 10 | 10
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1134.36 | 1134.36
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 6167.7 | 6167.7
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 6556.023 | 6556.023
YNE12: M62 J34-35 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 7224.3 | 7224.3
YNE13: M62 J35-36 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 7139 | 7139
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-09-30
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 106 | 106
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 24 | 24
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 101.7 | 101.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 10690.2 | 10690.2
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 7818.208 | 7818.208
YNE14: M62 J36-37 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-09-30: 3562.3 | 3562.3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-09-30: 82 | 82
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-09-30: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-09-30: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-09-30: 276.02 | 276.02
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-09-30: 9905.4 | 9905.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-09-30: 4345.958 | 4345.958
YNE15: M62 J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 9574.1 | 9574.1
YNE17: A63 SouthCave-Welton | No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 6422.8689 | 6422.8689
YNE18: A63 Welton-Melton | No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 20557.418 | 20557.418
YNE19: A63 Melton-WesternInt | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 5739.8 | 5739.8
YNE20: A63 WesternInt-PrioryWay | No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-03-31: 7061.7375 | 7061.7375
YNE21: A63 PrioryWay-BrightonSt | No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1084.1146 | 1084.1146
YNE22: A63 BrightonSt-DaltrySt | No - Enhanced Maintenance 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 186.2105 | 186.2105
YNE26: A1033 Southcoates-NorthernGate | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 7862.1945 | 7862.1945
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 3790.6 | 3790.6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 105 | 105
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 75 | 75
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 32 | 32
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5531.86 | 5531.86
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 7862.1945 | 7862.1945
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2016.9 | 2016.9
YNE27: A1033 NorthernGate-Marfleet | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 1874.2924 | 1874.2924
| No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2024-09-30: 514.7267 | 514.7267
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 567.4 | 567.4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 81 | 81
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 39 | 39
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 19 | 19
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 6249.48 | 6249.48
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 1874.2924 | 1874.2924
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 1218.6 | 1218.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 441.605 | 441.605
YNE28: A1033 Marfleet-Somerden | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 18638.5163 | 18638.5163
| No - Winter Programme | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-02-28: 213.4193 | 213.4193
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2981.1 | 2981.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 140 | 140
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 40 | 40
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 11707.36 | 11707.36
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 18638.5163 | 18638.5163
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2986.2 | 2986.2
YNE29: A1033 Somerden-SaltEnd | Enhanced Maintenance 5 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 5 | 2024-09-30: 18458.7662 | 18458.7662
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2976.1 | 2976.1
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 126 | 126
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 84 | 84
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 29 | 29
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 5529.02 | 5529.02
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 4 | 2024-08-31: 18458.7662 | 18458.7662
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3135.6 | 3135.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 3551.2084 | 3551.2084
YNE32: M621 Gildersome-J1 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 14238.8 | 14238.8
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 4 | 4
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 182 | 182
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 46 | 46
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 65 | 65
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 676.91 | 676.91
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 18108 | 18108
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 7150.56 | 7150.56
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 7127.9767 | 7127.9767
YNE33: M621 J1-2 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 360 | 360
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 101 | 101
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 28 | 28
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 34 | 34
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 708.37 | 708.37
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3563.1 | 3563.1
YNE34: M621 J2-2a | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 327 | 327
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 39 | 39
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 25 | 25
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 711.55 | 711.55
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3519 | 3519
YNE35: M621 J2a-3 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 177 | 177
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 40 | 40
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 90 | 90
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 2101.8 | 2101.8
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2329.2 | 2329.2
YNE36: M621 J3-4 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 392 | 392
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 62 | 62
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 50 | 50
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 42 | 42
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1159.38 | 1159.38
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5589.9 | 5589.9
YNE37: M621 J4-5 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 311 | 311
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 53 | 53
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 28 | 28
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 41 | 41
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 937.81 | 937.81
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3441.6 | 3441.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 381.3717 | 381.3717
YNE38: M621 J5-6 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 287 | 287
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 51 | 51
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 37 | 37
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 61.66 | 61.66
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 3103.2 | 3103.2
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 274.9273 | 274.9273
YNE39: M621 J6-7 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 277 | 277
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 32 | 32
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 20 | 20
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 23 | 23
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2871.9 | 2871.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 255.996 | 255.996
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 1206.8547 | 1206.8547
YNE4: M62 J25-26 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 3559.5 | 3559.5
YNE40: M621 J7-8 | Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 0 | 0
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 39 | 39
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 66 | 66
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 18 | 18
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 68.15 | 68.15
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 2880.9 | 2880.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 2280.822 | 2280.822
YNE41: A64 Bramham-Headley | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 8654.8 | 8654.8
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 19583.4 | 19583.4
YNE42: A64 Headley-A162 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 27708.5 | 27708.5
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 63408.9 | 63408.9
YNE43: A64 A162-Tadcaster | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 64519 | 64519
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 5321.2022 | 5321.2022
YNE44: A64 Tadcaster-Bilbrough | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3341.2697 | 3341.2697
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 7757.8 | 7757.8
YNE45: A64 Bilbrough-Askham | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 6646 | 6646
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-11-30: 20540.8 | 20540.8
YNE46: A64 Askham-Bondhill | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 33915.1 | 33915.1
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-12-31: 36843.7 | 36843.7
YNE47: A64 Bondhill-Fulford | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 25114.7 | 25114.7
|  |  | 4.8.2 | Woodland - thin / coppice | 2024-12-31: 56216.6 | 56216.6
YNE48: A64 Fulford-Grimston | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 57670.9 | 57670.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 95280.8 | 95280.8
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 4033.3178 | 4033.3178
YNE49: A64 Grimston-Hopgrove | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 18367.4 | 18367.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 61000.3 | 61000.3
YNE50: A64 NorthHopgroveSingle | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 33140.6 | 33140.6
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2550.7073 | 2550.7073
YNE51: A64 NorthHopgroveDual | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 989.5 | 989.5
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-01-31: 20900.6 | 20900.6
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2030.2258 | 2030.2258
YNE52: A64 SouthMusleySingle | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 1561.6369 | 1561.6369
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 40587.4 | 40587.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 32434.5 | 32434.5
YNE53: A64 Musley-PickeringInt | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 2252.5927 | 2252.5927
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-09-30: 59814.9 | 59814.9
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 27660.4 | 27660.4
YNE54: A64 PickeringInt-Brambling | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 41218.4 | 41218.4
YNE55: A64 Brambling-Rillington | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3619.7652 | 3619.7652
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 12727.7 | 12727.7
YNE56: A64 Rillington-Sherburn | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 28342.5546 | 28342.5546
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 17173.4 | 17173.4
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 20113 | 20113
YNE57: A64 Sherburn-Staxton | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 222.6 | 222.6
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 22661.5 | 22661.5
| Amenity Visit 3 | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 16544.0198 | 16544.0198
YNE58: A64 Staxton-Seamer | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3035.7815 | 3035.7815
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 18619.2 | 18619.2
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 2558 | 2558
YNE59: A64 Seamer-Dunslow | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 3144.5939 | 3144.5939
| No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 757 | 757
|  |  | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 12336.1 | 12336.1
YNE6: M62 J27-28 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 6330.9 | 6330.9
YNE60: A64 Dunslow-Musham | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 5367.4548 | 5367.4548
| No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2025-02-28: 4021.1 | 4021.1
YNE61: M1 J30-31 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2867.7 | 2867.7
YNE62: M1 J31-32 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 9850.1 | 9850.1
YNE68: M1 J35a-36 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3340.5 | 3340.5
YNE69: M1 J36-37 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 17111.8 | 17111.8
YNE70: M1 J37-38 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 12399.7 | 12399.7
YNE71: M1 J38-39 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 5550.4 | 5550.4
YNE72: M1 J39-40 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 426.5 | 426.5
YNE76: A628 Tintwistle-Crowden | No - to be booked if needed | (empty) | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 404.7546 | 404.7546
YNE77: A628 Crowden-Flouch | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3229.7 | 3229.7
YNE78: A616 Flouch-Deepcar | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 20226.8 | 20226.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2355 | 2355
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 334 | 334
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 25 | 25
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 20 | 20
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 7170 | 7170
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 6877.9819 | 6877.9819
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 21091.5 | 21091.5
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 25.6823 | 25.6823
YNE79: A616 Deepcar-Wortley | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7180.4 | 7180.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 582 | 582
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 84 | 84
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 2 | 2
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 5 | 5
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 317.63 | 317.63
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 1606.4603 | 1606.4603
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5238 | 5238
YNE80: A616 Wortley-Westwood | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2295.7 | 2295.7
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 753 | 753
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 136 | 136
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 120 | 120
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 566.66 | 566.66
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 452.8724 | 452.8724
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 6545.7 | 6545.7
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 266.8649 | 266.8649
YNE81: A616 Westwood-Stocksbridge | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 966.9 | 966.9
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 523 | 523
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 111 | 111
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 44 | 44
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 12 | 12
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 845.9 | 845.9
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2192.0802 | 2192.0802
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 4710.6 | 4710.6
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-08-31: 937.8153 | 937.8153
YNE82: A61 | No - Winter Programme | (empty) | 4.8.2 | Woodland - thin / coppice | 2024-10-31: 28642.3 | 28642.3
YNE83: M18 Link-J1 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3288 | 3288
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 3748 | 3748
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 6 | 6
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 118 | 118
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 96 | 96
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 22 | 22
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 346.7 | 346.7
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 18055.8 | 18055.8
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 13960.271 | 13960.271
|  |  | TBC | Grass and vegetation - Visibility Maintenance at Stopped Vehicle Detection sites | 2024-10-31: 2667.3 | 2667.3
YNE84: M18 J1-2 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 150550.8 | 150550.8
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 4687 | 4687
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 212 | 212
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 33 | 33
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 31 | 31
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 228.15 | 228.15
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 21987 | 21987
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 19495.889 | 19495.889
|  |  | 4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 2024-10-31: 1000.507 | 1000.507
YNE85: M18 J2-3 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 2949.7 | 2949.7
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [8 empty] | 1 | bar: 2024-10-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 1519 | 1519
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 54 | 54
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 4 | 4
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 128.85 | 128.85
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 6834.6 | 6834.6
YNE86: M18 J3-4 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 9811.4 | 9811.4
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 4247 | 4247
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-10-31: 2 | 2
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 109 | 109
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 7 | 7
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 282.71 | 282.71
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-10-31: 508.2991 | 508.2991
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 19112.4 | 19112.4
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 1279.48 | 1279.48
|  |  | 4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds | 2024-10-31: 2902.0477 | 2902.0477
YNE87: M18 J4-5 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 870.2 | 870.2
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-10-31: 3326 | 3326
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | [8 empty] | 1 | bar: 2024-10-31
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-10-31: 139 | 139
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-10-31: 32 | 32
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-10-31: 14 | 14
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-10-31: 40.06 | 40.06
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-10-31: 726.4171 | 726.4171
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-10-31: 15543.9 | 15543.9
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-10-31: 7469.444 | 7469.444
YNE90: M180 Ings-J1 | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 69977.5891 | 69977.5891
YNE91: M180 J1-2 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7912.7 | 7912.7
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 223013.4103 | 223013.4103
YNE92: M180 J2-3 | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 171996.5331 | 171996.5331
YNE93: M180 J3-4 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 256.6 | 256.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 130182.8958 | 130182.8958
YNE94: M180 J4-5 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 1763.4 | 1763.4
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-02-28: 126790.3807 | 126790.3807
YNE95: M181 | No - to be booked if needed | (empty) | 4.8.14 | Shrubs (Ornamental) - Maintain design requirements / amenity function | 2025-03-31: 6 | 6
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-09-30: 6 | 6
| No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 39192.9431 | 39192.9431
YNE96: A180 Barnetby-Brocklesby | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 32462.6 | 32462.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 224643.5395 | 224643.5395
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 4642 | 4642
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 469 | 469
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 27 | 27
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 1583.6 | 1583.6
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 4118.5325 | 4118.5325
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 22785.3 | 22785.3
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 9965.059 | 9965.059
YNE97: A180 Brocklesby-Stallingborough | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 10095.6 | 10095.6
|  |  | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 105066.008 | 105066.008
| Main intervention | (empty) | 4.8.17 | Wildlife Housings / Structures - Remove all material that could impair operation | [8 empty] | 1 | bar: 2024-08-31
|  |  | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2857 | 2857
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 157 | 157
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 16 | 16
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 925.15 | 925.15
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2836.1981 | 2836.1981
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 13715.1 | 13715.1
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 8425.708 | 8425.708
YNE98: A180 Stallingborough-GreatCoates | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 63469.5125 | 63469.5125
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 2290 | 2290
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 148 | 148
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 54 | 54
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 16 | 16
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 816.71 | 816.71
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2254.6435 | 2254.6435
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 10431 | 10431
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 10577.443 | 10577.443
YNE99: A180 GreatCoates-Pyewipe | No - Winter Programme | (empty) | 4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 2025-03-31: 28808.1637 | 28808.1637
| Main intervention | (empty) | 4.8.3.1 | Grass and vegetation - Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve | 2024-08-31: 1171 | 1171
|  |  | 4.8.3.2 | Grass and vegetation - Maintain and preserve CCTV camera operational visibility splays | 2024-08-31: 3 | 3
|  |  | 4.8.3.3 | Grass and vegetation - Maintain and preserve road users visibility of road traffic signs and signals | 2024-08-31: 142 | 142
|  |  | 4.8.4.1 | Grass and vegetation - Ensure illumination / lumination from lighting is not obscured | 2024-08-31: 110 | 110
|  |  | 4.8.4.2 | Grass and vegetation - Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 2024-08-31: 11 | 11
|  |  | 4.8.4.3 | Grass and vegetation - Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 2024-08-31: 457.88 | 457.88
|  |  | 4.8.5.1 | Grass and vegetation - Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features - ILM 3 | 2024-08-31: 2458.1919 | 2458.1919
|  |  | 4.8.5.2 | Grass and vegetation - Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year | 2024-08-31: 5421.6 | 5421.6
|  |  | 4.8.5.3 | Grass and vegetation - Grass cut the central reserve | 2024-08-31: 4176.14 | 4176.14
YNE7: M62 J29-30 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 7189.6 | 7189.6
YNE8: M62 J30-31 | No - Winter Programme | (empty) | 4.8.11 | Wildflower - Maintain habitat integrity including removal of scrub encroachment and undesirable weed species | 2024-10-31: 3347.5 | 3347.5
Total Result |  |  |  |  | 576552.8074 | 1172566.6716 | 786886.8249 | 175809.9 | 93060.3 | 210322.3 | 897904.9283 | 468247.9043 | 4381351.6365

## Sheet2 (hidden)
Asset Type | - all -
Sum of Quants

## Sheet4 (hidden)
4.2.1 | Check all road restraint systems
4.2.2.1 | VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.2.2 | VRS - Re-tension Wire Rope safety barriers
4.2.3 | Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332.
4.2.4 | Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 | Gully emptying including clearing of covers
4.3.11.1 | Edge scrapes and cut back and remove all build up from edge of carriageway through to filter material that could impair operation
4.3.11.2 | Weed spray
4.3.12 | Clear silt and all material that could impair operation
4.3.12 | Cycle isolation valves
4.3.13 | Clear all material that could impair operation and ensure fit for operation
4.3.14.1 | Remove any litter, debris and sediment that could impair operation
4.3.14.2 | Undertake a grass cut of the swale to maintain the grass sward betreen 100mm and 200mm in height
4.3.15.1 | Remove any litter, debris and sediment that could impair operation
4.3.15.2 | Undertake a grass cut of the grassed areas of the basin to maintain the grass sward betreen 100mm and 200mm in height
4.3.16.1 | Undertake a grass cut of all areas of the grassed surface water drainage system to maintain the grass sward at a maximum of 75mm in height |  | 250548.1667
4.3.16.2 | Remove any litter, debris and sediment that could impair operation prior to grass cutting | Woodland | 1503289 | 0.5 | 751644.5 | 125274.0833
4.3.17 | Clean surface by hydro mechanical means – (high pressure rotating water jets and powerful suction to recover disturbed silt) | Ditches | 109861 | 2.15 | 236201.15
4.3.18 | Remove any accumulated silt that is impairing the drainage operation. | Open grassland | 1216086 | 0.18 | 218895.48
4.3.2.1 | Low pressure / high volume combined kerb and drainage system jetting and proving | Ornamental shrubs | 7795 | 0.46 | 3585.7
4.3.2.2 | Clear slot drains (linear drainage)
4.3.2.3 | Sweep / clear concrete 'V' channel
4.3.3.1 | Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.3.2 | Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.3.3 | Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 | Clear/empty silt and debris from catch pits
4.3.5 | Clear ditches by removing all material that could impair operation
4.3.6 | Clear outfalls by removing all material that could impair operation
4.3.8 | Clear manholes by removing all material that could impair operation
4.3.9 | De-silt and remove all material that could impair operation
4.4.1.1 | Clean all traffic sign faces and reference numbers.
4.4.1.2 | Clean all traffic sign faces and reference numbers.
4.4.1.3 | Clean all traffic sign faces and reference numbers.
4.4.2 | Clean all post faces and reference numbers
4.4.3 | Clean bollards
4.5.1 | Bulk lamp clean and change
4.5.10 | Structural testing from 15 years old
4.5.2 | Bulk lamp clean and change
4.5.3 | Bulk lamp clean and change
4.5.4 | Bulk lamp clean and change
4.5.5 | Bulk lamp clean and change
4.5.6 | Bulk lamp clean and change
4.5.7 | Bulk clean
4.5.8 | Clean translucent surfaces
4.5.9 | Electrical testing
4.7.1 | Remove toxic, corrosive and flammable deposits and maintain light reflectance.
4.7.2 | Electrical testing
4.8.1 | Trim hedgerows, maintain and preserve clear carriageway width, sight lines and stopping distance, including junctions, access points, curves and bends
4.8.10 | Maintain habitat integrity, including removal of scrub encroachment and tree saplings throughout.
4.8.11 | Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.12 | Removal of scrub encroachment.
4.8.13 | Maintain habitat integrity, including removal of scrub encroachment.
4.8.14 | Maintain design requirements / amenity function.
4.8.15 | Maintain habitat integrity, including removal of scrub encroachment
4.8.16 | Maintain habitat integrity, including removal of undesirable species.
4.8.17 | Remove all material that could impair operation.
4.8.2 | Thin / coppice
4.8.3.1 | Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 | Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 | Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 | Ensure illumination / lumination from lighting is not obscured.
4.8.4.2 | Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment.
4.8.4.3 | Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas.
4.8.5.1 | Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features.
4.8.5.2 | Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year (in addition to visibility splay maintenance).
4.8.5.3 | Grass cut the central reserve.
4.8.6.1 | Remove obstructions and/or maintain vegetation to facilitate safe use of customer facilities. This includes but not limited to emergency roadside telephones and emergency refuge areas.
4.8.6.2 | Remove vegetation affecting the stability, integrity or operation of structures or other affected property assets.
4.8.7 | Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species.
4.8.9 | Maintain habitat integrity, including removal of scrub encroachment.
4.9.1 | Full sweep
4.9.2 | Full Sweep
4.9.3 | Litter pick to maintain to grade A
4.9.4 | Litter pick to maintain to grade A
4.9.5 | Litter pick to maintain to grade A
4.9.6 | Litter pick to maintain to grade B
4.9.7 | Litter pick to maintain to grade A
4.9.8 | Clean and maintain toilet blocks
N/A | Gully covers cleared
Schedule D | Clean / empty trapped material from interceptors
SOR TBC - | Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
SOR TBC - | Maintain in line with manufacturers requirements (TBC - await confirmation of maintenance requirements)
Clean priority soakaways
Clean non-priority soakaways
Maintain in line with EMP.
Maintain in line with current guidance, seek guidance of an ecologist.
Maintain habitat integrity, vegetation clearance to the maximum level of water storage, seek guidance of an ecologist.
Maintain in line with current statutory body requirements
Maintain in line with current species-specific legislation and current mitigation guidance
Note on A54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure this is needed as not clear what is over and above thin and coppice - should i change frequency to N/A and add to ILM?

## Sheet3 (hidden)
Activity
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.2.2 VRS - Re-tension Wire Rope safety barriers
4.2.3 Carry out bolt and weld check and clean cattlegrid to remove detritus. CEMAR GC332.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.17 Remove all material that could impair operation
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.2.2 VRS - Re-tension Wire Rope safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.2.2 VRS - Re-tension Wire Rope safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.3 Counterfort Drain Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.14 Maintain design requirements / amenity function
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.14 Maintain design requirements / amenity function
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.14 Maintain design requirements / amenity function
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.13 Clear all material that could impair operation and ensure fit for operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A - ILM
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.3.3 Counterfort Drain Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.3.3 Counterfort Drain Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.3 Counterfort Drain Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.3.3 Counterfort Drain Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.9.2 Full Sweep
4.9.3 Litter pick to maintain to grade A
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.3.1.1 Gully emptying including clearing of covers
4.8.2 Thin / coppice
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.9.2 Full Sweep
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.2.4 Inspect and maintain emergency crossing points in line with manufacturers recommendations, refer CEMAR GC334.
4.3.1.1 Gully emptying including clearing of covers
4.3.2.2 Clear slot drains (linear drainage)
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
SOR TBC - Check and maintain Trend P4 terminals in line with manufacturers recommendations, refer CEMAR GC333.
4.3.1.1 Gully emptying including clearing of covers
4.3.3.1 Grip Inlet and Non piped grip Clear/re-cut grips and counterfort drains, clear weed growth and debris
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.13 Clear all material that could impair operation and ensure fit for operation
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.7 Maintain affected property to control the spread or increase of identified instances of Injurious Weeds
4.8.8 Maintain affected property to control the spread or increase of identified instances of invasive plant species
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.14 Maintain design requirements / amenity function
4.8.17 Remove all material that could impair operation
4.9.2 Full Sweep
4.9.4 Litter pick to maintain to grade A
4.9.5 Litter pick to maintain to grade A
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.3.5 Clear ditches by removing all material that could impair operation (Non IDB)
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.2.1 Low pressure / high volume combined kerb and drainage system jetting and proving
4.3.2.2 Clear slot drains (linear drainage)
4.3.2.3 Sweep / clear concrete 'V' channel
4.3.4 Clear/empty silt and debris from catch pits
4.3.5 Clear ditches by removing all material that could impair operation
4.3.11.2 Weed spray
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.3.5 Clear ditches by removing all material that could impair operation (Non IDB)
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.8.11 Maintain habitat integrity including removal of scrub encroachment and undesirable weed species
4.8.17 Remove all material that could impair operation
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.2.1 Check all road restraint systems
4.2.2.1 VRS - Tighten or replace Screws & Bolts, Re-tension Tension Corrugated Beam (TCB) safety barriers
4.3.1.1 Gully emptying including clearing of covers
4.3.4 Clear/empty silt and debris from catch pits
4.8.3.1 Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve.
4.8.3.2 Maintain and preserve CCTV camera operational visibility splays.
4.8.3.3 Maintain and preserve road users visibility of road traffic signs and signals.
4.8.4.1 Ensure illumination / lumination from lighting is not obscured
4.8.4.2 Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment
4.8.4.3 Remove obstructions and maintain vegetation to provide safe access to and use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | areas
4.8.5.1 Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features
4.8.5.2 Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year
4.8.5.3 Grass cut the central reserve
4.8.9 Maintain habitat integrity, including removal of scrub encroachment
4.6.1.1 Replenish washer bottle fluid
4.6.1.1 Replenish washer bottle fluid
4.6.1.1 Replenish washer bottle fluid
4.6.1.1 Replenish washer bottle fluid
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Inspection of mast ropes and associated cabling, winch systems, pan/tilt/zoom mechanisms and mountings
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Greasing of winch assembly to manufacturers recommendations
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
CCTV Masts - Check mast breaking system
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Clean telephone internally and externally
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites pre-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season
Test and calibrate sites mid-winter season

## TM (hidden)
Item | Description | Actual Recovery % | Output | Recovery Against Rate | UoM | Recovery/UoM
4.2.1 | Check all Road Restraint System | 7.658% | 8000 | 102.9313 | m | 0.012866
4.2.2
4.2.2.1 | RRS - Tensioned Corrugated Beam (includes barrier length, transitions and Terminals) | 38.29% | 3000 | 514.6564 | m | 0.17155
4.2.2.2 | RRS - Wire Rope Safety Barrier (includes barrier length, transitions and Terminals) | 38.29% | 3000 | 514.6564 | m | 0.17155
4.2.3 | Treatment of weeds, remove scattered aggregate from carriageway and reprofile gravel bed
4.3.1
4.3.1.1 | Gully Emptying, including clearing aprons, covers and obstructions | 45.95% | 80 | 617.5877 | no | 7.7198
4.3.1.2 | Clear gully aprons, covers and obstructions | 76.58% | 180 | 1029.3129 | no | 5.7184
4.3.2
4.3.2.1 | Clearing, rodding, low pressure / high volume jetting and proving Combined Kerb and Drainage System | 45.95% | 500 | 617.5877 | m | 1.2352
4.3.2.2 | Clearing, rodding, jetting and proving Linear Drainage Channels (slot drains) | 45.95% | 500 | 617.5877 | m | 1.2352
4.3.2.3 | Remove debris, obstructions and sweep formed concrete drainage channel (concrete 'V' channel) | 22.97% | 4000 | 308.7939 | m | 0.077198
4.3.3
4.3.3.1 | Clear weed/vegetation growth and debris, clear, recut drainage Grip inlet and non piped drainage Grip | 33.09% | 32 | 444.7227 | no | 13.8976
4.3.3.2 | Clear weed/vegetation growth and debris clearing, rodding, jetting and proving of drainage Grip inlet and piped drainage Grip | 33.09% | 32 | 444.7227 | no | 13.8976
4.3.3.3 | Clear weed/vegetation growth and debris, clear, recut Counterfort drains | 57.43% | 12 | 771.9847 | no | 64.3321
4.3.4 | Clear weed / vegetation growth around frames, clear, empty silt and debris from Catch Pits | 38.29% | 24 | 514.6564 | no | 21.444
4.3.5 | Clear ditches by removing all material that could impair operation (weed / vegetation growth, silt, debris/rubbish, or eroded banks where present that impede flow and impair operation) | 30.63% | 600 | 411.7252 | m | 0.68621
4.3.6 | Clear outfalls by removing all material that could impair operation (Headwalls, Pipe outfall) | 3.829% | 8 | 51.4656 | no | 6.4332
4.3.7 | Clear weed / vegetation growth, around frames, clear, empty trapped material from Interceptors | 76.58% | 2 | 1029.3129 | no | 514.6564
4.3.8 | Clear manholes by removing all material that could impair operation (overgrown vegetation / weed, silt, debris / rubbish) | 76.58% | 40 | 1029.3129 | no | 25.7328
4.3.9 | De-silt and remove all material that could impair operation (silt, weed / vegetation growth, debris / rubbish, eroded bank material restricting the free flow of water through the culvert) | 22.97% | 4 | 308.7939 | no | 77.1985
4.3.10
4.3.11
4.3.11.1 | Edge scrape, clear weed / vegetation growth, cut back to remove build up of material from edge of carriage way through to filter material (Filter Drain and Combined carrier and Filter drain) that could impair operation | 57.43% | 2000 | 771.9847 | m | 0.38599
4.3.11.2 | Weed spray along Filter Drain and Combined carrier and Filter drain | 17.41% | 9500 | 234.0647 | m | 0.024638
4.3.12 | Cycle isolation valves | 44.34% | 8 | 590.1688 | no | 73.7711
4.3.13 | Clear all material that could impair operation and ensure fit for operation | 2.206% | 8 | 29.6482 | no | 3.706
4.3.14
4.3.14.1 | Clear weed / vegetation growth, remove any litter, debris and sediment that could impair operation
4.3.14.2 | Undertake a grass cut of the swale to maintain the grass sward between 100mm and 200mm in height
4.3.15
4.3.15.1 | Clear weed / vegetation growth, remove any litter, debris and sediment that could impair operation | 13.23% | 8000 | 177.8891 | m2 | 0.022236
4.3.15.2 | Undertake a grass cut of the grassed areas of the basin to maintain the grass sward between 100mm and 200mm in height | 13.8% | 16000 | 185.4213 | m3 | 0.011589
4.3.16
4.3.16.1 | Undertake a grass cut of all areas of the grassed surface water drainage system to maintain the grass sward at a maximum of 75mm in height
4.3.16.2 | Clear weed / vegetation growth, remove any litter, debris and sediment that could impair operation prior to grass cutting
4.3.17 | Cleaning (high pressure rotating water jets and powerful suction to recover disturbed silt) reservoir pavements for drainage attenuation (with pervious surface)
4.3.18 | Remove accumulated silt in wetlands (drainage purposes) that could impair operation
4.4.1
4.4.1.1 | Clean all traffic sign faces and reference numbers areas less than 5m2 | 3.829% | 60 | 47.9388 | no | 0.79898
4.4.1.2 | Clean all traffic sign faces and reference numbers areas greater than or equal to 5m2 | 22.97% | 24 | 287.6331 | no | 11.9847
4.4.1.3 | Clean all traffic sign faces and reference numbers of all Gantry Signs | 57.43% | 16 | 719.0827 | no | 44.9427
4.4.2 | Clean all marker post faces and reference numbers | 3.829% | 120 | 47.9388 | no | 0.39949
4.4.3 | Clean all illuminated and non illuminated(retroflective) bollards | 12.62% | 48 | 157.9604 | no | 3.2908
4.5.1 | Bulk lamp clean and change | 57.43% | 32 | 719.0827 | no | 22.4713
4.5.2 | Bulk lamp clean and change | 57.43% | 32 | 719.0827 | no | 22.4713
4.5.3 | Bulk lamp clean and change | 57.43% | 32 | 719.0827 | no | 22.4713
4.5.4 | Bulk lamp clean and change
4.5.5 | Bulk lamp clean and change
4.5.6 | Bulk lamp clean and change
4.5.7 | Bulk clean | 57.43% | 32 | 719.0827 | no | 22.4713
4.5.8 | Clean translucent surfaces | 57.43% | 48 | 719.0827 | no | 14.9809
4.5.9 | Electrical testing | 22.97% | 15 | 287.6331 | no | 19.1755
4.5.10 | Structural testing from 15 years old | 22.97% | 20 | 287.6331 | no | 14.3817
4.6.1
4.6.1.1 | Re-fill washer fluid bottles in Hard Shoulder camera cabinet and clean camera housing front screen using wash/wipe system | 38.29% | 20 | 479.3885 | no | 23.9694
4.6.1.2 | Manual clean camera housing front screen if wash/wipe system is not installed | 38.29% | 20 | 479.3885 | no | 23.9694
4.6.2
4.6.2.1 | Inspection of mast ropes and winch mechanism and the condition thereof | 30.63% | 32 | 383.5108 | no | 11.9847
4.6.2.2 | Greasing of winch assembly to manufacturers recommendations | 30.63% | 32 | 383.5108 | no | 11.9847
4.6.2.3 | Check mast breaking system | 30.63% | 6 | 383.5108 | no | 63.9185
4.6.3 | Clean telephone internally and externally | 0% | 16 |  | no | 0
4.6.4 | Clean telephone internally and externally | 0% | 16 |  | no | 0
4.6.5 | Test and calibrate sites pre-winter season and mid-winter season | 38.29% | 2 | 479.3885 | no | 239.6942
4.6.6 | Clean fog sensors | 0% | 4 |  | no | 0
4.6.7 | Check, clean and grease motor assemblies | 15.32% | 12 | 191.7554 | no | 15.9796
4.6.8
4.6.8.1 | Change Batteries | 19.14% | 8 | 239.6942 | no | 29.9618
4.6.8.2 | Inspect and clean battery connectors | 19.14% | 16 | 239.6942 | no | 14.9809
4.6.8.3 | Clean sign face | 19.14% | 16 | 239.6942 | no | 14.9809
4.6.9 | Optimisation of MIDAS detectors (loops and radar) in accordance with MCH 2584 [Ref 11.N] | 25.27% | 8 | 316.3964 | no | 39.5495
4.6.10
4.6.10.1 | Check alignment and condition of site and operation of any rotating tactile devices | 0% | 10 |  | no | 0
4.6.10.2 | Inspection and test in accordance with TD 101 [Ref 43.N] | 0% | 4 |  | no | 0
4.6.11 | Check alignment and condition of site | 0% | 6 |  | no | 0
4.6.12
4.6.12.1 | Inspection and Test network in accordance with BS7671 | 57.43% | 1.83 | 719.0827 | no | 392.9414
4.6.12.2 | RCD operation and visual inspection of cable terminations | 25.27% | 12 | 316.3964 | no | 26.3664
4.6.13
4.6.13.1 | Clean camera lens | 22.97% | 24 | 287.6331 | no | 11.9847
4.6.13.2 | Check camera functionality | 22.97% | 24 | 287.6331 | no | 11.9847
4.6.13.3 | Check data and power supply cables | 22.97% | 24 | 287.6331 | no | 11.9847
4.8.1 | Trim hedgerows, maintain and preserve clear carriageway width, sight lines and stopping distance, including junctions, access points, curves and bends | 44.34% | 6000 | 555.1716 | m | 0.092529
4.8.2 | Thin/ coppice | 15.32% | 600 | 191.7554 | m2 | 0.31959
4.8.3
4.8.3.1 | Maintain and preserve sight lines and stopping distance, including junctions, access points, curves, bends and central reserve. | 22.97% | 6000 | 287.6331 | m2 | 0.047939
4.8.3.2 | Maintain and preserve CCTV camera operational visibility splays | 22.97% | 12 | 287.6331 | no. | 23.9694
4.8.3.3 | Maintain and preserve road users visibility of road traffic signs and signals | 15.32% | 80 | 191.7554 | no. | 2.3969
4.8.4
4.8.4.1 | Ensure illumination / lumination from lighting is not obscured. | 15.32% | 32 | 191.7554 | no. | 5.9924
4.8.4.2 | Remove obstructions and / or maintain vegetation to facilitate safe access for inspection and maintenance of feeder pillars and technology equipment | 15.86% | 45 | 198.619 | no. | 4.4138
4.8.4.3 | Remove obstructions and maintain vegetation to provide safe access to an use of footways, cycle tracks, bridleways, footpaths and paved pedestrian areas | 13.23% | 8000 | 165.6988 | m2 | 0.020712
4.8.5
4.8.5.1 | Undertake amenity cut of amenity grass areas, including gate way features, village verges and special landscape features | 13.23% | 4000 | 165.6988 | m2 | 0.041425
4.8.5.2 | Undertake 2m wide swathe cut of all highway verges to ensure strip remains unobstructed by vegetation throughout the year (in addition to visibility splay maintenance) | 34.2% | 15000 | 428.2234 | m | 0.028548
4.8.5.3 | Grass cut the central reserve | 57.43% | 8000 | 719.0827 | m2 | 0.089885
4.8.6
4.8.6.1 | Remove obstructions and/or maintain vegetation to facilitate safe use of customer facilities. This includes but not limited to emergency roadside telephones and emergency refuge areas. | 0% | 16 |  | no | 0
4.8.6.2 | Remove vegetation affecting the stability, integrity or operation of structures or other affected property assets. | 44.12% | 32 | 552.3294 | no | 17.2603
4.8.7 | Maintain affected property to control the spread or increase of identified instances of injurious weeds | 22.06% | 5000 | 276.1647 | m2 | 0.055233
4.8.8 | Maintain affected property to control the spread or increase of identified instances of invasive plant species | 22.06% | 4000 | 276.1647 | m2 | 0.069041
4.8.9 | Maintain habitat integrity, including removal of scrub encroachment | 8.823% | 8000 | 110.4659 | m2 | 0.013808
4.8.10 | Maintain habitat integrity, including removal of scrub encroachment and tree saplings throughout | 8.823% | 8000 | 110.4659 | m2 | 0.013808
4.8.11 | Maintain habitat integrity, including removal of scrub encroachment and undesirable weed species | 8.823% | 8000 | 110.4659 | m2 | 0.013808
4.8.12 | Removal of scrub encroachment | 8.823% | 8000 | 110.4659 | m2 | 0.013808
4.8.13 | Maintain habitat integrity, including removal of scrub encroachment | 8.823% | 8000 | 110.4659 | m2 | 0.013808
4.8.14 | Maintain design requirements / amenity function | 4.412% | 3000 | 55.2329 | m2 | 0.018411
4.8.15 | Maintain habitat integrity, including removal of scrub encroachment | 4.412% | 5000 | 55.2329 | m2 | 0.011047
4.8.16 | Maintain habitat integrity, including removal of undesirable species | 13.23% | 6000 | 165.6988 | m2 | 0.027616
4.8.17 | Remove all material that could impair operation | 4.412% | 8 | 55.2329 | no | 6.9041
4.9.1 | Full sweep | 76.58% | 20000 | 958.7769 | m2 | 0.047939
4.9.2 | Full sweep | 9.518% | 16000 | 119.1714 | m2 | 0.0074482
4.9.3 | Litter pick to maintain to grade A | 19.14% | 10000 | 239.6942 | m2 | 0.023969
4.9.4 | Litter pick to maintain to grade A | 19.14% | 5000 | 239.6942 | m2 | 0.047939
4.9.5 | Litter pick to maintain to grade A | 11.5% | 11000 | 143.929 | m2 | 0.013084
4.9.6 | Litter pick to maintain to grade B | 76.58% | 8000 | 958.7769 | m2 | 0.11985
4.9.7 | Litter pick to maintain to grade A
4.9.8 | Clean and maintain toilet blocks

## Sheet1 (hidden)
Maintenance Route | 2 Year Activities for delviery 2024/25
DBFO 27 - technology assets only | Yes
YNE1: M62 J22-23 | No
YNE10: M62 J32-33 | No
YNE100: A160 Brocklesby-Habrough | Yes
YNE101: A160 Habrough-Manby | Yes
YNE102: A162 Ferrybridge | Yes
YNE103: A62 Gildersome | No
YNE104: A631 Tinsley | Yes
YNE105: A638 Redhouse | Yes
YNE106: A1M J34-35 | No
YNE107: A1M J35-36 | No
YNE108: A1M J36-37 | No
YNE109: A1M J37-38 | No
YNE11: M62 J33-34 | No
YNE110: A1 Redhouse-Barnsdale | Yes
YNE111: A1 Barnsdale-Wentbridge | Yes
YNE112: A1 Wentbridge-Darrington | Yes
YNE113: A1 Darrington-A162 | Yes
YNE114: A58 Chainbar | No
YNE12: M62 J34-35 | No
YNE13: M62 J35-36 | No
YNE14: M62 J36-37 | No
YNE15: M62 J37-38 | No
YNE16: A63 NorthCave-SouthCave | No
YNE17: A63 SouthCave-Welton | No
YNE18: A63 Welton-Melton | No
YNE19: A63 Melton-WesternInt | No
YNE2: M62 J23-24 | No
YNE20: A63 WesternInt-PrioryWay | No
YNE21: A63 PrioryWay-BrightonSt | No
YNE22: A63 BrightonSt-DaltrySt | No
YNE23: A63 DaltrySt-Mytongate | No
YNE24: A63 Mytongate-Garrison | No
YNE25: A63 Garrison-Southcoates | No
YNE26: A1033 Southcoates-NorthernGate | No
YNE27: A1033 NorthernGate-Marfleet | No
YNE28: A1033 Marfleet-Somerden | No
YNE29: A1033 Somerden-SaltEnd | No
YNE3: M62 J24-25 | No
YNE30: M606 J1-2 | No
YNE31: M606 J2-3 | No
YNE32: M621 Gildersome-J1 | No
YNE33: M621 J1-2 | No
YNE34: M621 J2-2a | No
YNE35: M621 J2a-3 | No
YNE36: M621 J3-4 | No
YNE37: M621 J4-5 | No
YNE38: M621 J5-6 | No
YNE39: M621 J6-7 | No
YNE4: M62 J25-26 | No
YNE40: M621 J7-8 | No
YNE41: A64 Bramham-Headley | No
YNE42: A64 Headley-A162 | No
YNE43: A64 A162-Tadcaster | No
YNE44: A64 Tadcaster-Bilbrough | No
YNE45: A64 Bilbrough-Askham | No
YNE46: A64 Askham-Bondhill | No
YNE47: A64 Bondhill-Fulford | No
YNE48: A64 Fulford-Grimston | No
YNE49: A64 Grimston-Hopgrove | No
YNE5: M62 J26-27 | No
YNE50: A64 NorthHopgroveSingle | No
YNE51: A64 NorthHopgroveDual | No
YNE52: A64 SouthMusleySingle | No
YNE53: A64 Musley-PickeringInt | No
YNE54: A64 PickeringInt-Brambling | No
YNE55: A64 Brambling-Rillington | No
YNE56: A64 Rillington-Sherburn | No
YNE57: A64 Sherburn-Staxton | No
YNE58: A64 Staxton-Seamer | No
YNE59: A64 Seamer-Dunslow | No
YNE6: M62 J27-28 | No
YNE60: A64 Dunslow-Musham | No
YNE61: M1 J30-31 | Yes
YNE62: M1 J31-32 | Yes
YNE63: M1 J32-33 | Yes
YNE64: M1 J33-34South | Yes
YNE65: M1 Tinsley | Yes
YNE66: M1 J34North-35 | Yes
YNE67: M1 J35-35a | Yes
YNE68: M1 J35a-36 | Yes
YNE69: M1 J36-37 | Yes
YNE7: M62 J29-30 | No
YNE70: M1 J37-38 | Yes
YNE71: M1 J38-39 | Yes
YNE72: M1 J39-40 | Yes
YNE73: M1 J40-41 | Yes
YNE74: M1 J41-42 | Yes
YNE76: A628 Tintwistle-Crowden | Yes
YNE77: A628 Crowden-Flouch | Yes
YNE78: A616 Flouch-Deepcar | Yes
YNE79: A616 Deepcar-Wortley | Yes
YNE8: M62 J30-31 | No
YNE80: A616 Wortley-Westwood | Yes
YNE81: A616 Westwood-Stocksbridge | Yes
YNE82: A61 | Yes
YNE83: M18 Link-J1 | Yes
YNE84: M18 J1-2 | Yes
YNE85: M18 J2-3 | Yes
YNE86: M18 J3-4 | Yes
YNE87: M18 J4-5 | Yes
YNE88: M18 J5-6 | Yes
YNE89: M18 J6-7 | Yes
YNE9: M62 J31-32 | No
YNE90: M180 Ings-J1 | Yes
YNE91: M180 J1-2 | Yes
YNE92: M180 J2-3 | Yes
YNE93: M180 J3-4 | Yes
YNE94: M180 J4-5 | Yes
YNE95: M181 | Yes
YNE96: A180 Barnetby-Brocklesby | Yes
YNE97: A180 Brocklesby-Stallingborough | Yes
YNE98: A180 Stallingborough-GreatCoates | Yes
YNE99: A180 GreatCoates-Pyewipe | Yes