# Research specification: CCRA3 Evidence Report Technical Chapters

# Tender Reference Number: KB/0918

Specification of Requirements

Invitation to Tender for research: To understand how behaviour change can influence climate change risks and opportunities

Tender Reference Number: KB/0918

Deadline for Tender Responses: 12 noon on 5th November 2018

Contents

1.	Introduction and summary of requirements / Preamble	3

2.	Background	3

3.	Aims and Objectives	3

4	Approach	4

5	Outputs Required	7

6	Ownership and Publication	7

7	Quality Assurance	8

8	Timetable	8

9	Challenges	9

10	Ethics	10

11	Working Arrangements	10

12	Skills and experience	10

13	Consortium Bids	11

14	Budget	11

15	Evaluation of Tenders	11

# Introduction and summary of requirements / Preamble

The Adaptation Sub-Committee (ASC) of the Committee on Climate Change (CCC) is the government’s statutory adviser on preparing for climate change. Under the Climate Change Act (2008) the ASC has two main roles:

- To provide independent, expert advice on the UK climate change risk assessment (CCRA).

- To report to Parliament on progress with implementation of the National Adaptation Programme (England only).

To do this the ASC conducts independent analysis into climate change science, economics and policy, and engages with a wide range of organisations and individuals to share evidence and analysis. The CCC and ASC’s past reports are available at http://www.theccc.org.uk/publications/.

To inform the ASC’s Evidence Report for the third UK CCRA, the ASC is commissioning through this contract a consortium of experts to undertake relevant analysis and draft the technical chapters for the Report.

# Background

The second CCRA (CCRA2) was published in 2017 and was supported by a comprehensive Evidence Report from the Adaptation Sub-Committee (ASC). Defra published their second National Adaptation Programme in July 2018 in response to the risks and opportunities set out in the report, and the devolved administrations are in the process of drafting their own updated national adaptation programmes.

The third CCRA will be published by the UK Government in January 2022, and Defra have asked the ASC to produce an accompanying independent Evidence Report by July 2021.

# Aims and Objectives

The aims of this project are to:

- Form a consortium of highly experienced technical experts on climate change impacts and adaptation;

- Bring together the evidence, undertake any required new analysis, engage with the relevant stakeholders, and write all of the technical chapters for the CCRA3 Evidence Report;

- Ensure that all of the chapters are robust, authoritative and comprehensive such that they can be signed off by the ASC, and;

- Make best use of the expertise within the consortium, plus the wider expertise of the UK adaptation and sector-based practitioner and academic communities.

There are six specific tasks involved in creating the CCRA3 technical chapters.  The approach section in the bid should set out what is proposed under each of the following tasks:

- Governance

- Chapter structures

- Literature review

- Chapter analysis

- Chapter drafting

- Chapter review

# Approach

Bids should set out an approach to producing the technical chapters, task by task.

In doing so, bids should show how they will apply the CCRA method to the chapters. The draft method for CCRA3 as a whole is provided in the accompanying document to this specification (Annex A).  The method sets out in detail how we see the whole CCRA3 project coming together, what we are aiming to achieve and how, and what the various outputs will be. Bidders should note that the method is still under review and though we do not necessarily expect major changes, the content of the method may change somewhat between now and November 2018, when it will be finalised.  Bids should be prepared and priced based on the information that is currently set out in the draft method as it is (but note the need for flexibility below).

The suggested chapter structure follows the structure used for CCRA2:

- Introduction

- Approach

- Natural Environment

- Infrastructure

- People and Built Environment

- Business

- International Dimensions

It is not planned at this stage to include a separate cross-cutting issues chapter in the CCRA3 technical chapters, but to integrate cross-cutting issues in each chapter (summarised in a dedicated section) and to pick up specific issues (such as social vulnerability) in the summary documents and synthesis report. The draft method contains specific details on the CCRA structure, products, approach and coverage of risks and opportunities.  The method is based on a customer requirement document provided to the ASC by Defra.  This is available on request to potential bidders.

As well as setting out an approach that implements the CCRA method, bids should include in their approach the following ‘tasks’:

- Governance

The CCRA3 technical chapters cannot be produced in isolation, but need to be created in partnership with the ASC, Defra and the devolved administrations, relevant stakeholders and experts that are not part of the consortium itself. The following table sets out the suggested governance structure for the technical chapters:

| Group | Role | What engagement is needed from the chapter consortium and what should be included in bids |
| --- | --- | --- |
| Adaptation Sub-Committee (ASC) | Managing the whole CCRA3 Evidence Report work programme. Drafting the CCRA3 Synthesis Report. | This contract will be managed by the ASC. The ASC will lead in overseeing the project, have final sign-off of the chapters, and have the final say on any contentious issues. Bids should include a suggested schedule of regular meetings with the ASC project manager. |
| Expert Advisory Panel (EAP) | The ASC will set up and manage an expert advisory panel (EAP) for the CCRA, made up of climate risk or sector experts, including some who have previously worked on CCRA1 and/or CCRA2. It is expected that EAP will have 10 -15 people on it, with one expert per chapter plus several experts on cross-cutting issues. The aim of the EAP is to provide input to the various CCRA outputs as they are being developed. The ASC will confirm the membership of the panel by December 2019, as its membership partly depends on who ends up undertaking this contract, as well as who undertakes the CCRA research projects. | The EAP should be used to help in developing the chapters from the beginning on the project, not as a review group at the end. The successful bidders must consult regularly and frequently with this panel and seek its steer on key issues that were considered and addressed in CCRA1 and/or CCRA2, the outline of each chapter, key evidence sources to use, how to frame the analysis, and for checking of drafts before they go out to review. Bids should include a suggested schedule for engaging with the EAP. As well as ongoing, ad hoc engagement with individuals in the EAP on specific chapters or issues, we suggest budgeting for at least five meetings with the group as a whole. |
| Research projects | The ASC is funding six CCRA3 research projects (see method) to feed new analysis into the chapters and other CCRA outputs. | Bids should set out the process for how the results of these research projects will feed in to each of the relevant chapters, taking into account what is set out in the CCRA3 method. The research projects will be starting in autumn 2018 and running until March 2020 at the latest. As well as ongoing ad hoc engagement as needed, it is expected that the chapter leads will meet with the relevant research projects leads at least twice, early in 2019, to help to steer the outputs of the research early on so that they can be fed in efficiently to the chapter drafting. |
| Stakeholders | Feed in views on the structure and approach for the chapters, and review the chapter drafts. The ASC and CCRA customers (Defra and the devolved administrations) will suggest attendees for stakeholder meetings. | The chapter consortium will need to consult with stakeholders at the planning stage for the chapters and as they are written. Bids should include at least three stakeholder meetings in the project, with government and non-government stakeholders who will use the CCRA findings. The first should be early in the process to obtain input on what the key issues are that stakeholders would like to see reflected in the chapters; the second to get information on the level and types of adaptation underway to manage the risks and opportunities; and the third to discuss emerging findings and urgency scores for the different risks and opportunities. Bids can suggest more stakeholder meetings as deemed appropriate. Bidders should consider whether it is preferable to hold meetings for each chapter separately (as was done for CCRA1), or all chapters together (as was done for CCRA2), taking into account the need for each chapter to consider how risks interact. Costs for venue and other logistics as well as staff time should be included in the proposed budget. |
| Review group | The ASC will organise three review groups; a technical peer review, government stakeholder review group and a non-government stakeholder review group as was done for CCRA2. These groups will all review the chapters at the same time. | The chapter consortium will need to respond to all review comments on drafts of the chapters. Bids should include three review rounds – one for early drafts, and two for the final drafts. All review comments will need to be documented and the responses to each logged, in the same way that was done for CCRA2. For CCRA2, the technical chapters received over 2,000 review comments in total, and bidders should consider that a similar sized review will take place for CCRA3. |

Please note that the ASC and Defra are also setting up two oversight groups for the whole CCRA:

- A CCRA Customer Group (chaired by the ASC) to ensure that the work programme meets the requirements set out in the customer requirement and,

- A Government Project Board (chaired by Defra) which will act as a coordination and contact point for the review of the main CCRA outputs by government stakeholders, and for identifying relevant contact points across government.

The ASC will work with the chapter consortium to decide how it should best interact with these oversight groups once the contract is awarded.  Bidders should be aware of the existence of these groups and are welcome to set out in bids how they would prefer to engage with them (e.g. directly, or through the ASC).

- Chapter structures

Bids should set out a suggested structure for each chapter, to be finalised once the contract is awarded:

- The structure of the chapters should be based around the application of the CCRA urgency framework, by risk.  Each chapter should also have a section on interacting risks and cross-cutting issues.

- It is expected that the chapters will be developed through a mixture of a) literature review, including through a Call for Evidence b) the results of the CCRA3 research projects, c) novel analysis done by the chapter consortium and d) input from the ASC, EAP, stakeholders and review groups.

- Literature Review

Bids should set out how the literature review will be conducted to identify and collate relevant evidence that has emerged since 2016:

- It is expected that the successful bidder will put out a call for evidence early in 2019 to obtain any new literature relevant to the CCRA that has been published since 2016.

- Bidders should consider how the consortium will access articles from peer-reviewed journals, as the ASC does not have subscriptions to most academic journals.

- Chapter analysis

The ASC expects that, compared to what was possible for CCRA2, the chapter writing teams will undertake additional analysis over and above the literature review in applying the three steps of the CCRA urgency method; in particular steps 2 and 3 (assessment of adaptation to manage the risk or opportunity) which were conducted in a fairly light touch way for CCRA2. Bids should set out what analysis is proposed to address steps 1 – 3 of the urgency method. Issues to consider include:

- How to apply both a literature review approach and new analysis across the chapters;

- How the analysis will result in place-based information to enable the production of summaries for types of area (cities, coasts, uplands, rural lowlands and marine), while also producing a national-level urgency score;

- How to assess the impacts of current and future adaptation on risks and opportunities;

- How to ensure a consistent approach to using climate and socioeconomic scenarios

- How to summarise risks and opportunities in 2ºC and 4 ºC worlds, bearing in mind that there may be gaps in the evidence for impacts under these scenarios for some risks or opportunities;

- How to fully integrate fully the use of natural and social science including economics in the chapter analysis from the beginning;

- More detailed economic analysis of risk and opportunities, including use of monetary valuation, cost benefit analysis and natural capital accounting where appropriate;

- Bids are encouraged, where appropriate, to explore how ‘systems thinking’ could be used in their analysis in order to support potentially moving to a more systems-based approach for CCRA4.

The list of risks and opportunities that will need to be included in the CCRA3 analysis is still being discussed between the ASC and the Customer Group, but will likely be similar to the CCRA2 list (i.e. between 50 and 60 risks or opportunities in total).

- Chapter drafting

Bids should outline in detail who will be on each chapter drafting group and how they will be organised and managed:

- Each chapter group should be led by an individual lead author with, ideally, at least 15 years’ experience in climate change impacts or adaptation, and preferably an individual who has been involved in or engaged with either CCRA1 or CCRA2. This individual will have overall accountability for the chapter and be the key point of contact for the ASC on that chapter.  Bids should set out how the chapter authors will collaborate and communicate effectively to ensure consistency between the chapters.

- We expect each chapter group to include natural and social scientists including economists, as well as experienced experts on impacts and adaptation in the relevant sectors for that chapter.  For the chapter groups to work effectively they should be fairly small e.g. fewer than ten authors per chapter.

NOTE - Need for Flexibility

While the ASC intends to avoid scope creep throughout the project by setting out the requirements clearly up front, some flexibility by the chapter writing consortium will be needed.  For example, the ASC may ask for additional meetings to be set up to discuss specific technical points around the chapters, or some additional research might be needed on specific risks.  Bids should set out how the consortium will ensure that they can accommodate this need for flexibility.  For significant additional pieces of work the ASC will offer contract variations, but would like to understand what the bidder’s policy is on absorbing minor additional requests within the contract budget.

# Outputs Required

The ASC requires:

- Each technical chapter set out as a formatted report using the template of the lead contractor (not the CCC template). The ASC requires both Word and PDF versions of the chapters.  Chapters should include a full bibliography and a summary of the key findings up front.

- A summary table from each chapter setting out the urgency scores by risk/opportunity, with justification (as was done for CCRA2).

- Accompanying spreadsheets containing any underlying data that has been created as part of the project, e.g. GIS layers created, CBA tools or other analytical work.

- Accompanying spreadsheets containing the underlying data used to create any charts or other diagrams used in the chapters.

- High resolution versions of all of the figures and charts included in the chapters.

# Ownership and Publication

The results of the analysis and all outputs produced will be owned by and published at the discretion of the Adaptation Sub-Committee.  It is likely that all outputs, including all review comments and responses, will be published and shared widely.

# Quality Assurance

All research tasks and modelling must be quality assured and documented. Contractors should:

- Include in their bids a quality assurance (QA) plan that they will apply to all of the tasks.

- Specify who will take lead responsibility for ensuring quality assurance and ensure that this responsibility rests with an individual not directly involved in the research, analysis or model development.

- Provide a QA log to demonstrate the QA undertaken, including who undertook the QA and the scope, type and level of QA that has been undertaken (e.g. a log entry only stating ‘the data were checked’ will not be sufficient).

Sign-off for the quality assurance must be done by someone of sufficient seniority within the consortium to be able take responsibility for the work done.  Acceptance of the work by the ASC will take this into consideration.

The lead contractor will be responsible for any work supplied by sub-contractors and should therefore provide assurance that all work in the contract is undertaken in accordance with the quality assurance expectation agreed at the beginning of the project.

For primary research, contractors should be willing to facilitate ASC staff to attend interviews or listen in to telephone surveys as part of the quality assurance process.

The consortium must demonstrate in their bid their ability to produce deliverables of quality, in particular following best practice regarding analysis and presentation of findings.

The ASC reserves the right to refuse to sign off outputs which do not meet the required standard specified in this invitation to tender, or where chapter consortium has not completed all of the tasks set out here, or outputs which have not adequately addressed review comments in the view of the ASC.

# Timetable

An indicative timeline for deliverables is presented below. The contractors can propose modifications to the timeline to better suit their analysis if appropriate, though the submission date of the third draft report and the final submission date must remain the same. Any proposed modifications should be set out in the bid and will require approval from the ASC.

| Phase | Deliverable | Date |
| --- | --- | --- |
| Bidding | Bid deadline | 5th November 2018 |
|  | Interviews conducted | w/c 26th November 2018 |
|  | Contract awarded | By 7th December 2018 |
|  | Kick-off meeting with ASC | w/c 10th December 2018 |
| Chapter planning and analysis | Chapter structures produced and reviewed by the ASC, EAP and Customer Group | By 30th March 2019 |
|  | First set of stakeholder meetings | By 30th March 2019 |
|  | Call for evidence conducted | By 31st May 2019 |
|  | Literature review conducted | January – June 2019 |
|  | Engagement with CCRA research projects | January – December 2019 |
|  | New analysis conducted | January – December 2019 |
| Chapter drafting | Drafting begins | September 2019 |
|  | Second set of stakeholder meetings | By end of January 2020 at the latest |
|  | First draft chapters ready for review by ASC | Early May 2020 |
|  | Second draft chapters ready for review by ASC and CCRA review groups | End June 2020 |
|  | Third set of stakeholder meetings | By end June 2020 at the latest |
|  | Third draft chapters prepared and given to authors of summary documents (contractors) and synthesis report (ASC) | End August 2020 |
|  | Third draft chapters ready for review by ASC and CCRA review groups | End August 2020 |
|  | Chapters finalised and signed off by ASC | December 2020 |

# Challenges

This is a complex, multi-faceted project.  The technical chapters for CCRA2 ran to well over 1,000 pages and involved input from approximately 200 individuals, and this project is likely to be similar in size and complexity.  There are many challenges that the ASC envisage with this project; some examples are below but bids should set out a detailed list with suggested mitigation strategies:

- The complexity involved in setting up chapter drafting teams that work effectively internally, as well as with the other governance and project groups for CCRA3.

- Ensuring consistency of approach in the assumptions made and evidence used across the chapters.

- Creating a risk assessment based on both a literature review and new analysis.

- Dealing with conflicting views from different authors, advisers and stakeholders.

- Dealing with illness or other issues that mean key experts may not be available throughout the whole project period.

- Obtaining robust data to support the economic analysis, level of current and potential future adaptation, and analysis of the size of the risk, now and in the future.

- Undertaking analysis and writing up in a way that includes results by risk, spatial area, and interacting issues.

- The chapters must be delivered by the deadline, so any delays or other issues must be absorbed into the timetable.

# Ethics

All applicants will need to identify and propose arrangements for initial scrutiny and on-going monitoring of ethical issues including the new GDPR rules on use of personal data. The appropriate handling of ethical issues is part of the tender assessment exercise and proposals will be evaluated on this as part of the ‘addressing challenges and risks’ criterion.

We expect contractors to adhere to the following GSR Principals:

- Sound application and conduct of social research methods and appropriate dissemination and utilisation of findings

- Participation based on valid consent

- Enabling participation

- Avoidance of personal harm

- Non-disclosure of identity and personal information

# Working Arrangements

The successful consortium will be expected to identify a single Project Director (PD) and a Project Manager (PM).  Both the PD and PM will meet regularly with the ASC. Within the ASC, the contract will be overseen as a whole by the Head of Adaptation (Kathryn Brown), but individual committee members and secretariat will be assigned as leads for the different chapters.

# Skills and experience

The ASC would like you to demonstrate that you have the experience and capabilities to undertake the project.

Contractors should propose named members of the project team, and include the tasks and responsibilities of each team member. This should be clearly linked to the work programme, indicating the grade/ seniority of staff and number of days allocated to specific tasks. Your tender response should include a summary of each proposed team member’s experience and capabilities

# Consortium Bids

It is expected that all the bids for this project will be from consortia of different organisations. Only one submission covering all of the partners is required but consortia are advised to make clear the proposed role that each partner will play in performing the contract as per the requirements of the technical specification.  We expect the bidder to indicate who in the consortium will be the lead contact for this project, and the organisation and governance associated with the consortia.

It is expected that some individual experts may be approached by more than one potential lead bidder to take part in their bid. The ASC has no issues with an individual being named in more than one bid.

Contractors must provide details as to how they will manage any sub-contractors and what percentage of the tendered activity (in terms of monetary value) will be sub-contracted.

If a consortium is not proposing to form a corporate entity, full details of alternative proposed arrangements should be provided. However, please note the Committee on Climate Change reserves the right to require a successful consortium to form a single legal entity in accordance with Regulation 28 of the Public Contracts Regulations 2006.

The Committee on Climate Change recognises that arrangements in relation to consortia may (within limits) be subject to future change. Potential Providers should therefore respond in the light of the arrangements as currently envisaged. Potential Providers are reminded that any future proposed change in relation to consortia must be notified to the Committee on Climate Change so that it can make a further assessment by applying the selection criteria to the new information provided.

# Budget

The budget for this project is up to £440,000 excluding VAT (£550,000 including VAT) of which the breakdown by financial year must be as follows:

- 2018/19 - £40,000 excluding VAT (£50,000 including VAT)

- 2019/20 - £240,000 excluding VAT (£300,000 including VAT)

- 2020/21 - £160,000 excluding VAT (£200,000 including VAT)

Contractors should provide a full and detailed breakdown of costs (including options where appropriate). This MUST include the funding allocated by each task as well as by person. Please include the number of days in the unpriced bid.

Cost will be a criterion against which bids which will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments can be adjusted and agreed with the contractor and Project Manager. Please advise in your bid how this breakdown reflects your usual payment processes.

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The Committee on Climate Change aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 50 pages, excluding CVs and corporate information. Tenders will be evaluated by at least three reviewers.

The ASC will select the bidder that scores highest against the criteria and weighting listed below, see the ITT for further information.

EVALUATION CRITERIA AND SCORING METHODOLOGY

| Criterion | Description | Weighting |
| --- | --- | --- |
| 1 | RELEVANT EXPERIENCE / DEMONSTRATION OF CAPABILITY OF THE PROPOSED PROJECT TEAM | 30% |
| 2 | QUALITY ASSURING THE SERVICES YOU PROVIDE | 10% |
| 3 | MANAGEMENT STRUCTURE AND MANAGING RELATIONSHIP WITH THE ASC | 10% |
| 4 | METHOD | 30% |
| 5 | UNDERSTANDING OF REQUIREMENTS | 15% |
| 6 | RISK AND CHALLENGES | 5% |
|  |  | 100% |

Scoring Method

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100.  Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

| Score | Description |
| --- | --- |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

Structure of Tenders

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above and supply a price schedule specifying the daily rates (ex-VAT) you will charge for each level of your staff.

Evaluation for Interviews, if held

The ASC reserves the right to award the contract based on applicants’ written evaluation only if one candidate emerges from the evaluation stage as significantly stronger than the others.

Should interviews go ahead, they are provisionally expected to be held on the week commencing 26th November 2018. If this date changes, the ASC will notify applicants.

The areas to be covered in the interview will be sent to the shortlisted bidders prior to interview.

Further details of interviews will be sent to successful applicants on selection.

Feedback

Feedback will be given by email.