# Annex A

| Title of project: | Goose and Swan Monitoring Programme |
| --- | --- |
| Date and time for return of tenders: | Wednesday 22 February 2017 @16:00 hours |
| Contract Reference No: | C16-0291-1095 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO ANNA ROBINSON, DORA IANTOSCA OR GORDON GREEN VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Email: David.Stroud@jncc.gov.uk Tel: +44 (0)1733 866810 OR Joint Nature Conservation Committee Email: Anna.Robinson@jncc.gov.uk Tel: +44 (0)1733 866851 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca or Gordon Green Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or Gordon.green@jncc.gov.uk Tel: 01733 866894 or 01733 866806 |
| Proposed start-date: | 1st April 2017 |
| Proposed end-date: | 31st March 2022 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	4

5.	Project Objectives: Detailed tasks	4

6.	Potential follow-on work	7

7.	Outputs	7

8.	Timescale	7

9.	Health and safety	8

10.	Data access, security, usage and ownership	8

11.	Project management	9

12.	Instructions for tender submission	9

13.	Evaluation Criteria	10

14.	Payment	11

15.	Additional Contractor requirements	12

Annex 1	12

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC website: http://jncc.defra.gov.uk/

## Project Aims

The Goose and Swan Monitoring Programme (GSMP) aims to deliver population estimates and trends both at UK and at site level, in order to assess the status of geese and swans wintering in the UK.

It also provides data and information about those demographic factors (e.g. breeding success) driving those trends: information that informs conservation action.

The outputs will help JNCC and other parts of government to fulfil statutory and international obligations for the conservation of wild birds, and the sites and habitats on which they depend. Data may also be used for adaptive management purposes, informing decisions regarding adaptation of populations to agreed target sizes – agreed within international frameworks as appropriate.

## Project Background

The UK supports fourteen populations of geese and migratory swans, and for seven, the UK has particular responsibility as most of the population winters in the UK, or stops-over on migration. The GSMP includes surveys to monitor these populations, collecting data on abundance and demography (e.g. annual productivity as expressed by proportion of young in winter flocks). The species GSMP collects data on are those for which data is most important for conservation and management purposes (listed in the table in section 5).

The GSMP has been a partnership between JNCC, SNH and WWT for many years.

WWT coordinates surveys primarily through their relationship with a volunteer network. The data collected are important for assessing both the biological and conservation status of geese and swans and guiding conservation action.

Data from the GSMP are fed into the Wetland Bird Survey (WeBS) database, and hence GSMP has linkages to the JNCC, WWT, BTO and RSPB partnership delivering WeBS.

In the future, the work of GSMP will also be linked to a planned project providing cross-taxon support for analysis and development.

## Project Objectives

To meet the overall aim of this project (Section 2), the objectives are annually to produce:

- Data on population numbers and trends, including national and site level population estimates;

- Data and information relevant to the requirements of the EU Birds Directive, the Ramsar Convention on wetlands, and the Agreement on the conservation of African-Eurasian migratory waterbirds (AEWA).  Data are critical for national Article 12 reporting under the Birds Directive which is used for multiple other national and international conservation policy purposes;

- Data and information relevant to the management of conflicts between some land users and goose populations, as well as improved management of populations of high conservation concern or those that require adaptive management, such as harvested species;

- A programme of work that would build expertise within the network, especially through the dissemination of training materials related to field techniques and methods;

- A continuation of long term data which complement WeBS and are fed into the WeBS database;

- A critical source of site-related data for Pink-footed Goose, Greenland White-fronted Goose, Icelandic Greylag Goose, and Greenland Barnacle Goose in the statutory site designation systems (Common Standards Monitoring).

## Project Objectives: Detailed tasks

Note, this section sets out JNCC’s key requirements for the GSMP. In addition to responding to these, the tenderer is welcome to set out any other work they are undertaking that would complement these requirements. The scope of the final contract will depend on funding available.

5.1 Coordination of national surveys of geese and migratory swans in the UK where these are not provided for by the Wetland Bird Survey (WeBS), through support of a volunteer network.  This will include population counts and breeding success (i.e. through making age assessments of populations). See table below for details of requirements for each species.

The tenderer is invited to propose the sampling strategy and which key sites (e.g. SPAs, pSPAs, Ramsar Sites, A/SSSIs, pA/SSSIs) should be included for the different species, but the final approach will be agreed with the Project Steering Group.  As is normal practise for biological surveys, all data are to be collected and delivered at the smallest possible scale, allowing aggregation upwards in increasingly larger units to give UK totals (and following inclusion with other data, international totals).

Where possible the tenderer should also propose collection of relevant co-variables where these would be useful to collect to help interpret the data. This could include factors linked to count conditions (e.g. disturbance), or factors that could be useful in wider scientific analyses (e.g. habitat type at recording sites).

We welcome responses that propose making best use of any existing activity. Thus the response for some species could include collating information from or providing support to existing survey groups.

| Species | UK Abundance | UK Trend | Key Sites | Annual Breeding Success |
| --- | --- | --- | --- | --- |
| Bewick’s Swan | Every 5 years (as a part of the International Swan Census) | Covered by WeBS | Annual survey in key area(s) not covered by WeBS | Annual |
| Whooper Swan | Every 5 years (as a part of the International Swan Census) | Covered by WeBS | Annual survey in key area(s) not covered by WeBS | Annual |
| Taiga Bean Goose | Annual (in Scotland covered by SNH contract and data from Bean Goose Action Group) | Annual (in Scotland covered by SNH contract and data from Bean Goose Action Group) | Annual (in Scotland covered by SNH contract and data from Bean Goose Action Group) | Annual (in Scotland covered by SNH contract and data from Bean Goose Action Group) |
| Pink-footed Goose | Annual (as a part of the International Goose Census in autumn/early winter) | Annual | Spring census of key sites every three years | Annual |
| European White-fronted Goose | Covered by WeBS | Covered by WeBS | Covered by WeBS | Annual |
| Greenland White-fronted Goose | Annual | Annual | Annual | Annual |
| Iceland Greylag Goose | Annual | Annual | 3-yearly cycle of spring counts at key sites | Annual |
| British Greylag Goose | Covered by WeBS | Covered by WeBS | Annual | Annual |
| Greenland Barnacle Goose | Every three years (from Spring 2018) | Covered by WeBS | Annual | Annual |
| Svalbard Barnacle Goose | Annual | Annual | Annual | Annual |
| Dark-bellied Brent Goose | Covered by WeBS | Covered by WeBS | Covered by WeBS | Annual |
| East Canadian High Arctic Light bellied Brent Goose | Sufficiently surveyed, primarily by Irish Brent Goose Research Group, Icelandic Institute of Natural History and WeBS | Sufficiently surveyed, primarily by Irish Brent Goose Research Group, Icelandic Institute of Natural History and WeBS | Sufficiently surveyed, primarily by Irish Brent Goose Research Group, Icelandic Institute of Natural History and WeBS | Annual |
| East Atlantic Light-bellied Brent Goose | Covered by WeBS | Covered by WeBS | Covered by WeBS | Annual |

  - Data management and routine data analysis

In addition to coordinating the survey work, there is a need to manage the resulting data and carry out routine analyses related to annual reporting.

The required analysis includes:

  - annual or periodic (as appropriate according to table above) estimates of the population size for species not adequately covered by WeBS.

  - annual or periodic (as appropriate according to table above) trends of relevant goose and swan populations for the UK as a whole and, where possible, for individual countries and regions within the UK, where not already covered by WeBS.

  - Measures of breeding success for relevant goose and swan populations where these data are collected.

The data gathered should be provided to WeBS on an annual basis, at a time specified by WeBS.

Where possible the contractor should ensure that data access is agreed at the stage of data collection, and that all data are licensed under Open Government Licence in accordance with Section 10.

The contractor should ensure databases are secure and backed up in accordance with the agreed data security policy (see Section 10).

Tenderers are invited to submit costed proposals for two options:

1.  Maintenance of basic data management procedure, and

2.  Any improvements that could be put in place to improve the process.

  - Reporting

The tenderer should propose cost effective means of communicating the results to volunteer recorders, the public and relevant statutory and other stakeholders.

This is likely to include an annual summary report on status and trends in population size and breeding success, and detailed information on the species on online webpages.  The online pages should refer to the WeBS report where this is the main mechanism for data collection.

Communication should aim to inform about the importance and use of the data (to the general public and policy makers), as well as provide feedback and maintain the motivation and interest of volunteer recorders.  It should also be designed to function as a recruitment tool to develop the capacity of the observer networks.

Specific reports may also be produced where relevant, for example on results of the International Swan Census.  Reports produced under the contract should be made publically accessible.

  - Collaboration

The contractor should maintain good links with organisations to enable collation of data collected by other groups.  This may include sub-contracting of surveys, for example to the Greenland White-fronted Goose Study Group, and Irish Brent Goose Research Group.

The tenderer should provide costed proposals for other activity that they think is important to improve collaboration in the context of monitoring geese and swans and to deliver the objectives of this project.

## Potential follow-on work

The project would be scheduled to end in March 2022; however, it may be subject to a limited extension if appropriate and agreed by Partners towards the end of the contract's term.

## Outputs

The main outputs will include:

- reports of survey results as detailed under section 5.3, for example webpages, and summary report(s).

- a motivated network of volunteer recorders skilled in goose and swan recording.

## Timescale

Provisional dates for delivery of the contact outputs are set out below.  Exact dates will be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | April 2017 |
| Publishing annual species accounts and reports | August each year of contract |

All work should be completed by 31st March 2022.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC.  The risk assessment must be agreed with JNCC before work commences.

Any incidents occurring within the contract should be immediately reported to the JNCC Nominated Officer.

## Data access, security, usage and ownership

JNCC’s policy is that where public money is invested in a surveillance scheme the resulting data will be made freely available for all legal purposes under an Open Government Licence, except where the data comprises sensitive information or where its release would harm the environment.  This includes all raw data at the resolution it is recorded at, and all derived products.  Data should be made available within one year of its production.  The tender should include a description of any data or products that these arrangements might not apply to, with a detailed justification showing how progress will be made towards full open data.  The tenderer should ensure any required permissions from volunteers are obtained as they collect and submit data, rather than having to retrospectively request permission for data to be open access.

Tenderers should describe the approach that they will take to data management and storage. The successful tenderer will be required to:

- Develop and implement a data access policy for data collected and any derived products, including any resource created under the contract that can be organised as a reusable data set.  The data access policy must allow free access and application of the datasets. The contractor will agree the data access policy with the Project Steering Group and operate the policy.

- Develop and implement a data security policy for any data held for the purposes of the contract.  The policy will prevent accidental or deliberate loss/alteration of the data, or disclosure outside the agreed data policies.  It will cover physical protection, IT network access, knowledge transfer between data management staff, database access, backup strategies, anti-virus policy and contingency. The contractor will agree the data access policy with the Project Steering Group and operate the policy.

- Ensure that confidential data is dealt with in accordance with the Data Protection Act.

- Provide draft and final documents to the JNCC for all peer-reviewed publications authored or co-authored by the contractor that use GSMP data, and notify the JNCC in advance of such articles going to press.  Ensure publications include appropriate acknowledgement to relevant funding organisations, and where the JNCC staff have contributed to the intellectual development of published articles, or have provided significant input into the drafting of publications, an offer of co-authorship should be provided.

Please note that all intellectual property rights in any information or material existing prior to the date of the contract shall remain the property of the Partner introducing such information.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

The Nominated Officer for JNCC will be:

Email: Anna.Robinson@jncc.gov.uk

Tel: +44 (0)1733 866851

An additional contact point for JNCC will be:

Email:  David.Stroud@jncc.gov.uk

Tel: +44 (0)1733 866810

The programme will be supported by a Steering Group, consisting of the contractor, JNCC, Scottish Natural Heritage (SNH) (and potentially other country agencies). The contractor will be responsible for organising and taking minutes of these meetings, which will occur once or twice a year throughout the contract at times that are most helpful to the progression of the annual workplan.

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract, through delivering the detailed tasks identified. This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time/cost required to achieve each task, and the different components within each task;

Details of Quality Control procedures to be followed including any internal Quality Management System to be used. (See JNCC’s Evidence Quality Assurance Policy, Evidence Quality Guidance Note #1 (Bias, Conflicting Evidence and uncertainty) and Evidence Quality Guidance Note #3 (Quality Assurance of Expert Knowledge and Opinion).

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough in April 2017.

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks and components of tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 13.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard is essential, and co-investment from the tenderer would be looked on favourably.

A tender will not be accepted if it scores below 50% overall in any of the three categories set out below (1. Quality of Proposal, 2. Details of Contractor, and 3. Cost).

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (40% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and understanding of goose and swan surveys, including making best use of existing survey effort) | 13 |  |
|  | Soundness and logicality of methods | 9 |  |
|  | Probability of success | 8 |  |
|  | Sub Totals | 40 |  |
| 2. Details of Contractor (20% of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 10 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (40% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required (including appropriateness of ratio of senior to junior staff time). | 10 |  |
|  | Ability of tenderer to invest their own resources into the Goose and Swan Monitoring Programme | 20 |  |
|  | Sub Totals | 40 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives and tasks, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

The Contractor must follow JNCC’s Evidence Quality Assurance Policy which is available at http://jncc.defra.gov.uk/default.aspx?page=6675.

# Annex 1

Summary of current sampling for geese and swan populations

Bewick’s Swan Cygnus columbianus bewickii

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | January | Every 5 years | Good | GSMP/Swan Specialist Group (SSG)/I-WeBS |
| UK trend | UK | Oct-Mar | Annual | Good | WeBS |
| Key sites | UK | Oct-Mar | Annual | Adequate | GSMP (International Swan Census - ISC)/WeBS |
| ABS | UK | Nov-Feb, focus on Jan | Annual | Good at WWT Centres | GSMP |
| Survival | Flyway | Ongoing | Annual | Poor | WWT and partners |

Whooper Swan Cygnus cygnus

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | January | Every 5 years | Good | GSMP/SSG/I-WeBS/IWSSG |
| UK trend | UK | Oct-Mar | Annual | Good | WeBS |
| Key sites | UK | Oct-Mar | Annual | Adequate | GSMP (ISC)/WeBS |
| ABS | UK | Nov-Feb, focus on Dec | Annual | Good at WWT Centres | GSMP/IWSSG |
| Survival | Flyway | Ongoing | Annual | Reasonable | WWT and partners |

Taiga Bean Goose Anser fabalis fabalis

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | UK | Oct-Mar | Monthly | Good | WeBS/Bean Goose Action Group (BGAG) /RSPB |
| UK trend | UK | Oct-Mar | Monthly | Good | WeBS/BGAG |
| Key sites | UK | Oct-Mar | At least monthly | Complete | WeBS/BGAG/RSPB |
| ABS | Slamannan Plateau | Autumn | Annual | Adequate | BGAG/WWT |
| Survival | Slamannan Plateau | - | - | Some birds marked in recent years which may be sufficient for basic survival estimates | WWT |

Tundra Bean Goose Anser fabalis rossicus

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | UK | Oct-Mar | Monthly | Low numbers involved | WeBS |
| UK trend | UK | Oct-Mar | Monthly | Low numbers involved | WeBS |
| Key sites | UK | Oct-Mar | Monthly | Low numbers involved | WeBS |
| ABS | UK | None | None | None | n/a |
| Survival | UK | None | None | None | n/a |

Pink-footed Goose Anser brachyrhynchus

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway (UK) | Oct/Nov | Annual | Good | GSMP (International Goose Census - IGC) |
| UK trend | UK | Oct/Nov | Annual | Good | GSMP (IGC) |
| Key sites | Various key roosts | Sep-Apr | Varies from monthly to 1-2 extra counts per winter | Good at some sites, but generally poor | GSMP / WeBS |
| ABS | Flyway (UK) | Sep-Nov | Annual | Good - c.5% of total population | GSMP |
| Survival | Flyway | n/a | No sustained marking programme exists but ad hoc. catches are made | None | WWT / Icelandic Institute of Natural History (IINH) |

European White-fronted Goose Anser albifrons albifrons

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | UK | Oct-Mar | Monthly | Good | WeBS |
| UK trend | UK | Oct-Mar | Monthly | Good | WeBS |
| Key sites | UK | Oct-Mar | Monthly | Good | WeBS |
| ABS | UK | Nov-Feb, focusing on Jan | Annual | Small, due to low numbers wintering in the UK | GSMP |
| Survival | Flyway | - | - | No marking in UK, but good sample from elsewhere in range | Helmut Kruckenberg and co-workers |

Greenland White-fronted Goose Anser albifrons flavirostris

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | Autumn and spring | Annual | Complete | Greenland White-fronted Goose Study (GWGS) (through contract under GSMP) with information also provided by Irish National Parks and Wildlife Service (NPWS) and SNH. |
| UK trend | UK | Autumn and spring | Annual | Complete | GWGS |
| Key sites | UK | Oct-Apr | Annual | Poor; some significant gaps for SPAs on Islay exist | GWGS/SNH and, in some cases, WWT |
| ABS | Flyway | Autumn | Annual | Good | GWGS/SNH (through SNH contract to Malcolm Ogilvie) |
| Survival | Flyway | - | - | Good | GWGS |

Iceland Greylag Goose Anser anser

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | Nov/Dec | Annual | Coverage good in UK (though not thoroughly assessed), limited in Iceland, needs elsewhere unknown; quality of counts compromised by presence of British Greylag Geese | GSMP (IGC) |
| UK trend | UK | Nov/Dec | Annual | Coverage good, but quality of trend compromised by presence of British Greylag Geese | GSMP (IGC) |
| Key sites | Various key roosts | Oct-Apr | Varies from monthly to 1-2 extra counts per winter | Adequate, but few counts outwith main IGC counts | Mostly local goose groups or reserve wardens |
| ABS | UK | Oct/ Nov | Annual | Low due to limited distribution in Britain and presence of British Greylag Geese | GSMP |
| Survival | Flyway | n/a |  | Some marking ongoing in Orkney, but sample sizes low since 2000 | Coordination by WWT/SNH; various ringing groups marking birds |

British Greylag Goose Anser anser

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | August and Oct-Mar | Annual winter counts, less frequent summer surveys | Incomplete and uncoordinated | WeBS and specific GSMP surveys in Scotland |
| UK trend | Flyway | Oct-Mar | Annual | c. 28% of population counted by WeBS; coverage reasonable in England, but poor in Scotland | WeBS |
| Key sites | Uists, Tiree/Coll, Orkney | Various, from monthly counts to estimates of breeding population | Annual | Complete | RSPB and SNH |
|  | Rest of Britain | Oct-Mar | Monthly | Poor; c.28% of population counted for WeBS | WeBS |
| ABS | Uists, Tiree/Coll, Orkney | August | Annual | Good but initiated recently | RSPB and SNH |
|  | Rest of Britain | None | None | n/a | n/a |
| Survival | Flyway | n/a |  | Patchy. Some good projects but most regions not covered | Various |

Greenland Barnacle Goose Branta leucopsis

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | Spring | Every 5 years | Complete | GSMP (UK), Irish NPWS (RoI) |
| UK trend | UK | Oct-Mar | Annual | Good | SNH/RSPB (collated by GSMP) |
| Key sites | Islay, Tiree and South Walls | Oct-Apr | Fortnightly | Complete | SNH Goose Project Officer, RSPB |
|  | Other sites | Oct-Apr | Irregular | Incomplete | Various volunteers, site staff, RSPB, SNH staff etc. |
| ABS | Islay, Tiree | Autumn | Annual | Good on Islay (c.25-40% of population) and initiated in 2004 on Tiree | Malcolm Ogilvie (Islay) and other local contacts as above |
|  | Other sites | n/a | n/a | None | n/a |
| Survival | Islay | Based on winter catching | Most winters | Catches on Islay (usually up to 100 birds each catch) and new SNH initiative (from 2016) will see ringing extended to five other key wintering areas | Steve Percival (privately) WWT |

Svalbard Barnacle Goose Branta leucopsis

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | Oct-Mar | Monthly | Complete | GSMP |
| UK trend | UK | Oct-Mar |  | Complete | GSMP |
| Key sites | UK | Oct-Mar | Monthly | Complete | GSMP (Solway) / WeBS (elsewhere) |
| ABS | UK | Autumn | Annual | Good | GSMP (undertaken by WWT, funded by SNH) |
| Survival | Flyway | n/a | n/a | Good | WWT and project partners |

Dark-bellied Brent Goose Branta bernicla bernicla

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | UK | Oct-Mar | Annual | Good, but coverage of feeding areas may be incomplete in a few locations | WeBS |
| UK trend | UK | Oct-Mar | Annual | Good, but coverage of feeding areas may be incomplete in a few locations | WeBS |
| Key sites | UK | Oct-Mar | Annual | Good, but coverage of feeding areas may be incomplete in a few locations | WeBS |
| ABS | UK | Oct-Mar, focusing on Oct-Nov | Annual | Good | GSMP |
| Survival | Flyway | n/a | Ongoing | Small sample from UK in most winters, mainly from Hampshire coast | Bart Ebbinge |

East Canadian High Arctic Light-bellied Brent Goose Branta bernicla hrota

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | Flyway | October | Annual | Good | IBGRG/IINH/WWT |
| UK trend | UK | Oct-Mar | Annual | Good | WeBS |
| Key sites | UK/Republic of Ireland | Oct-Mar | Monthly | Good | WeBS/I-WeBS |
| ABS | UK/Republic of Ireland | Autumn | Annual | Good | IBGRG |
| Survival | Birds ringed in Ireland, Iceland and Canada | Winter and spring catches | Annual | Approx 200 p.a.; high proportion of population currently marked | IBGRG/WWT |

East Atlantic Light-bellied Brent Goose Branta bernicla hrota

|  | Where | When | Frequency | Coverage/ Sample size | By whom? |
| --- | --- | --- | --- | --- | --- |
| Abundance | UK | Oct-Mar | Annual | Complete | WeBS |
| UK trend | UK | Oct-Mar | Annual | Good | WeBS |
| Key sites | UK | Oct-Mar | Annual | Complete | WeBS |
| ABS | UK | Oct-Mar | Annual | Complete (although limited date in recent years) | NE Site Manager (Lindisfarne) |
| Survival | Denmark | Spring catches | Near Annual | A modest proportion of the population is marked | Preben Clausen |

Summary of recommendations for GSMP 2017/18 – 2019/20

This document lists the recommendations given in the 2016 strategic review of the WWT/JNCC/SNH Goose & Swan Monitoring Programme. Note, this is given for information and does not form part of the specification for this project.

| Recommendations for 2017/18 to 2019/20 | Priority |
| --- | --- |
| Data management |  |
| Complete next phases of online data capture and reporting tools for active GSMP surveys and associated aspects such as mapping tools and other counter resources | High |
| Appraise all relevant data flows and management protocols to ensure all stakeholders are clear on how data reach GSMP and other relevant organisations (particularly Wetlands International) | High |
| Methods |  |
| Undertake assessment of the needs for feeding distribution data, and the ways in which this could be collected and resourced, and make recommendations | High/Medium |
| Appraise the statistical analyses undertaken by GSMP in order to ensure they remain fit-for-purpose | Medium |
| Continue to liaise with BTO to assess and document the scientific basis for national population estimates, including any associated assumptions | Medium |
| Reporting |  |
| Maintain production of annual newsletter, GooseNews, and bespoke reports for IGC and GWGS | High |
| Maintain GSMP website as main reporting mechanism for GSMP results | High |
| Undertake an online assessment of GSMP reporting and communication to provide contemporary information on the communication needs of counters/stakeholders | Medium |
| Complete electronic archiving of GSMP reports, papers and other outputs | Medium |
| Communication |  |
| Maintain existing communication with GSMP network | High |
| Organise a second GSMP counters’ conference, or hold smaller regional events, and review the needs for such events | High/Medium |
| Collaboration |  |
| Promote and help facilitate a flyway meeting, ideally in Iceland, to discuss and establish closer collaborative working across the Iceland-Britain-Ireland flyway | High |
| Initiate liaison meetings with collaborators in Ireland | Medium |
| Bewick’s Swan |  |
| Undertake a UK survey for the ISC in January 2020, and utilise all relevant data sources (e.g. BirdTrack) to determine the geographical scope of the survey | High |
| Encourage and support where possible prompt reporting of flyway-wide results. Relates to Action 6.1 in Nagy et al. (2012) | High |
| Enhance coverage of roost counts at the Ouse Washes | High |
| Maintain standardised monitoring of feeding distribution at Ouse Washes | Medium |
| Develop feeding distribution monitoring at all SPAs | Medium |
| Enhance collection of ABS data away from WWT centres | Medium |
| Whooper Swan |  |
| Coordinate the international survey for the ISC in January 2020, including utilisation of all relevant data sources (e.g. BirdTrack) to determine the geographical scope of the survey | High |
| Assess the need for random sampling in Scotland as part of the next ISC | Medium |
| Before the next ISC in January 2020, assess the status of North-west European Whooper Swan in the UK, in conjunction with the SSG | Medium |
| Maintain standardised monitoring of feeding distribution at Ouse Washes | Medium |
| Develop feeding distribution monitoring at all SPAs | Medium |
| Enhance collection of ABS data in Scotland and Iceland | Medium |
| Taiga Bean Goose |  |
| Ensure all count data are collated and reported annually | High |
| Maintain support, and conduct when necessary, for the collection of ABS data at Slamannan | High |
| Pink-footed Goose |  |
| Maintain annual IGC and enhance coverage in Iceland where possible | High |
| Use the results of ongoing telemetry studies to assess the completeness of IGC geographic coverage | Medium |
| Develop pilot study to assess benefit of rolling checking programme of other roosts for IGC | Medium |
| Maintain the 3-yearly cycle of spring counts, next due in spring 2018 | High |
| Design and implement programme of standardised monitoring of feeding distribution at SPAs in the UK | Medium |
| Maintain the collection of ABS data from as wide a geographic range as possible through WWT undertaken assessment or continued training of local counters | High |
| European White-fronted Goose |  |
| Maintain collection of breeding success, including brood size, data via network of counters at all key sites | High |
| Determine extent of existing feeding distribution data, and need for future monitoring | Medium |
| Clarify with SOVON how they estimate and report population scale estimate of ABS, and support coordination of this as required | Medium |
| Greenland White-fronted Goose |  |
| Maintain GWGS support to undertake the annual census and ABS estimate | High |
| In collaboration with GWGS, review the coverage of designated areas, and other key sites, to ensure their status is adequately monitored, and where necessary develop a framework for reporting on individual protected areas, particularly SPAs | Medium |
| Design and implement programme of standardised monitoring of feeding distribution at SPAs in the UK | Medium |
| Assess needs of GWGS network and whether GSMP developments can provide further support (e.g. online data submission) | Medium |
| Attend a range state flyway meeting, probably in Iceland, to discuss monitoring in the wider context of implementation of the AEWA action plan | High |
| Iceland Greylag Goose |  |
| Maintain annual IGC and enhance coverage in Iceland where possible | High |
| Use the results of ongoing telemetry studies to assess the completeness of IGC geographic coverage | Medium |
| Further support monitoring in Iceland and Ireland through contact with IINH and BirdWatch Ireland, and in particular work with Icelandic partners and government to increase support for monitoring there; promote and help facilitate a flyway meeting, probably in Iceland, to discuss monitoring needs and opportunities | High |
| Maintain the 3-yearly cycle of spring counts, next due in spring 2018 | High |
| Continue to implement recommendations from appraisal (Mitchell 2014) with respect to improved monitoring of British Greylag Geese, through liaison with WeBS, country agencies and other stakeholders | Medium |
| Design and implement programme of standardised monitoring of feeding distribution at SPAs in the UK | Medium |
| Maintain the collection of ABS data from as wide a geographic range as possible through WWT undertaken assessment or continued training of local counters | High |
| Establish ABS monitoring in Iceland during August and September in collaboration with IINH | High |
| British Greylag Goose |  |
| Maintain support for area-specific surveys of British Greylag Geese in order to provide abundance estimates to better determine the presence and abundance of wintering Icelandic Greylag Geese | High |
| Collate and map existing data on feeding distribution | Low |
| Develop the collection of ABS data from other areas of Britain through contact with the GSMP and WeBS observer networks | Low |
| Collate existing capture-reencounter data and undertake assessment of survival rates and movement patterns | Low |
| Greenland Barnacle Goose |  |
| Undertake international census in spring 2018 and then increase frequency to 3-yearly cycle (thus, spring 2021, 2024, etc) | High |
| Maintain annual counts at seven key sites in Scotland | High |
| Complete population review (JNCC/WWT Waterbird Review Series) | Medium |
| Design and implement programme of standardised monitoring of feeding distribution at SPAs in the UK | Medium |
| Maintain ABS monitoring on Islay and Tiree, and other key sites if possible | High |
| Svalbard Barnacle Goose |  |
| Maintain monthly coordinated counts on the Solway Estuary | High |
| Assess the need, costs and feasibility of aerial surveys for the continuation of effective census on the Solway | Medium |
| Assess the need for further knowledge of feeding distribution, particularly outwith existing protected areas | Medium |
| Maintain collection of ABS data on the Solway Estuary | High |
| Dark-bellied Brent Goose |  |
| Implement programme of standardised monitoring of feeding distribution at SPAs in UK | Medium |
| Maintain network for collection of ABS data | High |
| Support development of flyway scale assessment of ABS using common standards in conjunction with other key workers | Medium |
| Incorporate data from Rowell & Robinson (2004) into feeding distribution dataset | Medium |
| Canadian Light-bellied Brent Goose |  |
| Address causes of reporting difficulties so stronger formal working relationship develops between GSMP and IBGRG | High |
| Ensure mean brood size is monitored and reported | Medium |
| East Atlantic Light-bellied Brent Goose |  |
| Maintain close contact with the site manager at Lindisfarne to ensure that adequate surveillance is carried out and offer support where necessary | High |
| Maintain contact with relevant Danish researchers over flyway surveillance of this population | High |

Irish Whooper Swan Study Group

Nagy, S., Petkov, N., Rees, E., Solokha, A., Hilton, G., Beekman, J. & Nolet, B.  2012.  International Single Species Action Plan for the North West European population of the Bewick’s Swan.  AEWA, Bonn.