www.gov.uk/dfe

Invitation to Tender

(Open Procedure – PCR2015)

Tender for a National Partner for Early Years Continuing Professional Development

Tender Reference: [Number]

# Important Notice

All references in this Invitation to Tender (ITT) to the Authority include, where appropriate and unless the context otherwise requires, references to the Authority’s predecessors and successor(s).

The Information has been prepared to assist interested parties in deciding whether or not to submit a Response in relation to the procurement. It does not purport to be all-inclusive or to contain all of the information that a Tenderer may require. Tenderers are advised to submit a clarification question as soon as possible if they require any further information. Where the Information describes any contractual arrangements which are not yet in force, those arrangements are subject to change. Any reference to a contract or other document is qualified in full by reference to the entire terms of the contract or document to which reference is made.

The issue of this ITT in no way commits the Authority to award the contract to any person or party. The Authority reserves the right to terminate the competition, to award a contract without prior notice, to change the basis, the procedures and the timescales set out or referred to in this ITT, or to reject any or all Responses and to terminate discussions with any or all Tenderers at any time. Nothing in this ITT should be interpreted as a commitment by the Authority to award a Contract to a Tenderer.

The Authority does not make any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the Information.

Subject always to the provisions of the preceding paragraph, Tenderers considering entering a contractual relationship with the Authority should make their own investigations and enquiries as to the Authority's requirements beforehand. The subject matter of this ITT shall only have any contractual effect when it is incorporated into the expressed terms of an executed contract.

This ITT is subject to copyright. Neither this ITT, nor the Information, nor any other information supplied in connection with it, may, except with the prior written consent of the Authority, be published, reproduced, copied, distributed or disclosed to any person, nor used for any purpose other than consideration by each Tenderer of whether or not to submit a Response.

The Authority reserves the right at any time to issue further supplementary instructions and updates and amendments to the instructions and Information contained in this ITT.

The Authority will not be responsible for the costs or expenses of any Tenderer in relation to any matter referred to in this ITT howsoever incurred, including the evaluation of the service opportunity, the award, or any proposal for the award of the contract or negotiation of the associated contractual agreements.

Table of Contents

| Section | Contents | Action |
| --- | --- | --- |
| 1 | Response Particulars | For Information |
| 2 | Evaluation Overview | For Information |
| 3 | Specification of Requirements | For Information |
| 4 | Standard Selection Questionnaire | Complete online in Technical Envelope |

| Appendix | Contents | Action |
| --- | --- | --- |
| A | Form of Tender | Download, complete and upload to the appropriate space provided online in the Technical Envelope |
| B | Cost Matrix | Download, complete and upload to the appropriate space provided online in the Technical Envelope |
| C | Conditions of Contract | For Information |

SECTION 1: RESPONSE PARTICULARS

GLOSSARY

Unless the context otherwise requires, the following words and expressions used within this Invitation to Tender (except Appendix A) shall have the following meanings (to be interpreted in the singular or plural as the context requires):

| TERM | MEANING |
| --- | --- |
| “Authority” | means the Department for Education acting as part of the Crown. |
| “Bids” | refers to bids from tenderers to be the chosen Supplier to deliver the Programme. |
| “Charges Rebate” | means the rebate paid by the Supplier to the Authority if the Supplier fails to deliver according to the KPIs. This Charges Rebate will be made by way of a KPI credit against future Supplier Charges, or at the end of the term of the Contract. |
| “Contract” | means the contract to be entered into by the Authority and the successful Tenderer. |
| “Cost Matrix” | means the form accessed via the DfE e-Tendering Portal in which Tenderers are required to submit their pricing information as part of a Tender. |
| “CPD” | means Continuing Professional Development. |
| “CPD Champion” | means an individual working directly with children in an early years Setting, with a minimum Level 3 childcare qualification, nominated by a Local Authority to receive CPD activity from the Supplier and cascade CPD activity to a CPD Partnership. |
| “CPD Partnership” | means a group of pre-reception Settings convened by Local Authorities for the purpose of receiving CPD activity from CPD Champions under the Programme. |
| “Department” | means the Department for Education. |
| “DfE e-Tendering Portal” | means the e-Tendering system used by the Authority for conducting this procurement, which can be found at https://education.bravosolution.co.uk |
| “Early Years Practitioner” | means an individual working directly with children to deliver early education and childcare in an early years Setting. |
| “FOIA” | means the Freedom of Information Act 2000 (as amended) and any subordinate legislation made under that Act together with any guidance and/or codes of practice issued by the Information Commissioner or any Government Department in relation to that legislation. |
| “Implementation Plan” | means the plan and timetable for the delivery of the Services as set out in Schedule 4 (Implementation Plan) of the terms and conditions, as amended and updated from time to time in accordance with Schedule 5 (Change Control Procedure). |
| “Information” | means the information contained in the ITT or sent with it, and any information which has been made available to the Tenderer by the Authority, its employees, agents or advisers in connection with this procurement. |
| “ITT” | means this Invitation To Tender document and all related documents published by the Authority and made available to Tenderers. |
| “Local Authority” | means an English Local Authority that has agreed to participate, and be grant funded by the Department, to participate in the Programme. |
| Partnership | A group of early years practitioners from Settings, convened and supported by a Local Authority for the purposes of the Programme |
| “Pedagogy” | means the method and practice of teaching. |
| “Programme” | means the Early Years Professional Development Fund Programme with the overall purpose of providing training and support to pre-reception early years practitioners working with disadvantaged children aged 2-4. |
| “Regulations” | means the Public Contracts Regulations 2015. |
| “Response” | means the information submitted in response to the ITT via the online response forms on the DfE e-Tendering Portal including the Tenderer’s formal Tender. |
| “Services” | means the package of measures as described in the ITT which are required to deliver the Programme with the overall purpose of raising quality in the workforce of early years practitioners. |
| “Setting” | means a site of registered childcare provision for 2- , 3- and 4 year olds |
| “Specification of Requirements” | means the Authority’s requirements set out in Section 3 of the ITT. |
| “Supplier” | means the organisation or consortium of organisations that successfully wins the tender to deliver the Programme. |
| “Supplier Charges” | means the charges be payable to the Supplier as payment for delivery of the Services. |
| “Tender” | means the formal offer to provide the goods or services described in Section 1, paragrah 1.1 of the ITT and comprising the responses to the questions in the DfE e-Tendering Portal and the Cost Matrix. |
| “Tenderer” | means anyone responding to the ITT and, where the context requires, includes a potential tenderer. |
| “Third Party Evaluator” | means the third party evaluation partner appointed by the Department to conduct a robust analysis and review of the Programme. |
| “Timetable” | means the procurement timetable set out in Section 1 para 5.1 of the ITT. |

References to a “Section” and to an “Appendix” are references to a section and to an appendix in the ITT.

Reference to a statute or statutory provision is a reference to such statute or statutory provision as amended or re-enacted. A reference to a statute or statutory provision includes any subordinate legislation made under that statute or statutory provision, as amended or re-enacted.

GENERAL

  - The main purpose of the Early Years Professional Development Fund Programme is to support pre-reception early years practitioners to improve their practice in working with very young children between the ages of 2 and 4. This aims to improve outcomes in language, literacy and numeracy for the most disadvantaged children, with an emphasis on improving school readiness. The proposed contract period is from May 2019 to July 2021. A Third Party Evaluator will be appointed to undertake a robust assessment of the impact of the Programme.  Subject to supplier performance, Ministerial approval and funding being available, the Department may extend the Contract up to a further 24 months should the Programme prove effective.

  - This procurement is being carried out in accordance with the open procedure as set out in Public Contract Regulations 2015.  Contractors taking part in this competition are deemed to consent to the terms and requirements of this procurement.

  - The specification in Section 3 and the Terms and Conditions, together with any special requirements, will form the basis of the Contract between the successful tenderer and the Secretary of State for Education.

  - Your Response will be incorporated into the Contract as obligations that you must fulfil in performance of the services in addition to and without prejudice to your obligations pursuant to such specification, terms and conditions and special requirements.

  - The Department is using the DfE e-Tendering Portal for this procurement which means the ITT and the forms for submitting a Response are only available in electronic form. It can be accessed via your web browser https://education.bravosolution.co.uk.

  - Tenderers are required to submit their Response in accordance with the instructions set out in the DfE e-Tendering Portal and the ITT.

  - The Department requires all Tenderers to register with the Supplier Registration Service for Government. This is a Crown Commercial Service/Cabinet Office portal which contains details of over 225k suppliers, of which 4,300 are registered as delivering goods and services to the Department and its agencies. The portal provides both suppliers and buyers with a single place to create and share commercial information and if not already registered with the Supplier Registration Service, Tenderers are required to do so via the following link: https://supplierregistration.cabinetoffice.gov.uk.﷟ https://sid4gov.cabinetoffice.gov.uk/organisation/register

  - The information contained in the ITT is designed to ensure that all Responses are given equal and fair consideration. It is important that Tenderers provide all the information asked for in the format and order specified so that the Department can make an informed decision.

  - Tenderers should read the ITT carefully before submitting a Response. It sets out:

- the Timetable and process for the procurement;

- sufficient information to allow Tenderers to submit a compliant Response;

- information regarding the award criteria and evaluation criteria which will be used to assess Responses; and

- the administrative arrangements for the receipt of Responses.

  - Tenderers are responsible for ensuring that they understand the requirements for this procurement. If any information is unclear or if a Tenderer considers that insufficient information has been provided, it should raise a query via the clarification process described in Section 1, paragraphs 3.1 - 3.4.

  - Tenderers are responsible for ensuring that they have submitted a complete and accurate Response and that prices quoted are arithmetically correct for the units stated.

  - Failure to comply with the instructions set out in the ITT or the provision of false, inaccurate or misleading information, may result in the Tenderer’s exclusion from this procurement.

  - If there is any conflict between the information set out in the ITT and the information displayed in the DfE e-Tendering Portal, the information set out in the ITT shall take precedence over the information displayed in the DfE e-Tendering Portal.

  - The copyright in the ITT is vested in the Crown and may not be reproduced, copied or stored in any medium without the prior written consent of the Department. The ITT, and any document issued as a supplement to it, are and shall remain the property of the Crown and must be returned upon demand.

COMPLETION OF RESPONSE

2.1	By submitting a Response, Tenderers agree:

- to be bound by the terms of the ITT; and

- that if the Department accepts the Tender in writing, the Tenderer will execute the Contract in the form set out in Appendix A or in such amended form as may be agreed in writing by the Department promptly on being required to do so.

2.2	The Department may terminate or amend the procurement or the ITT at any time. Any such termination or amendment will be notified in writing to all Tenderers. In order to give Tenderers reasonable time in which to take an amendment into account in preparing their Responses, the Department may, at its discretion, extend the deadline for the submission of Responses and/or any other stages of the procurement.

2.3	Unless otherwise stated in the ITT or in writing by the Department, all communications from Tenderers (including Tenderers’ sub-contractors, consortium members, consultants and advisers) during the procurement must be made using the online message board attached to the ITT on the DfE e-Tendering Portal. The Department will not respond to communications made by other means and Tenderers should not rely on communications from the Department unless they are made through the DfE e-Tendering Portal. Tenderers can access this system at https://education.bravosolutions.co.uk where the details of how to register and the terms of free registration are presented.

Submission of Responses

  - Tenderers must complete all parts of the response form in the DfE e-Tendering Portal in accordance with the instructions therein.

  - Tenderers should print off the Form of Tender (Appendix A) which must be signed by an authorised signatory. The signed Form of Tender must be uploaded and submitted via the DfE e-Tendering Portal as part of a Response in accordance with the instructions in the DfE e-Tendering Portal.

  - The Response and any documents accompanying it must be in English.

  - Prices must be submitted in £ Sterling, and in accordance with the instructions in the Section 3, Specification of Requirements, Costs and Value for Money section, para. 4.2.

  - Responses will be checked for completeness and compliance with the requirements of the ITT and only compliant Responses will be evaluated.

  - Tenderers must be explicit and comprehensive in their Response as this will be the single source of information used to score and rank Responses. The Department will take into account only information which is specifically asked for in the ITT.

  - Where a length of response is stipulated, for example, a character count limit, only the information within the set limit (measured from the beginning of that response) will be evaluated.

  - Failure to provide the information required or supply documents referred to in the Response within the deadline for Responses may result in rejection of the Response.

  - Tenderers should avoid reference to general marketing or promotional information/material (except where this is specifically required by the relevant question).

  - Different persons may be responsible for evaluating different responses to questions in a Response. Therefore, Tenderers should not cross-refer to answers given elsewhere in a Response but should answer each question so that it acts as a stand-alone response. This may mean Tenderers need to repeat certain information in responses to different questions if this is required by those questions. Evaluators will not be required when evaluating a response to a question to take into account any answer/information submitted in relation another question, but may do so where there is any apparent inconsistency of which they become aware (whether through the moderation process or otherwise).

Clarifications Sought by Tenderers

  - Any request for clarification regarding the ITT should be submitted at the earliest opportunity via the online message board attached to the ITT in the DfE e-Tendering Portal and in any event no later than the deadline for clarifications set out in the Timetable. The Department shall be under no obligation to respond to queries raised after the clarification deadline.

  - The Department will respond to all reasonable clarifications as soon as possible but cannot guarantee a minimum response time. The Department will publish all clarifications and its responses to all Tenderers on the DfE e-Tendering Portal other than in exceptional circumstances. Published clarifications shall be anonymised.

  - If a Tenderer believes that a request for clarification is commercially sensitive or that publishing the same together with the Department’s response as set out above would reveal confidential information, disclosure of which would be detrimental to the Tenderer, it should clearly state this when submitting the clarification request. However, if the Department considers either that the clarification and response is not commercially sensitive, and/or all Tenderers may benefit from its disclosure, the Department will notify the Tenderer of this (via the DfE e-Tendering Portal), and the Tenderer will have an opportunity to withdraw the request for clarification. If the request for clarification is not withdrawn within 48 hours of the Department’s notification, the Department may publish the clarification request and its response to all Tenderers and the Department shall not be liable to the Tenderer for any consequences of such publication.

  - The Department may not respond to a request for clarification or publish such a request where the Department considers that the response may prejudice the Department’s commercial interests. In such circumstances, the Department will inform the Tenderer of its view.

Clarifications Sought by the Department

  - The Department reserves the right to further clarify any information or documentation, which appears to be incomplete or erroneous, or where specific documents are missing. The Department may request the Tenderers to submit, supplement, clarify or complete the relevant information or documentation within an appropriate time limit and will ensure that such requests are made in full compliance with the principles of equal treatment and transparency pursuant to regulation 56(4) of the Regulations. Tenderers should ensure all responses are explicit and complete and not rely on a potential opportunity to expand upon their written responses at a clarification stage.

  - Tenderers must give the names of two people in their organisation who can answer the Department’s clarification questions. The Department will not contact any other persons. Tenderers must notify the Department promptly of any changes.

  - All Tenderers may be invited to answer further clarification questions as part of the evaluation of their Tender. The clarification stage questions may be by correspondence (using the online message board attached to the ITT on the DfE e-Tendering Portal) and/or interview (phone, videoconference, or face-to-face). If the Department in exercise of the discretion hereby reserved decides to hold clarification meetings, all Tenderers (whose Tender has not been rejected) will be notified of the date and times for their individual meeting. The Department will notify each Tenderer in advance of the areas of its tender on which clarifications will be sought and a record of the meeting will be made in writing.  Please note that such clarification meetings will not be to provide Tenderers with an opportunity to add to and/or change their Responses. Scores may be adjusted downwards only (as appropriate) following the clarification meetings by re-applying the evaluation criteria and weighting to the clarified information.  A written record will be kept of the reasons for any such adjustment.

  - A further moderation meeting may be held after such further clarifications are received. Following the final moderation, Tenderers will be notified of the outcome in accordance with the Regulations. There will be a standstill period of at least 10 days during which the Contract will not be entered into.

Changes to Responses

  - Tenderers may modify their Responses prior to the deadline for Responses. No Responses may be modified after the deadline for Responses.

  - Tenderers may withdraw their Responses at any time by submitting a notice via the DfE e-Tendering Portal. Unless withdrawn, Tenders shall remain valid and open to acceptance by the Department for 120 days from the deadline for Responses.

Receipt of Responses

  - Responses must be uploaded onto the DfE e-Tendering Portal no later than the time and date set out in the Timetable as the deadline for Responses. The Department will not consider Responses received after the deadline. The Department may, however, at its own discretion, extend the deadline and in such circumstances the Department will notify all Tenderers of the change.

  - The Department recommends that Tenderers consider the volume of information that must be uploaded and allow enough time to process this, making reasonable allowances for any errors or problems that may occur during the process. If a Tenderer experiences problems when uploading its Response, it should contact the DfE e-Tendering Portal helpdesk for assistance (help@bravosolution.co.uk) and also inform the Department via the online message board.

Acceptance of Tenders

  - By issuing the ITT, communicating with a Tenderer or a Tenderer’s representative or agents or any other communication in respect of this procurement, the Department shall not be bound to accept any Tender or award the Contract.

Costs of Responding

  - Tenderers shall bear all their own costs and expenses incurred in the preparation and submission of their Responses, site visits and presentations and the Department will in no case be responsible or liable for those costs, regardless of the outcome of the procurement in relation to individual Responses, even if the procurement is terminated or amended by the Department.

Confidentiality of the ITT and Related Documents

  - The contents of the ITT and of any other documents or information published or provided by the Department in respect of this procurement are provided on condition that they remain the property of the Department, are kept confidential (save in so far as they are already in the public domain) and that the Tenderer shall take all necessary precautions to ensure that they remain confidential and are not disclosed, save as described below.

  - Tenderers may disclose information relating to the procurement to their advisers and sub-contractors if:

- disclosure is for the purpose of enabling a Response to be submitted and the recipient of the information undertakes in writing to keep it confidential on the same terms as the Tenderer;

- the Department gives prior consent in writing to the disclosure;

- the disclosure is made for the purpose of obtaining legal advice in relation to the procurement; or

- the Tenderer is legally required to disclose the information.

  - Tenderers shall not undertake any publicity activities in relation to the ITT without the prior written agreement of the Department, including agreement on the format and content of any publicity. For example, no statements may be made to the media regarding the nature of any Response, its contents or any proposals relating to it without the prior written consent of the Department.

  - Please note the following requirements, you must not:

- Tell anyone else what your tender price is or will be, before the time limit for delivery of tenders.

- Try to obtain any information about anyone else's tender or proposed tender before the time limit for delivery of tenders.

- Make any arrangements with another organisation about whether or not they should tender, or about their or your tender price.

Failure to comply with these conditions may disqualify your tender.

  - All Central Government Departments, their Executive Agencies and Non Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement, including ensuring value for money and related aspects of good procurement practice.

  - For these purposes, the Department may disclose within Government any of the Tenderer’s documents and information (including any that the Tenderer considers to be confidential and/or commercially sensitive) provided in its Response. The information will not for these purposes be disclosed outside Government during the procurement. Tenderers are deemed to consent to these terms as part of responding to this ITT.

Confidentiality: References and Third Party Evaluators:

  - When providing details of contracts as part of a Response, Tenderers agree to waive any contractual or other confidentiality rights and obligations associated with these contracts.

  - The Department reserves the right to contact any named customer contact given as a reference or otherwise referred to as part of a Response. Such named customer may incur liability to the Department where any statement or information would amount to a fraudulent misrepresentation or where he/she knowingly or recklessly provides information which is not true and accurate.

  - Subject to paras 4.22 - 4.26 below, the Department will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the Regulations.

  - The Department may use third parties in the course of its evaluation of Responses. The Department may disclose information contained therein to such third parties for the purposes of the Department’s evaluation of Responses in accordance with the ITT. Tenderers acknowledge that this right shall be in addition to the provisions of section 1, paras 4.15, 4.16 and 4.22 to 4.26.

  - See The Transparency of Suppliers and Government to the Public for more detail.

Freedom of Information and Environmental Information Regulations

  - In accordance with the obligations placed on public authorities by the FOIA and the EIR, which provide a public right of access to information held by public bodies, the Department may be required to disclose information submitted to it by a Tenderer.

  - If a Tenderer considers any information which it supplies to the Department to be commercially sensitive or of a confidential nature, it should complete the schedule of Commercially Sensitive Information set out in the DfE e-Tendering Portal and:

- clearly identify any information provided as confidential or commercially sensitive;

- explain the potential implications of disclosure of such information; and

- provide an estimate of the period of time during which the Tenderer believes that such information will remain confidential or commercially sensitive.

  - If a Tenderer identifies information as being confidential and/or commercially sensitive, the Department will endeavour to maintain the confidentiality of that information, and will, where practicable, consult with the Tenderer before information relating to that Tenderer is disclosed pursuant to a request for information under FOIA and/or EIR to establish whether an exemption from disclosure may apply.

  - However, even where information is identified by a Tenderer as being confidential or commercially sensitive, Tenderers acknowledge that there may be circumstances in which the Department may be required to disclose such information in accordance with the FOIA or the EIR (in addition to any other transparency obligations as set out in clause 5.19). In particular, the Department is required to form an independent judgment concerning whether the information is exempt from disclosure under the FOIA or the EIR including whether the public interest favours disclosure or not. The Department will make the decisions as to whether information should be disclosed.  Accordingly, the Department does not guarantee that any information marked “confidential” or “commercially sensitive” will not be disclosed and accepts no liability for any loss or prejudice caused by the disclosure of information.

  - If a Tenderer receives a request for information relating to this procurement under the FOIA or the EIR during the procurement, this should be immediately passed on to the Department and the Tenderer should not respond to the request without first consulting the Department.

Cyber Essentials Scheme

  - The Government has introduced its new Cyber Essentials Scheme in consultation with industry to mitigate the risk from common internet based threats.

  - Since 1st October 2014, it has been mandatory for new Central Government contracts, which feature characteristics involving the handling of personal data and ICT systems designed to store or process data at the OFFICIAL level of the Government Security Classifications scheme to comply with Cyber Essentials requirements.

  - All potential tenderers for Central Government contracts, featuring the above characteristics, should make themselves aware of Cyber Essentials and the requirements for the appropriate level of certification “or equivalent”.

  - You are required to demonstrate in your tender Response that you shall have achieved, and be able to maintain, independent certification to ISO/IEC 27001 (Information Security Management Systems Requirements). The ISO/IEC 27001 certification must have a scope relevant to the services supplied to, or on behalf of, the Department. The scope of certification and the statement of applicability must be acceptable, following review, to the Department, including the application of controls from ISO/IEC 27002 (Code of Practice for Information Security Controls. Any equivalent evidence must be verified by a technically competent and independent third party.

  - The successful tenderer will be required to provide evidence of ISO/IEC 27001 (Information Security Management Systems Requirements) certification prior to contract award.

  - The successful tenderer will be required to secure and provide evidence of ISO/IEC 27001 (Information Security Management Systems Requirements) re-certification on an annual basis.

  - Details of certification bodies are available at: https://www.cyberstreetwise.com/cyberessentials

General Data Protection Regulation (GDPR)

  - The GDPR applies from 25th May 2018, when it superseded the UK Data Protection Act 1998. This places a range of new obligations on organisations to be more accountable for data protection. Tenderers should ensure they familiarise themselves with the new legislation and refer to the Department on any matters with a potential implication. Further details are provided in the Conditions of Contract.

Intellectual Property

  - All materials and resources that are made available to anyone (including early years practitioners, schools, teachers, local authority staff) (“End Users”) via the Programme or activities under the agreements in this procurement must be freely available for use and development by End Users under the Open Government Licence. All such materials and resources must continue to be freely available for use and development by such End Users under the Open Government Licence terms indefinitely after termination or expiry of the Contract.

  - The Supplier must obtain all necessary consents and licences to enable use of materials and resources.

  - The Supplier will be required to give ongoing warranties in the Contract to confirm that the use of materials and resources by End Users under the Open Government Licence will not infringe any Intellectual Property Rights. It will indemnify the Department against any breach of this warranty and for any Third Party Intellectual Property Claim brought against the Department or any Replacement Supplier.

  - The Supplier should not use any materials or resources in the delivery of Services if it is unable to make these freely available for use on these terms.

Disclaimers

  - Whilst the information in the ITT and any supporting information referred to herein or provided to Tenderers by the Department have been prepared in good faith the Department does not warrant that this information is comprehensive or that it has been independently verified.

  - Neither the Department nor its respective advisors, directors, officers, members, partners, employees, other staff or agents:

- makes any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the ITT or of any other written or oral communication transmitted (or otherwise made available) to any Tenderer;

- accepts any liability for the information contained in the ITT or in any other written or oral communication (including any communications via the DfE e-Tendering Portal) transmitted (or otherwise made available) to any Tenderer, or for the fairness, accuracy or completeness of that information; or

- shall be liable for any loss or damage (other than in respect of fraudulent misrepresentation or any other liability which cannot lawfully be excluded) arising as a result of reliance on such information or any subsequent communication.

  - Any party considering entering into contractual relationships with the Department following receipt of the ITT should make its own investigations and independent assessment of the Department and its requirements for the goods and/or services and should seek its own professional financial and legal advice.

  - Neither the issue of the ITT nor any of the information presented in it should be regarded as a commitment or representation on the part of the Department to enter into a contractual arrangement. Nothing in the ITT or in any other communication made between the Department and any other party should be interpreted as constituting a contract, agreement or representation between the Department and any other party (save for a formal award of contract made in writing) or as constituting a contract, agreement or representation that a contract shall be offered.

Canvassing

  - Any Tenderer which directly or indirectly canvasses any officer, member, employee, or agent of the Department or its members or any other relevant body or any of its officers or members concerning the Contract or this procurement or which directly or indirectly obtains or attempts to obtain information from any such officer, member, employee or agent concerning any other Tenderer or Response will be excluded from this procurement and its Response rejected.

  - The Tenderer shall not make contact with any employee, agent or consultant of the Department which is in any way connected with this procurement during this procurement, unless instructed otherwise by the Department.

Inducements

  - Offering an inducement of any kind in relation to obtaining this or any other contract with the Department will disqualify your tender from being considered and may constitute a criminal offence.

Conflicts of Interest

  - The concept of a conflict of interest includes, but is not limited to, any situation where relevant staff members of the Department, involved in this procurement have, directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure and/or affect the integrity of the contract award.

  - Where the Tenderer is aware of any circumstances giving rise to a conflict of interest or has any indication that a conflict of interest exists or may arise you should inform the Department of this as soon as possible (whether before or after they have submitted a Response). The Tenderer shall at the same time provide a full explanation of all steps and measures it has put in place to remedy the conflict of interest and why it considers those steps and measure will ensure such conflicts are remedied. Tenderers should remain alert to the possibility of conflicts of interest arising at all stages of the procurement and should update the Department if any new circumstances or information arises, or there are any changes to information already provided to the Department. Failure to do so, and/or to properly manage any conflicts of interest may result in a Response being rejected.

  - Provided that it has been carried out in a transparent manner, routine pre-market engagement carried out by the Department should not represent a conflict of interest for the Tenderer.

Changes to a Tenderer’s Circumstances

  - The Department may:

- reject a Response if there is a subsequent change of identity, control, financial standing or other factor which may affect the Department’s evaluation of the Response;

- revisit information contained in a Response at any time to take account of subsequent changes to a Tenderer’s circumstances; or

- at any point during the procurement require a Tenderer to certify there has been no material change to information submitted in its Response and in the absence of such certificate, reject the Response.

Sub-Contracting

  - Where the Tenderer proposes to use one or more sub-contractors to deliver some or all of the contract requirements, all information requested in the Response should be given in respect of the prime contractor and a separate appendix should be used to provide details of the proposed bidding model that includes:

- members of the supply chain;

- the percentage of work being delivered by each sub-contractor; and

- the key contract deliverables each sub-contractor will be responsible for.

  - The Department recognises that arrangements in relation to sub-contracting may be subject to future change, and may not be finalised until a later date. However, Tenderers should be aware that where information provided to the Department indicates that sub-contractors are to play a significant role in delivering key contract requirements, any changes to those sub-contracting arrangements may affect the ability of the Tenderer to proceed with the procurement process or to provide the supplies and/or services required. If the proposed supply chain changes at any time after submission of its Response, the Tenderer should inform the Department immediately via the DfE e-Tendering Portal. The Department reserves the right to deselect the Tenderer prior to any award of contract, based on an assessment of the updated information.

Consortia

  - If the Tenderer completing the Response is doing so as part of a proposed consortium, the following information must be provided (in a separate Appendix to be uploaded in the appropriate space provided in the online Technical Envelope);

- names and details of all consortium members;

- the proposed governance model/ arrangements of the consortium;

- full details of the nature of the legal arrangements proposed for the consortium;

- if a separate legal entity is not being created, details of the consortium member(s) who will be operating and managing the Contract on a day to day basis;

- if a separate legal entity is being created, the name of the special purpose vehicle (SPV) and full details of the proposed ownership structure.

  - Please note that the Department may require the consortium to assume a specific legal form if awarded the Contract in accordance with regulation 19(6) of the PCR 2015 Regulations and/or may require the consortium members to accept joint and several liability in accordance with regulation 63.

  - The consortium lead will be required to provide the Information required in the Response on behalf of the consortium, as part of a single composite Response to the Department.

  - If the Tenderer proposes to create a separate legal entity the Tenderer should provide details of the actual or proposed percentage shareholding of the constituent members within the new legal entity in a separate appendix.

Pricing

  - As stated above, prices must be submitted in £ Sterling, and in accordance with the instructions in the Section 4, Specification of Requirements, Costs and Value for Money section, para. 4.2.

  - The Contract is to be awarded as a fixed price which will be paid according to the deliverables stated in the Specification of Requirements set out in Section 4 over. the proposed contract period from May 2019 to July 2021.

  - Subject to supplier performance, Ministerial approval and funding being available we may extend the Contract by up to 24 months from 2021 should the Programme prove effective.

  - The Cost Matrix sets out the minimum level of pricing information required for the Tender. The Department may request a detailed breakdown of any pricing submitted as part of a Tender.

Notification of Award and Standstill

  - The Department will notify successful and unsuccessful Tenderers in accordance with the Regulations. A ten day standstill period will take effect in accordance with regulation 87 of the Regulations before the Department enters into the Contract.

  - Following a decision to award the Contract, the Department will provide reasons for its decision in an award notification letter to all unsuccessful Tenderers.

TUPE

  - Tenderers should determine whether or not they believe the Transfer of Undertakings (Protection of Employment) Regulations 2006 (TUPE) applies to this procurement. Notwithstanding this, Tenderers will note that it is the Department’s view that TUPE is not likely to apply if this procurement results in a contract being awarded, although the Department is not liable for this opinion. The Department will wish to satisfy itself that Responses are responsibly calculated and take full account of any likely TUPE obligations.

  - If Tenderers have a contrary view to that of the Department on the applicability of TUPE they should advise the Department, giving reasons, prior to the deadline for Responses.

Tender Timescales

  - The Timetable below is provisional and may be subject to change, but will be adhered to by the Department as far as reasonably possible.

| Action: | Deadline: |
| --- | --- |
| Prior Information Notice (PIN) issued in Contracts Finder | Thursday 20 September 2018 |
| Tender documents issued | Friday 14 December 2018 |
| Deadline for submission of clarifications | Tuesday 22 January 2019 |
| Deadline for tender Responses to be received | Thursday 14 February 2019, 12 noon |
| Clarification meetings if required | Friday 8 March 2019 |
| Department announcement of preferred bidder | Friday 29 March 2019 |
| 10 day standstill period ends | Tuesday 9 April 2019 |
| Contract commencement | Friday 31 May 2019 |
| Contract ends | Friday 30 July 2021 |

Tender Validity Period

  - Due to the intensive evaluation process the Department requires tenders to remain valid for a period of 180 days.

Contract Term

  - The Contract will commence in May 2019 (the “Commencement Date”) and end in July 2021 (the “End Date”) unless it is terminated early in accordance with the Contract. Subject to supplier performance, Ministerial approval and funding being available the Department may exercise an option to extend the Contract by up to 24 months as specified in the Terms and Conditions. The Contract extension may involve the Supplier supporting a different set of CPD Champions and Local Authorities. Any contract extension is subject to an enhanced KPI regime.

# Exit Arrangements and Risk Management

  - The Supplier must effectively manage exit arrangements. These should cover: a transfer to a new supplier in the case of a change of supplier (covering staffing); the safe transfer of any data owned by the Department; timescales for any transfer; licensing requirements for software; and documentation covering any bespoke software that has been developed.

  - The exit agreement is not required as part of the Tender. A detailed exit agreement will be agreed between each Supplier and the Department within 6 months of the Contract being signed.

  - The above service should be delivered on time and within budget in accordance with agreed timescales. The supplier should manage the project’s exposure to risk, taking appropriate and cost-effective action to minimise the effects of such risks. This should be recorded in a risk register, with proposed mitigations, and should be shared with the Department in monthly reports.

Data Handling and Security

  - As the Supplier will receive data regarding early years practitioners and Settings throughout the course of this Contract, they must adhere to data security standards (i.e. how and where they will store this data, how they will plan to dispose of it once the Contract has expired) as outlined in the attached Terms and Conditions.

  - See the Terms and Conditions for full details of the data handling requirements (‘Cyber Essentials and data security’).

Contract Management

  - The Department’s contract manager will convene monthly meetings with the Supplier, at which management information will be discussed, and quarterly meetings at which progress against key performance indicators will be monitored.

  - Detailed requirements for management information will be agreed during contract negotiations and the early set-up period, but are likely to include progress against key performance indicators, for quantity and quality of training and support provided and any actions taken following the quality assurance review as described in paragraph 3.21 in Section 3 - Specification.

  - The Department’s contract manager and Supplier’s contract manager shall maintain regular contact via phone and email between meetings to ensure that day-to-day issues and ad hoc requests are addressed as necessary.

  - The Department will convene a quarterly Programme Board meeting, including membership from the Supplier, to oversee the strategic direction of the Programme, and ensure its overall direction remains on track, and continues to be coherent with wider related departmental priorities on social mobility. The Supplier will be expected to present a progress report at each meeting for the Department’s consideration. Any external evaluator will also be a member of the board.

Independent evaluation

  - The Supplier must ensure that mechanisms, including management information and data sharing, exist to liaise with any external evaluator appointed by the Department from the start of the Contract, and to engage in analysis and formative evaluation to ensure that lessons learned are incorporated into the ongoing delivery as part of an ongoing quality improvement cycle.  The Supplier will be required to co-operate (including but not limited to sharing relevant management information) with any independent evaluator contracted by the Department.

Child Sex Abuse

  - The Internet Watch Foundation (IWF) was established in 1996 by the UK internet industry to provide the UK internet Hotline for public and IT professionals to report potentially illegal online content and to be the “notice and take-down” body for this content. IWF works in partnership with the online industry, law enforcement, Government, the education sector, charities, international partners and the public to minimise the availability of this content, specifically, child sexual abuse content hosted anywhere in the world.

  - Access to the IWF URL list is available to ISPs, mobile operators, search providers and filtering companies only. All organisations that require access must sign a licence which sets out how the data can be used.

  - It is a contract condition that the successful contractor must block access to those Uniform Resource Locators (URLs) specified on the IWF’s list.

Government Policy in Relation to Transparency

  - Tenderers should be aware that the Government has set out the need for greater transparency in public sector procurement and that if they are awarded a Contract, the tender documents and Contract will be published on the Contracts Finder website:

www.gov.uk/contracts-finder. In some circumstances, limited redactions may be made to some contracts before they are published. The Department will make the decisions as to whether information should be disclosed. See ‘The Transparency of Suppliers and Government to the Public’ for more detail.

Armed Forces Covenant

  - The Armed Forces Covenant is a public sector pledge from Government, businesses, charities and organisations to demonstrate their support for the armed forces community. The Covenant was brought in under the Armed Forces Act 2011 to recognise that the whole nation has a moral obligation to redress the disadvantages the armed forces community face in comparison to other citizens, and recognise sacrifices made.

  - The Covenant’s two principles are that:

- the armed forces community should not face disadvantages when compared to other citizens in the provision of public and commercial services; and

- special consideration is appropriate in some cases, especially for those who have given most such as the injured and the bereaved.

  - The Department encourages all Tenderers, and their suppliers, to sign the Corporate Covenant, declaring their support for the Armed Forces community by displaying the values and behaviours set out therein.

  - Guidance on the various ways you can demonstrate your support through the Armed Forces Corporate Covenant is provided at The Corporate Covenant.

  - If you wish to register your support you can provide a point of contact for your company on this issue to the Armed Forces Covenant Team at the address below, so that the MOD can alert you to any events or initiatives in which you may wish to participate. The Covenant Team can also provide any information you require in addition to that included on the website.

Email address: covenant-mailbox@mod.uk

Address: Armed Forces Covenant Team

Zone D, 6th Floor, Ministry of Defence,

Main Building, Whitehall, London, SW1A 2HB

  - Paragraphs 5.20 – 5.24 above are not a condition of working with the Department now or in the future, nor will this issue form any part of the tender evaluation, contract award procedure or any resulting contract. However, the Department very much hopes you will want to provide your support.

Disability Confident Scheme

  - The Department for Education is a Disability Confident leader. Through the Disability Confident campaign, the government is working with employers to remove barriers, increase understanding and ensure that disabled people have the opportunities to fulfil their potential and realise their aspirations.

  - The Department encourage other employers to sign up to the disability confident scheme. It is open to all employers and there are three levels ranging from ‘Committed’ to ‘Leader’ with employers having to meet certain criteria to reach each level.

  - Employers who sign up to the disability confident scheme ensure that they can:

- draw from the widest possible pool of talent;

- secure and retain high quality staff who are skilled, loyal and hard working;

- save time and money on the costs of recruitment and training by reducing staff turnover;

- keep valuable skills and experience;

- reduce the levels and costs of sickness absences; improve employee morale and commitment by demonstrating that they treat all employees fairly.

  - Disability confident employers can use the disability confident branding in their communications and when advertising jobs.

  - Find out more about the aims of disability confident, why becoming a disability confident employer will be good for your business and how you will be supported through your journey to being a Disability Confident leader here.

Prompt Payment Policy

  - Government’s aim is to pay 80% of all correctly submitted invoices within 5 days of receipt and we are 100% committed to paying correctly submitted invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.

  - The payment period will be deemed to have started when a correctly submitted invoice reaches the nominated address. Contractors can assume receipt to be two days after mailing (by first class post). The thirty day “clock” therefore commences two days after mailing first class.

  - A correct invoice is one that is:

- delivered in accordance with the Contract including without limitation being submitted in accordance with the timing stipulated for invoice submissions delivered in timing in accordance with the Contract for the correct sum;

- In respect of goods / services supplied or delivered to the required quality (or are expected to be at the required quality);

- include the date, supplier name, contact details and bank details;

- which quote the relevant purchase order / contract reference;

- which has been delivered to the nominated address.

  - Any correctly submitted invoices that are not paid within 30 days will be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.

SECTION 2: EVALUATION OVERVIEW

The tender process will be conducted in a manner that ensures tenders are evaluated fairly to ascertain the most economically advantageous tender.  Evaluation of Responses will comprise the stages set out in the table below. Information on the specific evaluation criteria for each specific section of a Response are detailed below, against each relevant question as set out on the e-tendering Portal.

| Stage | Section Reference | Evaluation Criteria | Assessment |
| --- | --- | --- | --- |
| Stage 1 | Form of Tender | This stage is not scored but if you do not upload a complete, signed and dated Form of Tender in accordance with the instructions in the e-tendering Portal, your Response will be rejected as non-compliant. | Not Scored |
| Stage 2 | Standard Selection Questionnaire | This stage is designed to select those Tenderers who are suitable to deliver the Department’s requirements and will be evaluated in accordance with the Standard Selection Questionnaire. For the avoidance of doubt, where a Tenderer’s answer to any question is assessed as a ‘Pass’, the Response will proceed in the evaluation process but where a Tenderer’s answer to any question is assessed as a ‘Fail’, the Response will be rejected and will not proceed further in the evaluation process and the Tenderer will be excluded from this procurement process. | See below |
| Stage 2 | Standard Selection Questionnaire | Section 1 Potential Supplier Information | Section 1: For information only and not scored |
| Stage 2 | Standard Selection Questionnaire | Sections 2 and 3 Exclusion Grounds The responses to Section 2 ‘Grounds for Mandatory Exclusion’ will be assessed on a Pass/Fail basis where a Pass = either: - a ‘No’ answer to questions 2.1(a) and 2.3(a); - a ‘Yes’ answer to any part of questions 2.1(a) and/or 2.3(a) but in accordance with questions 2.1(b) and/or 2.3(b) (as the case may be), the relevant organisation has submitted evidence of “self-cleaning” (within the meaning of regulation 57) which the Department considers (in its absolute discretion) is sufficient to demonstrate the relevant organisation’s reliability despite the existence of a relevant ground for exclusion; or - a ‘Yes’ answer to any part of questions 2.1(a) and/or 2.3(a) but the Department either disregards the prohibition, on an exceptional basis, for overriding reasons relating to the public interest such as public health or protection of the environment or, in the case of question 2.3(a), in its absolute discretion, disregards the prohibition on the basis that it considers an exclusion would be disproportionate. The responses to section 2 ‘Grounds for Discretionary Exclusion’ will be assessed on a Pass/Fail basis where a Pass = either - a ‘No’ answer to all of the questions or - there is a ‘Yes’ answer to one or more of the questions and the relevant organisation has submitted evidence of “self-cleaning” (within the meaning of regulation 57) which the Department considers (in its absolute discretion) is sufficient to demonstrate the relevant organisation’s reliability despite the existence of a relevant ground for exclusion or in any event the Department exercises its discretion not to exclude the organisation. | Sections 2 and 3: Pass/Fail |
| Stage 2 | Standard Selection Questionnaire | Section 4 Economic and Financial Standing The Department will consult Supplier Registration reports in assessing Tenderers’ Economic and Financial Standing and Question 9.6 of the Standard Selection Questionnaire requires Tenderers to confirm that they have registered with Supplier Registration Service accordingly. Paragraphs 1.2 to 1.6 of this Evaluation Overview provide further details of the assessments to be undertaken and the criteria for awarding a Pass or Fail. | Section 4: Pass/Fail |
| Stage 2 | Standard Selection Questionnaire | Section 5 Group Details Pass: You have provided the information requested or have responded with N/A as appropriate. If N/A is inserted you have explained why this is the case. Fail: The Department has the discretion to disqualify you if you do not or cannot provide the information requested or have not responded with N/A as appropriate or have not explained why N/A has been used. | Section 5: Pass/Fail |
| Stage 2 | Standard Selection Questionnaire | Section 6 Questions 6.1 (or 6.3 if requested examples at 6.1 cannot be provided), 6.2 and 6.4 are all scored. Tenderers will fail the selection stage if a score of “3” or above is not achieved for the response provided to these (Technical and Professional Ability) questions. The score descriptors to be applied are those at paragraph 1.7 of this section (Section 2 Evaluation Overview). | Section 6: Scored |
| Stage 2 | Standard Selection Questionnaire | Section 7 Modern Slavery Either the relevant organisation answers N/A to Question 7.1 or answers Yes to Question 7.1 and then either answers Yes to Question 7.2 and a URL link is provided or answers No to Question 7.2 but the Department is (in its absolute discretion) satisfied with the explanation provided (for which the principles of “self-cleaning” in regulation 57(13)-(17) will be considered) or (in its absolute discretion) disregards the prohibition, on an exceptional basis, for overriding reasons relating to the public interest such as public health or protection of the environment. | Section 7: Pass/Fail |
| Stage 2 | Standard Selection Questionnaire | Section 8 Additional Questions Tenderers should self-certify that they meet the requirements to these questions; 8.1 to 9.6. Where indicated, a “response of “No” will result in exclusion from further participation in the procurement process. Tenderers will be required to provide evidence of meeting requirements, including any certification or equivalent, if they are successful at award stage 5. | Section 8: Pass/Fail |
| Stage 3 | Tender Quality Evaluation | This stage consists of an evaluation of Tenders in accordance with the criteria set out for each question below and in the Response form in the e-tendering Portal. | Scored |
| Stage 4 | Pricing/Cost Matrix Evaluation | Prices set out in the Cost Matrix in the e-tendering Portal will be evaluated in accordance with criteria below. | Scored |
| Stage 5 | Award | A Response which passes stage 1 and 2 will proceed to evaluation of Tenders in accordance with stages 3 to 4: The final score is calculated as follows: 80% is made up of the total of Stage 3 (Quality) 20% is made up from Stage 4 (Pricing) The most economically advantageous tender will be the Response which has the highest final score. | Scored |

# STAGE 2 - SELECTION STAGE

  - The selection stage has been designed to assess the suitability of a Tenderer to deliver the Department’s contract requirement(s). Tenderers who are unsuccessful at this stage of the procurement process will not have the remaining sections of their Response evaluated pursuant to the award stage of the process outlined in Stage 3.

  - The Department will consult the Supplier Registration Service reports and other credit rating or equivalent reports depending on where a Tenderer is located. The evaluation for this section will require all Tenderers to register with the Supplier Registration Service https://supplierregistration.cabinetoffice.gov.uk. Tenderers should ensure in their response to the SSQ (Question 9.6) that they have registered with the Supplier Registration Service.

  - The Department’s assessment of economic and financial standing will consider risk of business failure (as outlined in paragraph 1.4 below) and financial strength (as outlined in paragraph 1.5 and 1.6 below). A Tenderer will pass if all risk ratings are green. A Tenderer will fail if any risk ratings are red. If a Tenderer has an amber rating DfE shall determine (at its sole discretion) whether any additional assurance can be provided from the relevant Tenderer, for example a parent company guarantee, before a decision is taken. Unless additional assurance is provided, the bid will be rejected and removed from the procurement.

  - Risk of Business Failure is rated on a scale of 1 (minimal) to 4 (significant) obtained from the Supplier Registration Service. There is also a classification of insufficient information. The Department regards a score of 4 as indicating inadequate economic and financial standing for this procurement.

  - The Department will also use the Supplier Registration Service reports and other credit rating or equivalent reports to assess a Tenderer’s financial strength. The following will be calculated and evaluated for each Tenderer :

    - operating performance: growth or reductions in sales, gross profit, operating profit, profit before tax and earnings before interest, tax, depreciation, amortisation, exceptional items and profit/loss on sale of businesses;

    - liquidity: net current assets, movements in cash flow from operations, working capital and quick ratios, and average collection and payments periods; and

    - financial structure: gearing ratios and interest cover.

  - The Department will seek to ensure that suppliers possess the necessary economic and financial capacity to perform the Contract and suppliers should self-certify whether the average annual contract value (£1.7m) proposed exceeds 50% of their annual turnover (Question 4.2 of Standard Selection Questionnaire). This threshold reflects a general indication of financial stability used in the assessment of financial strength.  In the case of a consortium, the consortium lead must clearly explain in its Response which entity or entities it is relying upon to pass the minimum average annual turnover (and for the avoidance of doubt the same applies for any other resources on which it is relying). The Department may require information and/or evidence to satisfy the Department that such resources are sufficiently committed to the consortium for such purpose.

### Technical and Professional Ability Requirement (pass/fail)

  - Responses will be rejected as having failed this requirement where:

    - a Tenderer fails to achieve a score of “3” or above for the response provided to questions 6.1 or 6.3, 6.2 and 6.4. The method of scoring will be a 4 point scale as follows:

| Mark | Score | Descriptor |
| --- | --- | --- |
| Good | 4 marks | The answer includes the information and supporting evidence specifically requested by the question and demonstrates that the Tenderer possesses the relevant ability, understanding, skills, resource and quality measures required to meet the Department’s requirements in full. |
| Minor Omissions | 3 marks | The answer includes the information and supporting evidence specifically requested by the question and demonstrates that the Tenderer possesses the relevant ability, understanding, skills, resource and quality measures required to meet most of the Department’s requirements but with some minor omissions. |
| Major Omissions | 2 marks | The answer includes all or some of the information and supporting evidence specifically requested by the question and demonstrates that the Tenderer possesses the relevant ability, understanding, skills, resource and quality measures required to meet some of the Department’s requirements, but with some major omissions. |
| Unacceptable | 1 marks | The answer does not provide any information and/or supporting evidence specifically requested by the question and/or fails to demonstrate that the Tenderer possesses the relevant ability, understanding, skills, resource and quality measures required to meet the Department’s requirements. |
| No Answer Provided | 0 marks | No answer provided. |

In considering whether the Department’s requirements have been met, the Department will take into account the requirements as set out in the questions in 6.1 (or 6.3), 6.2 and 6.4 respectively.

STAGE 3 - TENDER QUALITY EVALUATION STAGE

| SCORE | DESCRIPTOR |
| --- | --- |
| 4 | The response fully and successfully meets the requirement and the Tenderer has demonstrated a consistent and coherent approach to show how their solution will meet and comply with all the requirements covered by the evaluation question. The solution as described has a high probability of successful delivery. And: full and relevant evidence is provided to support the response and explain how the Tenderer will satisfy the requirement criteria in full. |
| 3 | The response sufficiently meets the requirement and the Tenderer has demonstrated a consistent and coherent approach to how their solution will meet and comply with almost all of the requirements covered by the evaluation question. The solution as described has a high probability of successful delivery. Any omission from the solution would not compromise the operational integrity of the service to be provided. And: relevant and sufficient evidence is provided to support the response. The response and/or evidence may lack some clarity or minor detail in how the proposed solution will be achieved or how it will assure the requirement is met. Lack of clarity and any missing evidence or detail is only minor. |
| 2 | There may be some elements of the response which meet the requirement, but the response as a whole does not sufficiently meet and comply with the requirements covered by the evaluation question. The Tenderer has demonstrated a partially consistent and/or partially coherent approach to how their solution will meet and comply with the requirements covered by the evaluation question but is unlikely to lead to successful delivery. The solution contains omissions that would compromise the operational integrity of part or all of the service to be provided. And/or: the response has one or more omissions with regard to meeting or complying with the requirements covered by the evaluation question which are more than minor; and/or: some evidence is provided to support the response, but this is lacking in sufficient detail in one or more areas and such omission or deficit in the evidence is more than minor. |
| 1 | The response fails to meet the requirement. The Tenderer has not provided a consistent and/or coherent approach to how their solution will meet and comply with the requirements covered by the evaluation question and is unlikely to lead to successful delivery. Responses will in parts be vague or unclear with little or no detail given on how the specified solutions will be delivered. The solution contains omissions that would compromise the operational integrity of the service to be provided. And/or: the response has significant omissions with regard to meeting or complying with the requirements covered by the evaluation question, and/or: no supporting evidence has been provided to support the response or such evidence has major omissions or deficiencies. |
| 0 | No response provided. |

## IMPORTANT NOTE

## All references in the above table to meeting the “requirements” shall mean that in respect of each question, the answer must:

    - address any specific requirements contained in the question to which the Tenderer is responding (including requirements identifying any information to be supplied) and explain how those requirements will be met;

    - ensure the information and explanations which it contains satisfies the requirements in the paragraphs numbered 1, 2 and 3 below;

    - explain the way in which the approach, methodology and other proposals contained in the answer will ensure achievement of the specification of the services set out in Section 3 of this ITT (the Specification);

    - explain the way in which the approach, practices, systems, process, methodology and other proposals contained in the answer will facilitate the achievement of the objectives set out in the Specification as well as the outcomes which are indicated as desired to be achieved through delivery of the services in accordance with the Specification (to the extent that the subject matter of the question is capable of doing so);

## and that the answer is supported by evidence and other information which provides assurance to the Department that the Tenderer is committed to achieving the objectives and outcomes and delivering the services in accordance with the Specification (the “Deliverables”) and that the approach, practices, systems, process, methodologies and other proposals explained in the answer will in fact do so.

## The Department will not take into account for the purpose of supplementing a score that would be awarded for an answer in a response to a Tender Quality Evaluation question, any information or evidence supplied by the Tenderer in response to another Tender Quality Evaluation question.  However, the Department shall be entitled to take into account any inconsistency between such answers in a Response (including without limitation any apparent inconsistency with the Prices submitted in that Response) as undermining the level of assurance that is provided that the Tenderer is committed to achieving the objectives and outcomes and delivering the services in accordance with the Specification (the “Deliverables”) and that the approach, practices, systems, process, methodologies and other proposals explained in the answer will in fact do so.  Such inconsistencies between different parts of a Response may therefore have a negative impact on scoring of individual answers affected.

## In respect of each question:

  - you must explain any approach, practices, systems, process and methodologies that you will apply to ensure that the Deliverables will be achieved and also why the Department should be assured by such approach, practices, systems, process and methodologies that the Deliverables will be achieved.

  - you must identify any potential matters which might hinder or obstruct your ability to ensure the Deliverables are met together with an explanation of how you will manage such potential obstacles that you have identified in an efficient, economic and effective way.

  - you must also include in each answer to a question an explanation of how your approach, practices, systems, process and methodologies that you have put forward in the answer have been developed to reflect lessons learned from previous experience (whether that is your own or any market experience).

## It is for Tenderers to determine how best to provide assurances to the Department in their answers but you may wish to reflect on matters such as:

  - the impact that your quality assurance systems may have in respect of the approach, practices, systems, process and methodologies that you have put forward in the answer;

  - levels of external validation, certification, accreditation of approach, practices, systems, process and methodologies that you have put forward in the answer;

  - the extent to which your answer demonstrates your level of appreciation and understanding of risks and matters which may prevent or hinder the desired outcomes and also what works and doesn’t work to overcome such risks and matters;

  - the explanation of the approach taken in developing the proposals to ensure they reflect lessons learned from experience and have been adapted to the specific characteristics of these services (with an explanation of how and why those adaptations have been made, their impact assessed and how they will be implemented in a controlled and managed way); and/or

  - any financial guarantees or assurances that are offered in addition to those already set out in the proposed contract (for example KPIs with service credits which leave no doubt that the Tenderer will be commercially incentivised to deliver the expected outcomes and relays the Tenderer’s confidence that it will do so).

## Summary of Scores Weighting

## The Department is applying a multiplier in the calculation of the scores which is also the equivalent to the relevant weighting of each question.

Where the calculation of a scores results in a fraction of a number, it will be rounded up to two decimal places.

|  | Max score | Multiplier/ Weighting | Maximum weighted score |
| --- | --- | --- | --- |
| A: Develop a programme of training and support for CPD Champions | 4 | 25 | 100 |
| B: Provide support as required to Local Authorities and partners | 4 | 10 | 40 |
| C: Provide a cascade method, and follow-up support to CPD Champions, in their delivery of CPD | 4 | 20 | 80 |
| D1: Implementation Plan | 4 | 15 | 60 |
| D2: Project Management approach | 4 | 5 | 20 |
| D3: Risk management approach | 4 | 5 | 20 |
| Total Tender Quality Score A-D3 |  |  | 320 |
| E: Price and cost matrix | 80 | 1 | 80 |
| Total maximum score: |  |  | 400 |

The Quality score formula is:

Quality score for each question:  Mark awarded x Multiplier = Weighted Score

Total Quality score: Aggregate of the Weighted Scores for each question

Weighted Total Quality Score: Total Quality Score/Max. Possible Quality Score = Quality Achieved %.  Quality Achieved % * 0.80 = Weighted Total Quality Score * 100 = %

For example, if a Bid scored a Quality score of 295, and a Price score of 60:

Weighted Quality Score: 295/320 = 92% * 0.80 = 0.74 * 100 = 74%

Weighted Price Score: 60/80 = 75% * 0.20 = 0.15 * 100 = 15%

Overall Tender Score: 355/400 = 0.89 * 100 = 89%

EVALUATION CRITERIA

| Tender Quality Evaluation |  | Weighting: 80% |  |  |
| --- | --- | --- | --- | --- |
| IMPORTANT INFORMATION: Please provide an answer for each question explicitly Tenderers should ensure all responses are complete and should not rely on a potential opportunity to expand upon their written responses at a clarification stage. All information which a bidder wishes to include in its response to a particular question must be set out in the response to that particular question. References to answers in other questions/sections may not be considered, and could result in a lower score being applied. Please only upload the information requested and where directed to do so. Any additional documentation will not be evaluated. All criteria are scored out of 4 unless explicitly stated otherwise. The DfE e-tendering Portal will only permit responses to up to the character limits stated for each question. |  |  |  |  |
| Question and Reference | Evidence to Consider |  | Weighting | Max Score |
| A Develop a programme of training for CPD Champions that delivers the outcomes at para. 3.1 of the specification | Tenderers are asked to outline the content and structure of their proposed training programme, showing how this would meet the requirements in the specification at paras. 3.8 to 3.11 (inclusive), including (in no more than 10,000 characters – approximately 2,000 words): - how the training programme will deliver the desired objectives for early years practitioners at para. 3.8; and - the specific evidence that underpins your proposed programme content (including short references citing the source of the evidence). |  | 25 | 100 |
| B Provide support as required to Local Authorities and partners, to deliver the outcomes at para. 3.1 of the specification | Tenderers are asked to outline how they would work with Local Authorities and partners to deliver the Department’s objectives, by meeting requirements in the specification at paras 3.12 to 3.18, including (in no more than 5,000 characters – approximately 1,000 words): - how they would work with LAs to develop a national programme of CPD that complements existing early years CPD programmes that might be operating in local areas; - how they will work with Local Authorities to support effectiveness of the cascade delivery model, including identifying CPD Champions and practitioners to receive training, and helping LAs to plan the cascade of CPD activity from CPD Champions to Settings; and - how they propose to run in-person events for Local Authorities and CPD Champions across the UK, at Programme start-up and at Programme closure. |  | 10 | 40 |
| C Provide a cascade method, and follow-up support to CPD Champions, to deliver the outcomes at para. 3.1 of the specification | Tenderers are asked to outline how they would meet the requirements in the specification at paras. 3.19 to 3.21 (inclusive), including (in no more than 5,000 characters, approximately 1,000 words): - their proposed approach to delivering CPD activity to CPD Champions which can then be effectively cascaded to other practitioners. Tenderers must include short references citing the evidence that underpins the effectiveness of their proposed approach; - an overview of the resources they would develop to assist CPD Champions to cascade CPD; - how they will provide a continuing programme of support and quality improvement to CPD Champions, to ensure CPD Champions cascade the CPD with fidelity - meaning the activity is consistently delivered as intended, in terms of the content and quality of the CPD; and - how they would monitor the effectiveness of the training programme and cascade model, and how they would use feedback to make continual improvements to the training provision. |  | 20 | 80 |
| D1 Implementation Plan to deliver the outcomes at para. 3.1 of the specification | Tenderers are asked to provide an Implementation Plan to deliver their proposal in line with requirement 3.22 in the specification (attached as a Word document, referenced ‘D1’, uploaded in the appropriate space in the online Technical Envelope, containing no more than 15,000 characters, approximately 3,000 words). The Implementation Plan should show planned activities, milestones and success measures (quantifiable as appropriate). The activities should be broken down by quarter over the funding period May 2019 – July 2021 (see para 3.5), and should be phased in line with the programme milestones (see para 3.6). The Department requires evidence that: - plans that are consistent and coherent with the training activities proposed by tenderers in their response to parts A, B and C; - plans that reference the timescales and requirements at paras. 3.5 and 3.6; - plans that allow for flexibility of delivery over the lifetime of the Contract, allowing for attrition of Champions; - plans that include a clear explanation of how activity will be monitored and reviewed; and - plans that are realistic, with success measures identified that will feasibly deliver the outcomes at para 3.1 of the specification. |  | 15 | 60 |
| D2 Project Management approach to deliver the outcomes at para. 3.1 of the specification | Tenderers are asked to outline, in no more than 5,000 characters, approximately 1,000 words (excluding any CVs provided. Any CV’s should be attached as a Word document referenced ‘D2’, uploaded in the appropriate space in the online Technical Envelope): - details of the project management structure, governance and staffing for their proposal, demonstrating that the programme will be managed and controlled effectively; - how this will meet the requirements at paras. 3.23 to 3.30 of the specification. The Department requires evidence that, for example: - key roles/responsibilities have been identified (including where possible, named individuals, how many days they will be involved in developing and delivering the Programme, the percentage of their time that will be spent on the Programme, and their CVs); - where identified, individuals’ CVs demonstrate convincing expertise in developing CPD and working successfully in partnership with a range of early years stakeholders; - plans explain how management information will be provided, and how communication with DfE’s managers will be managed; and - a clear statement is provided on how value for money will be achieved relating to all key aspects of service delivery. |  | 5 | 20 |
| D3 Risk management approach to deliver the outcomes at para. 3.1 of the specification | Tenderers are asked to identify 4 key risks facing their proposal, their judgement on the likelihood of occurrence (high / medium / low), together with plans for managing and mitigating such risks including any contingencies or countermeasures (up to 5,000 characters, approximately 1,000 words). The Department requires evidence that: - the Tenderer has carefully considered, has identified (and fully understands) and has taken appropriate steps/actions to mitigate the potential risks and issues relating to their proposed Programme; - the Tenderer is able to demonstrate that it has in place robust systems, practices, procedures, methodologies and approaches to (1) predict the likelihood of potential for and provide early warning of future occurrence of any risks which might hinder, undermine or otherwise damage the delivery of the services and achievement of the objectives and desired outcomes of the programme as indicated by the Specification and (2) will ensure that appropriate steps and actions will be taken by the Tenderer to minimise the occurrence and impact of any such risks and maintain the continuity of service delivery in accordance with the Specification and to achieve the objectives and desired outcomes of the programme; and - the Tenderer has plans in place to ensure business continuity and continuation of contract delivery in the event that any disruptive event occurs (including but not limited to any changes to the structure of the bidder and/or its supply chain and/or its key personnel responsible for delivering the Contract during the term of the Contract) and how any gap in service provision will be met to ensure that the Contract continues to be delivered to agreed standards. |  | 5 | 20 |
| Pricing / Cost Matrix Evaluation |  |  | Weighting: 20% |  |
| E Pricing/ Cost Matrix Evaluation | Proposal to contain full and complete cost estimates set out in the Cost Matrix. Cost estimates should be clear and realistic. A good bid will clearly show that the proposed Programme can be delivered within the budget outlined in the Specification of Requirements at para. 4. If Bids should exceed the published budget, the Department reserves the right to reject the Bid in its entirety and if costs are not given in the format and with the detail requested as set out in the Cost Matrix and in the Specification of Requirements at paras 4 to 4.15 (inclusive), then no score will be awarded for this element. |  | 1 | 80 |

Competition Rules

  - Each Response will be checked initially for compliance with the requirements of this Tender. Tenderers are reminded that failure to comply with the requirements of this Tender may result in the exclusion of the Response.  If a Response is excluded on this basis it will not be evaluated. Compliance checks will include the Response is submitted before submission deadline and the Response is complete.

  - Once a Response progresses past the compliance checks the Response will be assessed in the Selection Stage as to whether it meets the selection criteria.  In the event that any answer in the Selection Stage is marked as a “Fail” the Response will be rejected and will not be evaluated further.

  - All Responses that pass the Standard Supplier Questionnaire (SSQ) requirements will proceed to the Tender Quality Evaluation. The questions along with the scoring criteria and weightings are detailed above.

Desktop Tender Quality Evaluation

  - The weighting applied to “Quality” for this procurement equates to 80% of the overall score.

  - All Responses proceeding to this stage will be evaluated against the tender quality evaluation criteria using the scoring methodology and relative weightings specified above.  Evaluation of Responses will be undertaken by a panel appointed by the Department. Each panel member will first undertake an independent evaluation of the Responses.

  - No reference will be made by panel members between the questions, except to check for consistency between a Tenderer’s proposed training activities and Implementation Plan, and between their cost estimates and proposed resourcing.

  - Then, a moderation meeting will be held at which the evaluation panel will reach a consensus on the marking of each question. Evaluators will provide their rationale and evidence to support the scores they have awarded, and the reasons for any subsequently revised scores will be fully documented. Where there is no consensus agreed for the score to be awarded, this will be determined by taking an average of the scores.

  - At any point in this process the Department may ask Tenderers clarification questions prior to making a final decision. This will be done as set out in Section 1, paragraphs 4.1 to 3 of this ITT. Any appropriate clarifications from the Department will be communicated to bidders via the e-tendering Portal.

Quality Threshold

  - Please note that the Department will refuse to consider Tenders where the overall score achieved in the Stage 3 Tender quality evaluation is lower than 66% of the total score available (i.e. 211 out of 320) or an unweighted score of less than a ‘3’ is awarded on any individual question, except where the Department believes that it is reasonable to exercise discretion to waive this requirement. The Department expects that this may occur where:

    - one or more Tender(s) has failed to meet this threshold by a small margin; and

    - the Department has confidence in the Tender overall; and

    - the Department considers that rejecting such Tender(s) at this stage would unduly restrict competition.

Quality Criteria Scoring Matrix

  - The method of scoring the tender quality evaluation sections will be a 5-point scale (0 to 4), as set out above. Evaluators will assign a score to each evaluation question response (and all marks will be in whole numbers i.e. there is no ability to award a mark with one decimal place). There are 320 marks available for this section, once the weighting to individual question responses have been applied.

  - Evaluators will make appropriate notes to validate all scores awarded. Unless otherwise stated against the criteria in this document, the scoring guidelines above shall apply.

  - The Weighted Total Quality score is calculated as indicated in Section 2 under the sub-section headed Summary of Scores Weighting.

STAGE 4 - PRICE / COST MATRIX EVALUATION

  - The weighting applied to “Price” for this procurement equates to 20% of the overall score.

  - Bids will only be evaluated against the Price Evaluation if they achieve or exceed a total weighted score in the tender quality evaluation equivalent to 66% (211 out of 320) and are awarded an unweighted score of at least ‘3’ on each individual question.

  - Tenderers are requested to detail the whole cost to deliver the Contract in the Cost Matrix, with reference to the requirements in the specification at paragraphs 4 to 4.15 (inclusive).

  - Tenderers must complete all aspects of the Cost Matrix, providing a full explanation and justification of the costs detailed. The Department reserves the right to not further consider a bid that does not include a fully completed Cost Matrix.

  - Clarifications may be sought during the evaluation to ensure that the evaluation panel have fully understood the pricing submission and are evaluating on a like for like basis.

  - All costs must be stand-alone for the whole life of this Contract only and not rely on interdependencies, shared costs etc. with any other government contract. Further information about this section is provided below.

  - Tenderers must identify if VAT will be chargeable.

  - The total whole life cost for each tender, excluding VAT, will be calculated and a score awarded based on the percentage difference from the lowest bid received.

  - The Tenderer who submits the lowest priced tender will achieve the maximum available Price score, namely 80 marks.

  - Every other Tenderer will be ranked from lowest to highest and awarded a percentage of the maximum available Price score on a reducing basis, based on the price submitted versus the lowest priced tender.

  - The process is illustrated in the example below:

The calculation used is:

| Score = | Lowest priced tender | x | Maximum available score (80) |
| --- | --- | --- | --- |
|  | Tender price |  |  |

Example:

- Tenderer A submits the lowest price of £1,000. Tenderer A is awarded the maximum available Price score of 80;

- Tenderer B submits a price of £2,000. As the price is twice as expensive as Tenderer A, Tenderer B is awarded a Price score which is 50% of the maximum available score, namely 40;

- Tenderer C submits a price of £2,500 and is awarded a Price score which is 40% of the maximum available score, namely 32.

  - The scoring of a Tenderer’s Price will be calculated to two decimal places.

  - The Price score of each Tenderer will be converted into the Weighted Price score by multiplying the Price score by 20% (and will still be calculated to two decimal points).

  - In respect of each Response, the Weighted Price score will be added to the Weighted Total Quality score to achieved the Total Weighted Score for that Response (which will be calculated to two decimal places).  The Tenderer that will be successful in this procurement is the one whose Response is awarded the highest Weighted score.

Evaluation Process

  - Evaluation of the answers provided to the Tender Quality Evaluation questions in each Response will be undertaken by a panel appointed by the Department. Each panel member will first undertake an independent evaluation of the Responses applying the relevant quality evaluation criteria.

  - The calculation of the scores for the prices submitted in respect of the Cost Matrix (the Price) in a Response will be undertaken in the first instance by a financial officer.

  - There will be an opportunity for evaluation panel members to request the Department to seek clarification from Tenderers (see Section 1 of this ITT) to assist each evaluator to undertake the assessment of the Responses. Tenderers are required to respond promptly to any such request for clarification.  In the event that a Tenderer fails to provide the requested clarification within the time set out for its receipt within the request then their Response may be rejected.  Clarifications received by the Department within the required time will be issued to all evaluators.

  - Once each of the evaluators has arrived at a provisional score for the Tender Quality Evaluation questions in each Response, a moderation meeting will be convened of all the evaluators on the evaluation panel under the guidance of a moderator (who will not be one of the evaluators).

  - The purpose of the moderation meeting will be focussed on testing, interrogating and understanding:

    - the level of consistency within the answers given by a Tenderer in its Response;

    - the reasoning being given by each of the evaluators in support of the scores being awarded and the level of consistency of interpretation of the answers given in each Response;

    - any reasons for any divergences in scoring of a Response between evaluators or the reasoning behind the scores; and

    - any further clarification required from any Tenderer before the scoring of the Response can be finalised,

with the intention of seeking consensus in the scores being awarded in respect of each answer to a question in a Response. This means that when evaluators have different views on the score a question should achieve, these will be discussed in the moderation meeting with the view to achieve a consensus score. However, please note when consensus cannot be achieved, the scores will be averaged (and calculated to two decimal places).

  - The moderation meeting will have the right to consider issues relating to potential inconsistencies between the Prices comprised within a Response, and the answers (including the evidence and assurances in support of those answers) provided in the Response to the Tender Quality Evaluation questions (the “Quality responses”).  This may result in consideration of whether the Tender is abnormally low (see further below) or whether it is necessary to revise downwards the scores being awarded in respect of the answers provided in the Response to the Tender Quality Evaluation questions. In the event of any concern expressed at the moderation meeting that there may be any such inconsistency then the Department will seek further clarification/explanation from the Tenderer which the Tenderer shall provide promptly and within the time stipulated in the request.

  - If such a request is issued, the Department will provide to each evaluator the clarifications/explanations received in accordance with the request and the moderation meeting will re-convene to consider whether it is appropriate to revise the scores for the Quality responses of that Tenderer downwards, or to treat the Response as potentially abnormally low for the purpose of initiating the process for dealing with abnormally low tenders (see further below).

  - In the event of a tied overall score (when Tender Quality Evaluation and Pricing/Cost Matrix Evaluation scores are combined), preference will be given to the bid with the highest score pursuant to the Tender Quality Evaluation.

Abnormally Low Tenders

  - Where the Department considers that the pricing/ cost matrix does not correlate with the quality of a Tenderer’s offer or to be abnormally low, the Department will request the Tenderer to explain its pricing/ cost matrix. This may include explanations of the following:

- the economics of the Services to be delivered;

- the technical solutions suggested by the Tenderer or the exceptionally favourable condition available to you for the provision of the Services;

- the originality of the Services;

- the Tenderer’s compliance with any regulatory provisions, including in relation to environmental, social and labour laws (referred to in Regulation 56(2) of the Public Contracts regulations 2015); and/or

- the possibility of the Tenderer obtaining state aid.

  - The Department will take account of the evidence provided and investigate further as necessary, to ensure that the Tenderer’s tender is sustainable for the duration of the Contract.

  - If in the opinion of the Department, the evidence supplied does not satisfactorily account for the low level of price or costs proposed by the Tenderer in its Tender, then the Tender will be rejected and excluded from the evaluation process.

  - Tenderers are referred to Regulation 69 of the Public Contracts Regulations 2015, which contains further information and detail in relation to abnormally low tenders.

Award Notice

  - Following the moderation, Tenderers will be notified of the outcome in accordance with the Public Contracts Regulations 2015.

  - Following notification, a ten-day standstill period will take effect in accordance with regulation 87 of the Regulations before the Department enters into the Contract.

SECTION 3:  SPECIFICATION

- Introduction

  - The Department for Education is seeking to procure an organisation to deliver a programme of Continuing Professional Development (CPD) activity, the Professional Development Fund (‘the PDF’).

  - The PDF will support pre-reception early years practitioners to improve their practice in working with very young children between the ages of 2 and 4, to improve outcomes in language, literacy and numeracy for the most disadvantaged children, with an emphasis on improving school readiness.

- Background

  - There is a strong evidence base and universal agreement that high quality early education can improve children’s outcomes. The first life stage up to age 5 is a unique opportunity to make sure that children develop the cognitive, social and emotional foundations required to build their future success in both school and later life.

  - There is widespread recognition that a ‘word gap’ exists between disadvantaged children and their more affluent peers. More affluent children, often with a richer home learning environment, can benefit from an in-built head start with their language meaning they are ahead of their peers when they arrive at school. Evidence shows that by the age of three, more disadvantaged children are – on average – already almost a full year and a half behind their more affluent peers in their early language development. We know that children behind in language development at age five are six times less likely to reach the expected standard in English at age eleven, and eleven times less likely to reach the expected level in maths. Vocabulary at age five is also a key predictor of whether a child from a disadvantaged background is likely to ‘buck the trend’, succeed at school and become socially mobile in later life. And yet on average, by this age, disadvantaged children are further behind in vocabulary than in other areas of cognitive development.

  - The Government’s plan to improve social mobility through education, ‘Unlocking Talent, fulfilling potential’ (UTFP) set out DfE’s ambition to improve outcomes for disadvantaged children and close the ‘word gap’ in the early years between more affluent children and their less advantaged peers at age 5.

  - The PDF is a £20m commitment in UTFP, confirmed in the Secretary of State’s speech on boosting social mobility (July 2018). Its aim is to drive improvements in children’s early language, literacy, and numeracy, through the provision of high quality, evidence-based CPD support for early years practitioners. This will help meet the Secretary of State’s ambition to halve the percentage of children that finish reception without the expected skills in early communication and reading in the next ten years (currently at 28%).

Raising quality through investing in CPD

  - A robust evidence base, built over decades, shows that attending good quality early years provision benefits children’s later outcomes, and that disadvantaged children can benefit in particular from this effect.

  - There is also extensive research defining good quality in early years provision. Good quality provision is the product of a range of interrelated factors across process (children’s day to day activities and interactions with adults) and structures (measurable inputs like group size, staff ratio and staff training and professional development). While higher qualifications and specialised training in early childhood education or development is both useful and highly desirable for staff working in Settings, systematic, sustainable and transformative CPD for the wider workforce also plays an important role in overall quality. Evidence suggests that preparatory and in-service training are both associated with increased positive outcomes for children in certain circumstances.

  - It is important to invest in CPD across the workforce to equip staff with the right skills and training to lead high quality interactions with children, starting with the areas most in need of support. The DfE’s Study of Early Education and Development demonstrated that quality can be associated with factors such as Settings having training plans for their staff and funding available for professional development activity. EEF evidence suggests that training existing staff is a more promising way to raise quality than increasing the number of hours children attend or improving the physical environment in Settings. Recent evidence shows that investing in focused professional development activity in the early years, to improve skills and practice in the existing workforce, can lead to rapid improvements in Setting-level quality, children’s cognitive outcomes in language and numeracy development, and their socio-emotional development.

  - Finally, the Programme is designed to help address some of the barriers that can make it difficult for early years practitioners (EYPs) to access effective CPD. These can include Settings not knowing the best CPD to access, and cost pressures that make it difficult for them to purchase training and cover the supply costs to release staff to attend.

- Purpose

  - The Department is seeking to procure a comprehensive and sustained programme of CPD for EYPs working in selected pre-reception Settings attended by more disadvantaged children. The overall purpose is to improve workforce capability to support children’s development between the ages of 2 and 4, to achieve the following outcomes:

- the quality of practice improves in the participating Settings;

- the children attending these Settings - now and in the future - are better-prepared for their school reception year, particularly through improved early language and literacy skills; and

- a network of effective local partnerships is developed, bringing together practitioners from schools and Private, Voluntary and Independent (PVI) Settings to focus on improving children’s outcomes in the locality; and which can be sustained in the longer term as a future mechanism for spreading best practice to improve Pedagogy and outcomes for children in the early years.

Structure of the Programme

  - Alongside the Supplier, we expect the selected Local Authorities (LAs) to play a key role in programme delivery by recruiting pre-reception Settings into CPD partnerships, and identifying skilled and experienced EYPs as CPD Champions, willing to cascade and lead CPD activity with the other settings. The PDF aims to reach the most disadvantaged children in England.  We believe local authorities are well-placed to identify the Settings that can benefit most from the available support, and to convene CPD Partnerships, based on local knowledge, and from their statutory responsibilities to ensure sufficient high quality childcare in their areas and support weaker early years providers to improve. The LAs will work with the local Partnerships to produce a plan to support the cascade of CPD activity from CPD Champions to Settings, and to administer funds for practitioner backfill costs so that the PDF is free for Settings to access.

  - We envisage the fund will establish more than 100 CPD Partnerships in areas identified by the Department as being in greatest need, and pay for at least 400 CPD Champions to be trained by the PDF Supplier. We anticipate there will be 12-15 Settings per CPD Partnership. The Department is inviting LAs to take part in the PDF in tandem with this procurement, hence the numbers stated in this paragraph are a best estimate, and should be used for the purposes of Tenderers modelling their Bids only, as the Department does not warrant that this information is comprehensive or that it has been independently verified. Flexibility will be required to deliver the Programme to the eventual agreed locations and Partnerships.

  - A separate procurement will be carried out for a Third Party Evaluator to conduct a robust analysis and review of the PDF. This analysis will focus on rigorously evaluating the CPD approach to understand whether the chosen approach is effective in improving speech and language outcomes, and the case for further investment in this type of Programme.

PDF Delivery Model

Phasing

  - Funding is available to commence development of the Programme from May 2019, and to sustain programme delivery to Settings over two full academic years, from September 2019 to July 2021. The Department invites potential suppliers to submit plans to deliver training to equip 400 CPD Champions to cascade CPD activity by 31 May 2020, and to provide follow-up support (in line with requirements at 3.19 to 3.21 below) for the CPD Champions as they cascade the material.

  - The Department invites Tenderers to submit plans to deliver the Programme to the milestones in table 1 below.  The Department is open to bidders suggesting alternative approaches to the phasing of delivery to reach 100 Partnerships and 400 CPD Champions, and, where feasible, proposals to maximise the reach and impact of the programme beyond the minimum scale expectations set out in these requirements.

Table 1: PDF Programme Milestones

|  | Milestone | Milestone Description | Accountability | Date |
| --- | --- | --- | --- | --- |
| 1 | LA Grants issued | Grants issued before end of FY 18/19 for LA recruitment activity to begin. | DfE | 01/03/2019 |
| 2 | Preferred Supplier announced | Preferred supplier notified, prior to standstill and contract finalisation period. | DfE | 31/03/2019 |
| 3 | Contract start date | Contract finalised and agreed – contract delivery starts. | Supplier / DfE | 31/05/2019 |
| 4 | Third Party Evaluator appointed | Competition concluded and winning contractor named. Contract agreed and signed. | DfE | 31/05/2019 |
| 5 | LAs confirm memberships of CPD Partnerships. | Settings / practitioners identified and recruited by LAs, with advice / info provided from supplier as required. LAs provide supplier and DfE with details of participating EY Settings (names, type of Setting, contact details and location) in their area. | LAs | 01/06/2019 |
| 6 | LAs complete recruitment of 400 CPD Champions. | CPD Champions identified and recruited by LAs, with advice / info provided from supplier as required. LAs provide supplier and DfE with contact details for CPD Champions. | LAs | 28/06/2019 |
| 7 | Draft CPD package, resources and piloting plan submitted to DfE. | Draft CPD package, resources and piloting plan developed by supplier and submitted to DfE for sign off. | Supplier | 01/07/2019 |
| 8 | DfE signoff of draft CPD package, resources and piloting plan. | Agreement to proceed to piloting phase of project delivery | DfE | 26/07/2019 |
| 9 | Piloting commenced. | Commence pilot phase of project - field testing of CPD training and resources in at least one LA area | Supplier | 01/09/2019 |
| 10 | Contractor submits piloting report and recommendations for any amendments to the training package and resources. | Report on piloting phase provided to DfE, final CPD package and resources submitted for DfE signoff prior to implementation phase. | Supplier | 01/11/2019 |
| 11 | DfE signoff of final CPD package, resources and piloting plan. | Agreement to proceed to next phase of project delivery – providing core training to the CPD Champions | DfE | 29/11/2019 |
| 12 | CPD Champions’ initial training commenced. | Implementation phase of initial core training and support to CPD Champions commenced | Supplier | 04/01/2020 |
| 13 | CPD Champions’ initial training completed. | ITT milestone – all 400 CPD champions trained by end May 2020. | Supplier | 31/05/2020 |
| 14 | Follow-up support for CPD Champions cascade commenced. | Follow-up support (coaching / mentoring support as defined in the ITT) is provided by the Supplier to CPD Champions after their initial training, during their cascade of CPD activity to Partnerships, for the remainder of the programme. | Supplier | 31/05/2020 |
| 15 | Interim evaluation findings | Third Party Evaluator prepares interim findings to be shared among stakeholders | Third Party Evaluator / DfE | 31/09/2020 |
| 16 | CPD Champions Cascade commenced. | CPD Champions’ cascade activity commenced in all CPD partnerships | LAs | 30/06/2020 |
| 17 | Follow-up support to CPD Champions concludes. | Follow-up support (coaching / mentoring support as defined in the ITT) provided by the Supplier to CPD Champions during their cascade to Partnerships concludes. Report on participants’ feedback produced and shared with DfE. | Supplier | 30/07/2021 |
| 18 | Contract end date | End of funding period. | DFE | 30/07/2021 |
| 19 | Final evaluation report published | Evaluation report completed by contractor and published on gov.uk | Third Party Evaluator / DfE | 31/09/2021 |

The Department’s Requirements and Objectives

  - The precise functions of the Supplier will include, but not be restricted to, the following areas:

- Develop and deliver a programme of training and support for CPD Champions

  - The Supplier will provide at least 45 hours of direct face-to face training (‘initial’ training) to each CPD Champion (there will be between 400-450 CPD Champions with numbers to be confirmed by Local Authorities by summer 2019.  Bids should be prepared on the basis of 400 CPD Champions). We expect, as far as practicable, for the ‘initial’ training of CPD Champions to be completed by the end of May 2020, after which time the Supplier will provide follow-up support to the CPD Champions as specified at requirements 3.19 to 3.21 below.  The initial training will be a single product (i.e. the same content will be delivered to all CPD Champions in all areas) with a focus on supporting children to develop early language, literacy and numeracy skills.  It will ensure the CPD Champions fully understand, and are able to cascade CPD activity to local practitioners via their local Partnerships, to meet the following objectives:

- Early years practitioners have a sound grounding of current early years child development research and theory to inform practice.

- Early years practitioners have the skills and knowledge to enhance the quality of adult-child interactions through Sustained Shared Thinking - encouraging ‘back and forth’ discussions to build vocabulary.

- Early years practitioners have improved subject knowledge and confidence to implement evidence-based approaches across early language, literacy and numeracy, including through activities like shared reading, reading to children on at least a daily basis, dance and rhymes.

- Early years practitioners have the knowledge and confidence to engage with parents around their children’s learning – to support the home learning environment.

- Early years practitioners are confident in and know how to identify children at risk of Speech Language and Communication Needs (SLCN) — and can put into place suitable and appropriate support strategies that do not add to any over-identification pressures on local speech therapy services.

- The CPD Champions have the skills, knowledge and confidence to cascade this learning to early years practitioners consistently as intended, in terms of the content and quality of the CPD – accepting that the precise method of cascade to Settings may differ according to local circumstances.

  - The Supplier must provide a high quality training programme for CPD Champions that will:

- Deliver at least 45-hours of direct face-to-face CPD activity to each CPD Champion, with timings / locations / methods designed to make the activity readily available for CPD Champions to access and attend, and seeking to minimise CPD Champions’ travel costs where possible (the supplier is not expected to reimburse Champions’ travel costs - these costs will be paid by Local Authorities).

- Have a focus on supporting children's early language, literacy and numeracy and the practical approaches practitioners can take to improve children’s skills in these areas.

- Be able to accommodate the different levels of knowledge, understanding and confidence of practitioners at the start of the training.  CPD Champions will hold as a minimum a relevant level 3 qualification.

- Provide appropriate resources that support the CPD Champions to put the learning into practice in their own Setting, and which support them to cascade the training to other practitioners.

- Includes a mechanism for assuring the quality of the CPD programme and the subsequent cascade by CPD Champions.  As a minimum this should include:

  - piloting of the CPD training package ahead of national roll-out;

  - regular participant feedback on training;

  - observing CPD Champions delivering training to other practitioners to ensure fidelity in the cascade of the training (consistently as intended, in terms of the content and quality); and

  - regular reporting to DfE on improvement measures being taken as a result of the intelligence outlined above.

  - Tenderers must build at least four days of time into their delivery plan during the development of CPD materials in order to work with colleagues at the National Mathematics Centre to incorporate pre-existing CPD content on early years numeracy approaches into their training Programme. This will require the supplier to work with the authors of the existing content on the following activities:

- Discussion of the findings of the National Mathematics Centre’s numeracy CPD pilot for 3-5 year olds, and the implications for the Programme;

- Workshop activities to adapt materials for 3-4 year olds

- Discussion on how to fit the pilot model into the reduced number of days available for the Programme, without losing the focus on effective pedagogies.

  - Tenderers must build in two further half days of time over the course of the Contract for continued consultation with the National Mathematics Centre after the initial development of the Programme to share updates, impact information and lessons learnt.

- Provide support as required to Local Authorities and partners, in the effective operation of the cascade model.

  - The Supplier should develop a Programme of CPD with standardised content that can be delivered nationally. In developing this CPD Programme, the supplier should consider how this Programme can sit alongside and add value to existing CPD activity that might already be on offer in local areas.

  - To support the alignment and integration of Programme delivery with other local CPD activity, the Supplier should:

    - Provide written information and guidance for Local Authorities on the content of the Programme.

    - On request, make provision for up to two staff from each Local Authority to observe the training provided to CPD Champions, so they can also support implementation.

    - Where a Local Authority seeks additional advice, provide follow-up guidance as required, to ensure Programme activity can be aligned with any other local initiatives.

    - On request, provide written information, guidance and advice on the Programme to any other local DfE delivery partners including Maths Hubs, English Hubs, The English Hubs Training Centre (once appointed), Opportunity Area leads and RSC offices. In addition to providing written guidance, the Supplier will work with existing partnerships where this is necessary to promote and support alignment with their work.

  - To support the effectiveness of the cascade delivery model, the Supplier should provide written information and guidance for Local Authorities, including how to identify practitioners suitable to take on the CPD Champion role, and the practitioners to recruit from Settings to form Partnerships. Where a Local Authority seeks additional support with this, the Supplier should provide follow-up guidance and advice as required.

  - Local Authorities will be responsible for ensuring the local delivery of the cascade model. The precise format of the cascade (e.g. arranging backfill cover, the timings for sessions, ensuring attendance, agreeing arrangements for follow-up support etc.) is to be confirmed by local cascade delivery plans produced by the Local Authorities.

  - The Supplier must work collaboratively to resolve issues raised by Local Authorities on the impact the cascaded training is having in the Settings participating in CPD Partnerships over the lifetime of the programme, offering further advice on the cascade model and suggesting best practice as appropriate.

  - The Supplier must plan, organise and deliver two Programme launch events, to encourage stakeholders to engage with the Programme, and for peer networking and support, open to practitioners and Local Authority participants, one which must be held in the North of England and one which must be held in the South of England.

  - The Supplier must plan, organise and deliver 2 events to identify lessons learnt,  share best practice and celebrate success at the end of the programme, open to practitioners and Local Authority participants, one which must be held in the North of England and one which must be held in the South of England.

- Provide a cascade method, and follow-up support to CPD Champions, in their delivery of CPD

  - The Supplier must provide resources to enable CPD Champions to deliver training and support to practitioners in local CPD Partnerships until July 2021. These resources will cover:

- A suggested best practice methodology for CPD Champions to use in cascading the CPD activity they receive to Settings in Partnerships (we expect the cascade model to be a mixture of face-to-face training sessions, participative action-based learning, and follow-up coaching support that could be provided face-to face, online etc.).

- The content of the Programme to be cascaded.

- Any specific resources required for CPD Champions to implement evidence-based approaches in language, literacy and numeracy.

- Materials to aid the CPD Champions to provide follow-up support to Settings.

  - After their initial training, the Supplier will ensure that CPD Champions are effectively supported to cascade the CPD activity with fidelity over content. High-quality follow-up support would include mentoring and coaching, and providing further advice and support to the CPD Champions as required to respond to local needs arising. It may include offering networking events. Further support to CPD Champions must be provided over the lifetime of the Programme to July 2021.

  - As per requirement 3.9 bullet 5 above, the Supplier will also quality assure the training being cascaded by CPD Champions from 2020 until the end of the Contract term, and provide a clearly defined feedback loop with CPD Champions to improve the programme as a whole, through a regular cycle of planning and evaluation, reporting back quarterly to the Department on any improvement measures taken.

- Project Management & Risk Management

  - Tenderers will include an Implementation Plan (as defined in the Contract), including realistic outputs and milestones. The Implementation Plan will cover the milestones set out at table 1 above. The Plan will include governance and project management arrangements, and set clear scope and work streams.

  - The Supplier will ensure that the Programme is run in accordance with good industry practices, particularly with regard to achieving good value for money, risk management and data management/protection. The Supplier must have processes and systems in place for ensuring costs and pricing are managed appropriately, and provide the Department with monthly spend reporting in line with the requirements at paragraphs 4.3 and 4.15 below.

  - The Supplier will ensure any issues that may adversely affect the quality of CPD activity raised by CPD Champions are addressed in a timely manner, making sure that channels of direct communication with the Supplier are available to both CPD Champions and Local Authorities, and putting in place effective, remedial intervention as soon as possible to improve the CPD activity delivered to Settings. The Supplier must identify a dedicated resource to manage the day to day relationship whose targeted role is to unblock issues and identify solutions rapidly.

  - The Programme risks and issues log should be reviewed and shared with the Department on a monthly basis.

  - The Supplier will maintain a central record of training attendance and participation of all training activities to CPD Champions led by the Supplier.

  - The Supplier will put in place systems to monitor and measure the impact of the delivery of CPD to CPD Champions, and that CPD Champions’ cascade of CPD activity to Settings is consistently as intended, in terms of the content and quality of the CPD activity.

  - Suppliers will need to provide to the Department with quarterly updates for purposes of monitoring and quality assurance, including the following as a minimum:

- Progress against milestones, including numbers of CPD Champions trained and the post code of the Settings involved.

- Feedback from participants.

- Risks, issues and mitigations.

- Suggested remedial actions.

  - The Supplier will ensure that mechanisms, including management information  and data sharing, exist to liaise with the Department and any relevant Third Party Evaluator appointed by the Department to support the delivery and evaluation of the Contract, and to engage in analysis and formative evaluation to ensure that lessons learned are incorporated into the ongoing delivery as part of an ongoing quality improvement cycle.

  - The Supplier will engage fully with any relevant Third Party Evaluator nominated by the Department to support the delivery and evaluation of the Contract and collect management information data and feedback from on various aspects of the Programme to evaluate the delivery and impact of the Programme.

Summary of Programme roles

The selected Supplier will:

- Design and deliver professional development activity and resources for early years practitioners nominated as CPD Champions

- Support Local Authorities as required to recruit practitioners and CPD Champions and develop local plans for CPD cascade

- Support LAs and local early years CPD Partnerships to facilitate the implementation of a high quality and effective cascade model for delivering professional development to pre-reception Settings (focused on early language, literacy and numeracy)

- After providing their initial training, provide ongoing coaching and development support for the CPD Champions as they cascade the professional development activity within their local CPD Partnership

- Perform monitoring and quality assurance of training to CPD Champions and CPD Champions’ cascaded activity, to ensure this is being delivered consistently as intended, in terms of the content and quality, with an ongoing quality improvement cycle.

- Work collaboratively with Local Authorities to address any local delivery issues identified with the cascade model.

- Facilitate national CPD Champions’ professional development network events to launch the Programme, and then at Programme closure to disseminate learning / best practice, helping to create a sustainable peer support model.

- Provide the Department with quarterly updates on all activity including milestone delivery, participant feedback on training, feedback on CPD Champions’ cascade of the activity, reporting on improvement measures taken plus risks and issues.

- Work with the Third Party Evaluator as required to support a process and impact evaluation of the Programme.

Local Authorities

It is anticipated that the Selected Local Authorities will:

- Facilitate the establishment of early years CPD Partnerships of schools and PVI pre-reception Settings for the purpose of participating in professional development activity to improve disadvantaged children’s early language and literacy outcomes – identifying and recruiting Settings in the areas of greatest need, based on agreed criteria.

- Work with Partnerships to identify and nominate practitioners as CPD Champions and therefore to participate in the professional development led by the Supplier.

- Work with the Partnerships to agree a delivery plan to ensure the cascade of CPD activity by the CPD Champions can be delivered locally over the lifetime of the Programme, using the most appropriate modes of CPD delivery in their area by identifying barriers and taking into account the needs of different provider types (e.g. twilight or weekend delivery, off-site/on-site etc.)

- When recruiting participants for the Programme, help ensure that CPD related to the Programme does not duplicate or otherwise unhelpfully overlap with existing CPD activity in the Local Authority provided by other DfE delivery partners such as Maths/English Hubs and Opportunity Areas.

- Organise and provide the venues for cascade activity, including any other logistics to ensure delivery of the cascaded CPD activity to Partnerships.

- Manage and monitor the budget for staff cover for practitioners to leave their Settings to participate in CPD, including reimbursing travel costs.

- Support the Third Party Evaluator to capture feedback from CPD Partnership members as required, and raise any concerns or issues with the Supplier and DfE.

- Facilitate links between Partnerships and other relevant services as required, e.g. Health Visitors, specialist speech and language services.

- Be responsible for dissemination of learning/sharing of practice more widely across other pre-reception/reception Settings in the LA area.

- To participate in any national level lessons learnt workshops convened by the Supplier to disseminate learning.

- Support and participate in local and national evaluation activity for the Programme as required.

The Selected Third Party Evaluator will:

- Perform an external process and impact evaluation of the Programme.

The Local Authorities invited to participate in the Programme are listed below:

| 1 | Barnsley | 28 | Liverpool |
| --- | --- | --- | --- |
| 2 | Blackburn with Darwen | 29 | Middlesbrough |
| 3 | Blackpool | 30 | Norfolk |
| 4 | Bolton | 31 | North Yorkshire |
| 5 | Bradford | 32 | Nottinghamshire |
| 6 | Brighton and Hove | 33 | Oldham |
| 7 | Bristol, City of | 34 | Plymouth |
| 8 | Calderdale | 35 | Redcar and Cleveland |
| 9 | Cambridgeshire | 36 | Rochdale |
| 10 | Cornwall | 37 | Rotherham |
| 11 | Cumbria | 38 | Salford |
| 12 | Derby | 39 | Sheffield |
| 13 | Derbyshire | 40 | Somerset |
| 14 | Doncaster | 41 | St. Helens |
| 15 | Dudley | 42 | Stockport |
| 16 | Durham | 43 | Stoke-on-Trent |
| 17 | East Sussex | 44 | Suffolk |
| 18 | Gloucestershire | 45 | Sunderland |
| 19 | Halton | 46 | Tameside |
| 20 | Hertfordshire | 47 | Telford and Wrekin |
| 21 | Kent | 48 | Wakefield |
| 22 | Kingston Upon Hull, City of | 49 | West Sussex |
| 23 | Lancashire | 50 | Wigan |
| 24 | Leeds | 51 | Wiltshire |
| 25 | Leicester | 52 | Wirral |
| 26 | Leicestershire | 53 | Wolverhampton |
| 27 | Lincolnshire | 54 | Worcestershire |

At the time of writing, 52 of the local authorities above had indicated their intention to participate in the Programme; however the list is subject to possible further change. During this tender process, the Department will engage further with the targeted Local Authorities and confirm the areas participating in the Programme in line with the indicative Programme milestones at table 1 above.

LA selection rationale

To prioritise the areas where disadvantaged children will benefit most from the Programme, data from the early years foundation stage profile (EYFSP) results: 2016 to 2017 was used to select the bottom third of local authorities (LAs) based on the following metrics:

- % of children known to be eligible for Free School Meals (FSM) achieving a good level of development (GLD)

- % of children known to be eligible for FSM achieving at least the expected level of development for communication and language (CL) in the Early Learning Goals (ELGs)

- % point gap between children known to be eligible for FSM in the LA and all other children in the LA achieving GLD

- % point gap between children known to be eligible for FSM in the LA and all other children in the LA achieving at least expected level for CL

- % point gap between children known to be FSM-eligible in the LA and the national average for all other children for GLD

- % point gap between children known to be FSM-eligible in the LA and the national average for all other children for CL

- the absolute number of children in each LA known to be eligible for FSM

- The overall percentage of children in each LA known to be eligible for FSM

- The 12 Opportunity Areas are also included, even where they would not be eligible on the criteria above. These areas were objectively chosen for their low social mobility outcomes, and their inclusion is in line with the approach taken for other early years interventions.

Costs and Value for Money

- The Department will allocate funding of up to £4m between May 2019 and July 2021 to the successful delivery partner in order to: deliver the programme of CPD activity to CPD Champions; and to provide further coaching and mentoring support as CPD Champions deliver CPD through their local CPD Partnership.

  - The £4m affordability envelope available is a gross total, inclusive of VAT and is the maximum amount payable, inclusive of any other service or consumption taxes. Tenders that exceed this figure (gross of all taxes) will not be considered.

  - Further to Paragraph 4.5, if a Tenderer intends to charge the Department VAT this must be identified in the Cost Matrix. Where a Tenderer fails to identify any applicable VAT in the Cost Matrix, the total price for the purposes of the Contract will be deemed to be inclusive of any VAT (for VAT applicable services), and if the Tenderer is successful, the Contract will reflect this. Further amounts will not be paid by the Department should a vatable supply claim be made at any later stage.

### Payment Schedule, Reporting and Invoicing

  - Tenders should include a summary of projected monthly costs for each financial year of the Programme. Costs should be detailed in the attached Cost Matrix document against each of the following categories:

- Set up costs (e.g. material development, IT equipment, marketing/brand development, recruitment costs);

- Programme management and overhead costs (e.g. staffing costs, premises rental/lease costs, marginal overheads for IT/finance/HR/facilities support);

- Programme delivery – staffing costs;

- Programme delivery – non-staffing costs (e.g. any IT or administrative costs, travel costs);

- Operating Profit;

  - Tenders must not include costs for capital expenditure relating to the purchase or construction of premises.

  - Please exclude VAT when submitting prices but state clearly in the Cost Matrix if you intend to charge the Department VAT.

  - It is the responsibility of tenderers to check the VAT position with HMRC before submitting a bid.

  - All estimated costs must be real, auditable and able to be justified. In the event of a successful Tender, the proposed Cost Matrix will become the budget profile and Payment Schedule for the Contract. No additional costs will be charged to the Department unless agreed with the Department prior to expenditure.

  - The Department will require monthly reporting against spending. The Department will have the right to request sight of any relevant receipts, invoices or other documentation to support any reports of spending. The Department may at any time during the period of the Contract, following a reasonable period of notice (at least one calendar month) undertake a full audit of the Supplier’s spending within the Contract.

  - Every monthly spending report will be reconciled against the budget profile, and any variance will be discussed. Due to the natural level of flexibility in the delivery of Services, the Department may allow some degree of flexibility in the Payment Schedule between months (i.e. if the Supplier underspends against the Payment Schedule in a given month, the Department may allow an equivalent overspend in a later month within the same financial year). The Department will not, however, permit any such transfer of funds across two or more financial years.

  - In any given financial year, the Department will not pay more than the figure set in the Payment Schedule.

  - In the event that the Supplier is likely to underspend in any given financial year, the Supplier must inform the Department of the estimated level of underspend at least three months before the end of the financial year.

  - The Department will retain any funds in the Payment Schedule not spent by the Supplier at the end of any financial year.

  - Payments of costs to the Supplier will be made monthly, in arrears, by BACS transfer following receipt of a valid invoice. Further details of the Department’s terms of payment are set out in the Contract.

  - Clarifications may be sought during the evaluation to ensure that the evaluation panel have fully understood the pricing submission and are evaluating Tenders on a like for like basis.

  - All costs must be stand-alone for the whole life of this Contract only and not rely on interdependencies, shared costs etc. with any other government contract.

Key Performance Indicators

- The Department will agree a number of KPIs with the Supplier. These will be used as a measure of the effectiveness of the Services performed by the Supplier. A total of 7.5% of the value of the Contract is linked to performance on the KPIs.

  - The Department will monitor progress against KPIs on a regular basis (progress will be monitored via quarterly progress reporting and review) and each KPI will be formally assessed by DfE at the end of July of each year by a date to be specified in the Contract (“Assessment Point”).

  - The required KPIs are set out in the table below:

| No. | Description | Method and frequency of assessment | Charges Rebate (if applicable) | Proportion of overall KPI score |
| --- | --- | --- | --- | --- |
| 1 | 80% of CPD Champions are confident in their ability to deliver the CPD provided by the Supplier | Assessed by survey of CPD Champions produced by Supplier. Monitored at the end of training period for CPD Champions. | 2.5% of the annual Supplier charges | 30% |
| 2 | CPD training is delivered to the agreed number of CPD Champions in all the selected LAs, with no more than 5% of CPD Champions withdrawing from the Programme before July 2021. | Assessed by MI data provided by the Supplier and/or LAs. Monitored on a quarterly basis; assessed annually. This KPI will only measure withdrawals for reasons within the Supplier’s control (e.g. those leaving due to issues with programme quality or appropriateness of the programme to their needs) | 0.5% of the annual Supplier charges | 10% |
| 3 | 80% of CPD Champions are confident that the CPD provided to them covers key subject content relating to early language, literacy and numeracy. | Assessed by survey of CPD Champions produced by Supplier Monitored on a quarterly basis; assessed at the end of the training period for CPD Champions. | 2% of the annual Supplier charges | 25% |
| 4 | All CPD Champions identified are provided with at least 45 hours of training provided for each CPD Champion, by 31 May 2020. | Assessed by MI data provided by the Supplier after conclusion of the CPD Champion training phase 31 May 2020. | 2% of the annual Supplier charges | 25% |
| 5 | 80% of CPD Champions are confident that the follow-up support provided by the Supplier after the initial training period Supplier has been high-quality and enabled them to effectively cascade CPD activity to Settings. | Assessed by survey of CPD Champions produced by Supplier. Monitored on a quarterly basis; assessed at the end of the training period for CPD Champions. | 0.5% of the annual Supplier charges | 10% |

5.3	The Supplier will be expected to meet/comply with all Service Levels as set out in the table below:

| Service Level | Measure | Compliance |
| --- | --- | --- |
| Reporting and Meetings | Monthly reporting: submit a monthly programme spending report by the third Business Day of the month, including any exception events within this report. Using templates provided by DfE. The Programme risk register should be reviewed and shared monthly. Quarterly progress reporting: submit a quarterly progress report covering delivery against milestones, participant feedback on the training, feedback on the CPD Champions’ cascade of CPD activity and improvement measures taken as a result of issues identified. | 100% - DFE monitoring |
|  | Contract Management meetings – monthly. |  |
|  | Programme Board meetings – quarterly. |  |
|  | Development and operations meetings – as required. |  |
| Administration/Communication | In delivering the Services offer a responsive and supportive service to participants and partners. Respond to 100% of queries and correspondence within 3 Business Days of receipt. |  |
| Finance | Ensure that valid invoices are submitted to DFE within 10 Business Days of the end of the relevant charging period/completion of the activity. |  |
| Commercial Management | Ensure that Change Control Notes are signed by both Parties prior to any additional work being undertaken (DFE or Contractor to ensure paperwork is issued in a timely fashion when change required). |  |
| Complaints | Ensure that all administrative Personnel are aware of and abide by relevant complaints procedures. |  |
|  | Main management contact to report all complaints orally and in writing to DFE within 3 Business Days. Main management contact to respond to all complaints orally and in writing, copying in DFE within 5 Business Days. |  |
| Records and surveys | Ensure that all records are maintained and kept up to date throughout the Term. Records must be updated within 5 Business Days of a request being made or an event taking place (subject to system availability). |  |
|  | Support the DFE to ensure appropriate surveys are completed throughout the Term. |  |
| Delivery | Supply appropriate equipment to support the delivery of the Services at any face to face events. | 100% - event surveys |
|  | Suitability of venue: events take place in venues and facilities which are relevant to the day. |  |
|  | Delivery of the Programme against the dates identified in Schedule 5 (Implementation Plan). |  |
|  | Training for CPD Champions shall take place in rooms which are suitable for the size of groups and set up in the style appropriate to the event |  |
| Workshop Events | ICT should be adequate and meet the minimum specification of the course. |  |
|  | Refreshments must be provided and where overnight accommodation is required the facilities must comply with the venue specification. |  |
| Evaluation | Contribute to the evaluation of the effects of its delivery by reviewing Service User satisfaction, learning outcomes for CPD Champions, improvements in practice in CPD Champions’ Settings, and the participation in impact studies produced by the Third Party Evaluator as required. | 100% - DFE monitoring |

# SECTION 4

# Standard Selection Questionnaire (SSQ)

Instructions

  - All sections of the SSQ must be fully completed even if you are an existing

Supplier of the Department or have made previous submissions or submitted tenders to the Department. It will not be sufficient to refer to earlier or other submissions or tenders. All questions must be answered in English.

  - Please ensure that you answer all the questions, where stated please ensure your answer is limited to an appropriate length. Unless instructed otherwise, when answering the questions please give details that specifically relate to your company, not to the whole of the group if your company forms part of a group. If you consider that a question is not relevant or applicable to your company, you should enter NOT APPLICABLE along with the reason or reasons why.

  - You should ensure that all enclosures and supporting documents are submitted as per the instructions on the e-tendering Portal. Failure to include attachments could result in your SSQ being rejected. Please do not include promotional material, company annual reports or general marketing material for your company, either as answers to any of the questions or for any other reason.

  - The Department will not enter into detailed discussion of the requirements at this stage. However, if the Department considers any question or request for clarification to be of material significance, both the query and the response will be communicated, in a suitably anonymous form, to all suppliers who have responded. All responses received and any communication from Suppliers will be treated in confidence.

  - If you respond "no" to any of the questions in this section (without providing, where applicable, sufficient explanation) the Department reserves the right to award a “fail” and reject your bid. Bids so rejected will not be assessed further and will be removed from the procurement.

Queries and Clarifications

  - All queries and clarifications must be submitted via the e-Tendering Portal online message board. Written responses will be provided to all suppliers via this message board, the identity of suppliers raising the queries will be confidential. Suppliers must keep their contact details up to date on the Portal or they will be unable to receive communications from the Department.

  - The Department will respond to all clarification queries received by midday on 21 January 2019. Best endeavours will be made to respond to queries received after this date; however a response cannot be guaranteed.

SSQ Submission

  - The deadline for the receipt of the completed questionnaire is 14 February 2019 - midday.

  - The Online Technical Envelope has a space in which each individual requested document can be uploaded. If more than one document is requested in an answer, please zip the files into a folder using Winzip and then upload the Winzipped folder in the space provided for you to supply more than one document.

  - You should wherever possible restrict the size of any attachment to 5MB.

  - All completed SSQs must be uploaded via the Department’s online Portal. To attach additional documents you wish to submit as part of your return, click the 'Attach Documents' button. NOTE: Large files may take some time to upload. When you have completed all the above steps and are ready to submit your SSQ return, click ‘Submit Return’.

  - Completed SSQs may be submitted at any time before the closing date. However, you should note that if you wish to change a submitted SSQ then you will need to check that nothing else has changed before re-submitting. Please note that completed SSQs received after the closing time and date will be rejected.

# Potential Supplier Information and Exclusion Grounds: Part 1 and Part 2

  - The Standard Selection Questionnaire is a self-declaration, made by you (the potential Supplier), that you do not meet any of the grounds for exclusion. If there are grounds for exclusion, there is an opportunity to explain the background and any measures you have taken to rectify the situation (we call this self-cleaning).

  - A completed declaration of Part 1 and Part 2 provides a formal statement that the organisation making the declaration has not breached any of the exclusions grounds. Consequently, we require all the organisations that you will rely on to meet the selection criteria to provide a completed Part 1 and Part 2. For example, these could be parent companies, affiliates, associates, or essential sub-contractors, if they are relied upon to meet the selection criteria. This means that where you are joining in a group of organisations, including joint ventures and partnerships, each organisation in that group must complete one of these self-declarations. Sub-contractors that you rely on to meet the selection criteria must also complete a self-declaration (although sub-contractors that are not relied upon do not need to complete the self-declaration).

Supplier Selection Questions: Part 3

  - The procurement document will provide instructions on the selection questions you need to respond to and how to submit those responses. If you are bidding on behalf of a group (consortium) or you intend to use sub-contractors, you should complete all of the selection questions on behalf of the consortium and/or any sub-contractors.

  - If the relevant documentary evidence referred to in the Selection Questionnaire is not provided upon request and without delay we reserve the right to amend the contract award decision and award to the next compliant Tenderer.

Consequences of misrepresentation

  - If you seriously misrepresent any information in filling in the Selection Questionnaire, and so induce an authority to enter into a contract, there may be significant consequences. You may be excluded from the procurement procedure, and from bidding for other contracts for three years. If a contract has been entered into, you may be sued for damages and the contract may be rescinded. If fraud, or fraudulent intent, can be proved, you or your responsible officers may be prosecuted and convicted of the offence of fraud by false representation, and you must be excluded from further procurements for five years.

Notes for completion

  - The “Authority” means the contracting authority, or anyone acting on behalf of the contracting authority, that is seeking to invite suitable candidates to participate in this procurement process.

  - “You” / “Your” refers to the potential supplier completing this Standard Selection Questionnaire i.e. the legal entity responsible for the information provided. The term “potential supplier” is intended to cover any economic operator as defined by the Public Contracts Regulations 2015 (referred to as the “regulations”) and could be a registered company; the lead contact for a group of economic operators; charitable organisation; Voluntary Community and Social Enterprise (VCSE); Special Purpose Vehicle; or other form of entity.

  - Please ensure that all questions are completed in full, and in the format requested. If the question does not apply to you, please state ‘N/A’. Should you need to provide additional information in response to the questions, please submit a clearly identified annex.  The Authority reserves the right to reject for incomplete answers.

  - The Authority recognises that arrangements set out in section 1.2 of the Standard Selection Questionnaire, in relation to a group of economic operators (for example, a consortium) and/or use of sub-contractors, may be subject to change and will, therefore, not be finalised until a later date. The lead contact should notify the Authority immediately of any change in the proposed arrangements and ensure a completed Part 1 and Part 2 is submitted for any new organisation relied on to meet the selection criteria. The Authority will make a revised assessment of the submission based on the updated information.

  - For Part 1 and Part 2 every organisation that is being relied on to meet the selection must complete and submit the self-declaration.

  - All sub-contractors are required to complete Part 1 and Part 2.

  - For answers to Part 3 - If you are bidding on behalf of a group, for example, a consortium, or you intend to use sub-contractors, you should complete all of the questions on behalf of the consortium and/ or any sub-contractors, providing one composite Response and declaration.

  - The Authority confirms that it will keep confidential and will not disclose to any third parties any information obtained from a named customer contact, other than to the Cabinet Office and/or contracting authorities defined by the regulations, or pursuant to an order of the court or demand made by any competent authority or body where the authority is under a legal or regulatory obligation to make such a disclosure.

Part 1: Potential Supplier Information

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

| Section 1: Potential Supplier Information |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 1.1(a) | Full name of the potential supplier submitting the information. |  |
| 1.1(b) – (i) | Registered office address (if applicable). |  |
| 1.1(b) – (ii) | Registered website address (if applicable). |  |
| 1.1(c) | Trading status - public limited company. - limited company. - limited liability partnership. - other partnership. - sole trader. - third sector. - other (please specify your trading status). |  |
| 1.1(d) | Date of registration in country of origin. |  |
| 1.1(e) | Company registration number (if applicable). |  |
| 1.1(f) | Charity registration number (if applicable). |  |
| 1.1(g) | Head office DUNS number (if applicable). |  |
| 1.1(h) | Registered VAT number. |  |
| 1.1(i) - (i) | If applicable, is your organisation registered with the appropriate professional or trade register(s) in the member state where it is established? | Yes ☐ No ☐ N/A ☐ |
| 1.1(i) - (ii) | If you responded yes to 1.1(i) - (i), please provide the relevant details, including the registration number(s). |  |
| 1.1(j) - (i) | Is it a legal requirement in the state where you are established for you to possess a particular authorisation, or be a member of a particular organisation in order to provide the services specified in this procurement? | Yes ☐ No ☐ |
| 1.1(j) - (ii) | If you responded yes to 1.1(j) - (i), please provide additional details of what is required and confirmation that you have complied with this. |  |
| 1.1(k) | Trading name(s) that will be used if successful in this procurement. |  |
| 1.1(l) | Relevant classifications (state whether you fall within one of these, and if so which one) - Voluntary Community Social Enterprise (VCSE). - Sheltered Workshop. - Public service mutual. |  |
| 1.1(m) | Are you a Small, Medium or Micro Enterprise (SME)? | Yes ☐ No ☐ |
| 1.1(n) | Details of Persons of Significant Control (PSC), where appropriate: - Name; - Date of birth; - Nationality; - Country, state or part of the UK where the PSC usually lives; - Service address; - The date he or she became a PSC in relation to the company (for existing companies the 6 April 2016 should be used); - Which conditions for being a PSC are met; - Over 25% up to (and including) 50%, - More than 50% and less than 75%, - 75% or more. (Please enter N/A if not applicable) |  |
| 1.1(o) | Details of immediate parent company: - Full name of the immediate parent company. - Registered office address (if applicable). - Registration number (if applicable). - Head office DUNS number (if applicable). - Head office VAT number (if applicable). (Please enter N/A if not applicable) |  |
| 1.1(p) | Details of ultimate parent company: - Full name of the ultimate parent company. - Registered office address (if applicable). - Registration number (if applicable). - Head office DUNS number (if applicable). - Head office VAT number (if applicable). (Please enter N/A if not applicable) |  |

Please note: A criminal record check for relevant convictions may be undertaken for the preferred suppliers and the persons of significant in control of them.

Please provide the following information about your approach to this procurement:

| Section 1: Bidding Model |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 1.2(a) - (i) | Are you bidding as the lead contact for a group of economic operators? If yes, please provide details listed in questions 1.2(a) (ii), (a) (iii) and to 1.2(b) (i), (b) (ii), 1.3, Section 2 and 3. If no, and you are a supporting Tenderer please provide the name of your group at 1.2(a) (ii) for reference purposes, and complete 1.3, Section 2 and 3. | Yes ☐ No ☐ |
| 1.2(a) - (ii) | Name of group of economic operators (if applicable). |  |
| 1.2(a) - (iii) | Proposed legal structure if the group of economic operators intends to form a named single legal entity prior to signing a contract, if awarded. If you do not propose to form a single legal entity, please explain the legal structure. |  |
| 1.2(b) - (i) | Are you or, if applicable, the group of economic operators proposing to use sub-contractors? | Yes ☐ No ☐ |
| 1.2(b) - (ii) | If you responded yes to 1.2(b) - (i) please provide additional details for each sub-contractor in the following table: we may ask them to complete this form as well. Name. Registered address. Trading status. Company registration number. Head Office DUNS number (if applicable). Registered VAT number. Type of organisation. SME (Yes/No). The role each sub-contractor will take in providing the works and /or supplies e.g. key deliverables. The approximate % of contractual obligations assigned to each sub-contractor. |

Contact details and declaration

- I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

- I declare that, upon request and without delay I will provide the certificates or documentary evidence referred to in this document.

- I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

- I understand that the Authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

- I am aware of the consequences of serious misrepresentation.

| Section 1: Contact Details and Declaration |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 1.3(a) | Contact name |  |
| 1.3(b) | Name of organisation |  |
| 1.3(c) | Role in organisation |  |
| 1.3(d) | Phone number |  |
| 1.3(e) | E-mail address |  |
| 1.3(f) | Postal address |  |
| 1.3(g) | Signature (electronic is acceptable) |  |
| 1.3(h) | Date |  |

Part 2: Exclusion Grounds

Please answer the following questions in full. Note that every organisation that is being relied on to meet the selection must complete and submit the Part 1 and Part 2 self-declaration.

| Section 2: Grounds for Mandatory Exclusion |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 2.1(a) | Regulations 57(1) and (2) The detailed grounds for mandatory exclusion of an organisation are set out on this webpage, which should be referred to before completing these questions. Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below and listed on the webpage. |  |
|  | Participation in a criminal organisation. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
|  | Corruption. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
|  | Fraud. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
|  | Terrorist offences or offences linked to terrorist activities. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
|  | Money laundering or terrorist financing. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
|  | Child labour and other forms of trafficking in human beings. If Yes please provide details at 2.1(b) | Yes ☐ No ☐ |
| 2.1(b) | If you have answered yes to question 2.1(a), please provide further details. Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction, Identity of who has been convicted. If the relevant documentation is available electronically, please provide the web address, issuing authority, precise reference of the documents. |  |
| 2.2 | If you have answered Yes to any of the points above, have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self-Cleaning). | Yes ☐ No ☐ |
| 2.3(a) | Regulation 57(3) Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | Yes ☐ No ☐ |
| 2.3(b) | If you have answered yes to question 2.3(a), please provide further details. Please also confirm you have paid, or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

Please Note: The Authority reserves the right to use its discretion to exclude a potential supplier where it can demonstrate by any appropriate means that the potential supplier is in breach of its obligations relating to the non-payment of taxes or social security contributions.

| Section 3: Grounds for Discretionary Exclusion |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 3.1 | Regulation 57 (8) The detailed grounds for discretionary exclusion of an organisation are set out on this webpage, which should be referred to before completing these questions. Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation. |  |
| 3.1(a) | Breach of environmental obligations? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(b) | Breach of social obligations? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(c) | Breach of labour law obligations? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(d) | Bankrupt or is the subject of insolvency or winding-up proceedings, where the organisation’s assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(e) | Guilty of grave professional misconduct? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(f) | Entered into agreements with other economic operators aimed at distorting competition? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(g) | Aware of any conflict of interest within the meaning of regulation 24 due to the participation in the procurement procedure? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(h) | Been involved in the preparation of the procurement procedure? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(i) | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(j) | Please answer the following statements |  |
| 3.1(j) - (i) | The organisation is guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria. If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(j) - (ii) | The organisation has withheld such information. If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(j) –(iii) | The organisation is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015. If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.1(j)-(iv) | The organisation has influenced the decision-making process of the contracting authority to obtain confidential information that may confer upon the organisation undue advantages in the procurement procedure, or negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award. If yes please provide details at 3.2 | Yes ☐ No ☐ |
| 3.2 | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self-Cleaning) |  |

Part 3: Selection Questions

| Section 4: Economic and Financial Standing Note: The Authority intend to consult the Supplier Registration Service reports and other credit rating or equivalent reports in assessing a suppliers economic and financial standing –see para 1.3 and 1.4 of Section 2, Evaluation Overview |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 4.1 | Are you able to provide a copy of your audited accounts for the last two years, if requested? If no, can you provide one of the following: answer with Y/N in the relevant box. | Yes ☐ No ☐ |
|  | (a) A statement of the turnover, Profit and Loss Account/Income Statement, Balance Sheet/Statement of Financial Position and Statement of Cash Flow for the most recent year of trading for this organisation. | Yes ☐ No ☐ |
|  | (b) A statement of the cash flow forecast for the current year and a bank letter outlining the current cash and credit position. | Yes ☐ No ☐ |
|  | (c) Alternative means of demonstrating financial status if any of the above are not available (e.g. forecast of turnover for the current year and a statement of funding provided by the owners and/or the bank, charity accruals accounts or an alternative means of demonstrating financial status). | Yes ☐ No ☐ |
| 4.2 | A minimum level of economic and financial standing has been specified within the evaluation criteria for this procurement (see para 1.6 of Section 2; Evaluation Overview). Please self-certify by answering ‘Yes’ or ‘No’ that you meet the requirement set out. Do you have a minimum yearly turnover of at least £3.4m - equal to twice the estimated annual value of the contract (£1.7m)? | Yes ☐ No ☐ |

| Section 5: If you have indicated in the Selection Questionnaire question 1.2 that you are part of a wider group, please provide further details below: |  |  |  |
| --- | --- | --- | --- |
| Name of organisation |  |  |  |
| Relationship to the Supplier completing these questions |  |  |  |
| 5.1 | Are you able to provide parent company accounts if requested to at a later stage? |  | Yes ☐ No ☐ |
| 5.2 | If yes, would the parent company be willing to provide a guarantee if necessary? |  | Yes ☐ No ☐ |
| 5.3 | If no, would you be able to obtain a guarantee elsewhere (e.g. from a bank)? |  | Yes ☐ No ☐ |

| Section 6: Technical and Professional Ability |  |
| --- | --- |
| Question Number | This section has a pass threshold of a score of “3” or above per question. |
| 6.1 | Relevant experience and contract examples Please provide details of up to three contracts, in any combination from either the public or private sector, voluntary, charity or social enterprise (VCSE) that are relevant to our requirement. VCSEs may include samples of grant-funded work. Contracts for supplies or services should have been performed during the past three years. The named contact provided (from the relevant client/customer to which the Contract relates) should be able to provide written evidence to confirm the accuracy of the information provided below. Consortia Bids should provide relevant examples of where the consortium has delivered similar requirements. If this is not possible (e.g. the consortium is newly formed or a Special Purpose Vehicle is to be created for this contract) then three separate examples should be provided between the principal member(s) of the proposed consortium or Special Purpose Vehicle (three examples are not required from each member). Where the Supplier is a Special Purpose Vehicle, or a managing agent not intending to be the main provider of the supplies or services, the information requested should be provided in respect of the main intended provider(s) or sub-contractor(s) who will deliver the contract. If you cannot provide examples see question 6.3 |

|  | Contract 1 | Contract 2 | Contract 3 |
| --- | --- | --- | --- |
| Name of customer organisation |  |  |  |
| Point of contact in the organisation |  |  |  |
| Position in the organisation |  |  |  |
| E-mail address |  |  |  |
| Description of contract |  |  |  |
| Contract Start date |  |  |  |
| Contract completion date |  |  |  |
| Estimated contract value |  |  |  |

| 6.2 | Where you intend to sub-contract a proportion of the contract, please demonstrate how you have previously maintained healthy supply chains with your sub-contractor(s). Evidence should include, but is not limited to, details of your supply chain management tracking systems to ensure performance of the contract and including prompt payment or membership of the UK Prompt Payment Code (or equivalent schemes in other countries). |
| --- | --- |
| 6.3 | If you cannot provide at least one example for questions 6.1, in no more than 500 words please provide an explanation for this e.g. your organisation is a new start-up or you have provided services in the past but not under a contract. |
| 6.4 | In no more than 1000 words in total outline how you can demonstrate that your organisation, or key individuals employed by your organisation have: - Knowledge and experience of England’s early years education sector for children aged 0-5 - Experience of developing CPD content and delivering training to early years professionals at scale - Experience of operating cascade models of CPD activity - Capability and capacity to deliver CPD activity at a national level and scale - Previous experience of successful programme delivery in collaboration with Local Authorities - Capability and capacity to effectively project manage a national programme of this scale |

| Section 7: Modern Slavery Act 2015: Requirements under Modern Slavery Act 2015 |  |  |
| --- | --- | --- |
| Question Number | Question | Response |
| 7.1 | Are you a relevant commercial organisation as defined by section 54 ("Transparency in supply chains etc.") of the Modern Slavery Act 2015 ("the Act")? | Yes ☐ N/A ☐ |
| 7.2 | If you have answered yes to question 7.1, are you compliant with the annual reporting requirements contained within Section 54 of the Act 2015? If Yes, please provide the relevant url If No, please provide an explanation below | Yes ☐ No ☐ |

Additional Questions

Suppliers who self-certify that they meet the requirements to these additional questions will be required to provide evidence of this if they are successful at contract award stage.

| Section 8: Additional Questions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Question Number | Question |  | Response |  |
| 8.1 | Insurance |  |  |  |
| a. | Please self-certify whether you already have, or can commit to obtain, prior to the commencement of the contract, the levels of insurance cover indicated below: Employer’s (Compulsory) Liability Insurance = £5,000,000 Public Liability Insurance = £5,000,000 Professional Indemnity Insurance = £2,000,000 Product Liability Insurance = £2,000,000 *It is a legal requirement that all companies hold Employer’s (Compulsory) Liability Insurance of £5 million as a minimum. Please note this requirement is not applicable to Sole Traders. |  | Yes ☐ No ☐ |  |
| 8.2 | Suppliers’ Past Performance - (please refer to supplier selection guidance - this question should only be included by central government contracting authorities) |  |  |  |
| a. | Can you supply a list of your relevant principal contracts for goods and/or services provided in the last three years? See question 6.1 of this questionnaire. |  | Yes ☐ No ☐ |  |
| b. | On request can you provide a certificate from those customers on the list? |  | Yes ☐ No ☐ |  |
| c. | If you cannot obtain a certificate from a customer can you explain the reasons why? |  | Yes ☐ No ☐ |  |
| d. | If the certificate states that goods and/or services supplied were not satisfactory are you able to supply information which shows why this will not recur in this contract if you are awarded it? |  | Yes ☐ No ☐ |  |
| e. | Can you supply the information in questions a. to d. above for any sub-contractors [or consortium members] who you are relying upon to perform this contract? |  | Yes ☐ No ☐ |  |
| 8.3 | Compliance with Equality Legislation |  |  |  |
| For organisations working outside of the UK, please refer to equivalent legislation in the country that you are located. If you answer “yes” to any of the questions in this module, please provide, as a clearly identifiable appendix on the attachments tab a summary of the nature of the investigation and an explanation of the outcome of the investigation to date. If the investigation upheld the complaint against your organisation, please use the appendix to explain what action (if any) you have taken to prevent unlawful discrimination from reoccurring. You may be excluded if you are unable to demonstrate to the Authority’s satisfaction that appropriate remedial action has been taken to prevent similar unlawful discrimination reoccurring. |  |  |  |  |
| a. | In the last three years, has any finding of unlawful discrimination been made against your organisation by an Employment Tribunal, an Employment Appeal Tribunal or any other court (or in comparable proceedings in any jurisdiction other than the UK)? |  | Yes ☐ No ☐ |  |
| b. | In the last three years, has your organisation had a complaint upheld following an investigation by the Equality and Human Rights Commission or its predecessors (or a comparable body in any jurisdiction other than the UK), on grounds or alleged unlawful discrimination? |  | Yes ☐ No ☐ |  |
| c. | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? |  | Yes ☐ No ☐ |  |
| 8.4 | Environmental Management |  |  |  |
| a. | Has your organisation been convicted of breaching environmental legislation, or had any notice served upon it, in the last three years by any environmental regulator or authority (including local authority)? If your answer to the this question is “Yes”, please provide details in a separate clearly identifiable Appendix on the attachments tab of the conviction or notice and details of any remedial action or changes you have made as a result of conviction or notices served. The Authority will not select Supplier(s)/Tenderer(s) that have been prosecuted or served notice under environmental legislation in the last 3 years, unless the Authority is satisfied that appropriate remedial action has been taken to prevent future occurrences/breaches. |  | Yes ☐ No ☐ |  |
| b. | If you use sub-contractors, do you have processes in place to check whether any of these organisations have been convicted or had a notice served upon them for infringement of environmental legislation? |  | Yes ☐ No ☐ |  |
| 8.5 | Health and Safety |  |  |  |
| a. | Please self-certify that your organisation has a Health and Safety Policy that complies with current legislative requirements. |  | Yes ☐ No ☐ |  |
| b. | Has your organisation or any of its Directors or Executive Officers been in receipt of enforcement/remedial orders in relation to the Health and Safety Executive (or equivalent body) in the last 3 years? If your answer to this question was “Yes”, please provide details in a separate Appendix of any enforcement/remedial orders served and give details of any remedial action or changes to procedures you have made as a result. The Authority will exclude Tenderer(s) that have been in receipt of enforcement/remedial action orders unless the Tenderer(s) can demonstrate to the Authority’s satisfaction that appropriate remedial action has been taken to prevent future occurrences or breaches. |  | Yes ☐ No ☐ |  |
| c. | If you use sub-contractors, do you have processes in place to check whether any of the above circumstances apply to these other organisations? |  | Yes ☐ No ☐ |  |
| Programme Specific Mandatory Requirements |  |  |  |  |
| 8.6 | Cyber Essentials and Data Security |  |  |  |
| In consultation with industry, the Government has developed the Cyber Essentials Scheme. The Cyber Essentials Scheme defines a set of controls which, when properly implemented, provides organisations with basic protection from the most prevalent forms of threats that come from the internet. The Government requires all Suppliers/Tenderers bidding for certain sensitive and personal information handling contracts to be certified against the Cyber Essentials scheme. It is mandatory for new Central Government contracts, which feature characteristics involving the handling of personal data and ICT systems designed to store or process data at the OFFICIAL level of the Government Security Classifications scheme to comply with Cyber Essentials requirements. You should make yourself aware of Cyber Essentials and the requirements for the appropriate level of certification “or equivalent”. |  |  |  |  |
| a. | In relation to the Services required, please confirm whether or not you comply with one of the following criteria: (i) You have a current and valid Cyber Essentials certificate which has been awarded by one of the government approved Cyber Essentials accreditation bodies within the most recent 12 months; OR (ii) You have not got a current and valid Cyber Essentials certificate which has been awarded by one of the government approved Cyber Essentials accreditation bodies but you are working towards gaining it, and will be in a position to confirm that you have been awarded a current and valid Cyber Essentials certificate by one of the government approved accreditation bodies within 6 months of the commencement date of the Agreement or at a later date when you receive sensitive and personal information with regard to the Services; OR (iii)You have not got a current and valid Cyber Essentials certificate which has been awarded by one of the government approved Cyber Essentials accreditation bodies, but you can demonstrate (or, will be able to demonstrate within 6 months of the commencement date of the Agreement) that your organisation meets the technical requirements prescribed by the Cyber Essentials Scheme as detailed in the following link: https://www.cyberstreetwise.com/cyberessentials/files/requirements.pdf |  | Yes ☐ No ☐ |  |
| b. | AND that you can provide evidence of verification by a technically competent and independent third party (which verification has taken place within the most recent 12 months) that your organisation demonstrates compliance with Cyber Essentials technical requirements; OR (iv)Your organisation is exempt from complying with the requirements at questions 12.01(i), 12.01(ii) and 12.01(iii) because your organisation conforms with the ISO27001 standard and the Cyber Essentials requirements have been included in the scope of that standard, and verified as such and the certification body carrying out this verification is approved to issue a Cyber Essentials certificate by one of the government approved Cyber Essentials accreditation bodies referred to in 12.01(i). Any equivalent evidence must be verified by a technically competent and independent third party. |  | Yes ☐ No ☐ |  |
| c. | If you are unable to answer Yes to 8.6 a & b, please give further details and reasons why below. |  |  |  |
| The successful Supplier/Tenderer will be required to provide evidence of Cyber Essentials certification “or equivalent” (i.e. demonstrate they meet the five technical areas the Cyber Essentials Scheme covers) prior to contract award. The successful Supplier/Tenderer will be required to secure and provide evidence of Cyber Essentials or re-certification “or equivalent” (i.e. demonstrate they meet the five technical areas) on an annual basis. Details of certification bodies are available at: https://www.cyberstreetwise.com/cyberessentials |  |  |  |  |
| Data Security Standards The contract requires the holding or processing of personal data and/or OFFICIAL data and so the successful Supplier/Tenderer will need to satisfy the Authority that it can comply with the Authority’s security standards, which are set out in the draft contract, which forms part of the ITB (see Statement of Requirement – List of Attachments). |  |  |  |  |
| e. | If you are successful in this procurement process, do you agree to comply with the Government’s Data Security Standards and to work with the Authority to facilitate the Authority’s compliance with the Government’s Data Security Standards throughout the life of the contract? If your answer to this question is, “No”, you will be excluded from further participation in this procurement process. |  | Yes ☐ No ☐ |  |
| Government Security Classifications All Supplier/Tenderers should make themselves aware of the Government Security Classifications (GSC) and identify any potential impacts in their bid, as the protective marking and applicable protection of any material passed to, or generated by, you during the procurement process or pursuant to any contract awarded to you will be subject to the GSC. The link below to the Gov.uk website provides information on the GSC: https://www.gov.uk/government/publications/government-security-classifications |  |  |  |  |
| f. | If you are successful in this procurement process, do you agree to comply with the Government’s Security Classifications and to work with the Authority to facilitate the Authority’s compliance with the Government’s Security Classifications throughout the life of the contract? If your answer to this question is, “No”, you will be excluded from further participation in this procurement process. |  | Yes ☐ No ☐ |  |
| Transparency The Government’s transparency principles require public procurers proactively to disclose contract and related information that may previously have been withheld on grounds of commercial confidentiality. This presumption in favour of disclosure of information requires procurers to set out in advance of a contract award, the types of information to be disclosed to the public, and then to publish that information in an accessible format. These principles are published at: https://www.gov.uk/government/publications/transparency-of-Supplier/Bidders-andgovernmentto-the-public |  |  |  |  |
| g. | If you are successful in this procurement process, do you agree to comply with the Government’s transparency principles and to work with the Authority to facilitate the Authority’s compliance with the Government’s transparency principles throughout the life of the contract? If your answer to this question is, “No”, you will be excluded from further participation in this procurement process. |  | Yes ☐ No ☐ |  |
| Programme Specific Questions (Please complete this section in full) |  |  |  |  |
| 9.1 |  | Does your organisation or consortium have the capacity to deliver against the specified delivery timescales (programme development/design to begin by May 2019 and 400 CPD Champions to be trained by 31 May 2020? |  | Yes ☐ No ☐ |  |
| 9.2 |  | Does your organisation or consortium have experience of working in collaboration with pre-reception early years practitioners and Local Authorities? |  | Yes ☐ No ☐ |  |
| 9.3 |  | If you are delivering this Contract as part of a consortium, does your organisation agree to enter into binding agreements with other consortium members to ensure service delivery and compliance with all contractual requirements and expectations and due diligence declarations are met? Tenderers are reminded that the lead organisation will be the single contract holder and will have overall accountability for service delivery and meeting the contract Key Performance Indicators (KPIs). |  | Yes ☐ No ☐ |  |
| 9.4 |  | Does your organisation agree to engage with a third party evaluation contractor? |  | Yes ☐ No ☐ |  |
| 9.5 |  | Does your organisation agree to put 7.5% of the annual projected Supplier Charges against the non- or under-achievement of the KPIs subject to the “Charges Rebate”? |  | Yes ☐ No ☐ |  |
| 9.6 |  | All prospective Tenderers are required to register (unless already registered) with the Supplier Registration Service at https://supplierregistration.cabinetoffice.gov.uk Please confirm that you have registered with the Supplier Registration Service |  | Yes ☐ No ☐ |  |

Department for Education (2015) (EPPSE 3-16+). How pre-school influences children and young people's attainment and developmental outcomes over time.

Read On. Get On. (2014) Read On. Get On. How reading can help children escape poverty. National Literacy Trust

Save the Children (2016) Early language development and children’s primary school attainment in English and Maths

Department for Work and Pensions (2006) ‘Bucking the trend’: What enables those who are disadvantaged in childhood to succeed later in life? http://dera.ioe.ac.uk/7729/1/WP31.pdf

Sutton Trust (2010), Low income and early cognitive development in the U.K. https://www.suttontrust.com/wp-content/uploads/2010/02/Sutton_Trust_Cognitive_Report-2.pdf

DfE (2015) EPPSE (Ibid.)

Bonetti & Brown, EPI (2018) Structural elements of quality early years provision: A review of the evidence

Melhuish & Gardiner (2017)  Study of Early Education and Development (SEED): Study of Quality of Early Years Provision in England

EEF Early Years Evidence Summary

NSW Dept. of Education (2018), Fostering Effective Early Learning Study

DfE (2017) SEED research report: Good Practice in Early Education

The selected Local Authorities and the rationale for their selection is below at page 59.

As a minimum we would expect CPD Champions to be level 3 qualified.

To clarify, the Supplier must ensure that overhead costs represent accurate marginal costs relative to the overall organisational costs within the categories listed here; the Authority may request evidence to verify any quoted marginal overhead costs.

For the list of the grounds of exclusion please see: https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/551130/List_of_Mandatory_and_Discretionary_Exclusions.pdf

See PCR 2015 regulations 71 (8)-(9)

See EU definition of SME https://ec.europa.eu/growth/smes/business-friendly-environment/sme-definition_en

UK companies, Societates European (SEs) and limited liability partnerships (LLPs) will be required to identify and record the people who own or control their company. Companies, SEs and LLPs will need to keep a PSC register, and must file the PSC information with the central public register at Companies House. See PSC guidance.

Central Government contracting authorities should use this information to have the PSC information for the preferred supplier checked before award.

See Action Note 8/16 Updated Standard Selection Questionnaire

Procurement Policy Note 04/15 Taking Account of Suppliers’ Past Performance