## Clarification Log
Attachment 8 – Supplier Clarification Log Template - DWP LSS2
Question ID | Date Received | Question | Response | Date Answered
1 | 15/12/2020 Pre ITT consulation session | Could you share with us the details of the integrators CAFM system | The integrators CAFM system currently is VX Maintain. There will be additional information in the ITT document pack | 2020-12-15
2 | 15/12/2020 Pre ITT consulation session | Are there any costs that we need to account for for using the Integrators system, such as handhelds, licence fees | Licences are not required. Sodexo provide vxM and Suppliers can have as many user accounts as required (their responsibility to manage starters and leavers on the system). Bidders will need to determine whether handhelds are required as appropriate to their proposal. | 2020-12-17
3 | 15/12/2020 Pre ITT consulation session | Is there are opportunity to develop an API proving two communications between the integrator's system and our own? | In theory yes but given the short mobilisation period of 2 months it might be impractical to do this. | 2020-12-15
4 | 15/12/2020 Pre ITT consulation session | Given there is a lot of emphasis being placed on the Integrators' CAFM. What consideration has been given to the fact that the integrators Contract is also coming to market? | Obviously difficult to assess at this stage. The LSS2 contract end date has been designed to coincide with the TFM Contract end date so we have the opportunity to re-think our overall FM Strategy. Until this happens it is difficult to say. The Department recognises that the CAFM system could change during the lifetime of this contract although there are no current plans to do so. | 2020-12-15
5 | 15/12/2020 Pre ITT consulation session | In the absence of site visits would you be able to do virtual site tours of some select sites to give the bidders a feel for the estate? | Unfortunatley, virtual site visits will not be possible at the moment. | 2021-01-04
6 | 15/12/2020 Pre ITT consulation session | If we were successful on this contract would it potentially exclude us from participating in the Integrator procurement process? | At this stage yes but this might change if our overall FM strategy and delivery model changes in the future | 2020-12-15
7 | 15/12/2020 Pre ITT consulation session | Are you able to update on the process that you started this time last year that had engagement sessions in february this year, has that now been delayed and is this a pre cursor to a wider FM deal | The process has been delayed. The future strategy for all FM services is under review and being developed. | 2020-12-15
8 | 15/12/2020 Pre ITT consulation session | NG Bailey started the contract in Dec 2019, do the DWP have an option to extend their contract? | There are no options to extend in the contract but the option to extend can be considered depending on the circumstaces. | 2020-12-15
9 | 15/12/2020 Pre ITT consulation session | You have said you are going to use special terms does that mean that most elements will be classed as Non Standard as far as teh CCS Cost model is concerned | We are clarifying with CCS colleagues about how the use of special terms affects the costing proposals bidders submitted in order to secure a place on the framework and will confirm. 06/01/21 As per clause 1.1 of Framework Schedule 3 for non standard services, the Framework Maximums for the service line are not applicable, however the maximum rates captured as a % (eg Overhead, Profit and Billable Works uplifts) within the suppliers bid to be placed on the framework still apply. Checking these areas of the bid against the framework maximums will form part of the bid compliance checks. | 2020-12-15
10 | 15/12/2020 Pre ITT consulation session | If possible at the supplier session on the 11th January could we get a demonstration of how the supplier will need to interact with the Integrator's CAFM system. Suppliers tend to cusomtise them to their needs so it would be great to have an insight as to how we interact with it. | This might be possible. We should be able to provide process flow diagrams as a minimum to illustrate interactions with the CAFM and handoffs. | 2020-12-15
11 | 2020-12-21 | Could you please confirm what the deadline for clarification questions is for this procurement? | The deadline for clarification questions is the 20th January 2021. This is stated in A2 How to bid document in point 1.2.5 | 2020-12-23
12 | 2020-01-31 | We note that reactive tasks are not included, could you please advise who carries these out, we assume Interserve(Mitie). Also could you share with us the process for differentiating between reactive and Remedial tasks please, particularly around those that are included within the IRT | Reactive tasks are completed by our TFM supplier Mitie Limited. A remedial task is identified by the person completing the PPM task. A reactive is generated by a call to the help desk when a need for maintenance is observed eg door off a hinge. Only remdials below £500 in the urgent critical and important priorities are included in the IRT. Please refer to A3F DWP Remedial Specification Document. | 2021-01-04
13 | 2020-01-31 | Can you please provide a breakdown of remedial works, split by volume/value and again by region. Also those that are included within the IRT and those outwith? | The data is contained in the A3A Deliverable Matrix under tab Remedials works (reactive works). The data includes region, value, volume and priority allowing for bidders to conduct further analysis. | 2021-01-04
14 | 2020-01-31 | We have reviewed the TUPE list and note that there are very few engineers on the list, we assume this may be down to the incumbent supplier sub-contracting. Is there likely to be any 2nd tier TUPE implications for this contract, if so could you provide details? | The TUPE list consists of all those staff who are likely to be in scope of TUPE. | 2021-01-04
15 | 2020-01-31 | Could you please provide regional requirements for the works, at present the data is fairly high level? This will enable us to assess our manpower requirements on a regional basis. | The site identification in the Portfolio Characteristics tab (in column MASTER) of the A3A Deliverable Matrix can be cross reference to identify locations by postcode, city, etc. This will allow bidders to allocate to their own regions . The site identification in each tab is under the following heading: PPM requirements = SITE_NAME Asset Collection = Site no. Remedial works (reactive works) = Site Number | 2021-01-04
16 | 2020-01-31 | Could you provide the number of locations in each of the asset classes- i.e. is lifts across 103 sites or is A/C across 400 sites etc.? | This information is provided to allow bidders to conduct their own analysis. | 2021-01-04
17 | 2020-01-31 | Is the estate currently compliant? If not could you provide details of the backlog and the expected contractual requirements for the start of the contract? | Yes, the estate is compliant. We would expect a remedials backlog of 1 month to be passed across to the new contract. This is in the region of 400 to 500 remedial tasks. | 2021-01-04
18 | 2020-01-31 | On the PPM list, please can you confirm whether the 'Number of PPM's' is the number of PPM visits, or the number of assets requiring a PPM visit, i.e. are we to assume that the asset count against each of the PPM's is 1? | The detailed list in document A3A tab PPM Requirement lists the tasks. The number of PPM visits per task is identifed in column N. The number of assests can be indentified in the Asset Collection tab, column J. | 2021-01-04
19 | 2020-01-31 | Do you have a current condition survey or asset survey, if so can you share? If not will we have the opportunity to carry this out during the initial months of the contract? | The asset collection data contains the full asset register. We do not envisage the successful will need to conduct an assest condition or asset verfication survey as part of this contract. | 2021-01-04
20 | 2020-01-31 | We note that Interserve had an existing relationship with DWP through the Integrator, as they have now been acquired by Mitie, can you confirm whether Mitie will be allowed to bid for this element of the contract? | Yes, Mitie will be allowed to bid for this contract. | 2021-01-04
|  | FURTHER CLARIFICATION FROM THE BUYER - ISSUED VIA GLOBAL EMAIL VIA DWP ESOURCING PORTAL | For further information, in tab “Asset Collection” column AC, Asset Condition of document A3A, the letter classification is as per the CIBSE Guide M definitions. | 2021-01-05
21 | 2021-01-05 | In relation to AQA4 - apologies if we have missed it but we cannot see that we have the DWP i supplier questionnaire that we are required to complete. In addition, the guidance at the end of AQA4 repeats the guidance for AQA2 and makes reference to signing the Call-off contract. | The Security Questionnaire is has been uploaed and placed in the attachements visbile to suppliers. The guidance should read:Providing a YES response means you have completed the and uploaded the DWP iSupplier Questionnaire for further review by the DWP security team. If you select NO (or do not answer the question) to indicate that you have completed and uplaoded the DWP information Security Questionnaire and you may be excluded from further participation in this competition. | 2021-01-05
22 | 2021-01-05 | In relation to AQB1, the question reads: The tasks you will undertake and the clear milestones you will work towards to ensure the required Services are fully operational at each Affected Property by the Service Commencement Date. including any; Should there be any further points following "including any; | No, the "including any" should be ignored | 2021-01-05
23 | 2021-01-05 | Would it be possible to split the contract into regional lots rather than national? This would provide more competition by enabling smaller contractors to take part | The splitting of the requirement was considered by the Department but was rejected prior to approaching the Market for operational and business reasons. | 2021-01-05
24 | 2021-01-05 | Would it be possible to provide further clarification of the event details for the supplier presentation/briefing set to take place on the 11th January? | The event on the 11th is to discuss the requirement in more detail and to clarify how bids should be presented back to the department eg. completion of the response template etc. The opportunity to ask questions at the event will also be given. | 2021-01-05
25 | 2021-01-05 | Can you please advise where we can locate the Information Security Questionnaire (iSupplier Questionnaire)? | The Security Questionnaire is has been uploaed and placed in the attachements visbile to suppliers. | 2021-01-05
26 | 2021-01-05 | Re document: A3B DWP LS2 Standards & Processes DWP Service Requirements; Section 4 Helpdesk Response Times, and, Section 5.0 Service Delivery Response Times. Can you confirm that these KPIs do not apply to this contract? | The Standards and processes document is from the CCS framework. We can confirm that all response times and KPI mentioned in Section 4 and Section 5 do not apply to this contract. The KPI and response times are detailed within the contract and specification documents. | 2021-01-05
27 | 11/01/2021 Mid ITT presentation | Where there are alternative maintenance proposals (other than SFG20), can you advise on how you would like this reflected within the technical and financial submissions | Please detail any alternative maintenance proposals in the question relating to PPM AQB3. | 2021-01-11
28 | 11/01/2021 Mid ITT presentation | How do you differentiate between a reactive task and a remedial task for example if a lift is awaiting a remedial task but a building user calls it out as a breakdown, does that go to LSS supplier or wider FM contractor? | Remedial tasks are identified by the engineer as part of the PMM visit. Reactive tasks can be identified by the occupants of a building by reporting to the helpdesk and an engineer as part of the "don’t walk by" H&S initiatives. The integrator will look at the asset to establish if there is any outstanding remedials and allocate to the relevant supplier dependant on the issue. | 2021-01-11
29 | 11/01/2021 Mid ITT presentation | Variable pricing, with regards to the management costs, does this have to be as CCS frameworks ? | Management costs covering and remedial tasks covered in the IRT must comply with upper prices cap as per Framework prices For management of billable remedial activity the management costs arising from roles contained on the Billable Works tab on the Pricing Matrix are a seperately priced element and therefore CCS framework capped prices do not apply. | 2021-01-11
30 | 2021-01-12 | We recognise the importance of compliance to DWP. We understand that as currently drafted a Critical Failure Event could be triggered by the failure of a supplier to provide a single PPM task marked “S” on the deliverables matrix. This has significant impact in terms of KPI Credits, the KPI Ratchet and risk of termination. Given that more than 80% of PPM tasks are marked “S” we are keen to understand fully what “provide” means in this context and how a Critical Failure Event would be triggered. If a single PPM task marked “S” was not delivered by the target date would this represent a Critical Failure Event? If it was not delivered by the target date, but was delivered in the month planned would this represent a Critical Failure Event? If it was not delivered by the target date but was delivered within a specified period of time (say a month, or perhaps three months) would this represent a Critical Failure Event? | "Provide" in this context means completion of the PPM task by the due date on the PPM Plan. The Critical Failure event would be triggered if the "S" PPM task is not completed by the due date The Contractor will have a full timetable of when PPMs need to be completed. The PPMs can be scheduled up to 14 days prior to when the PPMs are due, providing a window for completion. We would anticipate the supplier to maximise the utilisation of this window so a Critical Failure event is not generated. We are aware of the many factors which can affect delivery of a PPM and this has been accommodated by the creation of the Permitted Event and Buyer Cause clauses. | 2021-01-13
31 | 2021-01-12 | Our understanding of Permitted Events and Buyer Cause includes the failure of the supplier to deliver a PPM task due to factors outside the supplier’s control, such as being turned away from site by local DWP representatives due to local DWP operational requirements, assets not being present as indicated by the DWP CAFM system and access not being provided to the relevant equipment. We would be grateful if the Department could confirm that such examples would be considered Permitted Events. | It is not possible to provide an exhaustive list of Permitted Events and Buyer Cause examples as each instance will be considered as and when they arise taking into account the task history and other information available, however bidders should be reassured that these clauses have been specifically designed so the supplier is not unfairly held to account for issues beyond their control/influence. | 2021-01-13
32 | 2021-01-12 | We understand that whilst the Supplier will have relief from KPI Credits in such instances (QID 31) they will not be able to charge for any costs associated with such abortive visits. We would be grateful if the Department could confirm this understanding and that they wish bidders to accept the risk for situations for where the visit cannot be completed for reasons outside of their control. | It is correct that the DWP shall not apply KPI Credits where the Supplier has failed to complete a PPM Task by the relevant date and/or any item of Remedial Work by the relevant Remedial Work Completion Date due to the occurrence of a Permitted Event. It is also correct that the Supplier shall not be paid any Charges attributable to any Permitted Event as the intention is that this excludes Buyer Cause. However, it is clear in the contract (see the definition of Disallowed Costs and Schedule 5) that the Suppler may be entitled to a fair and reasonable increase in the Category C Remedial Work Fee and/or the Category D Remedial Work Fee where such increase was caused or contributed to by a Buyer Cause and the Supplier has notified the Buyer of such Buyer Cause within 2 working days of becoming aware. In addition, in relation to the Category B Remedial Work Fee and the Category E Remedial Work Fee, the Supplier may be able to recover their costs incurred due to the occurrence of a Buyer Cause provided that they have complied with the notification requirements set out in the definition of Disallowed Costs (and the remaining provisions of the contract will also apply). Bidders should also note the provisions in clauses 4.10 and 5 regarding relied for Supplier Non-Performance due to a Buyer Cause. | 2021-01-15
33 | 2021-01-12 | £250 charge for failure to Complete a PPM task or Remedial task We note that the Department wishes to be able to levy a £250 charge if a PPM or Remedial task is not Completed by the target time. It appears that this may be a case of double jeopardy as there is also potentially an effect on the KPI measurement leading to a KPI penalty as well. We would be grateful if the Department could confirm it is their intention that the Supplier would be liable for a £250 charge for each and every PPM or Remedial task that did not meet its target timescale, over and above any deductions associated with a KPI Credit? | Clause 10.11 of the Special Terms lays out a series of remedies for failure to deliver on a PPM / Remedial deliverable. The £250 charge is where the Supplier has failed to Complete the PPM/ Remedial delieverables after having being given the option to remedy but has failed to complete to the revised timescales. This means that the first failure does not attract a £250 charge. The first and any subsequent failure to deliver will be used in the KPI measurement calculations. | 2021-01-13
34 | 2021-01-12 | We note the definition of Remedial Work means any works required in relation to a PPM Task to ensure statutory compliance and/or proper functioning of the relevant Asset. • In instances where there are outstanding works that have arisen from PPMs (performed by others) or reactive works already logged against an asset, what is the process to ensure that the LSS2 IRT is not used for these tasks where the same issue is subsequently identified by the LSS2 provider performing a PPM task within the LSS2 scope? For example emergency light issues identified via monthly tasks or via a reactive call that is outstanding and subsequently identified by the LSS2 provider performing the annual emergency light PPM. | It is the intention that the IRT will be used for remedials directly arising from the PPM and not for reactive works and tasks which should be completed by other members of the supply chain. A process to manage this will be established during the mobilisation. | 2021-01-13
35 | 2021-01-12 | In instances where issues are identified that may have arisen from a failure (performed by others) to have performed a PPM or a failure to perform it to required standards, what is the process to ensure that the LSS2 IRT is not used for these outstanding works? | It is the intention that the IRT will only be used for remdials directly arising from PPM activity. Outstanding work will either be in the oustanding Remedial Plan if it was generated by a PPM visit or the reactive works plan both held on the CAFM. If there appears to be recurring issues with regard to previous interactions with the asset by other supply chain members this would need to be brought to the attention of the Integrator and Buyer to understand the scope and frequency of the issue before looking to remedy. | 2021-01-13
36 | 2021-01-12 | In instances where the LSS2 provider finds that an asset is not functioning at all and therefore a statutory task cannot be performed should a reactive job be logged by the LSS2 provider or should the LSS2 treat this as Remedial Work? For example, a refrigerated display cabinet is found to be not functioning at all. | A process for this scenario will be agreed with the integrator during mobilisation. The Integrator will be aware if the remedial or reactive work order has already been raised and will be able to advise. We reiterate that full replacements of assets are not in scope of this contract. | 2021-01-13
37 | 2021-01-13 | How out of hours working overtime is included in the pricing model With regards to A5A DWP LS2 Pricing Matrix (Final) “ PPM Pricing” tab, Column E, “Additional cost if the service needs to be delivered outside of core hours”. Values entered into these cells do not appear to carried forward to“Year1Deliverables” tab, therefore, these out of hours costs will not be included within the overall year 1 price. If it is the intention that additional out of hours costs are not to be included in the year 1 price, can you provide information / procedure on how these costs will be drawn down into the contract? Also, what value should we be entering into these cells in column E; it is not linked to column B “Number of PPMs” so, do we input the additional cost for the task and ignore the number of PPMs or should we be taking into account the number of PPMs and enter a value that takes the out of hours cost multiplied by number of PPMs? | The assumption in the pricing is that all works will be carried out in core hours and all bids will be evaluated on this basis. If a task is delivered out of hours the additional cost for that task provided in Colum E will be added to Column C to provide the charge for that deliverable. When entering values into Column E this is the additional price per PPM and should not be multiplied by the volume of PPMs for that task. | 2021-01-13
38 | 2021-01-13 | Delivery matrix virtual assets With regards to “A3A LS2 Deliverables Matrix all Lots, Asset collection” tab, within the worksheet you have an column heading “Taxonomy” within which there’s a description “Virtual Asset”. We note that there are no asset quantities for “Virtual Asset” with in column J, would it be right to assume that there are a number of asset within each asset description i.e. Distribution boards. If that is the case, can you advise how we should treat Virtual Assets when pricing, given your previous clarification response to CQ 19, to ensure we price for actual work required? | Where there is a zero against a virtual asset the volume information of the corresponding physical assets is contained in the Asset Collection tab of A3A LS2 Deliverables Matrix | 2021-01-13
39 | 2021-01-13 | Performance Bond We note the requirement for a Performance Bond at 10% of the contract value, for this do we assume the value indicated for the original term or the potential extended term? To obtain approval from our Bondsman we will require this confirmation and is an absolute value can be provided that would assist. | The performance bid will be for the original term. The absolute value will be based on the finanacial bid from the the winning supplier. This can only be confirmed once financial evaluation and the contract award has been completed. | 2021-01-13
40 | 2021-01-13 | Fire doors We note that in the Requirements tab of “A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm” some items are specified to be delivered to a different standard other than SFG20. Against 20.4 there is a comment – “Fire doors as Draft PPM (see Appendix xy)”. Can you please provide Appendix xy or tell us where this is located? | For the purposes of tender pricing assume that the fire doors will be maintained to SFG20. Further clarification of Fire Door Maintenance and Fire Risk Assessment requirements will be provided during the mobilisation period | 2021-01-15
41 | 2021-01-13 | Management Overhead (Work Package A - Contract Mgt) In DWP Client Presentation on the 11th January 2021, all bidders were informed that our management overhead % should not exceed the value within the individuals agreed CCS framework, however, “A7 DWP How to complete the Pricing Matrix” request that we “ Include the management overhead on the Pricing Variables Tab (as a percentage) to cover the cost of the management required for Work Package A necessary to deliver the following services. | We can confirm this is correct. | 2021-01-13
42 | 2021-01-13 | Are you able to share the presentation deck that you used on the event on the 11th with us? | The presentation has been added to the "Bid information" folder. | 2021-01-13
43 | 2021-01-18 | Please can you clarify that during due diligence if any variance is found between the assets within tab "asset collection" in "A3A DWP LS2 Deliverables Matrix all Lots (Final)" and what is on site then there will be a variation as per "special terms" 1.12? | 1.12 relates to impact of Due Dilligence. This can include discepancies of assets in the asset collection and assets on site and their impact on the Fixed Monthly Fee where these affect the volume of Remedial Work ( and therefore the IRT calculation) as per the Due Dilligence Information definition. | 2021-01-20
44 | 2021-01-18 | Please can you clarify what takes precedence in terms of pricing with regards to work package C between the PPM schedule and the asset quantities provided, these do not always align e.g. Distribution boards - Within "A3A DWP LS2 Deliverables Matrix all Lots (Final)" tab "PPM requirements" it shows 1,591 annual PPMs, which is mirrored in the price return, however tab "asset collection" states there are 206 in column J, or if the blanks are filled with a value of 1 there are 1,576. Fire risk assessments in the price return only show a PPM value of 3 where as in the deliverables "PPM requirements" tab there are 264. | For the purposes of tender pricing assume that the PPM numbers (shown in ‘A5A DWP LS2 Pricing Matrix (Final)’)are accurate | 2021-01-20
45 | 2021-01-18 | There appears to be a potential contradiction in the current clarification responses with regards to the management cost. Our understanding is that the management for PPM and remedials (excluding backlog) is part of the fixed fee. However within the "Pricing Matrix" the management overhead is applied as a percentage to the PPM and IRT cost. The PPM element we believe is variable and could therefore potentially decrease which within the pricing matrix would reduce our total management cost. Can you confirm that the value for the management overhead within our submission (rather than the %) is fixed independent of the volume of PPM and remedials? | Whilst the PPM is variable on a month by month basis it is envisaged that the annual value requirement for the PPM is fixed in accordance with the Statutory PPM requirement. On this basis please Refer "A7 DWP LS2 How to Complete the Pricing Matrix" which advises the following: Management Overhead (Work Package A - Contract Mgt) Include the management overhead on the Pricing Variables Tab (as a percentage) to cover the cost of the management required for Work Package A necessary to deliver the following services. • PPM Tasks (shown in PPM Pricing Tab (and Pricing Deliverables) • Mobilisation Cost • Remedial Task IRT • Cost of TUPE Change Note: the Management to deliver the Remedial Tasks arising from the PPM Tasks shall be priced separately and is detailed below) | 2021-01-20
46 | 2021-01-18 | The "Remedial task IRT" tab within the pricing matrix does not multiply the remedial charge per site by the number of sites, therefore the value which flows through to the "Total Charges" tab for the IRT cost will be a low value. When our management overhead as a % is then applied it won’t include a value reflective of our management cost, unless the percentage we apply gets uplifted accordingly, this may make it appear high at face value. Can you confirm this is your expectation for management %? | The IRT value should be the full value for the whole portfolio and should be calculated as "A7 DWP LS2 How to Complete the Pricing Matrix" which advises the following: "The cost for the Inclusive Repair Threshold shall be included on the “Remedial Task IRT” Tab. Labour and other costs should be included based on the Remedial volumes shown in Deliverables Matrix (“Remedial Works (Reactive Works)” Tab)." Note: A price should not be provided based on a breakdown by individual building | 2021-01-20
47 | 2021-01-18 | The pricing matrix and deliverable documents state emergency lighting is to be annual only, please can you confirm if this is correct? | We can confirm that the Tenderer should only price against the Prcing Matrix wich includes annual testing only. | 2021-01-20
48 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" we have been asked to use the "Remedial works (Reactive works)" tab data to inform our approach to the expected remedial volumes/costs. However there appears to be duplication of jobs for sites as you get many instances where the same job with the same value on the same day is raised multiple times e.g. Blackpool Warbreck House on the 11-03-2020 has many instances of the value £1,181.70. Can you confirm these are duplicates and should be removed? | Please assume for pricing purposes that the data is correct and contains no duplicates. Due Diligence for quantity of remedials will be assessed as defined in the Contract and at this stage the allowance for IRT will be adjusted (based on Tenderer assumptions and actual volumes) | 2021-01-20
49 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Remedial works (Reactive works)" tab in cell I1 it shows the total 12 month value for remedials to be £6,381m. This same value is used in the pricing matrix in table 3 in tab "total charges" cell I38 for the expected backlog remedial works value. Please can you clarify how these a would be the same value if the supplier will be carrying out these remedial works during year 1 of the contract? Or have none of the 2020 remedials been carried out and are therefore what will be passed over for completion in year 1 in addition to new remedials? | I38 is the "Assessed Value for Remedial Works during Contract" Year 1. This has been assessed using historical data available. It is not "Backlog" works; it is the assessed value of Remedial Works arising in a 12 month period. | 2021-01-20
50 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Portfolio characteristics" tab please could you clarify if we are to include the "pre-live" sites in our solution? | The "Portfolio Characteristics" were included to show location (for travel purposes) and core hours etc. If the Pre-live sites has an allocated PPM continue to price these PPM's and other appropriate costs for these sites; however we do not believe that many or any of the "pre-live sites" have associated PPM's. When the "pre-live sites" are added we will use your PPM rate to assess any additional costs for these sites. | 2021-01-20
51 | 2021-01-18 | Within the pricing matrix in tab "PPM pricing" there are no tasks associated with work package C10, please can you confirm this is correct? | There do not appear to be any "Automated Barrier Control System Maintenance" PPM's and we are therefore not expecting a price for any C10 tasks. In the event that an Automated Barrier asset is required to be maintained this will be a change to the contract | 2021-01-20
52 | 2021-01-18 | Within the pricing matrix in tab "remedial task irt" the cost per site is to be provided, please can you clarify the exact number of in-scope sites for the contract so this average per site can be established? | Please advise total IRT cost for the whole portfolio in Cell D20 and D21 We recognise that the heading shown in D19 is misleading ie "Cost per building" and this should be "Full Portfolio" as Cell D4 | 2021-01-20
53 | 2021-01-18 | Within the pricing matrix in tab "mobilisation" there are only two lines highlighted in yellow, please can you confirm we can use both tables in full? | Yes the tables can be used in full. | 2021-01-20
54 | 2021-01-18 | Within the pricing matrix in tab "billable works" in table 2 are we to include OH&P in our rates? Please can you also confirm that these are the rates which will be utilised in carrying out the backlog remedial works totalling £6.381m stated in the "total charges" tab table 3? | Rates in Table 2 should not include OH&P. The £6.381m is the volume of anticipated remedials works required per annum and not a backlog. The rates will be used where appropriate for the remedial task taking into account variables like complexity and length of task. | 2021-01-22
55 | 2021-01-18 | Just for absolute clarity please can you confirm that for Category A,B,C,D and E remedials the first £500 will sit with the supplier in all instances? | Category A is all contained within the IRT max of £500 per task With Category B, C and E the cost is greater than £500 and therefore the Supplier will bear the first £500 Category D "means that Remedial Work, which is categorised as Routine" and in this instance the Supplier recovers the full value of the works which are approved to proceed, as these are deemed to be advisory in nature and do not form part of the IRT calculation. | 2021-01-20
56 | 2021-01-18 | It is stated that fixed monthly fee and unit rates shall not increase during the contract period, please can you confirm this is correct i.e. year 2 is not indexed against inflation? | The initial term does not allow for any indexation increases. The issue of indexation can be discussed during any discussion on utilising any of the extension opportunities. | 2021-01-20
57 | 2021-01-18 | Within the current CQs there are several responses with regards to differentiating between reactives and remedials based on the integrators ability to report at an asset level within their cafm system, please can you clarify if this is the case? | It is anticipated that the Integrator solution will be able to identify the work outsanding on a particular asset and route work appropriately and avoid duplication and nugatory work. This can be further explored during mobilisation of the winning bidders solution. | 2021-01-20
58 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Remedial works (Reactive works)" tab, please can you confirm these are solely remedials as the tab states reactive as well which are not in scope? | We confirm that these are just Remedials. | 2021-01-20
59 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Remedial works (Reactive works)" tab in column B it provides two tags for jobs - " Management and IRT" and "Management only" please can you clarify what these mean and how they apply to this new contract? | All Remedials will need Management Input and should therefore be considered when building your Remedial Management Cost. However where the work is Routine or Category D these sit outside the IRT and are therefore "Management only". The remaining remidials sit in one of the other categories attacting the tag "Management and IRT". | 2021-01-20
60 | 2021-01-18 | Please can you confirm if it’s the expectation of the buyer that all of the £11,168m of backlog remedial works will be completed within the 21 month term? If not then could you please provide a provisional sum for year 1 and "year" 2 in line with expectations? | The £11,168 is not Backlog Remedial Works - it is Remedial work arising from the PPM tasks required over the 21 month initial term. | 2021-01-20
61 | 2021-01-18 | Within the document "A6 Anonymised TUPE Out ELI data for Hypercare Nov 2020 (Final)" please could you clarify what the individuals with the following job title do on a day to day basis - Service Controller. | Service Controller role • Allocating jobs, tracking jobs and updating job information. • To ensure delivery of PPM tasks to schedule and within SLAs • Liaising with suppliers to ensure job information on VX is accurate and up to date • To chase documentation • To update tags on Completed jobs with documents; • To manage Service Incompletes by collating evidence of the aborted visit of additional and missing assets. • To create Remedial Linked Work Orders and produce Purchase Orders for distribution to relevant suppliers; • To monitor approvals on high value work requests and action accordingly • To Liaise with Operations Managers and Technical support to validate remedial quotations • To report on supplier progress to the Senior Service Controller on in-month delivery of PPMs and remedials | 2021-01-20
62 | 2021-01-18 | Please confirm if there are any existing trade union recognition agreements that cover the employees on the TUPE list. If so, please provide details. | No Trade unions are recognised in relation to the employees on the TUPE list | 2021-01-20
63 | 2021-01-18 | Pension contribution rates. 10 employees are members of “NGB Worksave Section A” and 43 employees are members of “NGB Worksave Section B.” To allow bidders to accurately price, please provide the existing employer contribution rate for each individual. | Pension contribution rates. 10 employees are members of “NGB Worksave Section A” and 43 employees are members of “NGB Worksave Section B.” To allow bidders to accurately price, please provide the existing employer contribution rate for each individual. NG Bailey meets its pensions obligations, as required by TUPE regulations and the Pensions Act 2004. NG Bailey will comply with the employer duties under Part 1 of the Pensions Act 2008 in respect of employees’ employment. It will automatically enrol eligible job holders into a pension scheme as and when required by law. In order to meet the minimum standards set by the Government (as amended from time to time), the minimum amounts that both the employee and the Company will be required to contribute into a qualifying pension scheme are as shown on the table below as a percentage of Basic Salary. Employee Contributions 5% Company Contributions 4% Total contributions 9% NG Bailey will not operate salary sacrifice in any of the pension arrangements. | 2021-01-22
64 | 2021-01-18 | Please provide age data for each individual. | The incumbent will be release this data when providing full ELI if in a TUPE transfer situation to the successful bidder | 2021-01-20
65 | 2021-01-18 | Please provide the value of the existing weekly emergency standby allowance. | The incumbent will release this data when providing full ELI if in a TUPE transfer situation to the successful bidder | 2021-01-20
66 | 2021-01-18 | We note the option Parts within Call-Off Schedule 2 (Staff Transfer) have not been selected. Currently all optional clauses are included, which indicates staff will transfer from DWP directly, also from an outgoing supplier, former NHS staff will be transferring, and also Part C which says there will be no staff transferring at all. Please could you confirm the correct relevant options as this materially affects pension liabilities, which in turn affects the Charges? | Only staff of the encumbent supplier are expected to transfer. Of those optional clauses, only Part A: Staff Transfer at Start Date – Outsourcing from the Buyer is not an option. Part B and C are valid scenarios depentant on which organisation is successful in this opportunity. Part A: Staff Transfer at Start Date – Outsourcing from the Buyer (Optional) Part B: Staff Transfer at Start Date – Transfer from Former Supplier on Reprocurement (Optional) Part C: No Staff Transfer on Start Date (Optional) | 2021-01-20
67 | 2021-01-18 | Please could you confirm which option is applicable in Call-Off Schedule 6 (TUPE Surcharge)? | Option 3 - Further Competition - Fixed Fee TUPE Risk Premium | 2021-01-20
68 | 2021-01-18 | Please can you clarify if force majeure includes Covid? | As COVID is present and part of our day to day lives, in it's current state, COVID would is not be included in the force majeure definition. This is in line with guidance issued by the Cabinet Office. | 2021-01-20
69 | 2021-01-18 | Please can you confirm that the supplier awarded the contract will have exclusivity to all of the PPM works for the in scope work packages in line with the rates submitted within the pricing matrix "ppm pricing" tab? | Yes, the winning supplier will have exclusivity to all of the PPM works in scope of the contract. This is subject to: - The performance of the supplier meeting the requirements of the contract. Should the supplier fail to meet these the Buyer may take remedy action in relation to those PPMs. - Any contract variations which could impact on the scope of the PPM | 2021-01-20
70 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "PPM requirements" tab please can you confirm which column refers to when the next service is due? Our assumption is it is column k "Next Run", if this is correct please can you confirm that any asset which has a date which has elapsed is currently non-compliant? | The PPM requirements tab is provided for pricing purposes only and not resource planning. The data indicates how many of each task are required and an updated PPM plan will be issued during mobilisation. The frequency of the task and the date of the task give a reasonable view of when the task would likely be scheduled for delivery in the initial term. The data provided does not indicate the PPM has not been delivered and has resulted in a non-compliant asset. | 2021-01-20
71 | 2021-01-18 | Please can you confirm that any assets which are found to be non-compliant at their first maintenance visit or through lack of documentation would form part of the billable works to rectify this? Also any remedials associated with non-compliant assets would be chargeable? | The estate is in a compliant state. Should it come to light that any assets are non-compliant either the asset may end up being replaced which would mean out of scope of this contract or a remedial task would be raised. The ammount to which this remedial is then billable or covered by the IRT depends on which Category the remedial falls into as per Table 2 of A3F Remedial Specification (Final) v 1.1 | 2021-01-20
72 | 2021-01-18 | Schedule 13 mentions the supplier must ensure their staff have the necessary security clearance in place before the start date. Can the buyer please confirm the level of security required? | Baseline Personnel Security Standard (BPSS) is a mandatory staff vetting procedure for each member of contractor (and sub-contractor) staff who have access to Departmental Assets. Department Assets are defined as premises, systems, information or data. You must determine from the outset whether this guidance applies to your contract. https://www.gov.uk/government/publications/united-kingdom-security-vetting-clearance-levels/national-security-vetting-clearance-levels DWP does not require any enhanced security clearance over the above. | 2021-01-20
73 | 2021-01-18 | Can the buyer please confirm to what extend the supplier will have access to the Integrators CAFM system to be able to achieve the contract deliverables such as building a PPM Planner, managing tasks, uploading certificates, uploading quotes and performance reports. | Suppliers will have access to the vxMaintain CAFM system via web access. There are generally two types of access; Workspace and Mobile, each provides you with majority of the same access such as estimate and invoice processing, document review and upload, progressing of work orders through their workflow, adding log notes etc etc. Mobile is best used on phones and tablets, and so perfect for engineers as it can be locked down and just provide the areas an engineer will require to start & complete a work order, updates assets, add docs, create remedials etc. Many variations of roles can be created for either type of access to cater for all needs. Vast amounts of data can be exported directly from vxMaintain by the supplier to support in performance management. The updates to the system should be completed as near to real time as possible to allow for accurate completion of workorders and allowing for measurement of works completed in line with the contractual SLAs, which will feed up into the monthly KPI targets. Historic Compliance documentation will be available to view however, work orders against another supplier will not be viewable. The supplier will not have administrative rights to the CAFM system, changes will follow the agreed change process and be implemented by Sodexo. | 2021-01-20
74 | 2021-01-18 | Could you please provide a list of current subcontractors? | A list of the current subcontractors has been uploaded as a shared document | 2021-01-20
75 | 2021-01-18 | In the absence of the Order Form and other mandatory Schedules, and the overall amendments removing liabilities on the Supplier linked with the Framework or other Call Off orders, please could you confirm if the contract is being recognised by CCS as a Call Off order, or if the CCS terms are just being used as a template? | The contract will be recognised by CCS and we are not anticipating issuing a call off order form due to the use of special terms. If this situation changes an order form will be issued along with the contract at the award stage. | 2021-01-20
76 | 2021-01-18 | Thank you for providing the document ‘A3Gi Contractor Engineer User Guide’. Could the Authority please confirm if the portal described within is an optional feature that can be used if the Supplier deems it beneficial? | The VXMaintain system is the mandated CAFM for this contract and must be used by the supplier and is not optional. The CAFM will be used to provide a single port of call for all information on the DWP estate. | 2021-01-20
77 | 2021-01-18 | In reference to document titled ‘A3A DWP LS2 Deliverables Matrix All Lots’, Requirements tab, Service Reference A10, Column F comments: The requirements state that “Information necessary to demonstrate service performance will need to be sourced from the Integrator's CAFM Systems”. Could the Authority please confirm if the Supplier is required to use the Buyer’s reporting tools (e.g. Power BI) to produce the weekly/monthly/quarterly service performance reports or is the Supplier expected to extract data from Vx and produce these reports using their own reporting tools? | The Integrator will be producing the performance reports using the data extracted from VXMaintain. The supplier can provide additional commentary from their knowledge of the supply chain/on going activites which have not been reflected in the data. | 2021-01-20
78 | 2021-01-18 | Regarding the mandatory use of Vx by the Supplier and the delineation of responsibilities for asset/PPM management with the Integrator, could the Authority please confirm if our understanding of responsibilities is correct: a) Validate/Load the initial asset list in Vx Maintain – Integrator responsibility b) Develop the PPM schedule and load into Vx Maintain – Integrator responsibility c) Load the PPM schedule into Vx Maintain – Integrator responsibility d) Raise PPM work orders in Vx Maintain – Integrator responsibility e) Confirm PPM completion/progress in Vx Maintain – Supplier responsibility f) Load documentary evidence into Vx Maintain – Supplier responsibility g) Recommend remedial works – Supplier responsibility h) Raising remedial work orders in Vx Maintain – Supplier responsibility i) Changing the PPM schedule e.g. re-alignment of dates – Supplier to recommend, Integrator to make changes Vx Maintain j) Cancelling PPM work orders for decommissioned assets – Supplier to notify of decommissioned assets, Integrator to amend PPM schedule in Vx Maintain k) Changes to the asset list in Vx Maintain – additions, removals, updates etc – Supplier or Integrator to notify of changes, and Integrator to make changes to asset list in Vx Maintain | a) Validate/Load the initial asset list in Vx Maintain – Integrator responsibility – correct. b) Develop the PPM schedule and load into Vx Maintain – Integrator responsibility – partly correct – See response to question QID 113 c) Load the PPM schedule into Vx Maintain – Integrator responsibility – The PPM Schedule is the data held within the CAFM. There is no schedule to be uploaded encompassing all PPM tasks d) Raise PPM work orders in Vx Maintain – Integrator responsibility – correct – vxM will automatically raise WOs each night. e) Confirm PPM completion/progress in Vx Maintain – Supplier responsibility – correct. f) Load documentary evidence into Vx Maintain – Supplier responsibility – correct. g) Recommend remedial works – Supplier responsibility – correct. h) Raising remedial work orders in Vx Maintain – Supplier responsibility – correct (and work requests). i) Changing the PPM schedule e.g. re-alignment of dates – Supplier to recommend, Integrator to make changes Vx Maintain – correct. j) Cancelling PPM work orders for decommissioned assets – Supplier to notify of decommissioned assets, Integrator to amend PPM schedule in Vx Maintain – correct (and cancel relevant PPM WOs). k) Changes to the asset list in Vx Maintain – additions, removals, updates etc – Supplier or Integrator to notify of changes, and Integrator to make changes to asset list in Vx Maintain – correct – we are currently exploring a process where the supplier can notify Sodexo about asset changes directly in vxM. They will then sit on a PEND Asset Change table for Sodexo to review and either accept or reject back to the supplier. | 2021-01-20
79 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 1.3 refers to "sums which are expressed in the Pricing Matrix to be "subject to indexation" shall be adjusted… We can see no sums or amounts in the Pricing matrix expressed as "subject to Indexation". Can the Buyer confirm that is correct and it is the Buyers intention that no indexation during the Optional Extension Period? | Please see response to QID 56. | 2021-01-20
80 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 1.4 refers to Payment Index (capitalised), however we are unable to see a definitions in Joint Schedule 1. Can the Buyer please confirm the Payment Index? | Noted. A definition of this will be inserted into the executed contract. The Consumer Price Index will be used. | 2021-01-20
81 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6.1 refers to Clauses 25.5 - 25.7 (Change in Law). We are unable to see these clauses. Can the Buyer confirm the document these clauses are included within? | This is from the framework standard form and the clause references refer to the Special Terms. | 2021-01-20
82 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6.1 refers to increases to the Mandatory Wage exceeding any increase for the same period in the Payment Index, the Supplier may request an increase in the Charges. We can find no definition of the term Payment Index in the Definitions. Can the Buyer confirm the Supplier can submit an Impact Assessment for increases in Mandatory Wages above CPI? | This is from the framework standard form. Please see response to question 80 in relation to the Payment Index. The Payment Index will be defined. Any entitlement to an increase in the Charges will be determined in accordance with the provisions of Paragraph 6 of Schedule 5. | 2021-01-20
83 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6.3.1. refers to Indexation Rate. Joint Schedule 1 definitions does not include a rate. Can the Buyer confirm the basis of the indexation rate applied? | Please see response to QID80 | 2021-01-20
84 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6. Please confirm that the Buyer will, as a minimum, provided relevant evidence as required by Para 6 of Schedule 5 is provided, agree increased charges and will not use its discretion capriciously? | The Buyer is not required to accept the Variation request. Please refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6. Clause 6.3. | 2021-01-20
85 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6. Clause 6.3 states that they Buyer is not required to accept the Variation request to adjust charges to reflect changes to the Mandatory Wage. Please confirm that if the Buyer has asked the Supplier to pay employees Living Wage Foundation rates, that the charges will be increased to cover any increase in Living Wage Foundation rates over the term and that the Buyer is required to accept such Variation request? | If the Buyer requests employees are paid Living Wage Foundation Rates this will be discussed in detail at the time of any such change requst. As of this moment there are not impending change requests relating to this subject. | 2021-01-20
86 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 5 Pricing Para 6. Can the Buyer confirm if there is a requirement for the Supplier to pay the Real Living Wage? | This is from the Framework standard form. Mandatory Wage is defined and deals with this point. | 2021-01-20
87 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 6 TUPE para 2.2.1. Please confirm that to the extent that the supplier can evidence inaccuracies in the information required in accordance with Para 2.2. is supplied, the Buyer will pay for the costs of such discrepancies. | This is from the framework standard form. To the extent there are inaccuracies, this will be dealt with in accordance with the relevant paragraph in Schedule 6. | 2021-01-20
88 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 6 TUPE para 2.2.1. Please confirm the Buyer will be required to act reasonably in relation to all further use of the TUPE Risk Premium adjustment mechanics in Schedule X. | This is from the framework standard form, which sets out how the Buyer will act. | 2021-01-20
89 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 6 TUPE para 2.3. Can the Buyer confirm that the Annual Review Further Competition TUPE Risk Premium will only be adjusted where the reduction in the TUPE count is a permanent reduction and the role has not been refilled? | This is from the framework standard form, and it addresses how the reduction will be implemented. | 2021-01-20
90 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 6 TUPE para 3.1 refers to Annex 1 - Call -Off Schedule 5 (Pricing). We are unable to see an Annex 1 in Call Off Schedule 5 (Pricing). Can the Buyer review and advise if the reference is correct? | References to Annex 1 in Call-Off Schedule 6 will be deleted. | 2021-01-22
91 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 14 Key Performance Indicators. Please confirm that all Deductions will be capped at the “At Risk %”. In other words, all possible deductions that can be applied over the course of the contract (including under any ratchet mechanism) are all capped at the At Risk %. 2. Core Terms paragraph 11 states that Deductions are “not taken into consideration” when calculating the Supplier’s liability – we are expecting that all Deductions will be capped at the At Risk Amount, please clarify. | The KPI deductions ( and relevant ratchets ) are capped at the At Risk %. Any other deductions fall outside of this At Risk %. | 2021-01-20
92 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 14 Key Performance Indicators Para 2. Please confirm the Relevant Service Period would be the period from the start of a Persistent KPI Failure occurring until it ceases and that the charges to be withheld would be in relation to impacted services only from the occurrence and not all Services or back dated to the first KPI failure forming part of the Persistent KPI Failure. | This is from the framework standard form and paragraph 2 of Call-Off Schedule 14 sets out the Buyer’s entitlements in relation to a Persistent KPI Failure. We note the reference to “any Charges” in paragraph 2.1.2 and the Buyer’s ability to withhold such amount accrues on the occurrence of a Persistent KPI Failure. | 2021-01-22
93 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 14 Key Performance Indicators Para 3. Can the Buyer confirm the square bracket value/number of KPI credits to be included in para 3.3.1 and 3.3.2 (i)? | This will be amended to refer to the % at risk rather the KPI Credits. The proposed thresholds are as follows: Paragraph 3.3.1: 4% or less of the % at risk Paragraph 3.3.2: more than 4% of the % at risk | 2021-01-22
94 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 14 Key Performance Indicators Part A KPI's and KPI Credits. Para 3.1. Refers to "Paymech Calc Overview tab of the Payment Mechanism". We cannot see that the Payment Mechanism has been issued. Can the Buyer confirm where we can find this document? | The Pay Mec hasn’t been issued as a separate document because Call-Off Schedule 5 contains the relevant provisions. Cross-references to be updated in the executed contract. | 2021-01-22
95 | 2021-01-18 | We refer to document 2. Schedule - Part A and Part B. Call off schedule 14 Key Performance Indicators Part A KPI's and KPI Credits Para 4.1.2. Please confirm the ratchet does not apply to Critical Failure Events during the Bedding-In Period. | Please refer to paragraph 3.2.3 of Call-Off Schedule 14. The ratchet for a Critical Failure Event doesn’t apply during the Bedding In Period. However, after the Bedding In Period, any such failures will be taken into account in determining whether the Ratchet applies from month 4 onwards. | 2021-01-22
96 | 2021-01-18 | We refer to document 1. Special Terms. Para 3.14. Can the Buyer confirm the Supplier can recover cost incurred due to a Default caused by a Buyer’s Supply Chain Member? | Please see answer to QID 32 which has provided an aswer to this question. | 2021-01-20
97 | 2021-01-18 | We refer to document 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm'. We note that within tab 'PPM Requirements', there are some zero values in column ‘EXPECTED_ANNUAL_PPMS’ for PPM visits. However, within the client return model (Document ‘A5A DWP LS2 Pricing Matrix (Final).xlsx’, tab ‘PPM Pricing’) there are some lines which do not correspond this the same visit counts. For example, ‘P/Ultraviolet Disinfection Unit/2Y/065-08-00’ has zero visits in the matrix against the 4 asset lines, yet it requires pricing for 3 visits in the client output model. Can the Authority please clarify the correct pricing requirement? | Bidders should price the rates in A5A as described. The example you have provided is a 2 yearly PPM and will be required to be delivered during the 21 month period but may not be required in the first 12 months. In these cases we have given an average number of PPM's in the A5A Pricing Matrix to ensure that we have appropriate rates for the whole contract. | 2021-01-20
98 | 2021-01-18 | We refer to document 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm'. We note that some assets listed in and within tab 'PPM Requirements' do not fulfil all of the required frequencies. For example, when looking at Air Compressors and Receivers, they are listed as needing visits every 3M, 6M, 1Y, and 2Y, yet for asset numbers DWP178022 and DWP824346, they are only listed to need visits for 3M and 6M only. Likewise, asset numbers DWP036521 and PPM-620752-001-AF-0400802 are listed for visits 6M, 1Y and 2Y, but are not present for the 3M visits. Can the Authority confirm if these differences are intentional or have been done in error? | PPM Requirements as provided should be assumed to be correct. | 2021-01-20
99 | 2021-01-18 | We refer to document 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm'. In some cases, the asset name/type listed in the ‘Asset Type’ column within tab 'Asset Collection’ do not correlate to the asset type listed on the ‘PPM Requirements’ tab. Again, taking the example of the Air Compressors and Receivers, asset DWP824346 is listed as Air Compressors and Receivers in the ‘PPM Requirements’ tab, but this is listed as Sewage Package Systems in the ‘Asset Collection’ tab. Likewise, asset number DWP059233 is listed as Air Compressors and Receivers in the ‘PPM Requirements’ tab, but listed as Sprinkler Systems in the ‘Asset Collection’ tab. Can the Authority please confirm if this is an error? | In some cases, the component has been identified as a part of the main system (in the examples given, the assets are both Air Compressors and receivers, but the first is a component part of the Package Sewage System, and the second a component part of the Sprinkler System). The PPM task assigned should be assumed to be correct | 2021-01-20
100 | 2021-01-18 | We refer to document 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm'. We note that the correct or real PPM quantity is different when comparing them within tab 'Asset Collection’. For example, In the client output mode (Document ‘A5A DWP LS2 Pricing Matrix (Final).xlsx’, tab ‘PPM Pricing’), ‘S/Fire Doors/6M/023-17-00’ requires only 1402 PPM visits. This correlates to 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm' and within tab 'PPM Requirements’ where there are 701 listed Sites and Asset numbers (2 visits pa = 702 sites x 2=1402 PPMs). However, in the 'A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm' and within tab 'Asset Collection’, there are 23,611 individual doors listed (Physical assets) across those 701 sites. The required time in that asset code for SFG20 (23-17-00) is based on each individual asset, so we believe those times should be multiplied by the total number of doors across the sites x2 pa, and not across the number of sites x2 pa. Please confirm if that assumption is correct and whether we should ignore the PPM visit numbers in the output model for assets like this example. | When assessing the calculation for the Fire Doors and other multi asset PPM's such as Emergency Lights the pricing model is structured in a way that means that you will need to include an average "blended" PPM task rate to take into account the variable number of Fire Doors etc based on the information contained in the 'Asset Collection’ tab. This is to avoid requesting a seperate cost for each PPM task per site as part of this tender exercise. | 2021-01-20
101 | 2021-01-18 | Could the Authority please provide greater clarity on the approvals process for remedial works and the steps involved for the various categories of Remedial Works? For example, in Table 2 of Annex F – Remedial Specification, a Category A Remedial Works with a ‘P3 – Important’ priority is not described as requiring approval from the Buyer or the Buyer’s Authorised Representative before it can be carried out. Can the Authority confirm our assumption then that this means that Category A, P3 works can be completed following the addition of the remedial works requirement and estimated timescales to the Remedial Work Programme and shall not require further approval from the Buyer or Buyer’s Authorised Representative? | This is correct. A Category A Important remedial works will be included in the IRT and the Buyer would expect the remedial works to be carried out, preferably, during the PPM visit. The purpose of this is to ensure reduce down time of equipment and provide value to the Buyer and taxpayer. | 2021-01-20
102 | 2021-01-18 | We refer to document A1 DWP LS2 About the Procurements (Final). Can the Buyer confirm that the CQs and responses will form part of the contract and where there is any conflict, the CQs will take precedence? | The final contract including Schedule 22 will consist of the Information you provided in your tender submission, including quality question responses, pricing submissions and all clarification questions raised and answered. Should a conflict occur between the contract the clarification questions, the clarification question will take precedence. | 2021-01-20
103 | 2021-01-18 | We refer to document A1 DWP LS2 About the Procurements (Final). Can the Buyer confirm that the latest Facilities Management Marketplace RM3830 standard call-off schedules and joint schedules have been used as the basis for the contract agreement without amendment? If they have been amended, can the Authority provide a log of all changes made? | As stated at the awareness session on the 11 January and the slide deck which was distributed and made available within the documents available on the ITT , the Buyer has made use of Special Terms and it is the bidders responsibility to identify what changes have been made and how they affect their bid. | 2021-01-20
104 | 2021-01-18 | We refer to document A1 DWP LS2 About the Procurements (Final). Para 8.5 Contract Documents refers to Joint Schedule 11. There is no Joint Schedule 11 included in document "2. Schedule Part A and Part B (finals)". Can the Buyer please confirm this Joint Schedule is "not used"? | Joint Schedule 11 is not used. | 2021-01-20
105 | 2021-01-18 | We refer to document A1 DWP LS2 About the Procurements (Final). Para 8.5 Contract Documents refers to Call Off Schedule 15. Call off Schedule 15 is identified as "not used" in document "2. Schedule Part A and Part B (finals)". Can the Buyer please confirm the schedule is "not applicable"? | We confirm that Call off Schedule 15 is "not applicable" | 2021-01-20
106 | 2021-01-18 | We refer to document A2 DWP LS2 How to Bid. Para 6.8 table A states AQB2 The Supply Chain Integrator, Question Weighting 25% etc. However when you go further down i.e page 31 Section B Scored Questions is described AQB 2 as Utilisation of the CAFM 20%. Minimum Score 50. The Question relates to supply chain integrator. Can the Buyer confirm this is an error and it should read AQB2 Supply Chain Integrator 25%? | Confirm there a couple of errors made during the transferring of information. The Weighting for the Qualitative questions is as follows. AQB1 Mobilisation Requirement 10% AQB2 Utilisation of the CAFM 20% AQB3 The Statutory Compliance PPM Requirement 30% AQB4 Remedial Works Requriement 20% AQB5 Contract Management 20% A corrected Technical Envelope Response Document and How To Bid document will be reissued with the above corrections. | 2021-01-20
107 | 2021-01-18 | The TUPE/ELI data provided indicates the Pension scheme each individual is on, but it does not provide the contribution level that they are currently giving, which in turn does not provide us with the employer contribution level. Can the Authority please provide further details as to the contribution levels? | Please see response to QID 63 | 2021-01-22
108 | 2021-01-18 | Within document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final).xlsm’ and tab ‘Remedial Works (Reactive Works)’ the header on line one suggests the data below covers a period of 9 months. However, the annualisation of the value totals in cell I1 use the data as belonging to an 8 month period, not a 9 month period. This total is also taken and used on the CCS return model. Can the Authority please clarify if this is an error? | Confirm that this is a DWP error and that the total prorata value should be 12/9 and not 12/8. A revised A3A and A5A will be issued | 2021-01-20
109 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’ and the details set out in the ‘Requirements’ tab. a) With respect to section A1 – Integration, can the Authority advise on the location of the ‘A3A Appendix 1 Operating Model overview’ mentioned in para. 1.2 of additional service information? b) With respect to section A1 – Integration, in para 1.2 of additional service information, there is a requirement to ‘limit the requirement for asset survey/verification’. Can the Authority provide more information on their expectation for this? c) With respect to section A1 – Integration, in para 1.3 of additional service information, para 1.3 mentions Annex G Property Classification, Can the Authority confirm that this refers to the property classifications referenced within ‘Framework Schedule 1 Specification’? d) With respect to A4 – Service Delivery Plans, can the Authority expand on the definition of DWP taxonomy mentioned in para. 4.2.12? With respect to A4 – Service Delivery Plans, we note the content of para 4.2.27 – Process for managing reactive work is completed by others. Can the Authority expand on demarcation of responsibilities for this? e) With respect to A5 – Fire Safety, can the Authority expand on the extent of the ‘professional advice service’ required in para 5.2? f) With respect to A10 – Reporting, we note that paras 10.2.1, 10.2.2 suggest that additional reporting requirements may be required from Supplier systems. Should this be outside of the installed systems necessary for the Supplier’s normal operations, can the Authority confirm that this would be subject to a variation? g) With respect to B1 – Contract Mobilisation, para 19.20 of additional service information requires Suppliers to have outputs from the Integrator’s system during mobilisation. Can the Authority confirm that this will be available? h) With respect to Section C1 – Mechanical and Electrical Engineering Maintenance, we note that para 21.14 highlights the Client’s expectation for recording of performance of equipment and systems. Can the Authority confirm that the responsibility for this sits with the Supplier? i) With respect to Section C7 – Internal and external building fabric maintenance, we note the reference made in para 27.21 for ‘Appendix xy’. Can the Authority confirm where this can be found? j) With respect to Section C13 – High Voltage and switchgear maintenance. Para 33.3.4 covers DNO switching. Can the Authority expand on the requirement for DNO switching, i.e. number of times per year at which properties? k) With respect to Section C13 – High Voltage and switchgear maintenance. Para 33.3.8 covers HV switching activities. Can the Authority confirm what the volume of works are in terms of expected/number of jobs per annum? l) We refer to Section E1 – Generic statutory obligations and requirement. Para 49.3 mentions ‘Appendix xy’. Can the Authority conform where this can be found? m) We refer to Section E2 – Water hygiene maintenance. Can the Authority confirm that the Remedial Works mentioned in para 51.4 are fully chargeable as Billable Works, i.e. not in the IRT? n) We refer to Section E8 – Fire Risk Assessment. Within para 57.2 of additional service information, can the Authority confirm if the information highlighted is presently available to be used, or if it has to be created fully by the Supplier? Should it need to be created, can the Authority confirm that works will be chargeable as Billable Works? o) We refer to Schedules, Parts A and B, Page 23 – ‘Key Subcontractors’ (b). Can the Authority confirm if the Buyer is nominating any Key Subcontractors? | a) The Operating Model overview can be found on slide 7 of the "Supplier Briefing Pack Jan21 Post ITT issue.ppt" b) It is envisaged that ongoing effective management of the Contract will ‘limit the requirement for asset survey/verification’ and therefore there is no specific extra expectation beyond effective contract management. c) Confirm that this is the RM3830 Property Classifications d) The taxonomy is reflected in the Asset Register – this can be further clarified during mobilisation. e) Suppliers must have access to professional, competent and appropriately qualified individual(s) that can provide consistent and proficient advice on matters of fire safety as set out in the Regulatory Reform (Fire Safety) Order 2015. The advice will relate to the both physical fire precautions and the fire safety management of DWP premises. For example, DWP would like to introduce a new tea point into an office area and would like advice on whether this is feasible and what additional fire precautions are required. Another example would be to comment upon the risks associated with an increase in occupancy levels in a particular part of a DWP site, highlighting the impact on things like numbers of fire wardens, changes in procedures, or whether assembly points are suitable now that the numbers of staff have increased. The competent individual(s) must have a recognised industry qualification / accreditations e.g IFE and have experience at providing advice for similar building portfolios to those found on the DWP estate. f) It is envisaged that reports will only be required from Systems that should be part of Supplier's normal operations. If there are any areas that are outside of normal systems it is envisaged that this scope will be agreed with DWP and the Integrator to determine how appropriate information can be obtained. The requirement to supplement performance reporting with supplier analysis and narrative does is core to this specification and no variation will be considered for this element. g) Confirm these outputs will be made available during mobilisation h) To the extent that this is required as part of delivering the PPM tasks shown in the "PPM Requirements" Tab and associated remedials. i) This Appendix will not be issued during the tender process. Further clarification of Fire Door Maintenance and Fire Risk Assessment requirements will be provided during the mobilisation period j) DNO switching is rarely required, and would be on a chargeable basis when required. k) HV switching is rarely required, and is normally only anticipated to be needed as required for the regular maintenance of the HV substations, which are in-scope. l) Document Specification in Appendix xy has not and will not be issued and will not form part of this contract. The Special Terms and associated Schedules define "Documentation" m) Any Remedial Works including Water Hygiene should be taken into account and included in your pricing of the IRT. n) The price needs to include the full cost of undertaking an FRA including Drawings. In most cases hard copy Drawings have been included in previous FRA's but this is not universal. The price should include the full cost of producing an FRA o) The Buyer is not nominating any Key Subcontractors | 2021-01-22
110 | 2021-01-18 | We refer to document ‘A3F DWP Remedial Specification (Final)’. Can the Authority provide details of the Remedial Works outstanding, i.e. programme backlog and volume of works forecast? | No further Remedial Works information will be provided as part of the tender process. Backlog volumes will be provided during mobilisation. | 2021-01-20
111 | 2021-01-18 | We refer to document ‘A3F DWP Remedial Specification (Final)’. Within para 3.1, page 3 – can the Authority confirm that if Buyer requests Remedial Works that this then sits outside the IRT? | Please refer to Answer 55 | 2021-01-20
112 | 2021-01-18 | We refer to document ‘A3F DWP Remedial Specification (Final)’. Within para 3.8, page 4 – Clarification of ‘Category D Remedial Works’ is excluded from Table 1. Can the Authority confirm on how this differs for categories A-C shown? | An updated "A3F DWP Remedial Specification" was issued which has Category D and E added to Table 1 | 2021-01-20
113 | 2021-01-18 | Can the Authority clarify which organisation is responsible for the scheduling/re-scheduling of the PPM tasks given the following: • Tasks can be carried out outside of the due date • Asset replacements sit outside of the LSS2 contract • A number of tasks will have associated activities scheduled by, and carried out by the FM supplier, which in turn may affect the next due date | The LSS2 contractor has the responsibility for managing the PPM plan, and the Integrator has responsibility for loading any changes into the CAFM. If tasks are carried out substantially early (more than 14 days), it is the responsibility of the LSS2 contractor to submit a change request to reschedule the next due PPM in order to preserve the compliance of the asset or system. The integrator will make the changes within the CAFM. Reports exist to highlight those PPMs completed early. If tasks are carried out late, the next due date remains unchanged. Where asset replacements occur, whether through BAU maintenance, lifecycle replacement, new acquisitions or projects, the LSS2 supplier will, upon receipt of the new asset information, be required to identify a PPM start date for those assets and submit to the Integrator for checking and loading into the CAFM for delivery. There are no tasks carried out by the FM supplier which impact the tasks defined for the LSS2 contractor. In some cases this may result in both FM contractor and LSS2 contractor attending the same asset or system within the same period. (Eg, The FM contractor will continue to carry out the monthly Emergency Lighting Test in all months, even when if Annual test is due in the same month) | 2021-01-20
114 | 2021-01-18 | Can the Authority confirm that should remedials be identified by the LSS2 contractor then the expectation is that the LSS2 contractor will carry them out? | We confirm that where there are remedial works that the LSS2 will undertake these works, subject to the appropriate approvals. | 2021-01-20
115 | 2021-01-18 | Regarding Water/Fire Risk assessments can the Authority confirm that all requirements will be carried out by the LSS2 contractor e.g fire signage replacements, compartmentation surveys etc? | The Supplier will need to undertake all aspects of the FRA/WRA. For example FRA will require to be completed in accordance with the requirements of the Regulatory Reform Fire Safety Order (2005) and follow the best practice guides in accordance with the latest edition of PAS79. It is a requirement to provide updated floor plan drawing as part of the FRA delivery process. Historic AutoCAD and/or PDF fire precaution drawings exist for the majority of site which will be issued for review and update during the Fire Risk Assessment and updated as necessary to include the significant fire precautions including: • Significant layout changes • Location of extinguishers • Smoke heads • Fire alarm panel • Sounders • Fire doors • Fire Stopping / Fire resisting structures • Emergency Lighting • Fire Escape Signage • Disabled Refuge • Dry/Wet Risers In the case whereby an existing FRA or layout drawing does not exist e.g. for a new site – then provision is to be made for a drawing to be produced by the FRA supplier for the site and populated with detail specified above. It is a requirement to include the fire precaution drawings within the FRA submission as a PDF format and for a separate AutoCAD version to be made available to DWP for their archive. Where further remedial compartmentation surveys are required beyond PAS79 the Buyer may approve these as Billable Works. Remedials arising from the FRA / WRA will need to be approved in accordance with the Buyer approval process, depending on the level and type of works will determine where these works will be routed within the Buyer's supply chain. | 2021-01-22
116 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’. We note that the asset list has the condition rating of the asset but not the lifecycle rating /age or due replacement date. Can the Authority share this if available? Additionally can sight be given of any lifecycle replacement programme as it relates to the assets detailed? | This data is available – see uploaded spreadsheet Asset List LSS2 Scope - RYR Added (Note this document should only be used in connection with this question and the tenderer shall asume that where there are any discrpancies between this and other tender documentation that the other documentation is correct). This is calculated based on CIBSE lifecycles according to the installation date. This should not be taken to be the actual planned date of replacement, as asset renewals are based on criticality, condition and budget availability. The planned replacement for FY21/22 is still in the planning stage and not yet finalised. | 2021-01-20
117 | 2021-01-18 | We note the provision of a three months bedding in period, which facilitates the review of assets and their corresponding PPM tasks. To prevent the requirement for additional survey staffing needed during this period, would the Authority consider extending the verification of assets, conditions and PPM regimes to a six or twelve month period aligned to the PPM activity so that engineering resource can identify during the first scheduled maintenance visit, thereby negating any survey costs that may be needed? | There is no asset verifcation exercise or surveys required as part of this contract. | 2021-01-20
118 | 2021-01-18 | Can the Authority advise if it is the Integrator that has overall responsibility for the control of the asset list, and any updates made to it? Similarly, can the Authority advise who is responsible for updating the asset list if any remedial works lead to minor assets being replaced? | The Supplier will advise any changes that need to be made to the asset list (arising from their works). The Integrator will have overall responsibility for the control of the asset list. | 2021-01-20
119 | 2021-01-18 | If any minor assets are replaced, can the Authority advise on who is responsible for the updating of any asset tagging and the issuing of asset tags? | As the replacement of assets is specifically out of scope for LSS2 then the asset tagging will be done by the supplier carrying out the replacement. | 2021-01-20
120 | 2021-01-18 | With respect to the KPI mechanism and the bedding in period, can the Authority confirm that only month three of the bedding in period will be used to notify the ratcheting in month four of the contract? | Paragraph 4.1 should be read in conjunction with paragraph 3.3 of Schedule 14. We aim to publish some Worked examples of the KPI calculation and ratchet on the 25 January 21 | 2021-01-22
121 | 2021-01-18 | It was stated at the Supplier brief on 11/1/2021 that the Integrator will be responsible for the agreement of the monthly performance statistics. Can it be confirmed that should there be any disagreement to these metrics that the Authority will facilitate agreement, particularly in instances where the Integrator’s performance has affected the Supplier’s ability to perform? | In the first instance the Performance Statistics will be based on data provided by the Supplier onto Vx. There will then be a review of the performance (between the Integrator and Supplier) to determine whether there are any mitigations (for example for Buyer Cause). We expect that the Integrator will assess mitigations properly and fairly. In the event that the Supplier believes that they are not doing so the Supplier will need to escalate to the Buyer as defined in the contract and the Buyer will facilitate agreement. | 2021-01-22
122 | 2021-01-18 | With respect to document ‘A5A DWP LS2 Pricing Matrix (Final)’, where the PPM Pricing sheet suggests Zero PPMs against activities, can the Authority confirm that they don’t need to be priced? | Zero for PPM's were included in error and where a zero has been included the Supplier needs to price for this. An updated ‘A5A DWP LS2 Pricing Matrix (Final Updated)’ will be issued showing this zero value as "50" We have identified that there was a single instance of this error. | 2021-01-22
123 | 2021-01-18 | Can the Authority provide dates for when statutory maintenance is required on items that exceed a one year gap between visits i.e. for 5Y FWT, given the duration of the contract, it is probable that many of these will not need completion during the initial term. | Refer A3A DWP LS2 Deliverables Matrix all Lots (Final) PPM Requirements Tab Column O As the PPM plan is a living data source any updates and changes will be notified during mobilisation. | 2021-01-22
124 | 2021-01-18 | The TUPE data provided suggests that no delivery personnel have been included. Can the Authority confirm if all current contractors have advised that TUPE would not apply to resources not identified? | The data is as supplied by the Incumbent Supplier. A further confirmation has been requested from the incumbent to confirm that TUPE impact has been received from the chain. If the position changes with regard to the TUPE information this will be re-issued to bidders. | 2021-01-22
125 | 2021-01-18 | With regards to HV can the Authority advise which party will be responsible for the COMA agreement (e.g. LSS2 contractor or FM provider)? | LSS2 contractor to be responsible for COMA agreement | 2021-01-22
126 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’. Within the Asset Collection tab, we note the condition grading in column AC. Can the Authority advise if the rating given is a perceived operational rating or a CIBSE Rating? | This is an asset condition rating based on non-intrusive assessments by surveyors, using CIBSE condition ratings as defined by Guide M 2014. | 2021-01-22
127 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’. Within the Asset Collection tab, we note from column U that there are 1695 lines identified as ‘Not Working’. Can the Authority advise if these are to be included in the scope of PPM activities or to be isolated and managed through the proposed Remedial Backlog Programme? | These assets should be included in the scope of maintenance activities as the Not Working status may relate to an in-progress break-down | 2021-01-22
128 | 2021-01-18 | Can the Authority please advise the number of floors in each building? | This data is available and will be uploaded onto the ITT on 25/01/21 | 2021-01-22
129 | 2021-01-18 | Could the Authority advise on which party has responsibility for capturing asset condition and deterioration over time, and following which, responsible for updating the asset register? | The LSS2 and Fm Suppliers will be involved in capturing the asset condition. This will be shared with the Integrator to ensure the CAFM is updated. Further details will be shared during mobilisation. | 2021-01-22
130 | 2021-01-18 | Can the Authority confirm whether there's an additional requirement for providing PPM activities to non LSS2 assets e.g. Air Handling Unit and Circ. Pump maintenance, Terminal VRV's? We note that a number of these are present on the asset collection tab. | The LSS2 supplier is only responsible for providing PPM activities as listed on the PPM Requirements tab of the A3A Deliverables Matrix | 2021-01-22
131 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’ and Service A10 (reporting) within the ‘Requirements’ tab. With reference to para 10.12.8, can the Authority advise on how they anticipated this metric applying to the LSS2 Supplier? | With reference 10.12.8. Details of Assets or systems taken out-of-service for health and safety or operational reasons; it is envisaged that the Supplier will record any assets etc that it has had to take out of service on Vx and this information will be incorporated in ay reports agreed during mobilisation | 2021-01-22
132 | 2021-01-18 | We refer to document ‘A3A DWP LS2 Deliverables Matrix all Lots (Final)’ and Supplier responsibilities set out within the ‘Requirements’ tab. We note the reference to Buyer’s business critical systems within paras 20.14.1., 22.3, 33.3.1. Can the Authority advise if a criticality matrix will be made available to Bidders? | A criticality matrix will not be issued. | 2021-01-22
133 | 2021-01-18 | Can the Authority advise if the Supplier will have access to historic statutory documentation from the incumbent? | There is no documentation held at Asset level. PPM Compliance documentation are loaded at site level and will have asset detail within them. For a new contractor to view another’s documentation I have to create a specific role with relevant restrictions. So yes new suppliers can view the ‘all docs & cert’ tab. | 2021-01-22
134 | 2021-01-18 | As per your instructions we note that ‘The Tender should not contain any inserted, pasted or embedded pictures or documents’ within our responses, and ‘answers are to be self-contained’. However, if we cannot include a structure in our service line responses and we cannot refer you to the response where we have provided it, the reviewer will (potentially) not have sight of our organisation? Also, please can you advise whether we can include tables within our responses? | The organisation plan can be uploiaded as a separate document for review. The naming convention of the file must link back the question i.e. AQB1 Org Chart Tables can be inserted into responses as can diagrams, however they do count towards the overall page limit of the response which cannot be exceeded. | 2021-01-22
135 | 2021-01-18 | The defined term “Payment Index” is given in Call Off Schedule 5, but this doesn’t seem to be defined or detailed anywhere in the documents. As this forms part of the calculation for price increases, please could you confirm what the Payment Index is? | Please see response to QID 80 | 2021-01-22
136 | 2021-01-18 | The Authority’s response to Clarification Question 12 states that “Only remedials below £500 in the urgent critical and important priorities are included in the IRT”. The definition of the Inclusive Repair Threshold within the ‘Schedules Part A and B’ document, however, states that the IRT should cover both ‘the entirety of the costs of Category A Remedial Work’ (i.e. works under £500) as well as ‘the first £500 exclusive of VAT where payable for the Category B Remedial Work, Category C Remedial Work and/or Category E Remedial Work’ (i.e. works over £500). Can the Authority confirm that the definition contained in the ‘Schedules Part A and B’ document is the correct description of what the IRT should cover? | The definition for IRT is correct Schedules A and B. The response in QID12 reflects this. Any Routine (Category D) work is exluded from the IRT | 2021-01-22
137 | 2021-01-18 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Asset Collection " tab in column U it lists many assets as "not working", but then in column V it states they are "in service." Please can you confirm if we should exclude all assets stated as "not working?" | Please see response to QID 127 | 2021-01-22
138 | 2021-01-18 | Within document "A6 Anonymised TUPE Out ELI data for Hypercare Nov 2020 (Final)" it lists 28 roles as being on fixed term contracts who would appear to have finished their contracts by go live. For the purposes of the cost of change calculation should we assume these roles will have finished? | For pricing purposes please assume that all of the roles listed as Fixed Term will run until the end of the contract. | 2021-01-22
139 | 2021-01-18 | Within document "A5A DWP LS2 Pricing Matrix (Final)" in tab "PPM pricing" the tasks we are being asked to price against for specific assets do not always align to Statutory and Mandatory SFG20 tasks (standard B). Examples would be distribution boards do not have a 6 monthly task included for us to price against but this is a stat/man requirement, softeners we are being asked to price for a 6 monthly which isn't a statutory or mandatory requirement. Please can you confirm that we are to price for all line items in the "ppm pricing" tab, even if the task is not a stat/man requirement? And if so then please clarify it should be in line with SFG20 comparable times? | The existing pricing matrix should be priced against as provided. The estate does not have Distribution boards with AFDD, so the 6M task is not required. Where Distribution boards have RCD or RCBO installed, they are assigned a 3M PPM. Some non-statutory tasks have been included in the scope to ensure all maintenance on certain assets remains with a single contractor. The LSS2 contractor has the responsibility for adjusting the PPM plan where legislation or industry best practice changes, or other efficiencies are identified, after consultation with the Integrator. The tasks should be delivered in line with SFG-20 guidance unless stated otherwise or agreed during mobilisation. | 2021-01-22
140 | 2021-01-19 | Can you please confirm what version of SFG you are working to? We have noted that some of your tasks are obsolete and some have differing frequencies - i.e. Fire shutters (SFG-23-18) does not currently have a 3M task. As another example, mixing taps - your spec asks for 61-04 which is obsolete, shall we assume 61-21 or 61-22? | The LSS2 contractor has the responsibility for updating the PPM plan in line with any changes to SFG-20 or other Industry best practice, and should always use the most current version of SFG-20 to do so, however, for the purposes of pricing, please utilise the provided pricing matrix as it is. For the purposes of pricing for mixing taps, please assume 61-22, however, the TMV assets across the estate are currently under review, so the delivery may change in the future. | 2021-01-22
141 | 2021-01-19 | With respect to responses to clarification questions received after the clarification close date of 20th January, would the Authority permit the submission of further clarification requests from Bidders that were deemed necessary only as a result of those clarification responses? | Further Questions can be submited only in referance to answers form other clarification questions. These must be submitted no later than 12pm on 25th January 2021 | 2021-01-22
142 | 2021-01-20 | We notice that in the 'A2 DWP LS2 - How to Bid' document, that question AQB2 is titled 'The Supply Chain Integrator Requirement' and given a scoring percentage of 25%. However, in the 'Technical Envelope Template Response' document, AQB2 is titled 'Utilisation of the CAFM' and weighted at 20%. Please can you confirm the correct weighting? | Please see response to QID 106 | 2021-01-22
143 | 2021-01-20 | "Our" PI cover is maintained on an aggregate basis without reinstatements. Therefore we propose to increase the required aggregate cover from £5m to £10m without reinstatements. Please can you confirm whether the PI requirement may be amended to reflect this position? | We propose to ammend the Professional Indemnity Insurance requirement to state- Not less than £5,000,000 in respect of any one claim and in the aggregate subject to one annual reinstatement or £10,000,000 in respect of any one claim and without reinstatement. | 2021-01-22
144 | 2021-01-20 | Within document "A5A DWP LS2 Pricing Matrix (Final)" in tab "PPM pricing" there are specific line items which require a cost to be inputted but there are no associated assets within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Asset Collection " tab. Can you confirm this means we are to put a value of £0 as there are no assets, or are we to provide a bench mark value which will be subject to due diligence? How would you like these line items highlighted? | Please refer to QID 122 | 2021-01-22
145 | 2021-01-20 | Within document "A3A DWP LS2 Deliverables Matrix all Lots (Final)" in the "Asset Collection " tab there are assets provided which appear to align to the work packages in scope but do not have a specific place for their maintenance costs to be included in document "A5A DWP LS2 Pricing Matrix (Final)" in tab "PPM pricing." Are we to ignore these assets? e.g. Boilers LTHW up to 95 degrees. | For the purposes of tendering please price the A5A DWP LS2 Pricing Matrix (Final) which is based on a schedule of PPM tasks and not by asset. Note if you are missing asset information that allows you to price the PPM please refer to Q144 | 2021-01-22
146 | 2021-01-20 | We are assuming that existing employees who are eligible to TUPE transfer are security cleared to the required level and the successful bidder is not required to renew their clearances at the point of transfer. Please confirm if this is correct | Assume that employees who are eligible to TUPE transfer are appropriately security cleared for the role they perform. | 2021-01-22
147 | 2021-01-20 | Please can you confirm if weekly fire alarm ringing will fall in scope of the contract or if it to be undertaken by others? | The scope is for the PPM’s included in A3A DWP LS2 Deliverables Matrix all Lots (Final) PPM Requirements Tab. The weekly fire alarm testing is not in scope of this contract. | 2021-01-22
148 | 2021-01-20 | Please can you confirm if monthly tap temperature testing will fall in scope of the contract or if it to be undertaken by others? | The scope is for the PPM’s included in A3A DWP LS2 Deliverables Matrix all Lots (Final) PPM Requirements Tab. The monthly tap temperature testing is not in scope of this contract. | 2021-01-22
149 | 2021-01-20 | We refer to Annex F Remedial Works specification. At Para 5.1.2 (ii), it states that within twenty (20) Working Days of receiving the Outstanding PPM Task List, the Supplier will update the PPM Plan with the Programme Information. Then at Para 5.1.2 (iii) it states that within twenty (20) days of receiving the Outstanding PPM Backlog Programme the Supplier will complete the relevant PPM Tasks. Would we be correct to assume that this is an error and, as in the case of backlog remedial works described at para 5.1.1 (vii) that PPM tasks shall be completed within forty days of receipt of the Outstanding PPM Backlog Programme not twenty? | This is not an error: The process is Buyer shall provide the Supplier with a list of outstanding PPM Tasks (the “Outstanding PPM Tasks List”) Within twenty (20) Working Days of receiving the Outstanding PPM Task List the Supplier will create the Outstanding PPM Backlog Programme Within twenty (20) days of the Outstanding PPM Backlog Programme the Supplier will Complete the relevant PPM Tasks. This means that there will be up to 40 days to complete the PPM task from receipt of the “Outstanding PPM Tasks List” | 2021-01-22
150 | 2021-01-20 | We understand and appreciate nature of the DWP estate. In order for us to ensure that our solution delivers outcomes that align with DWP vision we feel it is necessary to understand the existing interfaces between the various parties and the current performance levels to ensure that we recognise the complexities and build them into our solution. We have drawn the process as we understand it, however, we have some observations which we have included on the attached. Could the buyer therefore please confirm our assessment of the process is correct and also describe the current interfaces between all parties. | The assessment of the process is incorrect as the Remedial arises from the Supplier PPM only and not from the Buyer or a reactive service provided by another supplier.The process for adding remedial works, their costs and programme are defined in the contract but the practical steps of doing so and gaining approvals for works will be developed further during mobilisation. | 2021-01-22
151 | 2021-01-20 | We note that the Remedial Works information provided does not include any reference to fire door remedials. Therefore there is no information against which to estimate the IRT. The fire door remedial work could be significant and therefore request guidance on this element of the IRT. | Assume 50% of fire door PPM tasks will result in a remedial value in excess of £500 and 50% will result in a remedial value of zero. This will be further reviewed during the due dilligence period in conjunction with the review of all remedial works. | 2021-01-22
152 | 2021-01-20 | We note the response to Clarification Question ID – 14. However, we have been made aware by members of the current Supply Chain that they are not able to provide prices for the new contract. This may therefore lead to these Suppliers putting forward employees for TUPE. Can you confirm if the current Suppliers Supply Chain will be asked to provide details of that there will no incumbent supplier sub-contractor employees employees eligible for TUPE? If there are, can you please provide the relevant ELI data? If current Suppliers do not provide ELI data prior to the tender date and subsequently do so how will this adjustment be made in the agreement of the final contract. | Please see response to QID124 | 2021-01-22
153 | 2021-01-20 | The “PPM Plan” is not properly defined in the Joint Schedule, can this be clarified please? | The PPM Plan is the data held in the CAFM which includes the Schedule of PPM Tasks, date due, location of delivery etc that the Supplier will need to deliver as part of this contract | 2021-01-22
154 | 2021-01-20 | Can you confirm that a Remedial Fixed Cost Quotation will be paid to the Supplier and that the only change to the payment to be made will be to adjust the Fixed Cost Quotation for an increase caused by Buyer Cause? In the instance of a Remedial Fixed Cost Quotation that the works carried out will be subject to agreement of actual costs and that in both cases the first £500 will not be payable. | This is correct . We remind again that Routine or Category D works are completely out of the IRT and all agreed costs are payable. | 2021-01-22
155 | 2021-01-20 | We note the response to clarification question 30 says “The Contractor will have a full timetable of when PPMs need to be completed. The PPMs can be scheduled up to 14 days prior to when the PPMs are due, providing a window for completion.” Our understanding of this is that the Integrator will produce the annual PPM programme and schedule the visits within Vx, then issue the PPM programme to the Contractor in order that they can plan delivery of the PPMs within the 14 day window. The Integrator will then raise PPM work orders for the Contractor on a daily/weekly basis in accordance with the programme. Please can the DWP confirm that our understanding is correct and that it is not the Contractor’s responsibility to plan or schedule PPMs within Vx? If this is not the case, please can the DWP explain which party/parties will be responsible for these activities and their specific responsibilities? In addition, if the Contractor completes a PPM prior to the due date within the 14 day window, please can the DWP confirm that the next scheduled PPM will be from the original due date and not the actual completion date so as to avoid the effect of gradually bringing the PPM schedule forward over time? | Please see response to QID 113 | 2021-01-22
156 | 2021-01-20 | Insurance Periodic inspections on Lifts – please confirm the 6-monthly task requirement is an insurance visit and not a PPM requirement? | Confirmed it is an insurance requirement under LOLER. It is not a PPM per se but does appear on the PPM Plan for scheduling purposes. | 2021-01-22
157 | 2021-01-20 | Where numerous visits are detailed on the return, we have assumed these will be stacked e.g.: Air Compressors require Quarterly visits, therefore our “Yearly” cost would be the Annual less the Quarterly visit cost. Please confirm we have interpreted this correctly? | Bidders should take into account of making efficiencies of tasks being scheduled for the same date. How this efficiency is presented within the PPM task costs is down to individual bidders to determine. | 2021-01-22
158 | 2021-01-20 | For the avoidance of doubt can DWP confirm your requirements to whether the scope of the statutory compliance is to deliver only statutory maintenance activities to the affected site/statutory life service assets listed here, or all maintenance to those statutory assets? I.e. with lifts? Will the LSS2 contractor be responsible for all maintenance to these lifts under sfg20 or just the statutory maintenance aspects of the PPM and another Contractor will be providing the remaining lift PPM activity? | The scope of the contract is to deliver statutory PPMs and remedials arising from those PPM's. Please refer to para 25.3 on Requirents Tab of the Deliverables Matrix for the maintenance regime aplicable for lifts | 2021-01-22
159 | 2021-01-20 | Where the specification calls for daily inspections of cooling towers for example, is this for the Contractor to deliver or are we to assume this will be delivered as part of the DWP regime on each? Is there an appetite in the interests of VFM to look at such split activities with the Contractor still taking the risk? | Please price as per the pricing model. DWP are in the process of installing a remote monitoring upgrade in the near future so this requirement may change during the contract. | 2021-01-22
160 | 2021-01-20 | Within document A2 DWP LS2 – How to Bid (Including Evaluation Criteria) (FINAL), within section 3 evaluating your bid, 3.1 states “The Supplier must pass all eligibility questions in the Qualification Envelope provisions and as specified in the Supplier Questionnaire ("Eligibility Questions")” Please confirm that this relates to the portal section 1. Qualification Response (Questions: 5) | 3.1 refers to the Qualification Envelope within the DWP eSourcing portal which consist of 5 pass/fail questions under 1. Qualification Envelope. Qualification / Technical Form then 1.1 Section A - Mandatory Pss/Fail | 2021-01-22
161 | 2021-01-20 | If a Supplier is proposing to sub-contract part of the contract and in doing so will rely on the capacity of a Sub-contractor to fulfill the selection criteria in the Supplier Questionnaire, then the Sub-contractor must complete Parts 1 and 2 of the Supplier Questionnaire using the template Supplier Questionnaire (attached as Annex A). Please advise where Annex A is located and if we are proposing a multi supply chain solution, will Annex A need to be completed for each subcontractor. In addition as Prime Contractor is this a separate area to complete in the portal from portal section 1. Qualification Response (Questions: 5) or is Annex A additional, which we are missing? | Sub contractors do not need to complete Parts 1 and 2 of the supplier questionnaire. This is an error and has been removed from the A2 How to Bid Document. The prime contractor needs to complete all questions in the Qualification and Technical Envelope. | 2021-01-22
162 | 2021-01-20 | We refer to document 1. Special Terms, para 3.10 (Defaults caused by Buyer Supply Chain Members). While the definitions are clear on what ‘Default’ means for the Supplier, it doesn’t include Buyer Supply Chain Members. Can the Authority provide more clarity around what the ‘default’ causes would be as applied to these Supply Chain Members? | A Default by a Supply Chain Member would in effect become a Buyer Cause please also see response to QID 31 | 2021-01-22
163 | 2021-01-20 | With respect to the ‘A3A DWP LS2 Deliverables Matrix’ spreadsheet, we note that a number of items on the ‘Asset Collection’ tab show zero or are blank for the asset quantity. Can the Authority advise if these items are to be considered as part of the PPM Requirements? If so, can more detail be added on how these items should be included? | Please see response to QID 122 | 2021-01-22
164 | 2021-01-20 | We ask the Authority if it is possible to extend the clarification window to the 25th January to facilitate further clarifications to be raised. | The Buyer will allow for clarification on clarification responses or additional provided only until the 26th January. No clarification questions on new subjects will be answered after the 20th January 2021 | 2021-01-22
165 | 2021-01-20 | can you please clarify the indexation rate to be applied after the initial term of the contract? | Please see response to QID 80 | 2021-01-22
166 | 2021-01-20 | Call Off Schedule 14 – KPIs, Clause 3.3.2 States 3.3 Without prejudice to paragraph 4.1 of Part A of this Schedule, during the first Month after the expiry of the Bedding-In Period: 3.3.1 if the Buyer accrues a total equal to or less than [***] KPI Credits for such Month, the Buyer shall not the adjust any invoices in respect of any applicable KPI Credits accrued by the Supplier during the Bedding-In Period; or 3.3.2 if: (i) the Buyer accrues more than [***] KPI Credits for such Month; and/or (ii) a Critical Failure Event occurs or is likely to occur in such Month, the Buyer may adjust any invoices in respect of any applicable KPI Credits accrued by the Supplier during the Bedding-In Period. Can you please clarify the Total KPI Credits accrued during the bedding in period. | Please see QID120 and QID93 | 2021-01-22
167 | 2021-01-20 | Can the buyer please confirm the clarification responses will be included in the final contract and how they will be included prior to execution | Please see response to QID 102 | 2021-01-22
168 | 2021-01-26 | Following your response to Clarification 149, and recognising your previous response to Clarification 17 can the Authority confirm if the Inclusive Repair Threshold shall be applicable in the case of backlog remedial works identified at the start of the contract which have not been completed by the previous contract? | The backlog remedials will not be included in the IRT. Any backlog remedials handled by the new supplier will be classed as fully billable.As mentioned in QID 35, outstanding work will either be in the oustanding Remedial Plan if it was generated by a PPM visit or the reactive works plan both held on the CAFM. | 2021-01-27
169 | 2021-01-26 | Reference clarification question response 115 As the requirement to update drawings or produce new drawings may only be applicable to some FRAs and as the size of sites varies greatly, can bidders assume that updates to drawings or production of new drawings will be approved as Billable Works? | Assume eletronic CAD floor plans can be provided for all buildings requiring an FRA. The bidder shall allow for updating these plans. Where plans are not available, the creation of these plans shall be deemed Billable Works. | 2021-01-27
|  | FURTHER CLARIFICATION FROM THE BUYER - ISSUED VIA GLOBAL EMAIL VIA DWP ESOURCING PORTAL |  | 2021-01-27