## 3. Schedule of Works
SPECIFICATION DOCUMENT
Marsh Lock House
SCHEDULE OF WORKS
Ref. | Description | £ | p
3 | SCHEDULE OF WORKS
3.1 | INTRODUCTION
3.1.1 | The contractor is to note that the proposed works forming this schedule are for external repair and replacement window and door works to various area of the building forming Marsh Lock House.
3.1.2 | The location of Marsh Lock House is shown in the Google Maps image below, as well as in more detail in Appendix E.
3.1.3 | Location of works: Marsh Lock House, Mill Lane, Henley-on-Thames, RG9 4HB.
3.1.4 | The Client will be: Environment Agency Address: Kings Meadow House, Kings Meadow Road, Reading, Berkshire, RH1 8DG.
3.1.5 | The Client Representative will be: Ridge & Partners LLP Address: Beaumont House, 59 High Street, Theale, Reading, Berkshire, RG7 5AL.
3.2 | GENERAL
3.2.1 | The schedule has been prepared in order for a detailed cost breakdown to be provided, to aid the assessment of the works and to assist with progress and payments.
3.2.2 | The contractor is to take responsibility for the schedule and is to ensure its completeness with regards to the proposed scope of works. No costs incurred by the contractor during the pricing of these works will be accepted by the Employer.
3.2.3 | The contractor should note that all items of work contained within this schedule have been described in reasonable detail, but the contractor shall consider them in conjunction with material manufacturers recommendations, and actual work on site. The contractor shall include in his price for everything that is necessary in order to allow him to carry out the works in the best manner whether specifically mentioned or not. If and where approximate quantities are stated, these are for guidance only and the contractor is to make his own assessment of the actual quantities required by visiting site prior to submitting their costed return.
3.2.4 | The contractor is responsible for checking all dimensions on site. Any alterations or amendments to those detailed in this document are to be confirmed in writing by Ridge & Partners LLP.
3.2.5 | Should there be any items of work which the contractor is unclear as to what is required, then the query should be raised to Ridge & Partners LLP for clarification, during the tender process.
3.2.6 | The contractor is to price the schedule boldly in black ink, or typed to facilitate the photocopying of priced copies.
3.2.7 | The contractor is to allow to price for each item individually where ever possible. Items should not be grouped together quoting lump sums prices.
3.2.8 | No qualifications or alterations of any kind are to be made by the contractor to this schedule of works without the written agreement by the CA (Ridge & Partners LLP) or Environment Agency.
3.2.9 | The contractor is to refer to the Preliminaries section of this document for all applicable standards of all products and materials described below. Strict adherence to the requirements are required at all times
3.2.10 | The contractor is to refer to Materials and Workmanship clauses included with the Preliminaries section of this document for all applicable standards of all products and materials described below. Strict adherence to the requirements are required at all times.
3.2.11 | The contractor must examine this specification document, to ascertain all local conditions and restrictions, accessibility and visit site to ensure they have allowed for all necessary works (all labour, materials and equipment). No claims arising from the failure to do so, will be considered. The client will not be held responsible for any additional works claims which are deemed to be reasonably foreseeable which the contractor should have included for.
3.2.12 | The contractor's attention is also drawn to the Appendices detailing additional information required to complete the works. The contractor must strictly adhere to the requirements of these sections at all times while completing the works.
3.2.13 | The contractor must notify Ridge & Partners LLP upon the discovery of any discrepancies, errors or omissions within the specification documents or the works required immediately.
3.2.14 | The contractor shall be responsible for ensuring all employees including sub-contractors fully understand and work in accordance with the site’s rules and procedures. All contractors must wear company clothing, ID badges and have the correct PPE provisions.
3.2.15 | Allow to submit a detailed and site specific Pre-start Health & Safety Plan for the proposed works to Ridge & Partners LLP for comment and approval.
3.2.16 | The contractor is to allow for regularly removing waste materials from site (noting that there is limited access to the property, due to its location on an island in the River Thames. Where items are to be set aside, allow to record their condition and for safe and secure storage.
3.2.17 | The contractor is to leave the working areas clean and tidy upon at the end of the each working day.
3.2.18 | The contractor is to price for all works to be undertaken during "normal working hours" unless otherwise stated. Exact timings: to be confirmed, prior to works starting on site. No weekend or Bank Holiday works is permitted. No noisy works are permitted before 8.30am.
3.2.19 | Access to the site is only permitted for working on the proposed works.
3.2.20 | The contractor shall carry out the works without undue inconvenience and nuisance and without danger to building owners, occupants and visitors.
3.2.21 | When undertaking the specified works, they are to be in accordance with manufacturer's recommendations and guidelines.
3.3 | WORKS PROGRAMMING/ PHASING
3.3.1 | The works are to be undertaken in an occupied residential property. Therefore the contractor is to consider the use and occupancy of the site as part of phasing the works.
3.3.2 | The contractor is to outline their proposals for programming the works below. A project programme must be provided with the tender.
3.3.3 | Prior to commencing works on site, the contractor must produce detailed plans for means of access, site compound, storage facilities, means of escape and evacuation routes from the building during the course of the works. This is to be issued to Ridge & Partners LLP and the Environment Agency for approval a minimum of two weeks prior to the commencement of works.
3.3.4 | The works are to be undertaken in strict accordance with all Statutory Consents and Conditions required by the local Building Control and Planning Department where necessary. The contractor shall be responsible for ensuring all works undertaken comply with current regulations and byelaws.
3.3.5 | The successful contractor is to undertake the works utilising trades persons and operatives who have the relevant experience, competence and technical skills required to achieve the applicable standards of all works, products and materials described below.
3.3.6 | The contractor is to make a reasonable allowance for the inspection, instruction and agreement of any works by Ridge & Partners LLP during the works as necessary to complete the works to the reasonable satisfaction of Ridge & Partners LLP.
3.4 | CONSTRUCTION (DESIGN AND MANAGEMENT REGULATIONS) 2015
3.4.1 | The Construction (Design & Management) Regulations 2015 apply in full to these works. The contractor must comply with these regulations and ensure all required information is provided.
3.4.2 | The building is to remain in operation through all of the works. The contractor must maintain safe access routes for all occupants, residents, visitors, deliveries and own workforce. Provide adequate segregation to separate occupied areas from the works.
3.5 | REFURBISHMENT AND DEMOLITION ASBESTOS SURVEY
3.5.1 | The Environment Agency has provided an Asbestos Survey Report (dated 28 August 2019) by EDP Health, Safety & Environment Consultants Limited within Appendix C of this report. The report provides R&D information relating to the internal and external areas of the property. Should any asbestos containing materials be found, the contractor is to allow for the safe removal and disposal of all asbestos containing materials as detailed within the report that are identified within the proposed works area.
3.5.2 | Prior to the commencement of any works on site (including any site set up etc.), the contractor is to fully review the extent of Asbestos identified in the Survey Report provided within the Appendices. Where required the contractor is to employ a UKAS accredited Asbestos Surveying Specialist to undertake full Refurbishment and Demolition (R&D) inspection and survey the areas of the building not included in the Survey Report provided. This is to include for full testing of samples where applicable. Allow for all necessary asbestos air sampling, fibre identification, bulk sampling and bulk sample identification as required.
3.5.3 | The contractor is responsible for ensuring that all asbestos containing materials are correctly removed (if any are found to be present within the proposed working area), upon advice from the CA) from site by a UKAS accredited company with an approved Waste Carriers Licence and disposed of in accordance with current HSE and regulatory guidelines. Copies of disposal certificates are to be issued to Ridge & Partners LLP & the Environment Agency.
3.5.4 | During the works the contractor is to give notice immediately of suspected asbestos-containing materials if discovered during the Works and avoid disturbing such materials. Statutory risk assessments and details of proposed methods for its safe removal are to be undertaken and submitted by the contractor.
3.5.5 | The contractor is to note that all work to be carried out in accordance with Health & Safety Executive (HSE) guidelines, including The Analysts' Guide (HSG248), Asbestos: The Survey Guide (HSG264) and the Control of Asbestos Regulations 2012.
3.6 | SITE MANAGEMENT & WELFARE
3.6.1 | The building is due to be occupied for the duration of the works. The contractor will submit proposals within the Construction Phase Plan that outline the safety of the occupants for the duration of the works. This will be reviewed by Ridge & Partners LLP & the Environment Agency, prior to agreement.
3.6.2 | The contractor is to submit proposals for site set up, site accommodation and welfare facilities which will be discussed and agreed at the pre-commencement meeting. Limited space maybe provided within the grounds of the building depending on the extent of the facilities required by the contractor, however the contractor must not assume that any areas will be made available for the duration of the works.
3.6.3 | The contractor is to provide all necessary barriers; safety signage and site security required to carry out the works. This must include adequate 1800mm timber hoarding and or "Heras" type fencing, double clipped, around any external works areas and site compounds. The property must remain secure at all times and once works are complete at the end of each day. All necessary lighting, warning and prohibition signs must be provided. The contractor is to ensure that no unauthorised access is permitted within the curtilage of the site or beyond the building secured entrances.
3.6.4 | The contractor is to provide all necessary facilities and on-site welfare facilities including WC’s and a mess area for the duration of the works. The contractor is to ensure that these are well maintained for the duration of the works. The contractor must ensure that all existing service covers, footpaths and other surfaces are adequately protected from damage from the use of site facilities during the works.
3.6.5 | The contractor shall provide and maintain all necessary mechanical equipment, plant etc. of all descriptions required for the satisfactory completion of the works and remove all, as and when required, or when directed by Ridge & Partners LLP.
3.6.6 | Due to the nature of the site all operatives must respect the surrounding residential area and be respectful to neighbours and members of the public.
3.6.7 | The contractor is to allow for removal and safe disposal of all waste from site including skips, chutes and double polythene sheeting for all hazardous waste material in accordance with current Control of Asbestos Regulations 2012 and all Health & Safety legislation.
3.6.8 | The contractor is to allow for regularly removing waste materials from site.
3.6.9 | The contractor is to allow for an appointed site foreman to be on site at all times for the duration of the works. The site foreman must be able to communicate well with all client representatives, occupant and member of the public and be available to liaise directly with them at all times. Contact details of the site foreman must be provided at the pre-contract meeting.
3.6.10 | The contractor shall be responsible for obtaining any required permission from the Local Authority, Client or other bodies for the positioning of any temporary facilities or structures outside the premises required for completing the works and ensuring all works undertaken comply with current regulations and byelaws.
3.6.11 | The contractor is to allow for all necessary protection to prevent surfaces and areas adjacent to the works from being damaged by the proposed works.
3.6.12 | The use of any electrical equipment is to be strictly controlled and steps are to be taken to ensure that leads are not long enough to touch the water. All equipment should be connected to lines to prevent their accidental dropping into water causing possible electric shocks etc.
3.7 | ACCESS & SCAFFOLDING
3.7.1 | The contractor is to provide all necessary access equipment required for completing the specified works. Any scaffolding and access equipment must be installed/ erected and maintained to current national standards. Where this is permitted the contractor is responsible for maintaining the access routes and providing all necessary barriers, signage etc. to maintain safe working routes for the occupants, visitors and site operatives. Upon completion all access routes to be thoroughly cleaned and reinstated to match the existing standard.
3.7.2 | Scaffolding must be installed / erected and maintained to current Building Regulations, NASCC and national standards.
3.7.3 | The contractor is to allow for safe access in order to carry out all elements of the works. The contractor is deemed to have allowed for all alterations and amendments to the scaffold design to allow works by different trades and operatives needed to complete the works.
3.7.4 | Any damage to existing structures arising as a result of scaffold assembly and the works will be made good at the expense of the contractor.
3.7.5 | The contractor must allow to supply continuous robust good quality clean debris netting to all scaffolding, where required.
3.7.6 | The contractor is to ensure that at all times, scaffolding / access provisions to undertake the works in no way reduces the security of the property. The contractor is to ensure that the scaffolding is suitably secured and protected from all persons, including any potential intruders at all times. All ladders are to be locked away at second lift level or above at the end of each working day.
3.7.7 | The scaffold at all times, should comply with the latest Building Regulations and requirements.
3.7.8 | The contractor must ensure that whilst erecting and dismantling scaffolding that noise is kept to a minimum.
3.7.9 | When painting and / or spray cleaning is being carried out in the vicinity of members of the public, the contractor is to display adequate warning notices.
3.7.10 | The contractor is to submit proposals for all high level access measures including risk assessments and method statements along with details of proposed specialist sub contractor. Risk assessments and method statement are to be reviewed and discussed with Ridge & Partners LLP prior to the works commencing on site. Any reasonably requested amendments to the submitted documents are to be made and subsequently included within the documents prior to works commencing.
3.7.11 | It should be noted that, due to the location of Marsh Lock, there is no vehicle access to the curtilage of the property. Therefore the contractor must make arrangement to access the property via the foot bridge. This will limit the type of plant and equipment etc. that can be carried over to the property. The contractor is to visit site prior to works starting. Method of material and operative transport to be provided within this tender. Possible use of an Environment Agency barge boat may possibly be arranged following review (upon further clarity and confirmation from the Environment Agency).
3.7.12 | When working near or over the water, the contractor must undertake works in accordance with the rules and requirement stated by the Environment Agency, including buoyancy aid, of a tested and approved pattern, is to be worn by all personnel working over water.
3.7.13 | The contractor is to familiarise themselves with the Environment Agency, Constructing a Better Environment - Safety, Health, Environment and Wellbeing, Code of Practice prior to works starting on site. This document provides guidance on working methods around the water. This is provided within Appendix F.
3.8 | EXISTING SERVICES
3.8.1 | No disruption of services to the building shall be allowed without written consent of the CA and without adequate notice of the disruption being provided.
3.8.2 | Adequate protection of the existing services to the building will be required and any damage shall be made good to the satisfaction of Ridge & Partners LLP, the Environment Agency and the appropriate Statutory Authority, with the minimum of delay at the contractor's expense.
3.8.3 | The contractor is to ascertain for themselves the location of all services (which shall include gas, water, electricity, telecommunications services, fibre optic, drains (foul and surface), ducts, tubes, tunnels and the like, on and adjacent to the Site (underground and over ground)), that may be affected by the carrying out of the works and is to allow for all costs in connection with upholding, protecting and, if necessary, temporarily and / or permanently diverting and reinstating these services. All costs associated with works undertaken by Statutory / Service Utility Companies, including builder's work in connection, are to be allowed for by the contractor.
3.8.4 | All chambers, manholes, draw pits, plant and the like shall be adequately protected and any damage shall be made good at the contractor's expense.
3.9 | PROPOSED EXTERNAL WORKS
3.9.1 | The contractor is to allow for undertaking the proposed works as detailed below. Various photographs have been provided in Appendix B as a guide, to show the areas of the building (where possible) more detail.
3.1 | CHIMNEY STACKS
3.10.1 | The contractor is to carefully inspect the 2 No. free standing brick built chimney stacks and associated pots, flaunching etc.
3.10.2 | The contractor is to undertake isolated brickwork and mortar repairs / replacement to the main chimney (located at ridge level) and to the lower chimney (located adjacent to the satellite TV dish). Allow to rake out (to a depth of 20mm) and repoint by hand isolated areas of deteriorated and eroded mortar joints at low level and finish with a neat joint to match the existing. Repointing works to be with a new suitable sand / cement mix. Include to carry out brick replacements to approximately 10 No. bricks. New brickwork is to match the appearance of the existing.
3.10.3 | The contractor is to carefully remove and dispose all of the mortar flaunching to the chimneys. Make good surrounding surfaces, re-bed existing chimney pots and install new flaunching with new suitable sand/cement mix. Ensure a compact and watertight covering is provided.
3.11 | ROOF
3.11.1 | The contractor is to allow a Provisional Sum of £2,500.00 to undertake isolated roof repairs, following closer inspection from the scaffold. Repairs are to include replacement of damaged roof tiles, replacement of flashings, clean down of tree debris and moss build up etc.
3.11.2 | Allow to rake out all damaged, cracked, defective and missing sections of cement/mortar to verges and dispose. At this tendering stage, allow for approximately 10lm. Allow for the correct mortar/cement mix. Allow to make good any roof tiles and surrounding surfaces damaged during the works.
3.11.3 | The contractor is to retain the existing uPVC vented soffit and fascia, to the rear lower roof area. Allow to inspect and secure all fixings where loose or missing (if any) and clean all surfaces, using a non abrasive solution.
3.11.4 | The contractor is to carefully remove and dispose all of the existing timber facias, soffits and bargeboards to the property, including associated fixings, brackets and supports etc. Allow to make good any affected surfaces.
3.11.5 | The contractor is to supply and install new 18mm uPVC facias and bargeboards to the locations where the timber ones have been removed. Allow for Eurocell or similar approved. The new facias are to match the size and profile of the existing facias. Allow for new stainless steel fixing nails. Fixings to be a minimum of 600mm centres. Fixings to have protective caps installed. Include for suitable fixing joints, to match the size and profile of the facias. Ensure a 10mm expansion gap is provided between joints. Install as per manufacturer's guidelines and recommendations. Colour: White.
3.11.6 | The contractor is to supply and install new uPVC soffit boards to the locations where the timber ones have been removed. Allow for Eurocell or similar approved. The new soffits are to match the profile of the other soffits and are to be suitably sized in relation to the fascias. Allow for suitable 30mm fixings with protective caps. Include for suitable fixing joints, end caps, to match the size and profile of the soffits. Fix to facias. Install as per manufacturer's guidelines and recommendations. Colour: White.
3.11.7 | The contractor is to clean and clear out all remaining debris, sediment and vegetation growth etc. from the rainwater goods. Leave rainwater goods free flowing.
3.11.8 | The contractor is to allow to undertake a detailed inspection to the existing uPVC rainwater goods. Allow to realign rainwater goods and leave in good condition. In addition, include a Provisional Sum of £500.00 for isolated replacement sections of rainwater goods (size, profile and colour to match existing).
3.11.9 | The contractor is to allow for a full CCTV survey and flush through/clean of all drainage on site following completion of works and include for written report to be issued to CA. Allow to price for any subsequent works once report is provided.
3.12 | FRONT PORCH (FRONT ELEVATION FACING LOCK & RIVER)
3.12.1 | The contractor is to allow undertake isolated timber repairs to the existing timber porch, located above the door within the front elevation (facing lock and river). Include for spliced repairs or fill using a two part filler, to all those areas of the porch that are rotten and defective. Ensure suitable detailing and bonding to surrounding surfaces. New repairs to match the existing profile, size and design. Leave ready for decoration.
3.12.2 | The contractor is to carefully remove and dispose of the existing lead roof covering to the entrance porch. Allow to inspect the timber decking forming the roof and make good affected surfaces (where required). Supply and install new lead roof covering. Provide a secure fixing / detailing to the adjacent elevation. Include to apply Calder or similar approved, patination oil to all of the leadwork. Allow for 2 No. coats. All works to be undertaken in accordance with The Lead Sheet Association and the manufacturer's recommendations and guidelines.
3.12.3 | The contractor is to fully rub down, prepare and redecorate the existing timber front porch, located to the front elevation. Allow for suitable Dulux external grade paint or similar approved, 1 No. undercoat and 2 No. top coats. Colour: White.
3.13 | HALLWAY ENTRANCE PORCH (LEFT HAND ELEVATION)
3.13.1 | The contractor is to allow to fully overhaul, repair and resecure the existing timber porch, located above the door within the left hand elevation (door leading to the internal hallway). Include for timber splice repairs or fill using a two part filler, to all those areas of the porch that are rotten and defective. Ensure suitable detailing and bonding to surrounding surfaces. Provide a secure fixing to the elevation. New repairs to match the existing profile, size and design. Leave ready for decoration.
3.13.2 | The contractor is to carefully remove and dispose of the existing lead roof covering to the left hand elevation entrance porch. Allow to inspect the timber decking forming the roof and make good affected surfaces (where required). Supply and install new lead roof covering. Provide a secure fixing / detailing to the adjacent elevation. Include to apply Calder or similar approved, patination oil to all of the leadwork. Allow for 2 No. coats. All works to be undertaken in accordance with The Lead Sheet Association and the manufacturer's recommendations and guidelines.
3.13.3 | The contractor is to fully rub down, prepare and redecorate the existing timber entrance porch, located to the left hand side elevation. Allow for suitable Dulux external grade paint or similar approved, 1 No. undercoat and 2 No. top coats. Colour: White.
3.13.4 | Cost Option: The contractor is to carefully remove and dispose of the existing timber porch and roof covering, located above the door within the left hand elevation (door leading to the internal hallway). Allow to make good and decorate all surround and affected surfaces, including any associated render repairs. Allow to supply and install a new timber frame porch with lead roof covering (ensure it is the same or very similar in appearance to the existing porch). Provide a secure fixing / detailing to the adjacent elevation. Include to apply Calder or similar approved, patination oil to all of the leadwork. Allow for 2 No. coats. All works to be undertaken in accordance with The Lead Sheet Association and the manufacturer's recommendations and guidelines. Allow for suitable Dulux external grade paint or similar approved, 1 No. undercoat and 2 No. top coats. Colour: White. Cost..................................................... | Cost Is Not To Be Carried Forward | Cost Is Not To Be Carried Forward
3.14 | WINDOWS & DOORS
3.14.1 | The contractor is to note that the external window and door replacement works are to be undertaken on a room-by-room basis (provide detailed breakdown, as part of programme of works). This is to allow the works to progress, whilst the residential property can maintain operational.
3.14.2 | The contractor is to allow to remove the existing windows and doors to the property, including the existing timber frame and cills. (including the Mess Room's windows and door) and allow to replace them with new uPVC ones throughout. The works also include to replace the existing timber framed circular window, within the front elevation.
3.14.3 | The contractor is to review the window and door replacement specification in Appendix A (allow to provide cost for windows and doors within this pricing document), as well as the elevation drawing in Appendix D.
3.14.4 | The contractor is note that all the window replacement works are to be undertaken in strict accordance with manufacturer's specification, recommendations and guidelines. All works are to achieve Building Regulations and British Standards.
3.14.5 | The contractor is to note that as part of the tender submission, the size of the existing window and door opening is to remain as existing for the installation of the new windows and doors. This includes cill heights. No alterations are at present planned to the opening sizes.
3.14.6 | The contractor is to carefully remove and set aside the existing secondary glazing provided to the circular window in Bedroom 2 (front elevation). Allow to suitably protect and reinstate on completion (subject to further instruction from the Environment Agency).
3.14.7 | The contractor is to note that the following doors are to be replaced, as part of the works, as scheduled in Appendix A: a) Kitchen (front elevation). b) Hallway (left hand elevation). c) Mess Room (left hand elevation) d) Utility Room (rear elevation). e) Log Store (rear elevation).
3.14.8 | The contractor is to ensure the exterior window and door reveals are suitably repaired, detailed and made watertight, prior to the installation of the new windows and doors. This includes any repairs that are required, to the reveals etc. following the removal of the existing windows and door, including the timber frames and cills. Allow a Provisional Sum of £3,000.00 for any associated repairs and remedial works to the reveals.
3.15 | ELEVATIONS
3.15.1 | A pre-application survey of the property is to be carried out by the contractor to determine the suitability of the substrate to receive the products and whether repairs to the building structure are necessary before application.
3.15.2 | The contractor is to determine preliminary treatment and existing condition of the background brickwork, detailing around existing windows, doors and at open eaves, damp-proof course level, exact position of movement joints, areas where flexible sealants must be used, any alterations to external plumbing.
3.15.3 | The contractor is to note that where they are due to undertake various render repairs (as stated below), if these are in the location of existing building features (signage, flood markings, cabling etc), then they are to carefully remove all detailing in order to necessitate the application of the new render. Care is to be taken to accurately record the positioning and levels to ensure detailing is replaced in the same position as was previously installed, in particular the level of the flood markers located to the front of the property. The contractor is to take photographic evidence of the location of the markers prior to commencement of the works.
3.15.4 | The contractor is to ensure that where items / existing building features have been removed for later reinstatement, they are to stored in a safe, watertight and secure location for the duration of the remedial works. All items are to be inspected prior to reinstatement. The contractor is to allow to reinstate upon completion of the render works.
3.15.5 | The contractor is to carefully rub down and clean the existing external elevation surfaces, prior to the commencing of brickwork mortar and render repairs. Leave surfaces ready for further repair works to be suitably undertaken.
3.15.6 | The contractor is to hack off all of the existing loose, cracked and defective render forming the elevations of the property and dispose. At this stage the contractor is to allow for 30 sqm. Exact locations of the render repairs are to be confirmed, following combined site inspection with the contractor, Ridge & Partners LLP and the Environment Agency.
3.15.7 | Where areas of the existing render have been removed, the contractor is to allow a Provisional Sum of £3,000.00 to make good any identified cracks and associated remedial works to the elevations before the render repairs can be undertaken.
3.15.8 | The contractor is to hammer test the render elevations to ensure all defective areas of render are allowed to be removed and replaced. Allow remove all areas of loose, cracked and debonding external render.
3.15.9 | Where required, the contractor is to allow to carefully rake out areas of existing perished and defective mortar to the elevations. Allow to rake out to a depth of 25mm. Allow to prepare joints and repoint with new suitable lime based mortar. New mortar is to match existing in terms of size, colour, style and design. In addition, if required, allow to treat the cracking with Wykamol Crack Sealer Plus Kit (or similar approved) as per manufacturer’s instructions and recommendations).
3.15.10 | To the areas of cracking, allow to dress off the wall surface a minimum 200mm from the defect in all directions and leave flat and suitable to receive the following treatment: Apply 400mm (minimum) wide stainless steel gauze centrally to and for the full length of the crack. Fix using fixings at maximum 300mm centres either side of the crack prior to the application of the new render.
3.15.11 | The contractor is to supply and install a new rendered finish to the defective area forming the external elevations. Ensure there is no bridging of any damp proof course, notably to the elevations forming the rear and side extensions.
3.15.12 | The contractor is to ensure the newly installed render is correctly formed and detailed around angles forming the elevation etc. and that surfaces are level, flush and match the shape and profile of the surrounding surfaces.
3.15.13 | The contractor is to supply and install a new lime based render to the previously rendered areas of the elevations, where the defective areas have allowed to be removed (30sqm for tendering purposes). Including for scratch coat and final float coat, and for providing a suitable key detailing to the surfaces, to ensure a suitable bond is applied. Allow for any movement joints, flashings, trims as necessary and to form a new suitable Bell Drip detail away from the ground level, at the base of the render. New render is to match the existing in terms of size and colour.
In addition, the contractor is to allow for the following:
a) Fix stainless steel expamet to external angles and render stops to both horizontal and vertical points.
b) Brush clean all surfaces to remove debris etc.
c) Apply a Unibond coat (or similar approved) to the affected wall surfaces.
d) The new render is to be a 19mm coat 1:1:6 cement: lime: sand, applied in two coat work (or similar appro. Apply first coat render a minimum of 12mm thick. Allow for a scratch coat. Apply the second float coat finished with steel trowel, to a smooth surface.
e) Leave surfaces ready for redecoration.
3.15.14 | Please note the above is not an exhaustive list and the contractor is responsible for installing the new render installation, in line with current regulations, manufacturer's guideline and recommendations and best practice.
3.15.15 | Cost Option: The contractor is to carefully remove and dispose of all the existing render to the external elevations of the property. Then allow to supply and install a new lime based render to all of the elevations forming the property. Including for scratch coat and final float coat, and for providing a suitable key detailing to the surfaces, to ensure a suitable bond is applied. Allow for any movement joints, flashings, trims as necessary and to form a new suitable Bell Drip detail away from the ground level, at the base of the render. New render is to match the existing in terms of size and colour. Confirm the sqm allowed for ....................................... Cost ..................................................... | Cost Is Not To Be Carried Forward | Cost Is Not To Be Carried Forward
3.15.16 | The contractor is to allow to check for initial shrinkage in the newly rendered layers. If shrinkage is noted, allow to repair accordingly and make good.
3.15.17 | The contractor is to ensure the newly installed render is correctly formed and detailed around angles forming the elevations etc. and that surfaces are level, flush and match the shape and profile of the surrounding surfaces.
3.15.18 | Following the completion of the various render and brickwork repairs (as stated above), the contractor is to fully prepare and decorate all the external elevation finishes throughout the building. Allow for applying 1 No. sealing coat and 2 No. full coats of Sandtex External Masonry paint (or similar approved). Colour: to be confirmed.
3.15.19 | The contractor is to fully rub down, prepare and redecorate previously decorated small section of decorated elevation brickwork at low level, to the perimeter of the property. Allow for two coats of Dulux external grade paint. Colour to match existing.
3.15.20 | The contractor is to refix any loose cabling which is present to the property, as a result of the works, using suitable fixings.
3.15.21 | The contractor is to fully rub down, prepare and decorate the exposed circular metal strengthening supports, located within the front and rear elevations. Allow to make good surfaces, prepare and redecorate all previously decorated elevations, using Dulux external grade paint or similar approved, 2 No. coats. Colour: Black.
3.15.22 | The contractor is to fully rub down, prepare and decorate the flood marker signage / plaques, located within the front elevation. Allow to make good surfaces, prepare and redecorate all previously decorated elevations, using Dulux external grade paint or similar approved, 2 No. coats. Colour: Black & White (to match existing).
3.15.23 | The contractor is to fully rub down, prepare and decorate the 4 no. metal hanging basket angled supports, located within the front elevation. Allow to make good surfaces, prepare and redecorate all previously decorated elevations, using Dulux external grade paint or similar approved, 2 No. coats. Colour: Black.
3.15.24 | The contractor is to fully rub down, prepare and decorate the various waste pipework and the soil and vent pipe (previously decorated), located on the left hand elevation. Allow to make good surfaces, prepare and redecorate all previously decorated elevations, using Dulux external grade paint or similar approved, 2 No. coats. Colour: to match existing.
3.15.25 | The contractor is to allow undertake isolated timber repairs to the various timber posts forming the flood barrier supports, either side of the external doors (front, side and rear elevations). Include for spliced repairs or fill using a two part filler, to all those areas that are rotten and defective. Ensure suitable detailing and bonding to surrounding surfaces. New repairs to match the existing profile, size and design. Leave ready for decoration.
3.15.26 | The contractor is to fully rub down, prepare and redecorate the existing various timber posts forming the flood barrier supports, either side of the external doors (front, side and rear elevations). . Allow for suitable Dulux external grade paint or similar approved, 1 No. undercoat and 2 No. top coats. Colour: to be confirmed.
3.16 | HARDSTANDING AREA ADJACENT TO KLARGESTER
3.16.1 | The area of the proposed is within the rear garden, adjacent to the septic tank / Klargester system.
3.16.2 | The contractor is to carefully lift, clean and set aside the existing areas of paving forming the patio area, adjacent to the septic tank / Klargester system. Remove any weed and / or root growth to the affected area and treat with weedkiller. Where any paviours are cracked and / or defective, allow to dispose. The area is approximately 8 x 11 no. paviours (contractor is to measure the exact size and area of works required).
3.16.3 | Following the removal of the existing paving (as noted above), the contractor is to excavate, bed and lay 25mm of sharp sand compacted base to form the ground for the new area of paving. Ensure the ground and area of paving is level (allow to adjust levels where required).
3.16.4 | The contractor is to relay the existing set side paving on the newly prepared compacted base. Where required allow to supply and install new paviours to replace any cracked and defective ones that have been disposed of. Any new paving is to match the remaining paving, in terms of style, size, profile, colour etc. Include for brushed sand joints. Ensure ground, paving and all surfaces are level throughout with surrounding surfaces.
3.16.5 | The contractor is to confirm the number of paviours they are to replace….....................
3.17 | HARDSTANDING AREA FORMING REAR PATIO
3.17.1 | The area of the proposed work is to the patio within the rear garden, adjacent to the rear elevation.
3.17.2 | The contractor is to carefully remove, set aside and protect any of the occupant's furniture / belongings etc. within the patio area. Upon completion of the proposed patio works allow to reinstate.
3.17.3 | The contractor is to carefully lift and dispose of any cracked / defective paviours in this area, and dispose. Allow to clean all areas of retained paving (using a non abrasive solution) to remove all areas of dirt build up and staining. Remove any weeds and vegetation growth to the affected area and treat with weedkiller.
3.17.4 | The contractor is to supply and install new paviours to replace any cracked and defective ones that have been disposed of. Any new paving is to match the remaining paving, in terms of style, size, profile, colour etc. Include for brushed sand joints.
3.17.5 | The contractor is to confirm the number of paviours they are to replace….....................
3.17.6 | The contractor is to ensure the ground, paving and all surfaces are level throughout with surrounding surfaces. New paving is to be installed on newly prepared compacted base of 25mm sharp sand Allow to excavate where required. Ensure the ground and area of paving is level (allow to adjust levels where required).
3.18 | HARDSTANDING AREA LEADING TO THE MESS ROOM ENTRANCE DOOR
3.18.1 | The area of the proposed work is to the hardstanding adjacent to the left hand elevation, leading to the Mess Room entrance door. This is a small area of paving (approx. 2 x 6 No. paviours).
3.18.2 | The contractor is to carefully lift and dispose of any cracked / defective paviours in this area, and dispose. Allow to clean all areas of retained paving (using a non abrasive solution) to remove all areas of dirt build up and staining. Remove any weeds and vegetation growth to the affected area and treat with weedkiller.
3.18.3 | The contractor is to supply and install new paviours to replace any cracked and defective ones that have been disposed of. Any new paving is to match the remaining paving, in terms of style, size, profile, colour etc. Include for brushed sand joints.
3.18.4 | The contractor is to confirm the number of paviours they are to replace….....................
3.18.5 | The contractor is to ensure the ground, paving and all surfaces are level throughout with surrounding surfaces. New paving is to be installed on newly prepared compacted base of 25mm sharp sand Allow to excavate where required. Ensure the ground and area of paving is level (allow to adjust levels where required).
3.19 | PROPOSED INTERNAL WORKS
3.19.1 | The contractor is to carefully remove, set aside and protect any surface or hung/mounted furniture, curtains, blinds or items / displays etc. to allow for the internal repairs and redecoration works around the window and door reveals. Upon completion of the works allow to reinstate.
3.19.2 | Following the completion of the various external repairs and the installation of the new external uPVC doors and windows, the contractor is to allow for various isolated internal repair and redecoration works to the affected window and door reveals within the property.
3.19.3 | The contractor is to hammer test the plaster forming each window and door reveal within the property. Allow remove all areas of loose and debonding plaster.
3.19.4 | The contractor is to allow to clean, fill, repair and make good areas of cracking (where required) to each window and door reveal within the property. Then replaster affected surfaces with British Gypsum 3mm Thistle Multi-Finish top coat (where required). Include to make good around the edges of the reveals, where they abut the other wall surfaces and the newly installed windows and doors. Allow a provisional quantity of 2lm per window and door opening for pricing purposes.
3.19.5 | The contractor is to allow to redecorate all affected window and door reveals where repairs have been undertaken (as stated above). Allow for all preparation and two coats of Dulux Trade Diamond High Performance Eggshell paint. Include for all preparation works as required and recommended by the manufacturer. Colours are to match existing.
3.2 | CLEANING & COMPLETION
3.20.1 | The contractor is to leave the property clear, debris free and tidy on completion of the works, to the satisfaction of Ridge & Partners LLP, including the removal of all debris, materials plant and equipment etc., ready for inspection and handover.
3.20.2 | The contractor is to clean all the window and door glazing and frames internally and externally throughout.
3.20.3 | Allow for providing all necessary installation certification and warranties for all materials and installations included within the works. All certification and testing must be undertaken by a nationally qualified specialist.
3.20.4 | The contractor is to provide and ensure Health and Safety File and Building Manual for the works has been issued for comment 1 week prior to completion. The Health and Safety File is to include all O&M information for the works.
3.20.5 | Upon completion ensure that 2 No. A4 sized paper copies of the Health and Safety file and as built drawings are provided to Ridge & Partners LLP for issue to the Environment Agency one week after Practical Completion. A full and completed electrical copy is also to be provided.
3.20.6 | The contractor is to ensure that upon completion of the works, all the insurance backed guarantees covering the external works, including the installation and workmanship etc., are to be handed to Ridge & Partners LLP and included within the O&M Manuals for the works.
3.21 | CONTRACTOR RATES
3.21.1 | The contractor is to provide rates for works, which will assist with any additional works which may be found to be required, once works commence on site. Any additional works are to be at the agreement of Ridge & Partners LLP and the Environment Agency. | Note | Note
3.21.2 | The contractor is to confirm their SQM rate for undertaking any additional external render replacement….........................(sqm). | N/A | N/A
3.21.3 | The contractor is to confirm their SQM rate for undertaking any additional external repointing of brickwork….........................(sqm). | N/A | N/A
3.21.4 | The contractor is to confirm their LM rate for undertaking any additional external repointing of brickwork….........................(lm). | N/A | N/A
3.21.5 | The contractor is to confirm their LM rate for undertaking any additional timber joinery replacement (fascia / soffit for example) ….........................(lm). | N/A | N/A
3.21.6 | The contractor is to confirm their SQM rate for undertaking any internal plaster replacement….........................(sqm). | N/A | N/A
SECTION 3 - COSTED TOTAL (Excl VAT) £