## Sheet1
Highways England Confirmation of Task Order
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties. Redacted under Section 40 and Section 43 of the FOI Act (2000)
Supplier: | Atkins
Project Title: | M20 Lorry Area Interim Solution – Task Order No.2
Contract Ref. | 2589 | CPA No.: | 4094486 |  | BPA No.: | 4097379
PIN Description: | M20 Op Stack Interim Solution | Sub Pin: | 12 |  | PIN No.: | 568002
HE Reference: | SE 67 17/18ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5142263.436 | Consultant Contact: |  |  | Redacted
Start & End Date: | 22/12/2017 - 31/03/2018 | CTO Authorisation No. |  |  | 11999
Task Overview
1. For Traffic Management Studies in relation to an Interim Solution to manage the effects of Brexit on the M20. 2. HE Project Manager Redacted maintains a ‘Works Brief’ document; the 1st revision was sent on 16/11/17, subsequently updated on 29/11/17. This document and the associated email communication form part of the formal instruction of works from HE to Atkins. 3. A combined PCF approach is proposed, this is reflected in the draft PCF Document sent to Atkins on 7th December 2017 07/12/17. This document and the products listed within will be refined as part of this Task Order 2 and changes will be communicated and agreed with Atkins accordingly. An indicative allowance of Redacted has been allowed in for tasks associated with PCF refinement and scope changes. 4. It's noted that this Task Order covers time on Task 2 from start of November 2017. However it also subsumes time from the start of October 2017 from Task 1 where we have agreed with Atkins that additional costs accounted will be reflected in this CTO and Task Order 2. 5. For the avoidance of doubt, Task Order 2 includes ‘DfT Optioneering’ (modeling) to support a full report to DfT and enable a decision to be undertaken in early 2018. In parallel to this, Atkins are to develop the 1st Stage Interim Solution (J8/J9 temporary contraflow on the M20 London-bound with temp signs and temp steel barriers), seen as the common ground for all options under consideration option. Note that Ch8 temporary traffic management design remain the responsibility of the Works Contractor, in this case, BB as the ECI Contractor providing Atkins with early deliverability and construction advice. Detail Design of a selected option will be undertaken under a separate CDF order.
Task Objectives and Milestones
Objectives • Provide timely and high quality advice to Highways England in respect of solutions to Operation Stack.
Task Outcomes
Outcomes • PCF Products (to be agreed). • Early delivery of alternatives to Operation Stack.
Project Risk and Management
Risks • Task includes open ended scope of requirement and timescales. Note rates build up therefore on basis of generic/estimates rates per grade. • Fees include circa Redacted sub-contractor costs for analysis of LiDAR data additional Redacted of pavement and drainage surveys as appropriate; itemized as 'additional items' and agreed with HE to be invoiced as expenses items Management • Framework Contract management – Redacted • Framework Task management – Redacted • Project Manager – Redacted • Project Director – Redacted. note that for the purpose of delivering the requirements of this bespoke task, it draws on specialist technical input; therefore to facilitate this we propose to charge Redacted at non-rate capped Redacted per hour
Project Title: | M20 Lorry Area Interim Solution – Task Order No.2 |  |  |  | HE Reference: | SE 67 17/18ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 67 17/18ATK | 376930 | 0 |  | 2018-01-05 | 376930 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 376930
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 376930
Total Project Fee Estimate |  |  |  |  | 376930
Name | Grade | Hours |  | Hourly Rate | (£)
M20 (Director) | Director | Redacted | @ | Redacted | Redacted
M20 (Associate Director) | Associate Director | Redacted | @ | Redacted | Redacted
M20 (Principal Planner/Engineer) | Principal Planner / Engineer | Redacted | @ | Redacted | Redacted
M20 (Senior Planner/Engineer) | Senior Planner/Engineer | Redacted | @ | Redacted | Redacted
M20 (Planner/Engineer) | Planner/ Engineer | Redacted | @ | Redacted | Redacted
M20 (Assistant Planner/Engineer) | Assistant Planner/ Engineer | Redacted | @ | Redacted | Redacted
M20 (Senior Technician) | Senior Technician | Redacted | @ | Redacted | Redacted
M20 (Technician) | Technician | Redacted | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2018-01-08 |  | Works Total |  | Redacted
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  | LiDAR Data Analysis |  | Redacted
|  |  | Sub Total |  | Redacted
|  |  | Expenses |  | Redacted
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 391930