Joint Schedule 2 (Variation Form)

Crown Copyright 2019

Joint Schedule 2 (Variation Form)

This form is to be used in order to change a contract in accordance with Clause 24

(Changing the Contract)

|  |  | The Infected Blood Inquiry ("the Authority”) Law Absolute Limited ("the Supplier") |
| --- | --- | --- |
| Contract name: | PROVISION OF 75 PARALEGALS FOR THE INFECTED BLOOD INQUIRY (“the Contract”) |  |
| Contract reference number: | CCCB20A03 |  |
| Variation initiated by: Variation number: Date variation is raised: Proposed variation | The Authority. 2 24/05/2021 1. The Contract is varied as follows: The Contracting Authority would like to invoke their extension option to extend the Contract from its original end date of 25th May 2021 for one year. This would mean the new end date will be the 24th May 2022. |  |
| Reason for the variation: | The Authority wishes to retain the Supplier’s services for the duration of the contract extension. |  |
| An Impact Assessment shall be provided within: | N/A |  |
| Likely impact of the proposed variation: | N/A |  |

| Financial variation: | None, but the Services during the extension period will be provided at the pre-agreed rate of up to a maximum of £4,031,232.00 Excluding VAT. |
| --- | --- |

1. This Variation must be agreed and signed by both Parties to the Contract and shall only be effective from the date it is signed by the Authority.

2. Words and expressions in this Variation shall have the meanings given to them in the Contract.

3. The Contract, including any previous Variations, shall remain effective and unaltered except as amended by this Variation.

Signed by an authorised signatory for and on behalf of the Authority.

Signature

Date

Name (in Capitals) Address

25/5/2021

REDACTION

REDACTION

Signed by an authorised signatory to sign for and on behalf of the Supplier

Signature

Date

Name (in Capitals) Address

27 May 2021

REDACTION

REDACTION