## Sheet1
CLARIFICATION LOG
Tender: | Riverbank repairs, Henley on Thames
Tender Reference:
Clarification deadline: | 3rd January 2025
Published Date: | 6th January 2025
Version number: | 2
Number | Clarification | Response | Reply date
1 | Is the contractor required to make good any damage to the grass and footpath as a result of anchoring the piles? | Yes | 2024-11-26
2 | Regarding 4.4.5 site security. The contractor must demonstrate in their construction phase plan how they will ensure that all areas where work is being carried are separated from areas remaining available to the general public. Marsh Bank Slip states road pins and tape is acceptable, New Street Slip says heras fencing. Please confirm that Heras fencing is not required to the bank slip and road pins, tape and crowd barrier fencing is acceptable | The contractor is responsible for site security and for risk assessing and providing the most appropriate option. If road pins, tape and crowd barrier fencing has proven sufficient for previous works then we are happy to accept this option. However, should it prove that more robust measures, such as heras fencing, are needed, then the contractor should allow for this. | 2024-11-26
3 | Please can you confirm that the new piles will be at least 6mm thick as per the requirement of a medium duty pile. | Yes | 2024-11-26
4 | Please can you confirm that the new anchor piles have to be at least 1m long driven piles and they cannot be flat plate, steel angle or suchlike. | Yes | 2024-11-26
5 | Please can you confirm whether the tropical marine hardwood rubbing boards can be 50mm thick and 150mm wide and that the capping pieces can be 50mm thick and 250mm wide. | Yes | 2024-11-26
6 | Regarding 4.9.2 Please confirm that we are to still price in CDM Welfare facilities and that the use of facilties does not negate this requirement | It is the contractors responsibility to provide any necessary welfare facilities. The public toilets should be accessible and open during the working hours. However, these should not necessarily be relied upon. | 2024-11-26
7 | 5.2.1 Services, will we be required to apply for a stat service pack? Because 5.11.2 says "All known services information will be supplied at time of bid". | We are not aware of any existing services in either location, but it is the responsibility of the contractor to check services. | 2024-11-26
8 | 5.3.5 States repairs to grass. It says "5.3.4 Any damage caused to grass is to be rectified by seeding the affected area as described in the attached Specification, at the Contractor’s own expense". We have not been provided with a copy of the specification. | The 'affected area' refers to the areas on which the works are being carried out. There are no exact specifications for the seeding, but it should be carried out to the Council's satisfaction. | 2024-11-26
9 | Occupancy of adjacent moorings, i.e. passed chaniage 100. Please can you confirm that no veseels will be moored there and that all boats will be removed prior to mobilisation. | The Council will ensure all boats are moved prior to mobilisation. This will include reasonable allowances for space adjacent to the moorings, to be agreed with the successful contractor. | 2024-11-26
10 | Do you have drawings for the repairs? | No, we would expect the successful contractor to provide technical drawings | 2024-12-03
11 | Can you confirm that you intend to contract the works with an unmodified standard form, such as NEC4:ECC? | Yes, we intend to use an NEC4 contract | 2024-12-03
12 | Is the project being conducted under permitted development? | Yes, it meets the criteria for permitted development under GPDO 2015 Part 12 | 2024-12-03
13 | Has a preliminary ecological appraisal been undertaken? If not, is the contractor to allow to perform one? | No, a PEA has not been undertaken and the contractor should allow to perform one. | 2024-12-03
14 | For the bidding purposes can we assume that there are no protected flora or fauna or INNS withing the proposed works areas, including the enabling and temporary works? | Yes. | 2024-12-03
15 | You are requesting a 5-year guarantee for all workmanship. Can you confirm if the defects liability period is 5-years beyond practical completion? If so, can this be reviewed to something more reasonable? | No, the defects liability period is expected to be c.6-12 months. | 2024-12-03
16 | Are we to presume that the frontage of the piled wall and the footprint of the slipoway is to remain within the current alignment / footprint without any extension towards the river channel? | Yes, the frontage should remain within the current alignment. | 2024-12-03
17 | Presumably the contractor is to be the Principal Contractor under CDM 2015, but who is destined to be the Principal Designer under CDM 2015? | The successful contractor would be expected to be the Principal Designer. | 2024-12-03
18 | There are a number of items that do not appear to be fully developed and designed and tehre is also no design scope or specification for the project. Are you expecting the contractor to develop the design fully? | Yes. | 2024-12-03
19 | What level of submission do you require (CG300? CESWI?) and have you categorised the structures (CAT0/1/2/3?) What periods within the programme would you like the contractor to allow for TAA? | We will work with the successful contractor on any additional requirements that may apply. The contractor can list any assumptions in their tender response form. | 2024-12-03
20 | Do you have a ground investigation report available with boreholes at least as deep as the proposed pile length? If not, and if the contractor is to develop the design, should we allow to conduct a ground investigation to inform the embedded wall design? | There is no ground investigation report and the contractor should allow for all measures they feel are prudent in developing the design for the works. These should be made clear in the tender response form. | 2024-12-03
21 | Do you have a design life requirement for the project? | We do not have a fixed design life requirement, but we would expect it to be within the range of 20-30 years minimum. | 2024-12-03
22 | If the contractor is not required to develop the design, please can you provide more details with respect to the piles, tie bars, walers, timber and concrete works? | N/A | 2024-12-03
23 | We note that the Contractor is to provide all buried and overhead service checks. Presumably you will accept a bid that qualifies the assumption that there is no service that interferes with the proposed works, including any enabling and temporary works? | Yes, the bid should be on the basis that there is no service that interferes with the proposed works. | 2024-12-03
In the event of queries please contact: Sheridan Jacklin-Edward, clerk@henleytowncouncil.gov.uk / 07595 608577.