## Sheet1
Clarification Log Pool Energy Centre Feasibility Study 2015
Number | Date | Document | Section | Subject | Page | Clarification Question | Response | Date Responded | Provided To
1 | 2015-08-21 | RFQ |  | Contract Length | 30 |  | It has come to our attention that the requirements of Phase 2 within the budget allocated may not be achievable. The commercial element of this tender will therefore be scored using the price quoted for Phase 1 only. Subject to the decision following the recommendations contained within Phase 1 and the the confirmation of the budget for Phase 2 a detailed scope of works for Phase 2 will be agreed with the successful applicant. Please provide a breakdown of anticipated costs for Phase 2 for information only. | 2015-08-21 | All
2 | 2015-08-21 | RFQ |  | Commercial Assessment | 26 and 27 |  | Due to the uncertainty of the funding situation for Phase 2 of the works the contract period is expected to be from 23/9/15 - 30/06/15 | 2015-08-21 | All
3 | 2015-08-19 | RFQ |  | Appendices | 18 and 20 | The Pool Energy Centre Feasibility Study RFQ (EDC/DN/01) makes reference to a tender undertaken in January 2013 for which no bids were received. Page 18 of the RFQ states “The reasons for this are outlined in the summary and recommendations document (Appendix 3).” We have reviewed the Appendix documents available and this document does not appear to be included. Also, page 20 of the RFQ refers to Appendix D (“A review and refresh of major constraints identified (please see Appendix D)”) and there is no Appendix D in the uploaded documentation. Please could you confirm if these documents will be made available as part of the tender process? | Apologies - these reports were missing from the original appendix list. These have been uploaded onto Contracts Finder and are referred to as:- PEC Tender Evaluation (appendix 3) Delivery Plan for Phases 1 & 1A (appendix d) | 2015-08-21 | All