| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of Consultancy for the Cabinet Office: Civil Service Pensions (The Contract) |  |  |
| Contract Reference: | CCCC20A58 | Contract Change Number: | 2 |
| Date CCN issued: |  | Date Change Effective from: |  |
| Between: The Cabinet Office (The Customer) and Acuity Business Solutions (The Supplier) - The Contract is varied as follows: - A value uplift of£27,200 for use on the following elements - Ongoing support for the Comms and Engagement Programme, including further development of the strategy and the production of various associated artefacts – Redacted - Ongoing development of the personae/Customer Journeys – Redacted - Handover and Skills transfer – Redacted - A Time extension of ten (10) weeks shall apply commencing from the date which this Change is effective from. - This Modification is permitted as per PCR 2015 regulation 72 (1)(B) “for additional works, services or supplies by the original contractor that have become necessary and were not included in the initial procurement, where a change of contractor cannot be made for economic or technical reasons such as requirements of interchangeability or interoperability with existing equipment, services or installations procured under the initial procurement, or would cause significant inconvenience or substantial duplication of costs for the contracting authority, Cost of extension does not exceed 50% of the value for the original contract “ - The original Contract had a value of £88,900.00. The value of this modification is £27,200. This is below 50% of the original Contract’s value. - Due to the limited value of the modification devotion of resources on going out to market will not be proportionate and will result in a significant inconvenience and substantial duplication of costs already incurred. - As the required services are in support of the original Contract, a change of economic operators would result in further delays and duplication of costs in order for a new Economic Operator to be brought up to speed and have the same level of understanding as the Supplier. - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| Change authorised to proceed by: (Customer’s representative): Signature; Print Name and Job Title; Date. |
| Authorised for and on behalf of the Supplier: Signature; Print Name and Job Title; Date. Redacted; Redacted; 23/11/2020. |
| Authorised for and on behalf of the Customer: Signature; Print Name and Job Title; Date. Redacted; Redacted; 06/11/2020. |