- Completed Commissioning Letter

Solutions Strategy Research Facilitation Ltd

‘REDACTED TEXT’

NN12 8EQ

22nd February 2018

Dear ‘REDACTED TEXT’

,

Research and Evaluation Framework Agreement – Lot 3

# Award of contract for the supply of Fraud and Error Deterrence and Prevention Message Testing

Thank you for your response to the Specification for the above Commission by Department for Work and Pensions (the Customer) through the Research and Evaluation Framework dated 26th March 2015 between (1) Secretary of State for Business, Innovation and Skills and (2) Solutions Strategy Research Facilitation Ltd (the Framework Agreement).

Attachment:	A.	Supplemental Tender dated 14/02/18

B.	Specification for 30/01/18

C. 	Feedback

The Call –off Terms and Conditions for this Contract are those set out in [Schedule 5] to the Framework.

The agreed total charges are £35,230.00 exclusive of VAT which should be added at the prevailing rate. The agreed invoice schedule is as follows:

| Invoice no. | Date | Activity | Invoice amount |
| --- | --- | --- | --- |
| 1 | 30/03/2018 | Project set up and fieldwork material development | ‘REDACTED TEXT’ |
| 2 | 27/04/2018 | Recruitment and fieldwork | ‘REDACTED TEXT’ |
| 3 | 29/06/2018 | Presentation and reporting | ‘REDACTED TEXT’ |

All invoices should be sent to Ralph Halliday:

Email –	‘REDACTED TEXT’

Telephone –	‘REDACTED TEXT’

Address –	Department for Work & Pensions, ‘REDACTED TEXT’

You are reminded that any Customer Intellectual Property Rights provided in order to perform the Services will remain the property of the Customer.  The following deliverables have been agreed:

Powerpoint slide deck outlining key research findings

Presentation of findings to key research team and policy stakeholders

Word report of no less than 25 pages outlining project background, methodology, detailed research findings, conclusions and recommendations.

The Services Commencement Date is 5th March 2018

The Completion date is 4th July 2018

The Contract may be terminated for convenience by giving 2 weeks’ notice in accordance with clause 37 of the Call-off Terms and Conditions.

Your invoice(s) for this work must include the following information:

Commission number:	CCSN17A41

The Authorised Representative for this Commission will be Ralph Halliday who can be contacted at:

Email –	‘REDACTED TEXT’

Telephone –	‘REDACTED TEXT’

Address –	Department for Work & Pensions, ‘REDACTED TEXT’

‘REDACTED TEXT’

is the nominated secondary contact for this project:

Email –	‘REDACTED TEXT’

Telephone –	‘REDACTED TEXT’

Address –	Department for Work & Pensions, ‘REDACTED TEXT’

We kindly request that you copy both ‘REDACTED TEXT’

to all email communications, and invite both of them to any meetings.

All data relating to this project (including, but not limited to sample files, recordings, transcripts, data files and findings) must be treated confidentially. Files must be transferred securely with encryption which meets the Departments minimum requirement standards. Please refer to the data handling agreement for further details.

Congratulations on your success in being selected to undertake this Commission.

Yours sincerely

Connie Hunt

BY SIGNING AND RETURNING THIS COMMISSIONING LETTER THE SERVICE PROVIDER AGREES to enter a legally binding contract with the Customer to provide to the Customer the Services specified in this Commissioning Letter and Annexes incorporating the rights and obligations in the Call-off Terms and Conditions set out in the Framework Agreement.

Signed on behalf of Solutions Strategy Research Facilitation Ltd

Attachment A Supplemental Tender

Attachment B Specification

Attachment C Feedback