Trialling and Sampling Framework Agreement – STA 0090

Call-Off Contract No:STA 0090/26

Title: Key Stage 2 Technical Pre-Test April 2017

Pursuant to the terms of the Trialling and Sampling Framework Agreement (STA 0090):

| Service Commencement Date: | 01/12/2016 |
| --- | --- |
| Call Off Value: | £1,292,434.84 |
| Trial Type: | Key stage 2 Technical Pre-Test |
| Awarded to: | NFER |
| Relationship Manager for Department for Education: |  |
| Relationship Manager for the Supplier: | [NFER to complete] |

- Background

A Technical Pre-Test (TPT) is required in the following National Curriculum subjects: Key stage 2 English reading; English grammar, punctuation and spelling; and mathematics. The TPT will provide data on the performance of all items included in the test papers.

- Functional Requirements

| Subjects: | English reading; English grammar, punctuation and spelling; and mathematics. |
| --- | --- |
| Key Stage or Other Measure: | Key stage 2 |

- Required Service Elements

The table below sets out which Service Elements the Supplier shall provide under this Call-Off Contract.

| KEY: | Included in trial |  | Not included in trial | X |
| --- | --- | --- | --- | --- |

| Service Element | Included / not included | Service Element Requirements |
| --- | --- | --- |
| Project Management |  | As per requirements set out in Invitation to Quote |
| Management of schools |  | As per requirements set out in Invitation to Quote |
| Informing schools of statutory participation |  | As per requirements set out in Invitation to Quote |
| Recruit and train administrators |  | As per requirements set out in Invitation to Quote |
| Printing |  | As per requirements set out in Invitation to Quote |
| Collation and distribution |  | As per requirements set out in Invitation to Quote |
| Administration |  | As per requirements set out in Invitation to Quote |
| Helpline |  | As per requirements set out in Invitation to Quote |
| Script Management during marking |  | As per requirements set out in Invitation to Quote |
| Data Capture |  | As per requirements set out in Invitation to Quote |
| Handling pupil background data |  | As per requirements set out in Invitation to Quote |
| Trial / Sample Administration Report |  | As per requirements set out in Invitation to Quote |
| Recruitment, management and payment of Supervisory and non- supervisory markers |  | As per requirements set out in Invitation to Quote |
| Sourcing a suitable venue for all training and marking events required for administrators and markers |  | As per requirements set out in Invitation to Quote |
| Marking |  | As per requirements set out in Invitation to Quote |
| Systems management |  | As per requirements set out in Invitation to Quote |
| Optional Services |  |  |
| * Disseminating an incentive payment to participating schools | X | X |
| * Drawing the sample | X | X |

- Performance Requirements

| No | Service Element | Performance Requirement | Performance Measure |
| --- | --- | --- | --- |
| 1 | Project management | Full attendance at project start-up meeting, process walk through, project management meetings and lessons learnt meeting (face to face and teleconference as necessary). Progress reports, product descriptions, recruitment and management strategy, exit and transition plan, including risk and issues reporting to be submitted. Daily management information (MI) provided on all deliveries of secure materials to and from administrators. Issue reports to be written for any deviations from the agreed contract. Security incident reports to be written for all breaches and potential breaches of security and confidentiality. 100% – meeting documents to be provided at least 24 hours prior to organised project meetings. MI submitted daily during agreed windows. | 100% - meeting documents to be provided at least 24 hours prior to organised project meetings. MI submitted daily during the agreed window, at the agreed time. |
| 2 | Equalities | The Supplier provided reports at intervals as agreed, fulfilling their obligations under the Equality Act 2010. | 100% |
| 3 | Apprentices | The Supplier provided a report detailing the number of apprentices employed during the delivery of each call-offs. | 100% |
| 4 | Exit and Transition | The Supplier provided and maintained a detailed, fully resourced and costed exit and transition plan. | 100% |
| 5 | Management of schools | Contact and manage all schools and LAs selected for statutory participation. Provide a submission report on number of schools/pupils participating and visits required showing allocation of schools to test combinations, and that minimum number for each booklet combination for each test was achieved, matching sample stratifiers. | 100% |
| 6 | Update Trialling documentation | Supplier to update the Administrator Guide, Pupil Data Forms, Administrator Questionnaire and Teacher Questionnaire to agreed quality level with STA. | 100% |
| 7 | Recruitment of administrators and all Marking roles | Recruit sufficient administrators and all marking roles in order to be administer the trials and mark all scripts in the stated timeframes and provide an assurance statement detailing the allocation of tests to administrators/markers. | 100% |
| 8 | Training of administrators and all supervisory marking roles | Training of administrators who have not been trained on DfE trialling administration within the last 2 years. STA to review and input into training. Organise and support the training of markers. Supplier must source a venue and arrange a training event that appropriate Markers should attend. The training should include the use of its OSM, if applicable, and a discussion / explanation of any administrative requirements. The format of System training must be proposed by the Supplier for the Trial and is subject to prior approval by STA. The Supplier must develop, print and collate all materials, following pre-marking that will be required for the delivery of marker training including any administrative guidance. | 100% |
| 9 | Administration | All test materials collated and distributed to correct test administrators. Trial is administered securely and completed on time. Number of pupils specified in Functional Requirements (section 1.c.) to sit each trial booklet combination in each subject. Return of all test papers, scripts and other test materials to and from administrators, with notification and acknowledgement of delivery of all materials. 100% – all materials accounted for at all stages of the administration process. | 100% - all materials accounted for at all stages of the administration process. |
| 10 | Pre-marking | FOR TPT only - The supplier must create an on-screen marking preview area and provide OSM training to TDRs and supervisory markers. Pre-marking sample of scripts is provided to STA by agreed date. Pre-marking event sourced and hosted by the Supplier and all related and standardisation materials selected in the given time frame. | 100% |
| 11 | Marking | The Supplier must provide a marking plan and ensure that all marking, including marking completeness QA, is completed within the marking window detailed. FOR IVT only - The Supplier must source a secure central venue and arrange a panel based marking event that all TDRS, Supervisory and non-supervisory markers must attend. Validate returned scripts and report nil responses. Supplier to confirm that all scripts used in the trial have been returned. Provide a written report on validated returned scripts and scripts removed due to nil response. Electronic delivery of pupil background. Securely transfer final pupil background characteristics that have been reconciled with finalised script manifest files and provided to STA. Marker quality assurance data - Supplier to capture and supply to STA all Standardisation, on-going marker quality assurance and re-marking data. Marker register - Supplier to capture and supply to STA a valid record in the Marker Register for all data fields required by STA. | 100% |
| 12 | Data capture and analysis | The Supplier must accurately capture of all responses from the teacher and administrator questionnaires and provide to STA in an electronic file format to be agreed with STA, the outcomes from the analysis of the questionnaires should be provided in a spreadsheet formatted as per STA instructions. The Supplier must data capture the responses highlighted by markers during marking, in the format agreed with STA. The Supplier must carry out data capture of information from the tests, including a 100% check of data entry from tests and data cleaning. The format of the data to be agreed with STA in advance. | 100% |
| 13 | Final administration report | IVT administration report; Part A administration report, Part B analysis of questionnaire responses. Part C – A prose, reporting on the trial papers. Report content to be reviewed and agreed by STA prior to handover. Parts A and B completed and submitted to STA by required date to agreed quality standard. | 100% |
| 14 | Handover - electronic archive | Electronic archive (questionnaires and scripts) handed over to STA on required date. All scanned script files should follow the naming convention: yeartest]_[subject]_[componentcode]_[pupilID]_[pagenumber] The Supplier must provide secure transfer of item level data to STA in compliance with the Data Protection Act and the requirements set out in the Framework Agreement. | 100% accurate |
| 15 | Printing | The Supplier must provide confirmation that printing and their proposed scanning process works. This must be provided to STA by the dates shown. Please see Framework Section PL2.2 for more information. The Supplier will supply print proofs for STA to check the quality of each booklet version, before printing commences. Test proofs must match the hard copy of the test provided to the Supplier. The Supplier must provide confirmation that printing of all test booklets and supporting materials has been complete by the agreed date. 100% tests must meet the print quality standards, on time, and are signed off by STA. | 100% |

- Payment Milestones

Payment will follow the completion of the milestones listed below:

[Redacted]

In witness whereof this Call-Off Contract has been duly executed.

Signed for and on behalf of the Department for Education:

Date:

Signed for and on behalf of the Supplier:

Date: