NTIS

SCHEDULE 6.1B

TRANSFORMATION PLAN

- Definitions

In this Schedule, the following definitions shall apply:

| “Detailed Transformation Plan” | the plan developed and revised from time to time in accordance with paragraph ‎6 of this Schedule; |
| --- | --- |
| “Outline Transformation Plan” | the outline plan set out in the Appendix of this Schedule; |
| “Service Transformation Blueprint” | has the meaning given to it in Schedule 4.1 (Service Provider Solution); |
| “Transformation” | the transformation of the Sites, the Services and/or the infrastructure used to deliver the Services by the Service Provider, as described in Schedule 6.1B (Transformation) and "Transformed" shall be construed accordingly; |
| “Transformation Phase” | the period commencing no earlier than the Effective Date and ending on the passing of the CPP in respect of Transformation; |
| “Transformation Plan” | the Outline Transformation Plan or (if and when approved by the Customer pursuant to paragraph ‎6 of this Schedule) the Detailed Transformation Plan, as updated in accordance with paragraph ‎6 of this Schedule from time to time; |
| “Transformation Project Initiation Documents” or “Transformation PIDs” | - a document satisfying the product description given for project initiation documentation in Managing Successful Projects with PRINCE2®, 2017 |
| “Transformation Projects” | a group of one or more projects undertaken by the Service Provider to reach the Service Transformation Blueprint; and |
| “Transformation Services” | the services provided by the Service Provider for the design, build, test, implementation and roll out of the improvements to the Services as described in Schedule 6.1B (Transformation) and the Transformation Plan. |

DELIVERY OF THE TRANSFORMATION PLAN

This Schedule describes the Customer’s requirements for the Service Provider’s Transformation Plan.

The Appendix to this Schedule documents, specifies and details the Service Provider’s Transformation Plan.

The Transformation Plan shall contain, as a minimum, each aspect addressed in this Schedule and in Schedule 6.2 (Milestones and Deliverables) and Annex 4 of Schedule 6.3 (Testing Procedure).

All changes to the Outline Transformation Plan shall be subject to the Change Control Procedure.  The Detailed Transformation Plan shall only be varied in accordance with the process set out in paragraphs ‎6.3 and ‎6.4 (Detailed Transformation Plan) of this Schedule.

The Transformation Plan shall be written by the Service Provider in such a way that it can be used by the Customer Relationship Manager to manage and support Transformation.

Any diagrams, charts and plans within the Appendix to this Schedule must have been labelled and supported with sufficient textual description by the Service Provider to support the requirement in paragraph ‎3.

REQUIREMENT

Transformation Phase

The Transformation Phase shall include the development, Testing and implementation of the Transformation Services, in line with the Service Provider’s Transformation Plan and to the timescale described in Schedule 4.1 (Service Provider Solution), that shall be achieved during the Transformation Phase.

The Transformation Services shall include all elements of Transformation to be able to demonstrate service delivery to meet or exceed the Target Performance Levels in respect of each Performance Indicator as defined in Schedule 2.2 (Performance Levels). This will include;

development, Testing and implementation of technology;

development, Testing and implementation of processes;

development, Testing and implementation of transformed organisational structure; and

development, Testing and implementation of transformed information exchanges.

Transformation principles

The Service Provider shall ensure that the Transformation arrangements are aligned with the need to deliver the Services to meet or exceed the Target Performance Levels in respect of each Performance Indicator as defined in Schedule 2.2 (Performance Levels) for the duration of the Transformation Phase and beyond.  The Service Provider shall undertake all agreed activities necessary to enable the Service Provider to provide the Operational Services.

The Service Provider acknowledges that it shall perform its obligations set out in this Schedule 6.1B (Transformation Plan) with a view to ensuring the successful execution of the Transformation Plan.  The Customer shall comply with its obligations as set out in Schedule 3 (Customer Responsibilities) to support the successful execution of the Transformation Plan.

The Service Provider’s progression through the Transformation Phase shall be tracked, by the appropriate governance forum as defined in Schedule 8.1 (Governance), against a series of Milestones specified in the Transformation Plan and the Transformation PIDs.

A Milestone shall be complete, and the Customer shall promptly issue the relevant Milestone Achievement Certificate, when the Test Success Criteria for that Milestone have been met in accordance with Schedule 6.3 (Testing Procedures).

The Service Provider and the Customer shall agree the detailed Test Success Criteria for each Milestone and record such Test Success Criteria in the relevant Transformation PID.

SCOPE OF TRANSFORMATION PLAN

The Transformation Plan shall detail the activities, which may be grouped into one or more Transformation Projects, that shall be undertaken by the Service Provider to reach the Service Transformation Blueprint as defined in Schedule 4.1 (Service Provider Solution).

The Transformation Plan shall provide confidence to the Customer that the Service Provider has considered, identified and documented all activities that shall be needed to Achieve Authority to Proceed for the Transformation release Milestone as documented in Schedule 6.3 (Testing Procedures).

The Transformation Plan shall include as appropriate statements, descriptions and evidence that shall demonstrate the Service Provider has a clear path to Achieve Transformation.  Areas that shall be addressed shall include:

a chronology of the Milestones that shall be met to Achieve Transformation from the Effective Date to the end of the Transformation Phase. This statement will also show the critical path to Achieve Transformation on time;

clarity of how the Achievement of each Transformation Milestone, as detailed in Schedule 6.2 (Milestones and Deliverables) and 6.3 (Testing Procedures), will result in the delivery of new or improved Services to the Users, as defined in Schedule 2.1 (Services Description), and the achievement of the Service Outcomes, as defined in Schedule 2.1 (Services Description);

clarity of each reasonable dependency on the Customer or its supply chain including the actions to be taken by the Service Provider to notify and secure the agreement of the Customer in discharging any actions associated with that dependency;

clarity of how the Service Provider shall secure the people it requires to Achieve Transformation.  This shall include a profile of numbers and locations of Service Provider Personnel at each stage of Transformation;

clarity of how the Service Provider shall ensure that each of the Service Provider Personnel have the appropriate skills to deliver the Service Transformation Blueprint as detailed in Schedule 4.1 (Service Provider Solution);

a clear communications strategy that shall demonstrate how the Service Provider shall be able to deliver both internal and external communications that shall be undertaken by the Service Provider, following agreement from the Customer.  The communications strategy shall consider areas such as:

ensuring that customers of the Service are aware that the Transformation has started,

what the Transformation will achieve,

how the Transformation will affect Services,

identification of points of contact,

when any changes can be expected, and

when Transformation has been completed;

a clear plan for transforming all security arrangements and responsibilities from those in place at the Effective Date to those incorporated in the Service Transformation Blueprint as detailed in Schedule 4.1 (Service Provider Solution);

associated start and end dates for each Transformation Project and go-live dates where they differ from Transformation Project end dates;

clarity of risks associated with the Transformation Plan, to include their impact and likelihood and how the Service Provider intends to mitigate the risk to an acceptable level;

clarity of the Service Provider’s governance arrangements through each stage of Transformation, including an indication of how that governance will interface with the Customer;

clearly demonstrate alignment to the Project Management standards as defined in Schedule 2.3 (Standards);

clarity of all external suppliers that shall be used to support the Service Provider in the delivery of tasks within the Transformation Plan;

a description of how the Service Provider shall set-up and maintain open, honest and collaborative relationships with all parties;

a fall back plan in the event that Services do not become operational in the agreed period.  Without prejudice to the Service Provider’s obligations under Clauses 7 to 14 (inclusive), the Service Provider shall conduct a review of the Detailed Transformation Plan and shall prepare Transformation contingency plans, which shall describe the procedures and actions that the Service Provider (and other relevant parties) shall take in the event that progress through the Transformation Phase is not maintained according to the Transformation Plans, Detailed Transformation Plan and the Transformation PIDs or where there are reasonable grounds to believe that one or more Milestones will not be met; and

clarity of all other activities necessary to Achieve Authority to Proceed for Transformation as detailed in Schedule 6.3 (Testing Procedures).

TRANSFORMATION GANTT PROJECT PLAN

In addition to the description on the Transformation Plan, the Service Provider shall provide a high level summary clearly showing key dates and overall transformation.

The Service Provider shall provide a detailed transformation programme in the format of a Gantt chart that shall form the basis for project reporting and as a minimum shall contain:

all Milestones, Deliverables and tasks for each Transformation Project separately identified;

project management and review activity;

a proposed set of meeting dates with the Customer;

latest dates for access / delivery of information, and means of allowing sufficient review time;

clear payment points linked to Schedule 7.1 (Charges and Invoicing);

outline timing of Test procedures, Testing periods and Test Success Criteria (to be fully defined in Schedule 6.3 (Testing Procedures)); and

latest dates for technical approvals by the Customer of IT links.

The Gantt chart shall be provided in an electronic format in addition to a paper format.

DETAILED TRANSFORMATION PLAN

Within forty (40) Working Days after the Effective Date and in accordance with Schedule 6.2 (Milestones and Deliverables), the Service Provider shall deliver to the Customer Relationship Manager for approval the Detailed Transformation Plan.  The Detailed Transformation Plan shall:

comply with the Standards;

meet the requirements of paragraphs 3 and 4 of this Schedule;

be based on the Outline Transformation Plan updated as appropriate;

articulate the roles, responsibilities and obligations of all parties concerned in order for the Service Provider to deliver the Services, including the identification of project reviewers and approvers;

identify objectives, scope, Deliverables, constraints, assumptions, business benefits, risks, project organisation, project quality approach, acceptance criteria, initial project plan, controls, tolerance, contingency, and any other information deemed necessary to define the Transformation Project appropriately; and

be subject to approval by the Customer Relationship Manager   (such approval not to be unreasonably withheld or delayed).

Prior to the submission of the Detailed Transformation Plan in accordance with paragraph ‎6.1 (Detailed Transformation Plan), the Customer Relationship Manager shall have the right, at any time, to review any documentation produced by the Service Provider:

in relation to the development of the Detailed Transformation Plan; and/or

for the purposes of developing the initial draft of the Detailed Transformation Plan into the agreed Transformation Plan, including:

details of the Service Provider’s intended approach to the Detailed Transformation Plan and its development;

copies of any drafts of the Detailed Transformation Plan produced; and

any other work in progress in relation to the Detailed Transformation Plan.

The Customer Relationship Manager shall have the right to require the Service Provider to include any reasonable changes or provisions in the Detailed Transformation Plan before it is submitted to the Customer Relationship Manager in accordance with paragraph ‎6.1  or paragraph ‎6.4 below, as appropriate.

After approval of the Detailed Transformation Plan, save for any amendments which are of a type identified and notified by the Customer Relationship Manager (at his  discretion) to the Service Provider in writing as not requiring approval, any material amendments to the Detailed Transformation Plan shall be subject to the Change Control Procedure (and for the avoidance of doubt any amendments to elements of the Detailed Transformation Plan which reflect the contents of the Outline Transformation Plan shall be deemed to be material amendments) provided that in no circumstances shall the Service Provider alter or attempt to alter any Milestone Date except in accordance with clause 39 (Customer Cause).  Until such time as the updated Detailed Transformation Plan is approved by the Customer, the Detailed Transformation Plan then existing (that is to say prior to the update) shall apply.

In addition to maintaining and updating the Detailed Transformation Plan in accordance with paragraph ‎6.4 of this Schedule, the Service Provider shall submit an updated Detailed Transformation Plan within twenty (20) Working Days of receiving notification from the Customer Relationship Manager, or such longer period as the parties may agree (provided that any failure to agree such longer period shall be referred to the Dispute Resolution Procedure), of being advised by the Customer Relationship Manager of an event reasonably identified by the Customer Relationship Manager as requiring a revised Detailed Transformation Plan.  Any such revised Detailed Transformation Plan shall be submitted by the Service Provider for approval in accordance with the procedure set out in paragraph ‎6.1 above.

Once agreed with the Customer Relationship Manager, the Service Provider shall monitor its performance against the Transformation Plan and provide the Customer Relationship Manager with weekly performance reports of its progress throughout the Transformation Phase.

The parties shall consider and review the Detailed Transformation Plan and progress towards its successful implementation at the Service Management Board meetings held in accordance with Schedule 8.1 (Governance).  In preparation for such meeting the current Detailed Transformation Plan shall be provided by the Service Provider to the Customer Relationship Manager not less than five (5) Working Days in advance of each meeting of the Service Management Board.

TRANSFORMATION PLANNING

During mobilisation, the Service Provider shall deliver a Transformation PID for each Transformation Project as identified in the Appendix to this Schedule.

The first view of Transformation PIDs shall be received by the Customer no later than forty (40) Working Days after the Effective Date.

Transformation PIDs shall:

each be uniquely referenced;

adhere to the project management standards as set out in Schedule 2.3 (Standards);

articulate the responsibilities and obligations of all parties required to complete the activities, including the identification of project reviewers and approvers; and

identify each Deliverable or Service to be delivered by the Transformation Project, including; objectives, scope, deliverables, constraints, assumptions, business benefits, risks, project organisation, project quality plan, acceptance criteria, initial project plan, controls, tolerance, contingency, and any other information deemed necessary to define the Transformation Project appropriately.

Transformation PIDs shall be subject to approval by the Customer  (such approval not to be unreasonably withheld or delayed).

APPENDIX

OUTLINE TRANSFORMATION PLAN