NTIS

SCHEDULE 8.2

CHANGE CONTROL PROCEDURE

Change Control Procedure

- Definitions

In this Schedule, the following definitions shall apply:

| “Change Request” | a written request for a Contract Change which shall be substantially in the form of Annex 1 of Schedule 8.2 (Change Control Procedure); |
| --- | --- |
| “Change Communication” | any Change Request, Impact Assessment, Change Authorisation Note or other communication sent or required to be sent pursuant to of Schedule 8.2 (Change Control Procedure); |
| “Change Schedule” | - has the meaning given to it in paragraph ‎12.1 of Schedule 8.2 (Change Control Procedure); |
| “Fast-track Change” | any Contract Change which the Parties agree to expedite in accordance with paragraph ‎9 of Schedule 8.2 (Change Control Procedure); |
| “Impact Assessment” | an assessment of a Change Request in accordance with paragraph ‎5 of Schedule 8.2 (Change Control Procedure); |
| “Impact Assessment Estimate” | has the meaning given in paragraph ‎4.3 of Schedule 8.2 (Change Control Procedure); |
| “Receiving Party” | the Party which receives a proposed Contract Change; |
| “Service Provider Change Manager” | the person appointed to that position by the Service Provider from time to time and notified in writing to the Customer Relationship Manager or, if no person is notified, the Service Provider Representative. |

General Principles of Change Control Procedure

This Schedule sets out the procedure for dealing with Contract Changes.

Operational Changes shall be processed in accordance with paragraph ‎10.  If either Party is in doubt about whether a change falls within the definition of an Operational Change, then it must be processed as a Contract Change.

The Parties shall deal with Contract Change as follows:

either Party may request a Contract Change which they shall initiate by issuing a Change Request in accordance with paragraph ‎4;

unless this Agreement otherwise requires, the Service Provider shall assess and document the potential impact of a proposed Contract Change in accordance with paragraph ‎5 before the Contract Change can be either approved or implemented;

the Customer Relationship Manager shall have the right to request amendments to a Change Request, approve it or reject it in the manner set out in paragraph ‎6;

the Service Provider shall have the right to reject a Change Request solely in the manner set out in paragraph ‎7;

save as otherwise provided in this Agreement, no proposed Contract Change shall be implemented by the Service Provider until a Change Authorisation Note has been signed and issued by the Customer Relationship Manager in accordance with paragraph ‎6.2;

where a proposed Contract Change is a Fast-track Change, it shall be processed in accordance with paragraph ‎8; and

if the circumstances or nature of a proposed Contract Change mean that it is a Customer Mandated Change then it shall be processed in accordance with paragraph ‎8.

To the extent that any Contract Change requires testing and/or a programme for implementation, then the Parties shall follow the procedures set out in Schedule 6.3 (Testing Procedures), and, where appropriate, the Change Authorisation Note relating to such a Contract Change shall specify Milestones and/or a Key Milestone and Milestone Date(s) in respect of such Contract Change for the purposes of such procedures.

Until a Change Authorisation Note has been signed and issued by the Customer Representatives in accordance with paragraph ‎6.2, then:

the Service Provider shall continue to supply the Services in accordance with the existing terms of this Agreement as if the proposed Contract Change did not apply; and

any discussions, negotiations or other communications which may take place between the Customer, the Customer Relationship Manager and the Service Provider in connection with any proposed Contract Change, including the submission of any Change Communications, shall be without prejudice to each Party’s other rights under this Agreement.

The Service Provider shall:

within ten (10) Working Days of the Customer Representatives’ signature and issue of a Change Authorisation Note, deliver to the Customer Relationship Manager a copy of this Agreement updated to reflect all Contract Changes agreed in the relevant Change Authorisation Note and annotated with a reference to the Change Authorisation Note pursuant to which the relevant Contract Changes were agreed; and

thereafter provide to the Customer Relationship Manager such further copies of the updated Agreement as the Customer Relationship Manager may from time to time request.

Costs

Subject to paragraph ‎3.4:

the costs of preparing each Change Request shall be borne by the Party making the Change Request; and

the costs incurred by the Service Provider in undertaking an Impact Assessment shall be borne by the Party making the Change Request, subject to paragraph ‎3.2 and provided that the Customer shall not be required to pay any such costs if:

such costs are:

in aggregate in respect of all Change Requests in the relevant Contract Year, below £50,000; or

once the aggregate amount referred to paragraph ‎3.1.2.1‎(a) has been exceeded in any Contract Year, in respect of a single Change Request, below £5,000; or

the Service Provider is able to undertake the Impact Assessment by using resources already deployed in the provision of the Services; or

such costs exceed those in the accepted Impact Assessment Estimate.

Where the Customer is obliged pursuant to paragraph ‎3.1 to bear the cost of incurred by the Service Provider in undertaking an Impact Assessment, such costs must be reasonable and proportionate in the circumstances, shall be calculated and charged in accordance with the principles and day rates or day costs (as applicable) set out in Schedule 7.1 (Charges and Invoicing) and shall be invoiced and paid as a Milestone Payment.

The cost of implementing any Contract Change shall be calculated and charged in accordance with the principles and day rates or day costs (as applicable) set out in Schedule 7.1 (Charges and Invoicing) and the provisions of paragraph ‎5.5 of this schedule.  The Service Provider shall be entitled to increase the Charges only if it can demonstrate in the Impact Assessment that the proposed Contract Change requires additional resources and, in any event, any change to the Charges resulting from a Contract Change (whether the change will cause an increase or a decrease in the Charges) will be strictly proportionate to the increase or decrease in the level of resources required for the provision of the Services as amended by the Contract Change.

Both Parties' costs incurred in respect of any use of this Change Control Procedure as a result of any error or Default by the Service Provider shall be paid for by the Service Provider.

Change Request

Either Party may issue a Change Request to the other Party at any time during the Term.  A Change Request shall be substantially in the form of Annex 1 and state whether the Party issuing the Change Request considers the proposed Contract Change to be a Fast-track Change or a Customer Mandated Change.

If the Service Provider issues the Change Request, then it shall also provide an Impact Assessment to the Customer Relationship Manager as soon as is reasonably practicable but in any event within ten (10) Working Days of the date of issuing the Change Request.

If the Customer Relationship Manager issues the Change Request, then the Service Provider shall provide as soon as reasonably practicable and in any event within ten (10) Working Days of the date of receiving the Change Request, where applicable in accordance with paragraph ‎3.1.2, an estimate (“Impact Assessment Estimate”) of the cost of preparing an Impact Assessment (in accordance with the provisions of paragraph ‎3.2) and the timetable for preparing it.  The timetable shall provide for the completed Impact Assessment to be received by the Customer Relationship Manager within ten (10) working days of acceptance of the Impact Assessment Estimate or within any longer time period agreed by the Customer Relationship Manager.

Where an Impact Assessment is to be provided pursuant to paragraph ‎4.3, if the Customer Relationship Manager accepts an Impact Assessment Estimate then following receipt of notice of such acceptance the Service Provider shall provide the completed Impact Assessment to the Customer Relationship Manager as soon as is reasonably practicable and in any event within the period agreed in the Impact Assessment Estimate.  Otherwise paragraph ‎4.2 shall apply.  If the Service Provider requires any clarification in relation to the Change Request before it can deliver the Impact Assessment, then it shall promptly make a request for clarification to the Customer Relationship Manager and provided that sufficient information is received by the Customer Relationship Manager to fully understand:

the nature of the request for clarification; and

the reasonable justification for the request;

the time period to complete the Impact Assessment shall be extended by the time taken by the Customer Relationship Manager to provide that clarification.  The Customer Relationship Manager shall respond to the request for clarification as soon as is reasonably practicable.

Where the Customer is to pay the costs incurred by the Service Provider in undertaking an Impact Assessment these may be invoiced by the Service Provider as a Milestone Payment (which must not without the prior written agreement of the Customer Relationship Manager exceed the cost set out in the Impact Assessment Estimate) following receipt by the Customer Relationship Manager of an Impact Assessment that complies with the provisions of paragraph ‎5 (and sufficient information to properly evaluate the Change Request and Impact Assessment) and shall be paid by the Customer in accordance with the provisions of Schedule 7.1 (Charges and Invoicing).

Impact Assessment

Each Impact Assessment shall be completed in good faith and shall include:

details of the proposed Contract Change including the reason for the Contract Change; and

details of the impact of the proposed Contract Change on the Services, the Optional Services (if any), the Service Provider’s Solution and the Service Provider's ability to meet its other obligations under this Agreement;

any variation to the terms of this Agreement that will be required as a result of that impact, including changes to:

the Services Description, the Performance Indicators and/or the Target Performance Levels;

the format of Customer Data, as set out in the Services Description;

the Milestones, Implementation Plan and any other timetable previously agreed by the Parties;

other services provided by third party contractors to the Customer, including any changes required by the proposed Contract Change to the Customer's IT infrastructure;

details of the cost of implementing the proposed Contract Change;

details of the ongoing costs required by the proposed Contract Change when implemented, including any increase or decrease in the Charges, any alteration in the resources and/or expenditure required by either Party and any alteration to the working practices of either Party;

a timetable for the implementation, together with any proposals for the testing of the Contract Change;

details of how the proposed Contract Change will ensure compliance with any applicable Change in Law; and

such other information as the Customer Relationship Manager may reasonably request in (or in response to) the Change Request.

If the Contract Change involves the processing or transfer of any Personal Data outside the European Economic Area, the preparation of the Impact Assessment shall also be subject to clause 31 (Protection of Personal Data).

Subject to the provisions of paragraph ‎5.4, the Customer Relationship Manager shall review the Impact Assessment and respond to the Service Provider in accordance with paragraph ‎6 within fifteen (15) Working Days of receiving the Impact Assessment, it.

If the Customer is the Receiving Party and the Customer Relationship Manager reasonably considers that it requires further information regarding the proposed Contract Change so that it may properly evaluate the Change Request and the Impact Assessment, then within five (5) Working Days of receiving the Impact Assessment, it shall notify the Service Provider of this fact and detail the further information that it requires.  The Service Provider shall then re-issue the relevant Impact Assessment to the Customer Relationship Manager within ten (10) Working Days of receiving such notification.  At the Customer Relationship Manager's discretion, the Parties may repeat the process described in this paragraph ‎5.4 until the Customer Relationship Manager is satisfied that it has sufficient information to properly evaluate the Change Request and Impact Assessment.

The calculation of costs for the purposes of Paragraphs ‎5.1.4 and ‎5.1.5 shall:

be based on the Financial Model;

facilitate the Financial Transparency Objectives;

include estimated volumes of each type of resource to be employed and the applicable rate card;

include full disclosure of any assumptions underlying such Impact Assessment;

include evidence of the cost of any assets required for the Change; and

include details of any new Sub-contracts necessary to accomplish the Change.

Customer’s Right of Approval

Within fifteen (15) Working Days of receiving the Impact Assessment from the Service Provider or within ten (10) Working Days of receiving the further information that it may request pursuant to paragraph ‎5.4, the Customer Relationship Manager shall evaluate the Change Request and the Impact Assessment and shall do one of the following:

approve the proposed Contract Change, in which case the Parties shall follow the procedure set out in paragraph ‎6.2;

in its absolute discretion reject the Contract Change, in which case it shall notify the Service Provider of the rejection.  The Customer Relationship Manager shall not reject any proposed Contract Change to the extent that the Contract Change is necessary for the Service Provider or the Services to comply with any Changes in Law.  If the Customer Relationship Manager does reject a Contract Change, then it shall explain its reasons in writing to the Service Provider as soon as is reasonably practicable following such rejection; or

in the event that it reasonably believes that a Change Request or Impact Assessment contains errors or omissions, require the Service Provider to modify the relevant document accordingly, in which event the Service Provider shall make such modifications within five (5) Working Days of such request.  Subject to paragraph ‎5.4, on receiving the modified Change Request and/or Impact Assessment, the Customer Relationship Manager shall approve or reject the proposed Contract Change within ten (10) Working Days.

If the Customer Relationship Manager approves the proposed Contract Change pursuant to paragraph ‎6.1 and it has not been rejected by the Service Provider in accordance with paragraph ‎7, then it shall inform the Service Provider and the Service Provider shall prepare two (2) copies of a Change Authorisation Note which it shall sign and deliver to the Customer Relationship Manager for signature on behalf of the Customer.  Following receipt by the Customer Relationship Manager of the Change Authorisation Note, both Customer Representatives responsible for signing Change Authorisation Note(s) (acting within the limits of their respective financial and contractual delegation authorities as set out in Appendix 1 to Schedule 9.3) shall sign both copies and the Customer Relationship Manager shall return one copy to the Service Provider.  On signature by both Customer Representatives (acting within the limits of their respective financial and contractual delegation authorities as set out in Appendix 1 to Schedule 9.3), the Change Authorisation Note shall constitute a binding variation to this Agreement.

If the Customer Representatives do not sign the Change Authorisation Note within ten (10) Working Days, then the Service Provider shall have the right to notify the Customer Relationship Manager and if the Customer Representatives do not sign the Change Authorisation Note within five (5) Working Days of such notification, then the Service Provider may refer the matter to the Dispute Resolution Procedure.

Service Provider’s Right of Approval

Following an Impact Assessment, if:

the Service Provider reasonably believes that any proposed Contract Change which is requested by the Customer Relationship Manager would:

materially and adversely affect the risks to the health and safety of any person; and/or

require the Services to be performed in a way that infringes any Law; and/or

the Service Provider demonstrates to the Customer Relationship Manager's reasonable satisfaction that the proposed Contract Change is technically impossible to implement and neither the Service Provider Solution nor the Services Description state that the Service Provider does have the technical capacity and flexibility required to implement the proposed Contract Change, then the Service Provider shall be entitled to reject the proposed Contract Change and shall notify the Customer Relationship Manager of its reasons for doing so within five (5) Working Days after the date on which it is obliged to deliver the Impact Assessment pursuant to paragraph ‎4.3.

CUSTOMER MANDATED CHANGES

Upon the Customer becoming aware of the occurrence of an event requiring a Customer Mandated Change, the Customer Relationship Manager may issue a Change Request in respect of such Customer Mandated Change.  If the Customer Relationship Manager does not issue a Change Request in respect of a Customer Mandated Change, the Service Provider shall also be entitled to initiate a Change Request for such Customer Mandated Change.

The following types of Contract Changes are "Customer Mandated Changes":

where the Contract Change is necessary to enable the Service Provider or the Services to comply with any Change in Law;

where the Contract Change is deemed by the Customer Relationship Manager to be necessary to make the Services comply with any ministerial decision; or

where any Contract Change is necessary for the Services to meet the Customer's requirements as detailed in Schedule 2.1 (Services Description).

Where a Contract Change is a Customer Mandated Change under paragraph ‎8.2.3, the Service Provider shall bear all Losses relating thereto and shall not be entitled to any compensation in respect of its costs associated with developing, impacting, documenting and implementing such a Contract Change.

Upon receipt of a Change Request in respect of a Customer Mandated Change, the Service Provider shall, within five (5) Working Days of such receipt (or such other reasonable timescale as may be agreed between the Parties having due regard to the operational urgency of the Customer Mandated Change and the complexity and scope of the Customer Mandated Change) provide the relevant Impact Assessment to the Customer Relationship Manager and the process set out in paragraphs ‎2.3.5, ‎3, ‎4, ‎5, ‎6, ‎7, ‎11 and ‎12 shall apply.

The Customer Relationship Manager may, where there is insufficient time to complete the applicable processes in this schedule, issue and the Service Provider shall comply with a written request (a "Customer Mandatory Request") to fully implement a Customer Mandated Change, notwithstanding that the relevant Impact Assessment and/or the processes set out in paragraphs ‎2.3.5, ‎3, ‎4, ‎5, ‎6, ‎7, ‎11 and ‎12 (as applicable) may not have been completed.

Where the Customer Relationship Manager issues a Customer Mandatory Request, the Parties agree that any outstanding activities and approvals required to comply with the processes contained in this Schedule 8.2 (Change Control Procedure) shall be determined and resolved in accordance with the Dispute Resolution Procedure.

Fast-Track Changes

The Parties acknowledge that to ensure operational efficiency there may be circumstances where it is desirable to expedite the processes set out above.

If:

the total number of Contract Changes in relation to which this Fast-track Change procedure has been applied does not exceed four (4) in any twelve (12) month period; and

both Parties agree the value of the proposed Contract Change over the remaining Term and any period for which Termination Services may be required does not exceed £25,000 (excluding VAT), subject to indexation, and the proposed Contract Change is not significant (as determined by the Customer Relationship Manager acting reasonably),

- then the Parties shall confirm to each other in writing that they shall use the process set out in paragraphs ‎4, ‎5, ‎6 and ‎7 but with reduced timescales, such that any period of fifteen (15) Working Days is reduced to five (5) Working Days, any period of ten (10) Working Days is reduced to two (2) Working Days and any period of five (5) Working Days is reduced to one (1) Working Day.

The Parties may agree in writing to revise the parameters set out in paragraph ‎9.2 from time to time or that the Fast-track Change procedure shall be used in relation to a particular Contract Change notwithstanding that the total number of Contract Changes to which such procedure is applied will then exceed four (4) in a twelve (12) month period.

Operational Change Procedure

Any Operational Changes identified by the Service Provider to improve operational efficiency of the Services may be implemented by the Service Provider without following the Change Control Procedure for proposed Contract Changes provided they do not:

have an impact on the business of the Customer;

require a change to this Agreement;

have a direct impact on use of the Services; or

involve the Customer in paying any additional Charges or other costs.

The Customer Relationship Manager may request an Operational Change by submitting a written request for Operational Change (“RFOC”) to the Service Provider Representative.

The RFOC shall include the following details:

the proposed Operational Change; and

the time-scale for completion of the Operational Change.

The Service Provider shall inform the Customer Relationship Manager of any impact on the Services that may arise from the proposed Operational Change.

The Service Provider shall complete the Operational Change by the timescale specified for completion of the Operational Change in the RFOC, and shall promptly notify the Customer Relationship Manager when the Operational Change is completed.

Communications

For any Change Communication to be valid under this Schedule, it must be sent to either the Customer Relationship Manager or the Service Provider Change Manager, as applicable.  The provisions of clause 53 (Notices) shall apply to a Change Communication as if it were a notice.

- REGISTRATION AND PRIORITISATION OF CHANGES

The Service Provider shall create and maintain a register of all proposed Contract Changes and Operational Changes (“Change Schedule”).

The Customer Relationship Manager will be entitled to require the Service Provider to prioritise certain Contract Changes and Operational Changes on the Change Schedule. The Customer Relationship Manager, acting reasonably, may decide the prioritisation and the Parties shall make the necessary amendments to the agreed plans for implementing the relevant Contract Changes and Operational Changes accordingly.

ANNEX 1

Change Request Form

| CR NO.: | TITLE |  |  | TYPE OF CHANGE |
| --- | --- | --- | --- | --- |
| CONTRACT: |  |  | REQUIRED BY DATE: |  |
| ACTION: |  | NAME: |  | DATE: |
| RAISED BY: |  |  |  |  |
| AREA(S) IMPACTED (OPTIONAL FIELD): |  |  |  |  |
| ASSIGNED FOR IMPACT ASSESSMENT BY: |  |  |  |  |
| ASSIGNED FOR IMPACT ASSESSMENT TO: |  |  |  |  |
| SERVICE PROVIDER REFERENCE NO.: |  |  |  |  |
| FULL DESCRIPTION OF REQUESTED CONTRACT CHANGE (INCLUDING PROPOSED CHANGES TO THE WORDING OF THE CONTRACT): |  |  |  |  |
| DETAILS OF ANY PROPOSED ALTERNATIVE SCENARIOS: |  |  |  |  |
| REASONS FOR AND BENEFITS AND DISADVANTAGES OF REQUESTED CONTRACT CHANGE: |  |  |  |  |
| SIGNATURE OF REQUESTING CHANGE OWNER: |  |  |  |  |
| DATE OF REQUEST: |  |  |  |  |

ANNEX 2

Change Authorisation Note

| CR NO: |  |  | TITLE: | DATE RAISED: |
| --- | --- | --- | --- | --- |
| CONTRACT: |  |  | TYPE OF CHANGE: | REQUIRED BY DATE: |
| [KEY MILESTONE DATE: [if any]] |  |  |  |  |
| DETAILED DESCRIPTION OF CONTRACT CHANGE FOR WHICH IMPACT ASSESSMENT IS BEING PREPARED AND WORDING OF RELATED CHANGES TO THE CONTRACT: |  |  |  |  |
| PROPOSED ADJUSTMENT TO THE CHARGES RESULTING FROM THE CONTRACT CHANGE: |  |  |  |  |
| DETAILS OF PROPOSED ONE-OFF ADDITIONAL CHARGES AND MEANS FOR DETERMINING THESE (E.G. FIXED PRICE BASIS): |  |  |  |  |
| SIGNED ON BEHALF OF THE CUSTOMER: |  | SIGNED ON BEHALF OF THE SERVICE PROVIDER: |  |  |
| Signature: _______________________ Contractual Delegation Holder |  | Signature: ________________________ |  |  |
| Signature: _______________________ Financial Delegation Holder |  | Signature: ________________________ |  |  |
| [Note: The signatories for Highways England must be different for contractual and financial delegation] |  |  |  |  |