## Prelims & Spec
LAMBETH COUNCIL - Adaptaion and Conversion of redundent Laundry Room 10 Bilton House, Springfield Estate SW8 4EP
No. | ITEM DESCRIPTION | Unit | Quantity | Rate | Amount (£)
1 | Preliminaries
1.01 | The Contractor shall note that the form of Contract to be used to administer the works will be the: JCT Intermediate Building Contract with Contractor's Design 2011: (ICD). All Contract Conditions shall apply, and a Contract will be signed prior to commencing the Works, or a Letter of Intent will be issued. | Item | 1
1.02 | Construction (Design and Management) Regulations 2015 will be applicable to all the works, and the Contractor will act as Principal Designer and Main Contractor. There will be design responsibilities in terms of bathroom layouts, and the Contractor is expected to take full responsibility for this under the terms of the Contract, and in relation to the CDM Regulations 2015. | Item | 1
1.03 | Constructor will be required to provide: Working Site Manager, Design co-ordination in line with the Contract, Resident Liaison Officer where necessary, welfare facilities, waste segregation skips at the site of the works and container storage within main compound area to support 'just in time delivery' of materials to the site. | Item | 1
1.04 | Material deliveries shall be delivered to site, from a central storage compound, on a 'just in time basis' to minimise on site storage requirements. Crew vehicles shall be provided for moving staff. A professional clean team shall be provided when the works are completed. Saturday working if required shall be at no additional cost | Item | 1
1.05 | Works constructor to provide all necessary materials, management and skilled & unskilled labour to complete the works. Site support – full time manager to be provided to ensure the works are managed and delivered. | Item | 1
1.06 | Works contractors to provide all necessary protection to working areas within dwellings and its surrounding areas including communal and public access routes and areas of use. | Item | 1
1.07 | Under no circumstance must asbestos or asbestos based material be used or unnecessarily disturbed. Apart from the areas in which it is being removed as part of the main works. | Item | 1
1.08 | Contractor to allow for carrying out asbestos surveys to all dwellings prior to the works, and providing the Client with a copy of all applicable documents to enable system updates. | Item | 1
1.09 | Constructor needs to consider and take due care as ajacent properties are occupied, therefore works can only take place during designated time 8.00am to 17.00pm Monday to Friday with some minor works being undertaken on a Saturday morning with the prior agreement on the CA. | Item | 1
1.11 | On-Site contingency “first aid Kit”. This is to provide contingency for any unforeseen errors that would otherwise inconvenience the programme . | Item | 1
1.12 | Where significant items of plant are required, such as lifting equipment, contractor to allow for this. | Item | 1
1.13 | All works to be in accordance with structural diagram provided and at the direction of the authorising officer. | Item | 1
1.14 | The contractor is to provide in advance of the works, a writern method statement and sequencing plan which details how the works will be executed and phased. | Item | 1
2 | Preamble
2.01 | It is intended that all prices will include the following: | Item | 1
1) Receipt Order from Client
2) Contact details for the occupied dwelling.
3) Asbestos survey to all working areas
4) Provide method statement
5) Provide details of the contractors Asbestos license and insurance
6) Agree commencement date for the works
7) Attend pre contract commencement meeting
8) Refer to Client for Client approval before ordering materials
9) Provide residents with a time of works
10) Commence works and complete
11) Carry out resident satisfaction survey on completion of the works
2.02 | All Works to be completed within 30 days of commencement | Item | 1
3 | Payment
3.01 | Payment shall only be made on completion of works and sign off by CA | Item | 1
3.02 | Materials on site will not be allowed in any valuation. | Item | 1
Section 4
4.01 | Works contractors are to ensure public walkways are kept clean and tidy at all times during the course of the works. | Item | 1
5 | Section 5 Materials and workmanship
5.01 | All workmanship and supply of materials shall comply with all current codes of practices and any relevant BS standards, Building Regulations and Health and Safety regulations and manufacturers guidance. Local labour to be used where possible. | Item | 1
5.03 | All saintaryware to be twyfords or similar approved chrome taps and bath mixer to be peglar or similar approved | Item | 1
Section 6 The Works
6.01 | Strip out existing services and clear from site, remove external door, frame and window form opening and install new window, brick up remainder of opening ensuring toothing and brickwork matches existing remove internal step and external thteshold, ensure external pointing matches existing, internal plastering using two coat finish to entire wall surface. break through 225mm party wall to form opening inserting 225mm x 75mm PRC concreate lintel with 100mm bearing either side of opening. Make good to openings and disturbed areas, removal of existing water heater concrete up-stand and door threshold detail. Removal of existing service pipework, remove / cap. | Item | 1
6.02 | Break out existing screed and relay to form new floor level ensuring level remains equal through out property, install 25mm thick timber door liner to form frame, installings architraves both sides and 38mm door stop complete with flush ply finish door and ironmongery with privacy latch, ensure new door and frame receives 3 paint coat finish, 1 primar, 1 undercoat 1 top coat white gloss coat. • Form asphalt up-stand detail to junction of walkway / external brickwork. Ensure all un-removed services are boxed installing suitable timber frame and two layers of 12.5mm plasterboard with angle trim and 3mm coat of thistle coat plaster. | Item | 1
6.03 | Install new Twyfords press steel 1700x700 bath including support legs, mixer taps and hand shower attachment, combined waste and overflow, all services to be taken and run from existing hot and cold supplys, all waste supplys from bath to be 40mm clipped and jointed and run into new boss connector on existing 75mm cast waste pipe. install Twyfords wash hand basin and pedestal with suitable taps, waste traps and 32mm pipe and fittings and run to existing 75mm soil waste pipe forming new boss, run hot and cold supplies to WHB from existing services, Note all hot and cold supply pipes to be manufactured from copper in either 22mm or 15mm, the use of flexable hoses and plastice pipe for water supplies are not allowed for. Form 110mm circula opening and install new soil waste for WC Pan and locate and install new to the newly formed bathroom, install with Twyfords close coupled WC Cistern, allowing for all supplies fittings and service valves to ensure the bathroom complies with Bye Law 30. ensure services are correctly installed and operational, fit bath with 50x50mm timber framework with white gloss finished hardboard side and end panels, with crome corner trim, 100mm chamferd skirting and mirror screw fixings for east removal and replacement of panel | Item | 1
6.04 | Install non slip sheet vinyl altro flooring bathroom area ensuring joints are welded in accourdance with the manufactures instructions with mastic finished edges. | Item | 1
6.05 | Install white 150x150mm Johnstone ceramic wall tiles to bath and wash hand basin, 3 courses high arround bath and 2 cources high over WHB, to include water proof adheasive, white grout and white tile trim and mastic. • dub out and plaster all wall and ceiling to laundry room walls / ceiling. | item | 1
6.06 | Electrics : Install suitable IP65 light fittings to bathroom ceiling with D/P pull cord fitting ajacent to newly formed bathroom door opening, ensure suitable pre works electrical test is carried out and NICEIC certificate is produced on completion. Cost to include mini trucking making good fiture and all fittings required. install low voltage 100mm vent axia VA fan to bathroom with timer and humidity overun, cost to include core hole and all cable fixtures and fittings required. | item | 1
6.07 | Remove old and exiting bath, WC and fittings from lounge including timber and plasterboard partition, cut back and isolate all services make good to all areas and decorate as instructed by CA. | item | 1
6.08 | Install 600 x 600 SP radiator to bathroom with TRV and connect to existing heating pipework, cost includes openings sleeving copper pipework clips fixtures and fittings required. | Item | 1
6.09 | Re decorate entire bathroom, 2 coats vinyl matt emulsion to walls, 2 coat vinyl matt emulsion to walls and previously painted surfaces and 1 undercoat and 1 gloss coat to timber work and skirting. • Certification of Electrical / Gas Installations certificates to be provided on completion of the works | Item | 1
Section 7: Contingency
7.01 | Contingency Sum: contingency sum is for measured works and at the entire descresion of the CA, the contingency sum will be omited from the total unless directed by the CA, to be used in part of full amount | Sum | 1 | 1500
|  | TOTAL - to Collection Page |  |  | £

## Summary (hidden)
AMP Valuation Master - Kitchens
Year:
Constructor:
Suply Chain:
Block Name:
Address:
Summary
UPRN | Flat No | AMP Total | Application | Certified
| 1 | #REF! | #REF! | #REF!
| 2 | #REF! | #REF! | #REF!
| 3 | #REF! | #REF! | #REF!
Total |  | #REF! | #REF! | #REF!

## Summary
LAMBETH COUNCIL - 10 Bilton House, Springfield, Laundry Adaptaion Conversion
NOTE TO CONTRACTORS:
When pricing the following work items / Sections, the Contractor should note that viewing the property is by appointment only, due to the structral instability of the internal floors access internally is restricted.
COLLECTION PAGE
SECTION
1 | Preliminaries | £
6 | Works | £
7 | Contingency Sum | 1500
| TOTAL | £
NB: | Total Tender Sum to be shown on Request for Quotation Form