## Implementation Stage 1
Implementation/Delivery (Stage 1) of Cheshire & Warrington Fair Employment Charter
Date | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-07 | 2024-11-14 | 2024-11-21 | 2024-11-28 | 5.12.24
Task
Inception meeting/Initial briefing with allocated resource
Recruitment of ongoing delivery post / identify 0.3 post
Draft and agree JD's
Advert placed
Review, interview and decision
Contract finalisation
Identify the 0.3 senior resource
Assumed start date
Website/Info Hub
Get specifications from other charters
Create application form and customer journey
Finalise charter/guidance wording
Create Policies and procedures
Commission IT provider to build online platform / liaise with Enterprise C&W website providers
Website build and application forms
Create initial set of content for online knowledge hub (examples of good practice, signposting resources)
Engagement and Promotion
Plan launch event (all event logistics, speakers, audience targeting etc)
Market event
Deliver launch event
Decide/agree engagement strategy/plan - target numbers etc
Plan engagement programme - quarterly seminars - for first year
Establish wider partnership and referral channels
Confirm and prepare FEC branding and collateral (in liaison with LEP/Marketing Cheshire teams)
Governance
Prepare Board arrangement and ToR
Prepare Panel arrangement and ToR
Approval to launch Charter (local authorities individually)
Assemble Panel and first meeting
Assemble Board and first meeting
Ongoing liaison with governance stakeholders
Handover to Ongoing Delivery team* assumed October, following staff in post

## Ongoing Delivery Stage 2
Ongoing Delivery Tasks (Stage 2) of Cheshire & Warrington Fair Employment Charter
Date | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30
Task
Stage 2 - Ongoing delivery
Engagement and comms
Coordinate engagement and comms team with Councils etc
Continue to commission, plan and deliver ongoing engagements e.g. seminars, events- and associated materials (quarterly seminars noted) | [10 empty] | seminar | [12 empty] | seminar | [12 empty] | seminar | [13 empty] | seminar | [12 empty] | seminar
Deliver plan to reach target memberships
Communication/PR plan and delivery/commissioning inc social media
Liaison with neighbouring Charters and relevant external agencies/organisations/all local stakeholders
Represent the Charter/C&W at external events etc/deliver presentations/be the face of the charter e.g. Altogether Fairer event (0.3)
Senior Stakeholder engagement (0.3)
Provide ongoing policy support and engagement (0.3)
Charter delivery
General programme and administration support to employers
Designing/overseeing passporting requirements
Delivery of actions requested by board/panel
Maintaining systems and files
Aspiring/entry level
Prospective member liaison/guidance x 40 per quarter including sourcing company target lists
Managing application process x c.20 per quarter
Full member
Planning for consultation on or launch of full member level 2025/6
Keeping up to date on required Charter wording updates
Quality Assurance
Attending good practice seminars, staying up to date on policy etc
Monitoring and evaluation of delivery
Budget
Oversee any financial arrangements with contractors e.g. for PR, IT or delivery
Governance
Board secretariat - Chair/Technical input/Notes
Panel secretariat - Chair/Technical input/Notes
Briefings to Boards/groups/senior officers as requested
Overseeing all governance work (0.3)
Supervision of coordinator (0.3)