Dear Sir or Madam:

Invitation to Tender:   PEOPLE IN THE LEAD - Understanding & Engaging the A Better Start Community & Workforce

Reference: BIG001-0764

You are invited by the Big Lottery Fund, to tender for the above referenced Contract. Our requirements are contained in this ITT document.

The Contract Terms and Conditions that you will be required to sign up to are available to view at this link: http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm.

The Contract will be awarded to a Service Provider.

The Preferred Bidder will not be permitted to enter into any negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Bidder being excluded from the tender process. In such circumstances the Fund reserves the right to invite the next highest scoring Bidder to enter into the Contract.

You must follow all the instructions set out in this Invitation to Tender when responding to it. The deadline for submission is 12.00 (Noon) on 4 January 2017.  Failure to provide all information required will result in rejection of the tender.

Yours faithfully,

Procurement

Big Lottery Fund

Email:	procurement@biglotteryfund.org.uk

CONTENTS:

SECTION ONE

Instructions to Bidders

SECTION TWO

Scope of Work

SECTION THREE

Annex 1 - 	Response to Tender and Evaluation Criteria

Annex 2 – 	Schedule of Charges

Annex 3 -	Bidder’s Details

Annex 4 - 	Form of Tender

Part I: Declaration

Annex 5-

Part I: Transparency Requirements

Part II Parent Company Guarantee (where appropriate)

Part III: Regulation 57 (1) Declaration

Part IV: Regulation 57 (8) Declaration

ANNEX 6 - 	List of a Better Start Wards

ANNEX 7 - 	Lambeth’s Pilot Survey

APPENDIX 1 - 	Leap Workforce Transformation Plan

# SECTION ONE

INSTRUCTIONS TO BIDDERS

- General Information

  - This is an invitation only.  The Big Lottery Fund reserves the right to vary any or all parts of the information contained in the Invitation to Tender.

  - The Big Lottery Fund intends to accept the tender which scores the most marks against the criteria set out below.  The Big Lottery Fund at its sole discretion, reserves the right to accept or reject any tender.  The Big Lottery Fund does not bind itself to accept the lowest priced or any tender and shall not be liable for any costs incurred in the production of your submission.

  - The Big Lottery Fund reserves the right to change the timing or any other aspect of the procurement process or to cancel the procurement process at any stage or not to proceed with the procurement for any reason whatsoever without prior notice. Under no circumstances will the Big Lottery Fund or any of its advisers be liable for any costs or expenses incurred by Bidders and/or their members in this procurement.

  - The Big Lottery Fund reserves the right not to disclose information that it feels would put them at a commercial or unacceptable contractual disadvantage.

  - Tenders, all documents and all correspondence relating to the tender must be written in English.

- Tender Documents

  - Tenders shall be submitted in accordance with the following instructions.

  - All pages of the tender shall be sequentially numbered (including any forms to be signed and returned).

  - The bidder is expected to examine all of the instructions, forms, Contract and specifications that comprise the tender documents. Unless the bidder provides all of the information required the tender will be rejected. If you have any queries about the information that must be submitted then you must raise them prior to the tender deadline in accordance with 3 (clarification) below.

  - All information issued in connection with the Invitation to Tender remain the property of the Big Lottery Fund and are to be used solely for the purpose of tendering.

  - The Preferred Bidder will not be permitted to enter into any post tender negotiations on the terms of the Contract. Any attempt to negotiate amendments will breach the terms of this ITT and will result in the Preferred Bidder being excluded from the tender process.  In such circumstances the Fund reserves the right to invite the next highest scoring bidder to enter into the Contract.

- Clarification

  - If you require clarification with respect to the contents of this ITT or this ITT process, please email                                   procurement@biglotteryfund.org.uk Questions or requests for clarification must be submitted prior to the closing date for the submission of questions.

  - The Big Lottery Fund will publish questions and responses (without identifying the author of the question) save where the Big Lottery Fund considers the question and response to be commercially sensitive. The Big Lottery Fund will upload responses to clarification questions on the following site regularly and it is bidder’s responsibility to review it regularly: http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm

- Schedule of Charges

  - Bidders shall complete Section Three, against each capitalised description, detailing a total and full cost for the service provision.

  - The rates and or percentage charges entered in Section Three shall be deemed to include complete provision for full compliance with the requirements of the Contract.

  - The rates and or percentage charges contained within Section Three are, unless otherwise expressly agreed between the parties, firm and fixed and will not be subject to any variation.

  - The Charges must be quoted in pounds sterling and inclusive of VAT and Expenses.

  - The Big Lottery Fund reserves the right to discuss and agree with the Contractor a maximum sum for all expenses.

  - ANY ATTEMPT TO QUALIFY PRICING OR INCLUDE ASSUMPTIONS IN THE SCHEDULE OF CHARGES THAT YOU ARE REQUIRED TO SUBMIT WILL RESULT IN THE REJECTION OF YOUR TENDER.

- Timetable

The indicative timetable for the procurement is as follows:

| Key Actions | Dates |
| --- | --- |
| Publish OJEU Notice and Issue of Invitation to Tender | 22 November 2016 |
| Closing Date for Questions | 12.00 Noon 13 December 2016 The Fund will upload responses to clarification questions on this site regularly and it is bidder’s responsibility to review it regularly. http://www.biglotteryfund.org.uk/index/about-uk/procurement_portal.htm |
| Tender Return Deadline | 12.00 Noon 4 January 2017 |
| Initial review/evaluation of tenders | 5 January 2017 |
| Clarification* and modify scores post clarifications and identification of Preferred Bidder | Week Commencing 23 January 2017 |
| Notification and Intention to Award Contract | Week Commencing 30 January 2017 |
| Standstill period | 31 January – 9 February 2017 |
| Contract Award | 10 February 2017 |
| Contract Work Commencement Date | Week Commencing 20 February 2017 |

*The Big Lottery Fund may vary these dates.

*The Fund reserves the right to carry out clarifications via email or by inviting Bidders to a clarification meeting.

Scores will be moderated based on any clarifications provided during this meeting.

- Legal Documentation

  - Achieving greater transparency of public sector procurement and contracting

Government has set out the need for greater transparency across its operations to enable the public to hold public bodies and politicians to account. This includes commitments relating to public expenditure, intended to help achieve better value for money.

As part of the transparency agenda, Government has made the following commitments with regard to procurement and contracting:

- All new central government tender documents for contracts over £10,000 and Contracts over £10,000 to be published on a single website from September 2010, with this information to be made available to the public free of charge.

Bidders should be aware that if your organisation is awarded this contract, the resulting contract between you and the Big Lottery Fund will be published.  In some circumstances, limited redactions will be made to some contracts before they are published in order to comply with existing law and for the protection of national security.

  - Bidders must complete and return all documents in Section 3

- Annex 1	Response to Tender and Evaluation Criteria

- Annex 2	Schedule of Charges

- Annex 3	Bidders Detail

- Annex 4 	Form of Tender

Part 1 Declaration

- Annex 5

Part I: Transparency Requirements

Part II Parent Company Guarantee (where appropriate)

Part III: Regulation 57 (1) Declaration

Part IV: Regulation 57 (8) Declaration

Bidders shall notify The Big Lottery Fund of any errors, omissions or details contained within the documents, which precludes them from tendering for this service.

  - Where a group of companies are bidding jointly for this Contract, the bid will need to identify a lead bidder and outline the individual roles and responsibilities of each company in relation to the delivery of the Contract. The Big Lottery Fund will enter into a contract with the lead organisation, and the lead organisation will ultimately be accountable for overall contract delivery. The lead organisation will be required to enter into a sub-contract with its partners on terms mirroring those of the main contract with the Big Lottery Fund (i.e. back-to-back contracts).

  - Bidders are required to detail within their tender submission if it is their intention to sub contract any element of the services detailed in section 2, ‘Scope of Works’.

  - NB: Bidders must declare any known or potential conflicts of interest.

- Submission Of Tenders

  - Bidders must submit an electronic copy of their tender submissions in a zip folder to procurement.procurement@biglotteryfund.org.uk  no later than 12.00 Noon on                   4 January 2017.    The subject line should be as follows;

“BIG001-0764 PEOPLE IN THE LEAD - Understanding & Engaging the A Better Start Community & Workforce”

Tenders received after that time will not be considered and it is your responsibility to ensure the tender is submitted in a zip file and that we have received it. If you do not submit the information in this way it may be too large for our email inbox and we will not receive it. Please ensure your emails are not larger than 7MB.

  - By submitting a tender, the bidder agrees to keep that tender open for acceptance by the Big Lottery Fund for 60 days following the closing date for submission of tenders.

  - The Big Lottery Fund does not bind itself to award a contract or contracts and shall not be liable for any costs incurred in the production or submission of ITT. Under no circumstances will the Big Lottery Fund or any of its advisers be liable for any costs or expenses incurred by Bidders and/or their members in this procurement.

- Notification Of Award Of Contract

  - Following the notification of outcome and the intention to award, a mandatory standstill period of TEN (10) calendar days will be observed. At the successful end of the standstill period the contract will be awarded.  The issue of a signed Contract shall constitute the Big Lottery Fund’s acceptance of the tender.

# SECTION TWO-SCOPE OF WORK

- INTRODUCTION

This contract is to support the five A Better Start local partnerships to gain a more detailed understanding of the capacity, capability and motivations of local people – professionals and community alike – and plan how they can best be engaged to deliver the A Better Start vision.

- BACKGROUND

Big Lottery Fund

The Fund is a non-departmental public body sponsored by the Cabinet Office.  We operate across all countries in the UK.

The Fund’s Mission and Values state that it is committed to bringing real improvements to communities, and to the lives of people most in need. To achieve this, we have three values that underpin all our work:

- Making the best use of Lottery money

- Using knowledge and evidence

- Being supportive and helpful

The Fund’s Vision and Principles

The Big Lottery Fund’s vision is that people should be in the lead in improving their lives and communities.  Our approach will focus on the skills, assets and energy that people can draw upon and the potential in their ideas.

We feel that strong, vibrant communities can be built and renewed by the people living in them – making them ready for anything in the face of future opportunities and challenges.

Our work and the choices will be guided by the following principles:

- Confidence, not control

We trust in people’s ability to make great things happen, believing that our funding should enable rather than control.

- Simple processes, good judgements

We use simple, proportionate processes which enable us to make good judgements.

- The strengths people bring

We start with what people can contribute, and the potential in their idea.

- A catalyst for others

We listen to, learn from, act on and facilitate the things that matter to people, communities and our partners.

- Shared direction, diverse approaches

We value the diversity of communities we work with across the UK, are consistent in the quality and opportunities we offer, and support people to tackle
inequalities.

- Using resources well

We make informed choices about the resources given to us by National Lottery players: with knowledge, with people and with money, and in an environmentally sustainable way.

Further details about the Big Lottery Fund, including our vision and principles are available on our website (www.biglotteryfund.org.uk/about-big/strategic-framework/our-vision).

- OVERVIEW & AIMS OF CONTRACT

‘A Better Start’ (ABS) is a major strategic programme focussed on developing and testing new approaches to improving Early Childhood Development. The programme addresses three child development outcomes:

- Improving diet and nutrition

- Improving language and communication

- Improving social and emotional development

Following a competitive application process, five local partnerships - Blackpool, Bradford, Lambeth, Nottingham and Southend - were awarded funding by the Big Lottery Fund in summer 2014 to begin implementation of their ten-year local programmes and strategies.  Since then, the five ABS partnerships have successfully established their core teams and are well underway with programme set-up and implementation.

A cornerstone of the Better Start approach is the conviction that meaningful and sustained change starts with local people. Successful programme implementation requires a supportive climate across all partner organisations with genuine and explicit buy-in from community members.

This cross-site project is designed to support the five ABS partnerships with understanding the barriers and enablers to engaging and mobilising the A Better Start community and workforce.  Findings and recommendations from the project will directly feed into local workforce, community and communications strategies.

The services rendered under this contract will support the partnerships in gaining a more detailed understanding of the capacity, capability and motivations of local people, professionals and community alike, and plan how they can best be engaged to deliver the Better Start Vision.

Learning and insights from this Contract will directly feed into the partnerships’ workforce, community and communications strategies.

- STRUCTURE OF CONTRACT

The contract is structured around 3 strands of work:

Strand 1. Insight and exploration: in-depth qualitative research in the five areas

Strand 2. Measurement: surveys of workforce and community

Strand 3. Applying findings: action planning

4.1  STRAND 1 - INSIGHT & EXPLORATION

Activities under Strand 1 are likely to include:

- Set up meetings

- Visits to each of the five sites

- Multiple focus groups in all five areas

- Depth interviews

- Analysis, interpretation and reporting of findings

- Detailed study of feasibility and design considerations for Strand 2

Objectives to be covered under Strand 1 are as follows:

4.1.1A) THROUGH THE EYES OF THE CORE ABS TEAMS

VISION & DEFINITION

- To work with the ABS core teams to explore their shared vision for the support children need to achieve better outcomes:

  - What are the ‘guiding principles’ for the ‘Better Start’ approach to service delivery?

  - What are the features of the common ethos they want to create?

  - What core knowledge, skills and competencies will be needed to deliver the vision?

  - What common systems (shared language/messaging, joint training, data sharing etc.) will need to be in place to enable this new approach?

- To work with the ABS core teams to develop a shared definition and conceptualisation of the ‘ABS workforce’:

  - Who would their definitions include?

  - Are there helpful ways of segmenting the workforce into particular categories (e.g. those with a direct v. indirect focus on ABS outcomes; by different levels of specialism; ‘active’ v. ‘potential’ volunteers etc.)?

CURRENT PERCEPTIONS

- To work with the ABS core teams to explore their perceptions of the current capacity, capability and motivations of different practitioner groups and community members in relation to the ABS vision and strategy.

- To understand the perceived barriers and opportunities to achieving the vision.

- To understand who are the key local stakeholders who can help or inhibit achievement of the vision

CURRENT APPROACHES

- To capture current and planned approaches to engagement and transformation and assess:

  - Which approaches seem most successful?

  - Have they found any specific methodologies or tools particularly useful?

  - What further ideas do the teams have for overcoming the barriers?

4.1.1B) THROUGH THE EYES OF KEY LOCAL HR LEADERS

Based on the vision and goals described in Strand 1A, to work with local HR leaders:

- To explore their perceptions of the current capacity, capability and motivations of different practitioner groups and community members in relation to the ABS vision and strategy.

- To identify what they consider to be the most important strengths, weaknesses, opportunities and threats to achieving the vision.

- To understand their organisational contexts, including: alignment and tensions with the goals of ABS; major change processes within their organisation (such as restructures, new strategies, changes in funding or key personnel); histories of managing change; and histories of collaborative working

- To understand how specific professional roles and identities align with the ABS programme and where there may be tensions.

- To understand the impacts of changing professional and policy contexts, driven by national and local agendas (e.g. professional codes/standards/guidance, national workforce strategies, inspection and monitoring regimes; changes in funding/commissioning etc.)

- To identify what common systems (shared language/messaging, joint training, data sharing etc.) will need to be in place to enable this new approach?

- To understand who are the key local stakeholders who can help or inhibit achievement of the vision

4.1.1C) THROUGH THE EYES OF PRACTITIONERS

Based on the definitions agreed in Strand 1A, to work with defined practitioner groups:

PRACTITIONER PERSPECTIVES

- To explore awareness and perceptions of the ABS vision and programme

- To explore what distinctive role and contributions they already play in helping families achieve the ABS outcomes.

- To identify drivers of, and barriers to, engagement and action

- To find out if, and how, they might ideally like to be involved in ABS; and what further contributions they could imagine.

ORGANISATIONAL CONTEXTS

- To understand their organisational contexts, including: alignment and tensions with the goals of ABS; major change processes within their organisation (such as restructures, new strategies, changes in funding or key personnel); histories of managing change; and histories of collaborative working

PROFESSIONAL AND POLICY CONTEXTS

- To understand how specific professional roles and identities align with the ABS programme and where there may be tensions.

- To understand the impacts of changing professional and policy contexts, driven by national and local agendas (e.g. professional codes/standards/guidance, national workforce strategies, inspection and monitoring regimes; changes in funding/commissioning etc.)

4.1.1D) THROUGH THE EYES OF COMMUNITIES

Based on the definitions agreed in Strand 1A, to work with defined groups from the community:

- To explore and articulate their shared vision for the support children and families need to achieve better outcomes:

  - Which people (and organisations) do people turn to for help?

  - What characteristics are most important and valued in these people?

  - What skills and competencies do they need to possess?

- To explore awareness and perceptions of the ABS vision and programme (spontaneous and prompted)

- To explore what distinctive role and contributions they already play in helping families achieve the ABS outcomes.

- To identify and explore potential drivers of engagement and action (amongst those already involved in ABS; those involved in other community activities; and those not currently involved in any voluntary activities)

- To identify and explore potential barriers to engagement and action (e.g. availability and awareness of opportunities; confidence and skills; time; accessibility etc.)

- To find out if, and how, they might ideally like to be involved in ABS; and what further contributions they could imagine.

4.2 STRAND 2 MEASUREMENT

Activities under Strand 2 are likely to include:

- Survey design (expert consultation, questionnaire design, piloting)

- Local feasibility assessments

- Preparation of sample frames for professional and community strands

- Piloting data collection for both professional and community components

- Web-based interviews with c. 7,500 members of the workforce across the five sites

- Recruitment of community survey respondents

- In-home interviews with a representative sample of community members

- Data preparation

- Data analysis

- Report writing (national and local reports) – including recommendations of priority actions

Objectives to be covered under Strand 2 are described below:

4.2.1	SURVEY DESIGN & SAMPLING STRATEGY

- To design surveys to measure the ABS ‘workforce’ (see definition of scope later).  This should include both professional and community surveys in each of the five locations.  The surveys should provide a consistent baseline picture allowing comparisons between areas.

- To develop a sampling strategy that ensures representation of the breadth of the ABS workforce and community.

Survey Design Considerations

- Definition of the final population and sample frame should be informed by findings from Strand 1, as well as by practical and methodological considerations about administration of the surveys.

- As far as possible, the sampling strategy should allow comparisons between different segments of the workforce and the methodology should allow for the possibility of repeating the survey in the future and being able to compare change over time.

- A small scale pilot study by the ABS Lambeth partnership has demonstrated the feasibility of conducting a web-based survey among members of the paid workforce.  This pilot had a more limited scope, focussed specifically on skills and knowledge relevant to ECD.  A copy of the report from the Lambeth pilot is available alongside this ITT pack.

- However, we anticipate that achieving a representative sample of community members is likely to require a different approach to sampling and fieldwork, such as quota sampling and in-home interviewing.

- Whilst it is understood that modes of data collection are likely to be different between the paid workforce and members of the community, we would be keen to see how you would maximise the comparability between the two.

- Full sample size assumptions and justifications should be set out in your proposal

4.2.2	QUESTIONNAIRE DESIGN

- To carefully design and structure the survey instruments based on appropriate theory (e.g. relevant engagement and organisational change theories; and relevant community, social capital and social network theories) and a clear logic model

- To capture key descriptive and explanatory information about the ‘workforce’: socio-demographics; current role(s)/activities; core competencies; knowledge of early childhood development; relevant specialist skills and experience; values and beliefs, attitudes and motivations.  Where possible and appropriate you should make use of previously validated measures.

- To capture relevant descriptive and explanatory information from the community sample about social capital and social networks

- To capture key outcome data on: awareness and understanding of ABS; engagement; intention to act; and current contributions and ‘actions’ (i.e. activities that directly help the ABS programme delivery and/or help expectant and new families in ways likely to achieve the ABS outcomes).

Whilst some questions will need to be tailored for respondents who are not practitioners to measure their experiences, we would hope that where possible, the surveys will include items that allow comparisons between community members and practitioners.

4.2.3	PILOT TESTING

- To pilot test the surveys and recruitment processes to ensure that the methodology and survey instruments are effective and ready for main stage fieldwork.  You should pay particular attention to ensuring that instruments and analyses are designed in a way which is likely to elicit findings which can readily support action planning.

4.2.4	FIELDWORK

- To carry out the main-stage fieldwork across all five local areas, monitoring progress closely and ensuring that fieldwork is completed to time and budget

- To ensure that all fieldwork is conducted in accordance with rigorous quality and ethical standards.

- We would welcome proposals that consider the training and use of local community members in the research process.  You are invited to include this as an option (within the overall cost of this contract).  You should detail any specific methodological considerations as well as how you would ensure data quality would be achieved.

4.2.5 ANALYSIS

- To develop a clear and rigorous analytical plan, defining the basic descriptive, as well as the multivariate analyses that you will use to interrogate the data and draw your conclusions and recommendations for action.  This should include details of the hypotheses and statistical tests that will be used in your analysis.

You should ensure that the analyses are carried out in a way that will provide clear and directly actionable information for the local partnerships.  In particular, your analysis should enable the partnerships to identify the most important barriers and enablers to engagement and action in their local areas; and which audiences/groups are the most important to prioritise in workforce, community and communications plans.

4.3 STRAND 3 APPLYING THE FINDINGS & ACTION PLANNING

Activities under Strand 3 are likely to include:

- Designing and delivering workshops in all five localities

- Presenting to and engaging Senior Stakeholders locally

- Helping sites to produce robust local action plans to apply recommendations to their workforce, community engagement and communications strategies

- Developing a toolkit or resources to enable future replication of the methods used in this project

Objectives to be covered under Strand 3 are described below:

- To report findings from Strands 1 and 2 of the project, clearly setting out key themes, priority issues and specific recommendations for each of the partnerships.

- To support local partnerships in interpreting what the findings mean for their local areas

- To support local partnerships in making sense of the opportunities and threats of dynamic operating contexts and new directions in policy.

- To work with the local partnerships and their key local stakeholders to develop concrete action plans, applying findings from the research to their local communications, workforce and community plans.

- To support the partnerships in identifying the most appropriate tools and methodologies for implementing change, bearing in mind their specific local contexts.

5.	SCOPE

All of the ABS partnerships conceive of the ‘workforce’ as something wider than the professional paid workforce.  And whilst it is important to be cognisant of the current context in particular professions, we are keen that this project should avoid traditional traps in thinking about individual professions in silos.

This project aims to cover the diverse pool of people with the potential to improve children’s early development.  It includes volunteers and members of the community as well as those working in professions that directly - and less directly - serve expectant parents and families with babies.  We currently have a limited picture of who these people are and what knowledge, skills, values, motivations and experiences they bring.

5.1	In scope:

- Paid practitioners with a direct focus on the ABS outcomes and pregnancy to three life stage:  health visitors, midwives, practice nurses, SAL therapists, family support workers social workers, paediatricians, obstetricians, dieticians, children’s centre workers, General Practitioners, parent-infant psychologists, psychotherapists, psychiatrists, day care workers, Home Start, charity sector. This is not intended as an exhaustive list and will need to be refined and agreed under Strand 1a.

- Paid practitioners with indirect focus/influence on the ABS outcomes and pregnancy to three life stage: housing officers, CAB/Advice services, drug and alcohol treatment services, adult mental health services, domestic abuse services; employment advisors. This is not intended as an exhaustive list and will need to be refined and agreed under Strand 1a.

- Community members: current volunteers with a direct focus on the ABS outcomes and pregnancy to three life stage

- Community members: current volunteers not directly focussed on ABS outcomes or pregnancy to three life stage

- Community members: not current volunteers.  This group may include a number of different segments reflecting different levels of activity and attitudes and motivations towards the programme.

5.2	Not in scope:

- Effectiveness of specific models of intervention (including interventions delivered by volunteers or peer supporters)

- Behaviour change interventions seeking to influence parents around their own children’s outcomes

- Roles that do not impact on early childhood development and the ABS outcomes

6.	REQUIREMENTS

6.1	The Service Provider will:

- Work closely and collaboratively with Directors and other representatives from the five ABS partnerships, ensuring that they are well informed about project activities and ensuring their positive engagement in the process.

- Nurture the ethos of collaboration and co-production within and between the ABS partnerships.  In particular, working closely with the ABS Communities of Practice for ‘workforce’ and ‘community’.  They will provide an important reference group for the project. These Communities of Practice are facilitated by the ABS Development Support Advisor.  The Communities of Practice meet quarterly and we would expect this project to be a regular focus of their work during 2017 and into 2018.

- Work closely with the Director of Development for A Better Start at the Big Lottery Fund.  The Director has overall responsibility for the Development Support programme, including oversight of other related development support projects, Learning & Development Events and the communities of practice.

- Set out how you will access specialist expert advice to guide the project, including the composition and role of any advisory groups proposed during the lifetime of the project.

- Ensure effective communication and coordination with other contracted service providers working with the Big Lottery Fund and the five partnerships, including: the National Evaluation team at Oxford University; the team at King’s College London who are providing consultancy about delivery of the Healthy Child Programme; and the Frameworks Institute (subject to contract) who are supporting the sites with development of a shared communications campaign to promote early social, emotional and language development.

- Carefully consider wider transferability of learning.  For example, by designing approaches and tools that could be applied in other areas in the future; and proactively identifying ways in which learning might be shared.

6.2	Delivery of this Contract will require a broad skill set.  We expect the contracted team to be able to offer a strong combination of skills and experience including:

ESSENTIAL SKILLS & EXPERIENCE:

- High level of capability in designing, conducting and analysing complex survey and qualitative research in deprived communities, with robust research ethics and quality assurance standards

- Access to subject expertise in: organisational change (including organisational psychology, implementation science, complex adaptive systems); and in community development and social capital/social network theories

- Experience of working collaboratively with local communities, local public services and local voluntary organisations.

- Ability to work effectively with local partnerships to apply findings and develop robust local action plans and strategies.

- Ability to write well and deliver clear, user-friendly and actionable outputs and recommendations.

7.	ACTIVITIES

Bidders are encouraged to suggest activities that will form the methodology to best achieve the aims of this project.  Bidders should set out specific methods and improvement approaches which will best achieve the aims of this project. The methodology should include clear descriptions of each of the methods and activities to be employed, with clear justification and cross referencing to the specific aims and strands.

Bidders must include a clear overview of the project timetable showing key activities and milestones and any interdependencies between different strands of work.  This may be in the form of a Gantt chart or other similar diagrams.

Bidders should make clear in your response to the ITT any demands on, or expectations of, the Big Lottery Fund, the local partnerships or other stakeholders.

8.	OUTPUTS

8.1	Bidders should provide a schedule of project outputs, including a description of the aims, audience and format for each deliverable.

In designing the schedule of outputs, bidders should consider the needs of the five partnerships at each of the key stages of the project.  It will be important to consider how analysis and recommendations in interim reports (or other deliverables) might most usefully support the partnerships in developing their thinking during subsequent stages of the project and beyond.

An explicit aim of the project is that the work should be useful not only to the five ABS sites, but also for other areas who share the ambitions.  We would therefore welcome proposals which include outputs which support wider transferability of learning.

All reports should be clear, authoritative and of a publishable standard.  The ABS partnerships and the Fund will wish to have the opportunity to comment on draft reports.  The Fund encourages the use of peer review for key deliverables, particularly where these are intended to support learning beyond the partnerships.

8.2	We would expect to see as part of the outputs:

- A report of findings from Strand One, setting out key themes, analysis and implications across the 5 partnerships

- Concise local area summaries of findings from Stage One, highlighting any specific local findings, priority issues and recommendations

- An update report with top-line findings from the pilot survey

- Regular update reports on the progress of survey fieldwork

- A full report of findings from the main stage survey.  This should highlight the priority issues that would have the biggest positive/enabling impact on local programme delivery.

- A technical report from the survey, including detailed methodology and all design and data collection instruments

- Data tabulations from the main stage survey

- Full clean data sets (with all weights and derived variables) and full code book.

- Local action plans developed with each of the 5 areas.  These should be based on clear area-specific priorities and recommendations from the strands 1 and 2 fieldwork.

- Toolkit (or equivalent means of dissemination) describing the project methodology for areas who might wish to repeat the approach in the future.

9. CONTRACT TERM, BUDGET & PAYMENT SCHEDULE

The Contract is for a term of 1 year and 3 months. The Contract value shall not exceed £658,000 including VAT and expenses.

Payment will be made by milestones. Bidders are invited to suggest milestones and the deliverables that evidence the achievement of the milestone in Table C of Annex 2.

10. COMMUNICATION AND ACCOUNTABILITY

The Service Provider will maintain excellent communications with the Fund at all times ensuring that it is well informed, aware of issues and central to decision making in relation to progress.  The successful bidder will:

- Identify a named contact acting as Contract Manager. The designated person will carry prime responsibility for the contract and will be the Accountable Officer

- Identify a named contact person as Service Manager. The designated person will carry prime responsibility for the delivery and implementation of services under this contract. The Service Manager and Contract Manager can be the same person, provided they have the relevant skills

- The Contract Manager/Service Manager will liaise with and take instruction from the Fund’s Contract Manager.

11. DELIVERABLES

The Service Provider must provide the following deliverables to the Fund:

| Action | Due Date/timescale |
| --- | --- |
| Interim report covering Strand 1 | 6 July 2017 |
| Final Report covering Strand 1 | 27 July 2017 |
| Interim report covering Strand 2 | 15 Dec 2017 |
| Final Report covering Strand 2 | 26 Jan 2018 |
| Interim report covering Strand 3 | 17 April 2018 |
| All final reporting, including strand 3 | 6 May 2018 |

* The Fund reserve the right to amend this timetable where required.

# SECTION THREE

## ANNEX 1

Response to Tender & Evaluation Criteria

You are required to respond to ALL of the criteria below.  To assist our evaluation of your tender submission, please ensure you clearly cross-refer your responses to the assigned numbers. Any relevant supporting tender documentation must also be clearly identifiable by a criteria number.

Initially we will evaluate your tender to see if you meet our minimum PASS/FAIL CRITERIA set out below.

Bidders who do not pass all the Pass/Fail criteria (A-F) below will be excluded from further consideration in the competition (i.e. their tenders will not be evaluated further and will be excluded from the competition).

Pass/Fail Criteria

| Pass Fail Criteria A | PASS/FAIL |
| --- | --- |
| The Fund requires the provider to have a minimum of 3 years relevant experience successfully delivering similar projects. Please provide Evidence of 3 years experience of undertaking similar projects (similar in scale, value and complexity) successfully and supporting references demonstrating this. Contact details of referees to support each example must also be provided. The customer contact should be prepared to speak to the Fund to confirm the accuracy of the information provided. |  |

| Pass Fail Criteria B |  |
| --- | --- |
| Financial PASS/FAIL TEST (Where the bidder is a consortium, this test will be carried out on the lead organisation who the Fund will enter into a contract with and the Lead Organisation should submit the information requested below) Please submit a copy of your last two years annual accounts. We will review these to ensure you have adequate financial standing to perform the services without putting the Fund at risk. Where we have concerns we may request further information/comfort from you. Where our concerns are not addressed you will be excluded from further participation in the competition. In order for us to carry out this assessment please provide copies of last two year’s audited accounts and annual reports to include: - Balance Sheet - Profit & Loss Account and Cost of Sales - Full notes to the accounts - Director’s report/auditor’s report If you are unable to submit the information requested above because your organisation is below the threshold for which audited accounts are required, please submit the following documents instead: - Balance Sheet - Profit and Loss Statement |  |
| Pass Fail Criteria C |  |
| Bidders must confirm they either have: - Hold an accredited independent third party certificate of compliance in accordance with BS EN ISO 9001 (or equivalent); or - Have documented procedures for periodically reviewing, correcting and improving quality performance including processes for ensuring that the bidder’s quality management is effective in reducing/preventing incidents of sub-standard delivery, this must include the quality of output and general performance. The winning bidder will be required to provide documentary evidence upon contract award |  |
| Pass Fail Criteria D |  |
| Bidder has submitted a complete tender that accords with every instruction and requirement set out in this ITT. |  |
| Pass Fail Criteria E |  |
| Bidder has completed Parts III and IV of Annex 5 and confirmed none of the circumstances set out there in apply. |  |
| Pass Fail Criteria F |  |
| The Bidder’s Total Costs in Table A do not exceed £658,000 (including VAT and expenses). Bidders whose costs exceed this amount will be excluded from further consideration in the tender process. |  |

If you pass all of the pass/fail criteria set out above, we will evaluate your tender response using quality and price criteria which are set out below.

Your Bid will be scored out of 100:

- 80% of the marks will be allocated to your response to the Quality Questions

- 20% of the marks will be available for your Price Proposal.

Methodology for Scoring Quality: 80% overall

Answers for each Quality Question will be scored between 0 (Poor) of 5 (Excellent) using the definitions below:

| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the Fund confidence in the ability of the Bidder to deliver the Contract. |
| --- | --- | --- |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the Fund confidence in the ability of the Bidder to deliver the contract. Meets the Fund’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the Fund a high level of confidence in the ability of the Bidder to deliver the contract. Exceeds the Fund’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the Fund a very high level of confidence the ability of the Bidder to deliver the contract. Exceeds the Fund’s requirements in most respects. |

Your score for each question will be calculated by multiplying the quality score you receive with the weighting for that question, set out in the table below.

The final quality score will be your total score divided by the maximum available score and multiplied by 80

Maximum Available Score = 500

Question 1:  5 x 40 = 200

Question 2: 5 x 15 = 75

Question 5:  5 x 25 = 125

Question 5: 5 x 10 = 50

Question 5:  5 x 10 = 50

Example: assume Bidder A scores

3 for Question 1:  3 x 40 = 30

5 for Question 2: 5 x 15 = 75

3 for Question 3:  3 x 25 = 75

5 for Question 4: 5 x 10 = 50

3 for Question 5:  3 x 10 = 30

Bidder Total Score = 350

The formula will be

Bidder’s Total Score (350) /Maximum Available score (500) * % Quality Weighting (80) =56%

Quality Questions: 80% overall

Please note – Though questions are numbered, this does not relate to any order of importance.

Your responses should be supported by evidence/previous successful implementation of proposed solution for meeting our requirements.

|  | Quality: 80% | weighting |
| --- | --- | --- |
| Question:1 | Please detail your proposal to meet our requirements including your methodology and understanding of the aims. Your response should outline a description of all proposed activities under each of the three work strands as headings. | 40 |
| Question: 2 | Please provide a clear and realistic project plan that clearly responds to the requirements set out in Section 2 | 15 |
| Question: 3 | Please detail your proposed delivery team including their relevant skills and expertise to deliver against each of the three work strands. Outline where they have undertaken similar work You should state clearly what roles they will play and suggested resource allocations. | 25 |
| Question: 4 | Please explain how you would ensure a collaborative and effective working relationship with the 5 partnerships and the Fund | 10 |
| Question: 5 | Please describe the risks to delivering this project to time, budget and quality, together with your detailed proposals for mitigating them. | 10 |

Responses to each question above will be allocated a score based on the methodology contained in the table below. This score will then be multiplied by the weighting in the column on the right.

Price scoring methodology: 20% overall

Price: The evaluation of price will be carried out on the Schedule of charges you provide in response to Annex 2 Table A

## The scores for quality and price will be added together to obtain the overall score for each Bidder. The Bidder with the highest score will be the preferred Bidder.

ANNEX 2

Schedule of Charges

Bidders must complete the schedule of charges table A below estimating the number of days and travel and subsistence costs associated with their bid. The total fixed price will be inclusive of VAT and inclusive of expenses and all costs to be incurred.

| TABLE A: (firm and fixed costs) |  | e.g. Project Manager/ Director | e.g. Senior Consultant/manager/researcher | Junior Consultant/equivalent | Total days | Total Fees |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | e.g. £500 | e.g. £300 | e.g. £200 |  |  |
|  | Quantity |  |  |  |  |  |
| Inception meeting to agree plans and finalise requirements with the Fund | 1 | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| Other (insert additional rows to include other deliverables as per section two of the tender) |  |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |  |
| Expenses |  |  |  |  |  |  |
| Travel and subsistence |  |  |  |  |  |  |
| Other (non-staff) costs – Please specify |  |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  |
| VAT |  |  |  |  |  |  |
| Total Costs including VAT and expenses (this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements ) |  |  |  |  |  |  |

Notes: 	The Fund reserves the right to reject abnormally low tenders.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

* The Fund reserve the right to amend this timetable where required.

Please note any contract awarded will be based on the Fund’s standard terms and conditions of contract and you will be required to sign up to these if successful.

Table B:  Cost Plans per Strand

The completed Table A must be accompanied by a separate cost plan for each Strand setting out how the above costs have been arrived at.

Please expand columns as required.

| Cost Plan for Strand 1 |  | e.g. Project Manager/ Director | e.g. Senior Consultant/manager/researcher | Junior Consultant/equivalent | Total days | Total Fees |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | e.g. £500 | e.g. £300 | e.g. £200 |  |  |
|  | Quantity |  |  |  |  |  |
| Inception meeting to agree plans and finalise requirements with the Fund | 1 | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| [Add as necessary] |  |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |  |
| Expenses |  |  |  |  |  |  |
| Travel and subsistence |  |  |  |  |  |  |
| Other (non-staff) costs – Please specify |  |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  |
| VAT |  |  |  |  |  |  |
| Total Costs including VAT and expenses (this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements ) |  |  |  |  |  |  |

| Cost Plan for Strand 2 |  | e.g. Project Manager/ Director | e.g. Senior Consultant/manager/researcher | Junior Consultant/equivalent | Total days | Total Fees |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | e.g. £500 | e.g. £300 | e.g. £200 |  |  |
|  | Quantity |  |  |  |  |  |
| [Add as necessary] | 1 | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| [Add as necessary] |  |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |  |
| Expenses |  |  |  |  |  |  |
| Travel and subsistence |  |  |  |  |  |  |
| Other (non-staff) costs – Please specify |  |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  |
| VAT |  |  |  |  |  |  |
| Total Costs including VAT and expenses (this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements ) |  |  |  |  |  |  |

| Cost Plan for Strand 3 |  | e.g. Project Manager/ Director | e.g. Senior Consultant/manager/researcher | Junior Consultant/equivalent | Total days | Total Fees |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | e.g. £500 | e.g. £300 | e.g. £200 |  |  |
|  | Quantity |  |  |  |  |  |
| [Add as necessary] | 1 | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| [Add as necessary] |  |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |  |
| Expenses |  |  |  |  |  |  |
| Travel and subsistence |  |  |  |  |  |  |
| Other (non-staff) costs – Please specify |  |  |  |  |  |  |
| Sub-total |  |  |  |  |  |  |
| VAT |  |  |  |  |  |  |
| Total Costs including VAT and expenses (this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements ) |  |  |  |  |  |  |

SCHEDULE OF PAYMENT-LINKED MILESTONES

Table C:

Propose milestones, the deliverables that will evidence their achievement and suggested payment. The FUND will review it and reserve the right to amend it.

| Milestone | Strand (1,2 or 3) | Deliverable | Date | Payment Amount |
| --- | --- | --- | --- | --- |
| [Add as necessary] |  |  |  |  |
| [Add as necessary] |  |  |  |  |
| [Add as necessary] |  |  |  |  |
| Total Amount |  |  |  |  |

ANNEX 3

Bidder’s Details

| Company Details |  |
| --- | --- |
| 1. | Registered Company Name: |
| 2. | Company Registration Number: |
| 3. | Main Operational address for the service: |
|  | Tele: |
|  | Fax: |
|  | Email: |
| 4. | Address for all contractual correspondence – |
|  | (If one of the above, please specify) |
| 5. | Address for all service management correspondence |
|  | (If one of the above, please specify) |
| 6. | Contacts: |
|  | a. Responsible Person for the Contract |
|  | Tele: |
|  | Fax: |
|  | Mobile: |
|  | Email: |
|  | b. Responsible Person for the Service: |
|  | (If different to the above) |
|  | Tele: |
|  | Fax: |
|  | Mobile |
|  | Email: |
| 7. | VAT registration Number (if applicable) |
| 8. | Payment Details |
|  | Account Name: |
|  | Bank Name: |
|  | Address: |
|  | Sort Code: |
|  | Account Number: |

## ANNEX 4

Form of Tender

Part I – Declaration

##### Note: The Bidder is to type the following on its own letter headed paper

Dear Big Lottery Fund

CONTRACT FOR Tender Title: PEOPLE IN THE LEAD - Understanding & Engaging the Better Start Community & Workforce ref (‘the Contract’)

Having examined the proposed Contract comprising, we do hereby offer to enter into a Contract with THE FUND on the terms and conditions in the said Contract.

We undertake to keep the Tender open for acceptance by THE FUND for a period of sixty (60) days from the return date.

We declare that this is a bona fide Tender, intended to be competitive, and that we have not fixed or adjusted the amount of the Tender by, or under, or in accordance with, any agreement or arrangement with any other person.  We further declare that we have not done, and we undertake that we will not do, any of the following acts prior to award of this Contract:

- Collude with any third party to fix the price of any number of Tenders for this Contract;

- Offer, pay, or agree to pay any sum of money or consideration directly or indirectly to any person for doing, having done, or promising to be done, any act or thing of the sort described herein and above.

We understand that you are not bound to accept the lowest priced, or any, Tender.

Signed:

Date:

Name:

In the capacity of:

Duly authorised to sign tenders for and on behalf of:

ANNEX 5

Part I: Transparency

Note: In compliance with the Government’s transparency agenda, all Big Lottery Fund contracts over £10,000 (net of recoverable VAT) issued on or after 1 January 2011 will be published on the Government’s Contracts Finder website. We are required to publish contracts in full, and as a minimum must publish the specification, terms and conditions and associated schedules (which may include the winning bidder’s bid).

In limited circumstances redactions can be made prior to publication to protect certain types of information. Redactions are permitted in line with the exemptions set out by the Freedom of Information Act 2000. Examples of information which may be exempt under the FOIA include: personal data; information amounting to a trade secret; and information which if disclosed would or would be likely to prejudice the commercial interests of any person.

If the Bidder believes redactions ought to be made, these should be identified by the Bidder in the following table on their own letter headed paper. Bidders must provide explicit justification and reasoning for each redaction requested. The Big Lottery Fund is responsible for determining in its absolute discretion whether any information is exempt from publication.

CONTRACT FOR Tender Title: Understanding & Engaging the Better Start Community & Workforce BIG001-0764

| Contract clause or section of tender to be redacted | Justifications for redaction |
| --- | --- |

Part II: Parent Company Guarantee

Note:  To be submitted in full on Contractor's ultimate Holding Company's headed notepaper.

Dear Big Lottery Fund

Contract for the Provision of Understanding & Engaging the Better Start Community & Workforce BIG001-0764

With reference to the Tender for the above services submitted by [insert name of Bidder] (hereinafter referred to as "the Contractor"), as a condition precedent for and in consideration of the Big Lottery Fund (a non departmental Public Body sponsored by the Cabinet Office) (hereinafter referred to as "THE FUND") entering into a contract (hereinafter referred to as "the Contract") with the Contractor for the above services, we, as the Contractor's ultimate holding company do hereby enter into the following unconditional and irrevocable undertakings with THE FUND. These undertakings being on condition that THE FUND enters into the Contract with the Contractor for the above services and in consideration of the same:

- The Contractor shall perform all its obligations contained in the Contract;

- If the Contractor shall in any respect fail to perform the said obligations contained in the Contract or commits any breach thereof we shall ourselves perform on simple demand by THE FUND, or take whatever steps may be necessary to achieve performance of the obligations under the Contract of the Contractor, and shall indemnify and keep indemnified the Authority against any loss, damages, costs and expenses howsoever arising from the said failure or breach for which the Contractor may be liable;

- We shall not be discharged or released from our undertakings hereunder by any waiver or forbearance by THE FUND, whether as to payment, time, performance or otherwise;

- This guarantee shall be unconditional and irrevocable and shall continue in force, notwithstanding any variations or additions to or deletions from the scope of services to be performed under the Contract, until all the Contractor's obligations there under have been performed; and,

- This document shall be construed and take effect in accordance with English Law and, furthermore, we submit to the jurisdiction of the English Courts.

Yours faithfully

Signed:

Date:

Name:

In the capacity of:

Duly authorised to sign tenders for and on behalf of:

Part III: Regulation 57 (1) Declaration

Important Notice:

In some circumstances the Fund is required by law to exclude you from participating further in procurement. If you cannot answer ‘no’ to every question in this section it is very unlikely that your application will be accepted, and you should contact us for advice before completing this form.

| 2.1 Within the past five years, has your organisation (or any member of your proposed consortium, if applicable), Directors or partner or any other person who has powers of representation, decision or control been convicted of any of the following offences? | Please indicate your answer by marking ‘X’ in the relevant box. |  |
| --- | --- | --- |
|  | Yes | No |
| - conspiracy within the meaning of section 1 or 1A of the Criminal Law Act 1977 or article 9 or 9A of the Criminal Attempts and Conspiracy (Northern Ireland) Order 1983 where that conspiracy relates to participation in a criminal organisation as defined in Article 2 of Council Framework Decision 2008/841/JHA on the fight against organised crime; |  |  |
| - corruption within the meaning of section 1(2) of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906; |  |  |
| - the common law offence of bribery; |  |  |
| - bribery within the meaning of sections 1, 2 or 6 of the Bribery Act 2010; or section 113 of the Representation of the People Act 1983; |  |  |
| - any of the following offences, where the offence relates to fraud affecting the European Communities’ financial interests as defined by Article 1 of the Convention on the protection of the financial interests of the European Communities: |  |  |
| (i) the offence of cheating the Revenue; |  |  |
| (ii) the offence of conspiracy to defraud; |  |  |
| (iii) fraud or theft within the meaning of the Theft Act 1968, the Theft Act (Northern Ireland) 1969, the Theft Act 1978 or the Theft (Northern Ireland) Order 1978; |  |  |
| (iv) fraudulent trading within the meaning of section 458 of the Companies Act 1985, article 451 of the Companies (Northern Ireland) Order 1986 or section 993 of the Companies Act 2006; |  |  |
| (v) fraudulent evasion within the meaning of section 170 of the Customs and Excise Management Act 1979 or section 72 of the Value Added Tax Act 1994; |  |  |
| (vi) an offence in connection with taxation in the European Union within the meaning of section 71 of the Criminal Justice Act 1993; |  |  |
| (vii) destroying, defacing or concealing of documents or procuring the execution of a valuable security within the meaning of section 20 of the Theft Act 1968 or section 19 of the Theft Act (Northern Ireland) 1969; |  |  |
| (viii) fraud within the meaning of section 2, 3 or 4 of the Fraud Act 2006; or |  |  |
| (ix) the possession of articles for use in frauds within the meaning of section 6 of the Fraud Act 2006, or the making, adapting, supplying or offering to supply articles for use in frauds within the meaning of section 7 of that Act; |  |  |
| - any offence listed— |  |  |
| (i) in section 41 of the Counter Terrorism Act 2008; or |  |  |
| (ii) in Schedule 2 to that Act where the court has determined that there is a terrorist connection; |  |  |
| - any offence under sections 44 to 46 of the Serious Crime Act 2007 which relates to an offence covered by subparagraph (f); |  |  |
| - money laundering within the meaning of sections 340(11) and 415 of the Proceeds of Crime Act 2002; |  |  |
| - an offence in connection with the proceeds of criminal conduct within the meaning of section 93A, 93B or 93C of the Criminal Justice Act 1988 or article 45, 46 or 47 of the Proceeds of Crime (Northern Ireland) Order 1996; |  |  |
| - an offence under section 4 of the Asylum and Immigration (Treatment of Claimants etc.) Act 2004; |  |  |
| - an offence under section 59A of the Sexual Offences Act 2003; |  |  |
| - an offence under section 71 of the Coroners and Justice Act 2009 |  |  |
| - an offence in connection with the proceeds of drug trafficking within the meaning of section 49, 50 or 51 of the Drug Trafficking Act 1994; or |  |  |
| - any other offence within the meaning of Article 57(1) of the Public Contracts Directive— |  |  |
| (i) as defined by the law of any jurisdiction outside England and Wales and Northern Ireland; or |  |  |
| (ii) created, after the day on which these Regulations were made, in the law of England and Wales or Northern Ireland. |  |  |
| Non-payment of taxes (Regulation 57(3)) Has it been established by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which your organisation is established (if outside the UK), that your organisation is in breach of obligations related to the payment of tax or social security contributions? If you have answered Yes to this question, please use a separate Appendix to provide further details. Please also use this Appendix to confirm whether you have paid, or have entered into a binding arrangement with a view to paying, including, where applicable, any accrued interest and/or fines? |  |  |

Part IV: Regulation 57 (8) Declaration

Important Notice.

The Fund is entitled to exclude you from consideration if any of the following apply but may decide to allow you to proceed further. If you cannot answer ‘no’ to every question it is possible that your application might not be accepted. In the event that any of the following do apply, please set out (in a separate Annex) full details of the relevant incident and any remedial action taken subsequently. The information provided will be taken into account by the Authority in considering whether or not you will be able to proceed any further in respect of this procurement exercise.

| Within the past three years, please indicate if any of the following situations have applied, or currently apply, to your organisation or member organisation of your proposed consortium. | Please indicate your answer by marking ‘X’ in the relevant box. |  |
| --- | --- | --- |
|  | Yes | No |
| - your organisation has violated applicable obligations referred to in regulation 56 (2) of the Public Contracts Regulations 2015 in the fields of environmental, social and labour law established by EU law, national law, collective agreements or by the international environmental, social and labour law provisions listed in Annex X to the Public Contracts Directive as amended from time to time; |  |  |
| - your organisation is bankrupt or is the subject of insolvency or winding-up proceedings, where your assets are being administered by a liquidator or by the court, where it is in an arrangement with creditors, where its business activities are suspended or it is in any analogous situation arising from a similar procedure under the laws and regulations of any State; |  |  |
| - your organisation is guilty of grave professional misconduct, which renders its integrity questionable; |  |  |
| - your organisation has entered into agreements with other economic operators aimed at distorting competition; |  |  |
| - your organisation has a conflict of interest within the meaning of regulation 24 of the Public Contracts Regulations 2015 that cannot be effectively remedied by other, less intrusive, measures; |  |  |
| - the prior involvement of your organisation in the preparation of the procurement procedure has resulted in a distortion of competition, as referred to in regulation 41, that cannot be remedied by other, less intrusive, measures; |  |  |
| - your organisation has shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions; |  |  |
| - your organisation— (i) has been guilty of serious misrepresentation in supplying the information required for the verification of the absence of grounds for exclusion or the fulfilment of the selection criteria; or (ii) has withheld such information or is not able to submit supporting documents required under regulation 59 of the Public Contracts Regulations 2015; or |  |  |
| - your organisation has undertaken to |  |  |
| (aa) unduly influence the decision-making process of the contracting authority, or |  |  |
| (bb) obtain confidential information that may confer upon your organisation undue advantages in the procurement procedure; or |  |  |
| - your organisation has negligently provided misleading information that may have a material influence on decisions concerning exclusion, selection or award. |  |  |

ANNEX 6: LIST OF A BETTER START WARDS

| Ward Name | Local Authority | All Ages* |
| --- | --- | --- |
| Coldharbour | Lambeth | 17,504 |
| Stockwell | Lambeth | 15,312 |
| Tulse Hill | Lambeth | 16,440 |
| Vassall | Lambeth | 15,665 |
| Bowling and Barkerend | Bradford | 21,877 |
| Bradford Moor | Bradford | 21,209 |
| Little Horton | Bradford | 22,187 |
| Bloomfield | Blackpool | 6,712 |
| Claremont | Blackpool | 7,312 |
| Clifton | Blackpool | 6,786 |
| Talbot | Blackpool | 6,461 |
| Victoria | Blackpool | 6,827 |
| Arboretum | Nottingham | 16,496 |
| Aspley | Nottingham | 18,377 |
| Bulwell | Nottingham | 16,104 |
| St Ann's | Nottingham | 20,944 |
| Kursaal | Southend-on-Sea | 11,585 |
| Milton | Southend-on-Sea | 11,748 |
| Shoeburyness | Southend-on-Sea | 11,896 |
| Victoria | Southend-on-Sea | 11,283 |
| Westborough | Southend-on-Sea | 11,072 |
| West Shoebury | Southend-on-Sea | 10,387 |

*ONS 2015 Ward population estimates for England and Wales, mid-2015 (experimental statistics)

ANNEX 7: LAMBETH’S PILOT SURVEY

- Below is the link to the questionnaire from Lambeth’s pilot survey.

https://www.snapsurveys.com/wh/s.asp?k=145468024578

- To gain access to the survey, you simply need to enter any 4 digit number combination.

A list of the A Better Start Wards is provided in Annex 6, together with 2015 mid-year population estimates