## Sheet1
Question | Answer
The incoming electrics will need to be moved by the electric authority who deal with the area | A quote has been recived for these works from National Grid. A plan has been put on the tender page called 'Plan to move electrics'
There is no asbestos survey | The Parish Council are getting quotes for the asbestos survey and will provide it.
Please provide a mechanical design and schedule of works for the project | Mechanical Design for space heating / water heating / ventilation to subcontractor design. To comply with current UK Building Regulations suitable for changing rooms building. If the main contractor wants a design from a Mechanical Engineer, then an engineer will need to be appointed.
Could you please confirm scope of work / spec for external works? We assume this would be to match similar to the existing paving slabs around the perimeter. | The contractor will need to make good any external works immediately around the building. Paving to the front of the building and tarmac to the sides and rear
Please confirm existing brickwork specification? | New bricks to match existing bricks - contractor to arrange brick matching
Is there a NBS specification available for the project ? | Not at the moment
Please provide a door / window schedule for pricing? | Any dimensions given will be for pricing purposes only. All dimensions to be checked on site.
Please provide a specification & scope of works for the electrical package? | An electrical layout has been produced as part of the Building Regs / Tender pack. Final design to be confirmed by the end user. If the contractor wants a specification / further details, an electrical engineer will need to be appointed
We note a ACO drain to the front elevation - please confirm any external drainage requirements? | An Aco drain was added to the external doors simply to keep water away from the entrances. It is my understanding we cannot add additional water to the grass as this is a sports pitch and need to minimise the ground becoming waterlogged. There are inspection chambers within close proximity to the building which I believe are combined foul and storm. Subject to building control approval I hope we can connect into this.