# Annex A

| Title of project: | The role and value of natural capital and development of indicators for use in disaster preparedness in the UK’s Overseas Territories of the British Virgin Islands |
| --- | --- |
| Date and time for return of tenders: | 12 July 2019 @ 13:00 hours |
| Contract Reference No: | C19-0303-1361 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO AMANDA GREGORY or DORA IANTOSCA TO THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Amanda Gregory Joint Nature Conservation Committee Email: Amanda.gregory@jncc.gov.uk Tel: 01733 866852 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | Mid-end July 2019 |
| Proposed end-date: | 20 December 2019 |

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC website.  http://jncc.defra.gov.uk/page-1729

## Background and aims

The British Virgin Islands are highly dependent upon the natural environment for their economic and social wellbeing.  They are also reliant on limited manmade assets.  In the Caribbean in particular, these manmade capital assets, and human life, are vulnerable to both natural and manmade disasters.  The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economy and reducing its ability to protect manmade assets and human well-being.

The 2016 Conflict, Stability & Security Fund (CSSF) funded programme of work, ‘Enhancing economic security through environmental resilience’ in the UK Overseas Territories (OTs) (Caribbean Territories of Anguilla, British Virgin Islands, Montserrat and Turks and Caicos Islands and the South Atlantic Territories of Falkland Islands, St Helena, Ascension and Tristan da Cunha) aimed to improve the long-term economic planning to support growth and development.  Embedding the role of the natural environment in economic and spatial planning through existing or new policies or legislation is one element, with the objective to protect and enhance the value of the OTs vital natural environment.

The suite of projects mapped and valued the natural assets by integrating satellite data, Geographical Information Systems (GIS) and economic assessments of the priority environmental goods and services (derived from natural capital).  In the Caribbean, a GIS based model was developed to assess the vulnerability to storm surge and flooding events and their impacts on infrastructure and human life.

This CSSF funded project aims to support BVI in developing plans, policies and procedures to deal with natural disasters by enhancing their ability to prepare for / recover from the impact of storm events.  Work will also contribute to the UK Government’s new hurricane preparedness plans for the British Overseas Territories in the Caribbean.

Building upon the work to date, this project will assess the role and economic value of the whole of BVI’s natural capital in protection of manmade capital – to assess the vulnerability (susceptibility) of manmade capital to natural hazards such as (but not limited to) storm surge, in the coastal zone and landslip or flash flooding in the terrestrial environment; and develop a framework of indicators, incorporated into the national GIS, to monitor change over time to support disaster resilience.

This contract is associated with mapping the value of natural capital assets across the whole island and the development of environmental and natural capital indicators for use in national reporting and disaster preparedness.  The study does not intend to cover the wide variety of BVI’s ecosystems and their associated services but focus on those associated with enhancing disaster resilience in BVI.

The natural capital assessment will also focus on supporting the current fiscal planning instruments and the proposed Environment Bill.

## Project Objectives

The work will be undertaken in parallel with JNCC’s own BVI data and disaster management project and other projects which are producing maps such as shallow marine habitat map, ecosystem service maps and terrestrial habitat map.  Consideration of risks to this project should be accounted for in the tender application.  For example, production of the value maps could be at risk due to dependencies of mapping outputs from parallel projects.  Therefore, project timings should reflect this.

The wider project aims to: maximise the ability of BVI Government (BVIG) to manage, analyse and provide long-term data security and provide training and support in the use of the International Disasters Charter for disaster response and preparedness.

The objectives of the work to be done under this contract are to build upon 2018 BVI project, the Development of environmental indicators for the British Virgin Islands project and 25 Year Environmental Plan indicators project to:

- Map the value of natural capital assets (in relation to disaster resilience and response - value for storm protection) over the whole island system;

- Develop a framework of environmental indicators and protocols for application for:

  - long-term Indicator framework to support new environmental legislation;

  - short-term disaster response indicators to monitor post-hurricane impacts on the natural and built environment; and

  - Support the integration of these frameworks with BVI Government.

- Work with JNCC staff to enhance the existing information management systems to support the integration of indicators into the Environment Bill, Disaster and Needs Assessment (DANA) and national (BVI) & international reporting mechanisms.

These objectives are detailed below.

## Project Objectives: Detailed tasks

The successful contractor will need to build in time to exchange knowledge, ideas, share data and information.  This will include recommendations, integrated data from island wide storm surge modelling and data needs in relation to indicators, ecosystems service mapping (JNCC will provide these as outputs from parallel projects) and information management support.  JNCC will cover the costs of JNCC staff outside this contract.

There are two component parts to this contract.  Tenderers can submit for one or both component parts.

Component 1: economic assessment of BVI

- Undertake an economic assessment of the functional role and value of the natural environment across the British Virgin Islands in mitigating terrestrial and coastal hazards (eg those associated with disaster resilience and protection) and map these values.

  - Produce a natural capital asset register identifying datasets available, monitoring frequency and gaps;

  - Use natural capital indicators to evaluate socio-economic costs of assets important for protection (these will be based on ecosystem service and opportunity maps created from other ongoing projects);

  - Produce value maps for the BVI island system;

  - Develop an environmental economic indicator, or metric, to support BVI reporting; and

  - Support BVIG to develop a methodology to quantify (financially) post-event loss, or gain, of the value of ecosystem services.

Component 2:  Indicator framework

- Develop the relevant environmental indicators already identified by BVI Government to:

  - Build a useable framework of short-term indicators and protocol for their use, incorporating available data, to monitor post-hurricane impacts on the natural and built environment to meet the requirements of the Disaster and Needs Assessment (DANA) and support short term disaster response;

  - Identify gaps in current indicators and monitoring to support short-term disaster response;

  - Build a useable framework of long-term priority environmental indictors and protocol for their use to support new Environmental Bill and fiscal planning & reporting.

  - Document for each of the indicators, the data sources, analytical methods, quality criteria, sources of uncertainty and scientific relevant publications

- Prepare reports in an agreed format for submission to BVI Government and JNCC.

- Present findings at a November 2019 Disaster Resilience workshop.

The work will be conducted in collaboration with the Government of the British Virgin Islands that the JNCC, reporting to a BVI Oversight Group.  The contractor will be expected to travel to the BVI as necessary to review existing data, collect new data and collaborate with BVI officials in several government departments.

## Potential follow-on work

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake additional work on this contract into the financial year 2019/20.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Tenderers are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

- Maps of the distribution of natural capital assets across BVI

- Natural capital value maps for BVI (with JNCC)

- A natural resource inventory (asset register with identified data sets)

- Integrated (into national system) framework of short-term indicators to support post-event responses, environmental monitoring and sensitivity

- Framework methodology for post hazard economic assessment of environmental financial and economic losses.

- Participation at stakeholder demonstration workshop to be held in British Virgin Islands in November 2019.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | Mid-end July 2019 |
| - Natural capital asset register and framework of indicators | Mid October 2019 |
| - Draft report and final mapping outputs complete | End November 2019 |
| - On-island workshop | w/c 18 November 2019 |
| - Final report | December 2019 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2019/20 is subject to availability of funds.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house style http://jncc.defra.gov.uk/pdf/JNCC_DesignID_v1.3.pdf stated otherwise. The draft and final guidance should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

The successful contractor must ensure this project is in compliance with the new JNCC Evidence Quality Assurance Policy. Tenderers are asked to note the Evidence Quality Assurance Policy document and Guidance Notes that accompany the Invitation to Tender.

(Note for author. If research project/contract See Evidence Quality Guidance Note #4 (Communicating Evidence Quality).  Ensure that data management and storage requirements are stipulated, taking into account relevant policy for data access; see Evidence Quality Assurance Policy document 2018/19).

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point will be:

Ms Amanda Gregory

Email: Amanda.Gregory@jncc.gov.uk   Tel: +44 (0)1733 866811

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed;

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team representative for a start-up meeting in Peterborough on or around 1 July 2019 (remote meeting via telephone or Skype acceptable)

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of current public and employer liability insurance certificates.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 12.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

## Evaluation Criteria

## JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (55% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 15 |  |
|  | Understanding of, and relevance to, the requirements in particular, the adequacy of the details of the proposed process for achieving the required outputs and clarity of proposal in respect of mechanisms to access the necessary data to undertake the work in the listed OTs in particular those identified for detailed modelling studies. | 25 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Identification of potential problems/risks to delivery | 5 |  |
|  | Proposed solutions to identified problems/risks | 5 |  |
|  | Sub Totals | 55 |  |
| 2. Details of Contractor (20 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team, including demonstrable experience of working with small islands in general and the listed UK OTs in particular. | 10 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Appropriateness of ratio of senior to junior staff time | 5 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made in two instalments each representing 50% of the total contract value including VAT on the basis of the following schedule:

- On satisfactory completion of milestone 1, expected to be in mid-October 2019;

- On satisfactory completion of milestone 2, 3 & 4, expected to be end of December 2019.

In each case payment will follow the submission of invoices and based on satisfactory undertaking of the relevant contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

Hurricane preparedness plans for the British Overseas Territories in the Caribbean, July 2019

Medium Term Fiscal Plan 2018-2020 (last accessed June 2019)

An assessment of the value of natural capital in protective service against coastal and inland flooding in the UK Overseas Territory of the British Virgin Islands (last accessed June 2019).

Technical note: Development of environmental indicators for the British Virgin Islands report available upon request from JNCC

25 Year Environmental Plan indicators for British Virgin Islands available upon request from JNCC