## Sheet1
Refer to Works Information and Site Information documents for details
Section 1: Preliminaries
Item Ref | Description | Quantity | Units | Rate (£) | Amount | Remarks / Evidence
1.1 | Contractual Documentation | 1 | sum
1.2 | PM acceptance of Programme | 1 | sum
1.3 | PM acceptance of Health and Safety, Environmental, Quality Plan | 1 | sum
1.4 | Bonds, Warranties and Insurances as required | 1 | sum
1.5 | Mobilisation & site setup | 1 | sum
1.6 | Demobilisation & site clearance | 1 | sum
1.7.1 | Maintenance of site facilities and supervision of the works during Construction - Period 1 | 1 | sum
1.7.2 | Maintenance of site facilities and supervision of the works during Construction - Period 2 | 1 | sum
1.7.3 | Maintenance of site facilities and supervision of the works during Construction - Period 3 | 1 | sum
Sub-Total
Section 2: Area 4
Item Ref | Description | Quantity | Units | Rate (£) | Amount (£) | Remarks / Evidence
2.1 | Approval of Risk Assessments and Method Statements | 1 | Sum
2.2 | Removal of existing timber quay structure | 1 | Sum
2.3 | Making good of remaining structures, including removal of redundant remnants (e.g. fixings, etc.) and repairs associated with the demolished timber quay | 1 | Sum
2.4 | Disposal of waste from site | 1 | Sum
2.5 | Access and temporary works | 1 | Sum
2.6 | Completion of Area 4 incl demob and associated documentation for QA and H&S File | 1 | Sum
Sub-Total
Section 3: Area 5
Item Ref | Description | Quantity | Units | Rate (£) | Amount (£) | Remarks / Evidence
3.1 | Approval of Risk Assessments and Method Statements, including Lifting plan | 1 | Sum
3.2 | Removal of derelict steel gate of Dock 1 (Structure 5A) | 1 | Sum
3.3 | Removal of derelict timber gate of Dock 2 (Structure 5C) | 1 | Sum
3.4 | Removal of derelict steel gate of Dock 3 (Structure 5F) | 1 | Sum
3.5 | Making good of remaining structures, including removal of redundant remnants (e.g. hinges, fixings, etc.) and repairs associated with the removed dock gates | 1 | Sum
3.6 | Disposal of waste from site | 1 | Sum
3.7 | Access and temporary works | 1 | Sum
3.8 | Completion of Area 5 incl demob and associated documentation for QA and H&S File | 1 | Sum
Sub-Total
Section 4: Area 7
Item Ref | Description | Quantity | Units | Rate (£) | Amount (£) | Remarks / Evidence
4.1 | Approval of Risk Assessments and Method Statements | 1 | Sum
4.2 | Detailed defect survey of R.C piles and infill planks | 1 | Sum
4.3 | Concrete Repairs to R.C piles (Repair Type 1) | 96 | m |  |  | 3000mm crack length per pile for 32 piles
4.4 | Concrete Repairs to R.C piles (Repair Type 2) | 32 | m2 |  |  | 100mm deep, 1m2 repair area per pile, for 32 piles
4.5 | Replacement of concrete infill plank and backfilling of voids | 4 | No. |  |  | 2200x300x300mm per plank, for 4No. planks
4.6 | Access and temporary works | 1 | Sum
4.7 | Completion of Area 7 incl demob and associated documentation for QA and H&S File | 1 | Sum
Sub-Total
Section 5: Area 8
Item Ref | Description | Quantity | Units | Rate (£) | Amount (£) | Remarks / Evidence
5.1 | Approval of Risk Assessments and Method Statements | 1 | Sum
5.2 | Final Design of the engineered rock revetment | 1 | Sum
5.3 | Procurement of Materials for engineered rock revetment | 1 | Sum |  |  | confirmation of order
5.4 | Construction of engineered rock revetment | 1 | Sum
5.5 | Completion of Area 8 incl demob and associated documentation for QA and H&S File | 1 | Sum
Sub-Total
Grand Total
Notes: | 1. Contractor to provide required evidence of completion of each Activity with their Application for Payment
2. Refer to Works Information and Site Information for Details
3. For the avoidance of doubt, the figure totalling in F57 will be used for evaluation purposes.
4. All costs must be excluding VAT