FEE/0485: Preliminaries

Refurbishment of Warren Cottage, Lynford

Table of Contents

Title	Page

A10 	PROJECT PARTICULARS 	3

A11 	TENDER AND CONTRACT DOCUMENTS 	5

A12 	THE SITE/ EXISTING BUILDINGS 	6

A13 	DESCRIPTION OF THE WORK 	7

A20 	JCT MINOR WORK BUILDING CONTRACT (MW) 	8

A30 	TENDERING/ SUBLETTING/ SUPPLY 	11

A31 	PROVISION, CONTENT AND USE OF DOCUMENTS 	14

A32 	MANAGEMENT OF THE WORKS 	18

A33 	QUALITY STANDARDS/ CONTROL 	21

A34 	SECURITY/ SAFETY/ PROTECTION 	26

A35	SPECIFIC LIMITATIONS ON METHOD/  SEQUENCE/  TIMING	31

A36 	FACILITIES/ TEMPORARY WORK/ SERVICES 	32

A37 	OPERATION/ MAINTENANCE OF THE FINISHED WORKS 	34

A53 	WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS 	35

A54 	PROVISIONAL WORK/ ITEMS 	36

A10  PROJECT PARTICULARS

110  	The Project

Name:

Refurbishment of Warren Cottage

Nature:

Refurbishment of 3-Bedroom Residential Property

Location:

Warren Cottage, Lynford, Thetford, Norfolk, IP26 5ET

Length of contract:

15 weeks

120  	Employer (Client)

Name:

Forestry Commission

Address:

East England Forest District, Santon Downham, Brandon, Suffolk, IP27 0TJ

Contact:

Mr Simon Coombe

Telephone:

0300 067 4523 / 07785 528444

E-mail:

simon.coombe@forestry.gsi.gov.uk

130  	Principal contractor (CDM)

Name:

TBC

Address:

TBC

Contact:

TBC

Telephone:

TBC

E-mail:

TBC

140  	Architect / Contract Administrator (Pre-Contract)

Name:

Hamson Barron Smith Ltd

Address:

Townshend House, 30 Crown Road, Norwich, Norfolk, NR1 3DT

Contact:

Mr Max Harrison

Telephone:

01603 227132 / 07785 503746

E-mail:

max.harrison@hamsonbarronsmith.com

150  	Principal designer (Pre-Contract)

Name:

Hamson Barron Smith Ltd

Address:

Townshend House, 30 Crown Road, Norwich, Norfolk, NR1 3DT

Contact:

Mr Max Harrison

Telephone:

01603 227132 / 07785 503746

E-mail:

max.harrison@hamsonbarronsmith.com

A11  TENDER AND CONTRACT DOCUMENTS

110  	Tender drawings

The tender drawings are:

18-3-6022 HBS-DR-B 10/11/20/21/22/23/24/25/140 & HBS-DR-M (50) -001/002 & HBS-DR-

E (60) -003/004

120  	Contract drawings

The Contract Drawings: The same as the tender drawings.

160  	Preconstruction information

Format: The Preconstruction information is described in these preliminaries in Section A34. It

refers to information given elsewhere in the preliminaries and other tender documents.

A12  THE SITE/ EXISTING BUILDINGS

110  	The site

Description:

Residential property with soft landscaped front garden and large rear garden. Water bore

hole located to end of rear garden. The site is situated within Thetford Forest

120  	Existing buildings on/ adjacent to the site

Description:

3-bedroom semi-detached residential property

200  	Access to the site

Description:

Via vehicular access road

Limitations:

None

210  	Parking

Restrictions on parking of the Contractor's and employees' vehicles:

All contractor parking to be off the vehicular access road to minimise disruption to highway

220  	Use of the site

General: Do not use the site for any purpose other than carrying out the Works.

Limitations:

None

230  	Surrounding land/ building uses

General: Adjacent or nearby uses or activities are as follows:

Adjacent residential properties

240  	Health and safety hazards

General: The nature and condition of the site/ building cannot be fully and certainly

ascertained before it is opened up. However the following hazards are or may be present:

None

Information: The accuracy and sufficiency of this information is not guaranteed by the

Employer or the Employer's representative. Ascertain if any additional information is required

to ensure the safety of all persons and the Works.

Site staff: Draw to the attention of all personnel working on the site the nature of any possible

contamination and the need to take appropriate precautionary measures.

250  	Site visit

Assessment: Ascertain the nature of the site, access thereto and all local conditions and

restrictions likely to affect the execution of the Works.

Arrangements for visit:

Mr Simon Coombe - 0300 067 4523 / 07785 528444

A13  DESCRIPTION OF THE WORK

110  	Preparatory work by others

Works: Carried out under a separate contract and completed before the start of work on site

for this Contract.

Description:

Clearance of garden and vegetation growth to garden areas, except those areas detailed

within the tender package

120  	The works

Description:

Refurbishment of 3-bedroom residential property

130  	Work by others concurrent with the contract

Description:

Utilities providers - TBC

140  	Completion work by others

Description:

None

A20  JCT MINOR WORK BUILDING CONTRACT (MW)

JCT MINOR WORKS BUILDING CONTRACT

The Contract: JCT Minor Works Building Contract 2016 Edition.

Requirement: Allow for the obligations, liabilities and services described.

THE RECITALS

First  The Works and the Contract Administrator

The work comprises:

Refurbishment of 3-bedroom residential property

Architect/ Contract Administrator: See clause A10/140.

Second  Contract documents

Contract drawings: As listed in clause A11/120.

Contract documents: The following have been prepared which show and describe the work

to be done

A specification

Third  Priced documents

Documents to be priced or provided by the Contractor:

Contract specification

THE ARTICLES

3  Architect / Contract Administrator

Architect / Contract Administrator: See clause A10/140.

4 and 5  Principal Designer/ Principal Contractor

Principal Designer: See clause A10/150.

Principal Contractor: See clause A10/130.

CONTRACT PARTICULARS

Fourth Recital and Schedule 2  Base date

Base date:

Friday 22nd December 2017.

Fourth Recital and clause 4.2  Construction industry scheme (CIS)

Employer at the Base Date

is not a 'contractor' for the purposes of the CIS.

Fifth Recital  CDM Regulations

The project

is not notifiable.

Seventh Recital and Schedule 3  Supplemental provisions

Collaborative working: Paragraph 1

applies

Health and safety: Paragraph 2

applies

Cost savings and value improvements: Paragraph 3

applies

Sustainable development and environmental considerations: Paragraph 4

applies

Performance indicators and monitoring: Paragraph 5

does not apply

Notification and negotiation of disputes: Paragraph 6

applies. Where paragraph 6 applies, the respective nominees of the parties are:

- Employer's nominee:

Mr Simon Coombe

- Contractor's nominee:

TBC

Or such replacement as each party may notify to the other from time to time.

Article 7  Arbitration

Article 7 and Schedule 1

apply

Clause 2.2  Commencement and Completion

Date for Commencement of the Works:

Monday 22nd January 2018

Date for Completion:

Monday 5th May 2018

Clause 2.8  Liquidated damages

At the rate of

£900.00per

calendar month or pro-rata thereto

Clause 2.10  Rectification period

Period:

Twelve monthsfrom the date of practical completion.

Clause 4.3  Percentage of the total value of the work etc.

Percentage:

95 per cent

Clause 4.4  Percentage of the total amount to be paid to the Contractor

Percentage:

97½ per cent

Clause 4.8.1  Supply of documentation for computation of amount to be finally

certified

Period:

Three monthsfrom the date of practical completion.

Clause 4.11 and Schedule 2  Contribution, levy and tax changes

Clause 4.11 and Schedule 2 will be deleted.

Clause 5.3.2  Contractor's insurance - injury to persons or property

Insurance cover (for any one occurrence or series of occurrences arising out of one event):

Not less than £10,000,000

Clauses 5.4A, 5.4B and 5.4C  Insurance of the works etc - alternative provisions

Clause

5.4B (Works and existing structures insurance by Employer in Joint Names)applies.

Clauses 5.4A.1 and 5.4B.1.2  Percentage to cover professional fees

Addition:

15per cent.

Clause 7.2  Adjudication

The Adjudicator is:

To be appointed by the nominating body

Nominating body:

Royal Institution of Chartered Surveyors

Schedule 1 paragraph 2.1  Arbitration

Appointor of Arbitrator (and of any replacement): President or a Vice president of the:

The Royal Institution of Chartered Surveyors

THE CONDITIONS

Section 1: Definitions and Interpretation

Section 2: Carrying out the Works

Section 3: Control of the Works

Section 4: Payment

Section 5: Injury, Damage and Insurance

Section 6: Termination

Section 7: Settlement of Disputes

EXECUTION

The Contract: Will be executed

as a deed

A30  TENDERING/ SUBLETTING/ SUPPLY

MAIN CONTRACT TENDERING

110  	Scope

General: These conditions are supplementary to those stated in the Invitation to Tender and

on the form of tender.

145  	Tendering procedure

General: The method of evaluation will be found within the ITT documents.

Errors:

Alternative 2 is to apply.

160  	Exclusions

Inability to tender: Immediately inform if any parts of the work as defined in the tender

documents cannot be tendered.

Relevant parts of the work: Define those parts, stating reasons for the inability to tender.

170  	Acceptance of tender

Acceptance: No guarantee is offered that any tender will be recommended for acceptance or

be accepted, or that reasons for non-acceptance will be given.

Costs: No liability is accepted for any cost incurred in the preparation of any tender.

190  	Period of validity

Period: After submission or lodgement, keep tender open for consideration (unless

previously withdrawn) for not less than

60 days

Date for possession/ commencement: See section A20.

PRICING/ SUBMISSION OF DOCUMENTS

210  	Preliminaries in the specification

The Preliminaries/ General conditions sections (A10-A56 inclusive) must not be relied on as

complying with SMM7/ NRM2.

250  	Priced schedules of work

Alterations: Do not alter or qualify the priced schedules of work without written consent.

Tenders containing unauthorised alterations or qualifications may be rejected.

Measurements: Where not stated, ascertain from the drawings.

Deemed included: Costs relating to items, which are not priced, will be deemed to have been

included elsewhere in the tender.

Submit:

within one week of request

310  	Tender

General: Tenders must include for all work shown or described in the tender documents as a

whole or clearly apparent as being necessary for the complete and proper execution of the

Works.

510  	Alternative method tenders

General: In addition to and at the same time as tendering for the Works as defined in the

tender documents, alternative methods of construction/ installation may be submitted for

consideration. Alternatives, which would involve significant changes to other work, may not

be considered.

Alternative tenders: Such alternatives will be deemed to be alternative tenders and each

must include a complete and precise statement of the effects on cost and programme.

Safety method statement: Carry out a health and safety risk assessment for each alternative

and where appropriate provide a safety method statement suitable for incorporation in the

Health and Safety Plan.

Full technical data: Submit for each alternative together with details of any consequential

amendments to the design and/ or construction of other parts of the Works.

Submit:

With tender

515  	Alternative time tenders

General: In addition to and at the same time as tendering based upon the date or period

specified in section A20, an alternative tender based upon a different date for completion or

period may be submitted.

Date for completion: If any such tender is accepted the date for completion inserted in the

Contract will be the date stated in the alternative tender or determined from the period stated

in the alternative tender.

530  	Substitute products

Details: If products of different manufacture to those specified are proposed, submit details

with the tender giving reasons for each proposed substitution. Substitutions, which have not

been notified at tender stage, may not be considered.

Compliance: Substitutions accepted will be subject to the verification requirements of clause

A31/200.

550  	Health and safety information

Content: Describe the organisation and resources to safeguard the health and safety of

operatives, including those of subcontractors, and of any person whom the Works may

affect.

Include:

- A copy of the contractor's health and safety policy document, including risk assessment

procedures.

- Accident and sickness records for the past five years.

- Records of previous Health and Safety Executive enforcement action.

- Records of training and training policy.

- The number and type of staff responsible for health and safety on this project with details of

their qualifications and duties.

Submit:

With the Tender

570  	Outline construction phase health and safety plan

Content: Submit the following information within one week of request:

- Method statements on how risks from hazards identified in the pre-construction information

and other hazards identified by the contractor will be addressed.

- Details of the management structure and responsibilities.

- Arrangements for issuing health and safety directions.

- Procedures for informing other contractors and employees of health and safety hazards.

- Selection procedures for ensuring competency of other contractors, the self-employed and

designers.

- Procedures for communications between the project team, other contractors and site

operatives.

- Arrangements for cooperation and coordination between contractors.

- Procedures for carrying out risk assessment and for managing and controlling the risk.

- Emergency procedures including those for fire prevention and escape.

- Arrangements for ensuring that all accidents, illness and dangerous occurrences are

recorded.

- Arrangements for welfare facilities.

- Procedures for ensuring that all persons on site have received relevant health and safety

information and training.

- Arrangements for consulting with and taking the views of people on site.

- Arrangements for preparing site rules and drawing them to the attention of those affected

and ensuring their compliance.

- Monitoring procedures to ensure compliance with site rules, selection and management

procedures, health and safety standards and statutory requirements.

- Review procedures to obtain feedback.

A31  PROVISION, CONTENT AND USE OF DOCUMENTS

DEFINITIONS AND INTERPRETATIONS

110  	Definitions

Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions

and specification are as stated therein or in the appropriate British Standard or British

Standard glossary.

120  	Communication

Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or

obtain information, consent or instructions, or make arrangements.

Format: In writing to the person named in clause A10/140 unless specified otherwise.

Response: Do not proceed until response has been received.

130  	Products

Definition: Materials, both manufactured and naturally occurring, and goods, including

components, equipment and accessories, intended for the permanent incorporation in the

Works.

Includes: Goods, plant, materials, site materials and things for incorporation into the Works.

135  	Site equipment

Definition: All appliances or things of whatsoever nature required in or about the construction

for completion of the Works but not materials or other things intended to form or forming part

of the Permanent Works.

Includes: Construction appliances, vehicles, consumables, tools, temporary works,

scaffolding, cabins and other site facilities.

140  	Drawings

Definitions: To BSRIA BG 6 A design framework for building services. Design activities and

drawing definitions.

CAD data: In accordance with BS 1192.

145  	Contractor's choice

Meaning: Selection delegated to the Contractor, but liability to remain with the specifier.

155  	Submit proposals

Meaning: Submit information in response to specified requirements.

160  	Terms used in specification

Remove: Disconnect, dismantle as necessary and take out the designated products or work

and associated accessories, fixings, supports, linings and bedding materials. Dispose of

unwanted materials. Excludes taking out and disposing of associated pipework, wiring,

ductwork or other services.

Fix: Receive, unload, handle, store, protect, place and fasten in position and disposal of

waste and surplus packaging including all labour, materials and site equipment for that

purpose.

Supply and fix: As above, but including supply of products to be fixed. All products to be

supplied and fixed unless stated otherwise.

Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing

materials. Stack neatly, adequately protect and store until required by the Employer/

Purchaser or for use in the Works as instructed.

Make good: Execute local remedial work to designated work. Make secure, sound and neat.

Excludes redecoration and/ or replacement.

Replace: Supply and fix new products matching those removed. Execute work to match

original new state of that removed.

Repair: Execute remedial work to designated products. Make secure, sound and neat.

Excludes redecoration and/ or replacement.

Refix: Fix removed products.

Ease: Adjust moving parts of designated products or work to achieve free movement and

good fit in open and closed positions.

Match existing: Provide products and work of the same appearance and features as the

original, excluding ageing and weathering. Make joints between existing and new work as

inconspicuous as possible.

System: Equipment, accessories, controls, supports and ancillary items, including

installation, necessary for that section of the work to function.

170  	Manufacturer and product reference

Definition: When used in this combination:

- Manufacturer: The firm under whose name the particular product is marketed.

- Product reference: The proprietary brand name and/ or reference by which the particular

product is identified.

Currency: References are to the particular product as specified in the manufacturer's

technical literature current on the date of the invitation to tender.

200  	Substitution of products

Products: If an alternative product to that specified is proposed, obtain approval before

ordering the product.

Reasons: Submit reasons for the proposed substitution.

Documentation: Submit relevant information, including:

- manufacturer and product reference;

- cost;

- availability;

- relevant standards;

- performance;

- function;

- compatibility of accessories;

- proposed revisions to drawings and specification;

- compatibility with adjacent work;

- appearance;

- copy of warranty/ guarantee.

Alterations to adjacent work: If needed, advise scope, nature and cost.

Manufacturers' guarantees: If substitution is accepted, submit before ordering products.

210  	Cross references

Accuracy: Check remainder of the annotation or item description against the terminology

used in the section or clause referred to.

Related terminology: Where a numerical cross-reference is not given the relevant sections

and clauses of the specification will apply.

Relevant clauses: Clauses in the referred to specification section dealing with general

matters, ancillary products and execution also apply.

Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.

220  	Referenced documents

Conflicts: Specification prevails over referenced documents.

230  	Equivalent products

Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or

equivalent' is to be deemed included.

240  	Substitution of standards

Specification to British Standard or European Standard: Substitution may be proposed

complying with a grade or category within a national standard of another Member State of

the European Community or an international standard recognised in the UK.

Before ordering: Submit notification of all such substitutions.

Documentary evidence: Submit for verification when requested as detailed in clause

A31/200. Any submitted foreign language documents must be accompanied by certified

translations into English.

250  	Currency of documents and information

Currency: References to published documents are to the editions, including amendments

and revisions, current on the date of the Invitation to Tender.

260  	Sizes

General dimensions: Products are specified by their co-ordinating sizes.

Timber: Cross section dimensions shown on drawings are:

- Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.

- Finished sizes for non-structural softwood or hardwood sawn and further processed

sections.

DOCUMENTS PROVIDED ON BEHALF OF THE EMPLOYER

410  	Additional copies of drawings/ documents

Additional copies: Issued free of charge.

440  	Dimensions

Scaled dimensions: Do not rely on.

450  	Measured quantities

Ordering products and constructing the Works: The accuracy and sufficiency of the

measured quantities is not guaranteed.

Precedence: The specification and drawings shall override the measured quantities.

460  	The specification

Coordination: All sections must be read in conjunction with Main Contract Preliminaries/

General conditions.

DOCUMENTS PROVIDED BY CONTRACTOR/ SUBCONTRACTORS/ SUPPLIERS

630  	Technical literature

Information: Keep on site for reference by all supervisory personnel:

- Manufacturers' current literature relating to all products to be used in the Works.

- Relevant British, EN or ISO Standards.

640  	Maintenance instructions and guarantees

Components and equipment: Obtain or retain copies, register with manufacturer and hand

over on or before completion of the Works.

Information location: In Building Manual.

Emergency call out services: Provide telephone numbers for use after completion. Extent of

cover:

office hours only

650  	Energy rating calculation

Calculation documentation:

- Number of copies:

One

- Deliver to: Energy Performance Certificate Assessor and also lodge in the Building Manual.

A32  MANAGEMENT OF THE WORKS

GENERALLY

110  	Supervision

General: Accept responsibility for coordination, supervision and administration of the Works,

including subcontracts.

Coordination: Arrange and monitor a programme with each subcontractor, supplier, local

authority and statutory undertaker, and obtain and supply information as necessary for

coordination of the work.

120  	Insurance

Documentary evidence: Before starting work on site submit details, and/ or policies and

receipts for the insurances required by the Conditions of Contract.

130  	Insurance claims

Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss

or damage to the Works or injury or damage to persons or property arising out of the Works,

immediately give notice to the Employer, the person named in clause A10/140 and the

Insurers.

Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to

give such notice.

140  	Climatic conditions

Information: Record accurately and retain:

- Daily maximum and minimum air temperatures (including overnight).

- Delays due to adverse weather, including description of the weather, types of work affected

and number of hours lost.

150  	Ownership

Alteration/ clearance work: Materials arising become the property of the Contractor except

where otherwise stated. Remove from site as work proceeds.

PROGRAMME/ PROGRESS

210  	Programme

Master programme: Immediately when requested and before starting work on site submit in

an approved form a master programme for the Works, which must include details of:

- Planning and mobilisation by the Contractor

- Subcontractor's work.

- Running in, adjustment, commissioning and testing of all engineering services and

installations.

- Work resulting from instructions issued in regard to the expenditure of provisional sums.

- Work by others concurrent with the Contract.

Submit

one copy

245  	Start of work on site

Notice: Before the proposed date for start of work on site give minimum notice of

two weeks

250  	Monitoring

Progress: Record on a copy of the programme kept on site.

Avoiding delays: If any circumstances arise which may affect the progress of the Works

submit proposals or take other action as appropriate to minimize any delay and to recover

any lost time.

Key Performance Indicators:

- Details:

None

- Record progress against each of the KPIs. If performance against KPI falls short of target,

submit proposals for remediation.

260  	Site meetings

General: Site meetings will be held to review progress and other matters arising from

administration of the Contract.

Frequency:

Every week

Location:

Warren Cottage

Accommodation: Ensure availability at the time of such meetings.

Attendees: Attend meetings and inform subcontractors and suppliers when their presence is

required.

Chairperson (who will also take and distribute minutes):

Contract Administrator

290  	Notice of completion

Requirement: Give notice of the anticipated dates of completion of the whole or parts of the

Works.

Associated works: Ensure necessary access, services and facilities are complete.

Period of notice (minimum):

Two weeks

310  	Extensions of time

Notice: When a notice of the cause of any delay or likely delay in the progress of the works is

given under the contract, written notice must also be given of all other causes which apply

concurrently.

Details: As soon as possible submit:

- Relevant particulars of the expected effects, if appropriate, related to the concurrent

causes.

- An estimate of the extent, if any, of the expected delay in the completion of the Works

beyond the date for completion.

- All other relevant information required.

420  	Removal/ replacement of existing work

Extent and location: Agree before commencement.

Execution: Carry out in ways that minimize the extent of work.

430  	Proposed instructions

Estimates: If a proposed instruction requests an estimate of cost, submit without delay and in

any case within seven days.

440  	Measurement

Covered work: Give notice before covering work required to be measured.

450  	Daywork vouchers

Before commencing work: Give reasonable notice to person countersigning daywork

vouchers.

Content: Before delivery each voucher must be:

- Referenced to the instruction under which the work is authorised.

- Signed by the Contractor's person in charge as evidence that the operatives' names, the

time daily spent by each and the equipment and products employed are correct.

Submit: By the end of the week in which the work has been executed.

470  	Products not incorporated into the Works

Ownership: At the time of each valuation, supply details of those products not incorporated

into the Works which are subject to any reservation of title inconsistent with passing of

property as required by the Conditions of Contract, together with their respective values.

Evidence: When requested, provide evidence of freedom of reservation of title.

A33  QUALITY STANDARDS/ CONTROL

STANDARDS OF PRODUCTS AND EXECUTIONS

110  	Incomplete documentation

General: Where and to the extent that products or work are not fully documented, they are to

be:

- Of a kind and standard appropriate to the nature and character of that part of the Works

where they will be used.

- Suitable for the purposes stated or reasonably to be inferred from the project documents.

Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the

Contract nor release the Contractor from any obligations or liabilities under the Contract.

120  	Workmanship skills

Operatives: Appropriately skilled and experienced for the type and quality of work.

Registration: With Construction Skills Certification Scheme.

Evidence: Operatives must produce evidence of skills/ qualifications when requested.

130  	Quality of products

Generally: New. (Proposals for recycled products may be considered).

Supply of each product: From the same source or manufacturer.

Whole quantity of each product required to complete the Works: Consistent kind, size, quality

and overall appearance.

Tolerances: Where critical, measure a sufficient quantity to determine compliance.

Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate

sequence.

135  	Quality of execution

Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in

alignment.

Colour batching: Do not use different colour batches where they can be seen together.

Dimensions: Check on-site dimensions.

Finished work: Without defects, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.

Location and fixing of products: Adjust joints open to view so they are even and regular.

140  	Compliance

Compliance with proprietary specifications: Retain on site evidence that the proprietary

product specified has been supplied.

Compliance with performance specifications: Submit evidence of compliance, including test

reports indicating:

- Properties tested.

- Pass/ fail criteria.

- Test methods and procedures.

- Test results.

- Identity of testing agency.

- Test dates and times.

- Identities of witnesses.

- Analysis of results.

150  	Inspections

Products and executions: Inspection or any other action must not be taken as approval

unless confirmed in writing referring to:

- Date of inspection.

- Part of the work inspected.

- Respects or characteristics which are approved.

- Extent and purpose of the approval.

- Any associated conditions.

160  	Related work

Details: Provide all trades with necessary details of related types of work. Before starting

each new type or section of work ensure previous related work is:

- Appropriately complete.

- In accordance with the project documents.

- To a suitable standard.

- In a suitable condition to receive the new work.

Preparatory work: Ensure all necessary preparatory work has been carried out.

170  	Manufacturer's recommendations/ instructions

General: Comply with manufacturer's printed recommendations and instructions current on

the date of the Invitation to tender.

Changes to recommendations or instructions: Submit details.

Ancillary products and accessories: Use those supplied or recommended by main product

manufacturer.

Agrément certified products: Comply with limitations, recommendations and requirements of

relevant valid certificates.

180  	Water for the works

Private water supply: Assume clean and uncontaminated.

Other: Do not use until:

- Evidence of suitability is provided.

- Tested to BS EN 1008 if instructed.

SAMPLES/ APPROVALS

210  	Samples

Products or executions: Comply with all other specification requirements and in respect of

the stated or implied characteristics either:

- To an express approval.

- To match a sample expressly approved as a standard for the purpose.

220  	Approval of products

Submissions, samples, inspections and tests: Undertake or arrange to suit the Works

programme.

Approval: Relates to a sample of the product and not to the product as used in the Works. Do

not confirm orders or use the product until approval of the sample has been obtained.

Complying sample: Retain in good, clean condition on site. Remove when no longer

required.

230  	Approval of execution

Submissions, samples, inspections and tests: Undertake or arrange to suit the Works

programme.

Approval: Relates to the stated characteristics of the sample. (If approval of the finished work

as a whole is required this is specified separately). Do not conceal, or proceed with affected

work until compliance with requirements is confirmed.

Complying sample: Retain in good, clean condition on site. Remove when no longer

required.

ACCURACY/ SETTING OUT GENERALLY

320  	Setting out

General: Submit details of methods and equipment to be used in setting out the Works.

Levels and dimensions: Check and record the results on a copy of drawings. Notify

discrepancies and obtain instructions before proceeding.

Inform: When complete and before commencing construction.

330  	Appearance and fit

Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early

as possible either:

- Submit proposals; or

- Arrange for inspection of appearance of relevant aspects of partially finished work.

General tolerances (maximum): To BS 5606, tables 1 and 2.

340  	Critical dimensions

Critical dimensions: Set out and construct the Works to ensure compliance with the

tolerances stated.

Location: Detailed on drawings

None

350  	Levels of structural floors

Maximum tolerances for designed levels to be:

- Floors to be self-finished, and floors to receive sheet or tile finishes directly bedded in

adhesive: +/- 10 mm.

- Floors to receive dry board/ panel construction with little or no tolerance on thickness: +/-

10 mm.

- Floors to receive mastic asphalt flooring/ underlays directly: +/- 10 mm.

- Floors to receive mastic asphalt flooring/ underlays laid on mastic asphalt levelling coat(s):

+/- 15 mm.

- Floors to receive fully bonded screeds/ toppings/ beds: +/- 15 mm.

- Floors to receive unbonded or floating screeds/ beds: +/- 20 mm.

360  	Record drawings

Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and

profiles. Retain on site throughout the contract and hand over on completion.

SERVICES GENERALLY

410  	Services regulations

New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory

Authority.

435  	Electrical installation certificate

Submit: When relevant electrical work is completed.

Original certificate: To be lodged in the Building Manual and provided to the Contract

Administrator.

440  	Gas, oil and solid fuel appliance installation certificate

Before the completion date stated in the Contract: Submit a certificate stating:

- The address of the premises.

- A brief description of the new installation and/ or work carried out to an existing installation.

- Any special recommendations or instructions for the safe use and operation of appliances

and flues.

- The Contractor's name and address.

- A statement that the installation complies with the appropriate safety, installation and use

regulations.

- The name, qualification and signature of the competent person responsible for checking

compliance.

- The date on which the installation was checked.

Certificate location:

Building Manual and provided to the Contract Administrator

445  	Service runs

General: Provide adequate space and support for services, including unobstructed routes

and fixings.

Ducts, chases and holes: Form during construction rather than cut.

Coordination with other works: Submit details of locations, types/ methods of fixing of

services to fabric and identification of runs and fittings.

450  	Mechanical and electrical services

Final tests and commissioning: Carry out so that services are in full working order at

completion of the Works.

Building Regulations: Note that the Forestry Commission are not required to comply with the

Building Regulations under Crown Exemption although the Forestry Commission do wish to

comply within the 'spirit' of the regulations.

SUPERVISION/ INSPECTION/ DEFECTIVE WORK

525  	Access

Extent: Provide at all reasonable times access to the Works and to other places of the

Contractor or subcontractors where work is being prepared for the Contract.

Designate:

Contract Administrator

530  	Overtime working

Notice: Prior to overtime being worked, submit details of times, types and locations of work to

be done.

- Minimum period of notice:

Two days

Concealed work: If executed during overtime for which notice has not been given, it may be

required to be opened up for inspection and reinstated at the Contractor's expense.

540  	Defects in existing work

Undocumented defects: When discovered, immediately give notice. Do not proceed with

affected related work until response has been received.

Documented remedial work: Do not execute work which may:

- Hinder access to defective products or work; or

- Be rendered abortive by remedial work.

560  	Tests and inspections

Timing: Agree and record dates and times of tests and inspections to enable all affected

parties to be represented.

Confirmation: One working day prior to each such test or inspection. If sample or test is not

ready, agree a new date and time.

Records: Submit a copy of test certificates and retain copies on site.

580  	Continuity of thermal insulation

Record and report: Confirm that work to new, renovated or upgraded thermal elements has

been carried out to conform to specification. Include:

- The address of the premises.

- The Contractor's name and address.

- The name, qualification and signature of the competent person responsible for checking

compliance.

- The date on which the installation was checked.

Submit: Before completion of the Works.

Copy: To be lodged in the Building Manual.

595  	Energy performance certificate

Assessment: Undertaken by a member of an approved accreditation scheme. Submit details

of scheme name and evidence of qualifications when requested.

- Building Type:

Dwelling

- Method:

Standard Assessment Procedure for dwellings (SAP)

Format:

- Certificate: To be incorporated in the Building Manual.

- Report:

To be provided to the Employer upon completion

Submit:

Before the date for completion stated in the contract

610  	Defective products/ executions

Proposals: Immediately any work or product is known, or appears, to be not in accordance

with the Contract, submit proposals for opening up, inspection, testing, making good,

adjustment of the Contract Sum, or removal and re-execution.

Acceptability: Such proposals may be unacceptable and contrary instructions may be issued.

WORK AT OR AFTER COMPLETION

710  	Work before completion

General: Make good all damage consequent upon the Works.

Temporary markings, coverings and protective wrappings: Remove unless otherwise

instructed.

Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and

voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.

Cleaning materials and methods: As recommended by manufacturers of products being

cleaned, and must not damage or disfigure other materials or construction.

COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are

used only as recommended by their manufacturers.

Minor faults: Touch up in newly painted work, carefully matching colour and brushing out

edges. Repaint badly marked areas back to suitable breaks or junctions.

Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and

efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and

controls.

720  	Security at completion

General: Leave the Works secure with, where appropriate, all accesses closed and locked.

Keys: Account for and adequately label all keys and hand over to Employer with itemized

schedule, retaining duplicate schedule signed by Employer as a receipt.

730  	Making good defects

Remedial work: Arrange access with

Contract Administrator

Rectification: Give reasonable notice for access to the various parts of the Works.

Completion: Notify when remedial works have been completed.

A34  SECURITY/ SAFETY/ PROTECTION

140  	Construction phase health and safety plan

Submission: Present to the Employer/ Client no later than

Two weeks prior to commence

Confirmation: Do not start construction work until the Employer has confirmed in writing that

the Construction Phase Health and Safety Plan includes the procedures and arrangements

required by the CDM Regulations.

Content: Develop the plan from and draw on the Outline Construction Phase Health and

Safety Plan, clause A30/570, and the Pre-tender Health and Safety Plan/ Preconstruction

information.

150  	Security

Protection: Safeguard the site, the Works, products, materials, and any existing buildings

affected by the Works from damage and theft.

Access: Take all reasonable precautions to prevent unauthorized access to the site, the

Works and adjoining property.

Special requirements:

Building to be kept secure at all times during the works

160  	Stability

Responsibility: Maintain the stability and structural integrity of the Works and adjacent

structures during the Contract.

Design loads: Obtain details, support as necessary and prevent overloading.

200  	Mobile telephones and portable electronic equipment

Restrictions on use:

None although no disturbance must be caused to the adjacent residential properties

210  	Employer's representatives site visits

Safety: Submit details in advance, to the Employer or the person identified in clause

A10/140, of safety provisions and procedures (including those relating to materials, which

may be deleterious), which will require their compliance when visiting the site.

Protective clothing and/ or equipment: Provide and maintain on site for the Employer and the

person stated in clause A10/140 and other visitors to the site.

330  	Noise and vibration

Standard: Comply with the recommendations of BS 5228-1, in particular clause 7.3, to

minimize noise levels during the execution of the Works.

Noise levels from the Works: Maximum level:

60 dB(A) when measured from

Adjacent residential property

Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type

recommended by manufacturers of the compressors, tools or vehicles.

Restrictions: Do not use:

- Percussion tools and other noisy appliances without consent during the hours of

5pm-9am Monday to Friday and weekends

- Radios or other audio equipment or permit employees to use in ways or at times that may

cause nuisance.

340  	Pollution

Prevention: Protect the site, the Works and the general environment including the

atmosphere, land, streams and waterways against pollution.

Contamination: If pollution occurs inform immediately, including to the appropriate Authorities

and provide relevant information.

350  	Pesticides

Use: Not permitted.

360  	Nuisance

Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.

Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas

and roads.

370  	Asbestos containing materials

Duty: Report immediately any suspected materials discovered during execution of the Works.

- Do not disturb.

- Agree methods for safe removal or encapsulation.

371  	Dangerous or hazardous substances

Duty: Report immediately suspected materials discovered during execution of the Works.

- Do not disturb.

- Agree methods for safe removal or remediation.

380  	Fire prevention

Duty: Prevent personal injury or death, and damage to the Works or other property from fire.

Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites',

published by Construction Industry Publications and The Fire Protection Association (The

'Joint Fire Code').

390  	Smoking on site

Smoking on site: Not permitted.

400  	Burning on site

Burning on site: Not permitted.

410  	Moisture

Wetness or dampness: Prevent, where this may cause damage to the Works.

Drying out: Control humidity and the application of heat to prevent:

- Blistering and failure of adhesion.

- Damage due to trapped moisture.

- Excessive movement.

420  	Infected timber/ Contaminated materials

Removal: Where instructed to remove material affected by fungal/ insect attack from the

building, minimize the risk of infecting other parts of the building.

Testing: carry out and keep records of appropriate tests to demonstrate that hazards

presented by concentrations of airborne particles, toxins and other micro organisms are

within acceptable levels.

430  	Waste

Includes: Rubbish, debris, spoil, surplus material, containers and packaging.

General: Minimize production. Prevent accumulations. Keep the site and Works clean and

tidy.

Handling: Collect and store in suitable containers. Remove frequently and dispose off site in

a safe and competent manner:

- Non-hazardous material: In a manner approved by the Waste Regulation Authority.

- Hazardous material: As directed by the Waste Regulation Authority and in accordance with

relevant regulations.

Recyclable material: Sort and dispose at a Materials Recycling Facility approved by the

Waste Regulation Authority.

Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in.

Waste transfer documentation: Provide a copy to the Contract Administrator.

440  	Electromagnetic interference

Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.

460  	Power actuated fixing systems

Use: Not permitted.

470  	Invasive species

General: Prevent the spread of species (e.g. plants or animals) that may adversely affect the

site or Works economically, environmentally or ecologically.

Special precautions:

None

Duty: Report immediately any suspected invasive species discovered during execution of the

Works.

- Do not disturb.

- Agree methods for safe eradication or removal.

510  	Existing services

Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of

proposed works not less than one week before commencing site operations.

Identification: Before starting work, check and mark positions of utilities/ services. Where

positions are not shown on drawings obtain relevant details from service authorities,

statutory undertakers or other owners.

Work adjacent to services:

- Comply with service authority's/ statutory undertaker's recommendations.

- Adequately protect, and prevent damage to services: Do not interfere with their operation

without consent of service authorities/ statutory undertakers or other owners.

Identifying services:

- Below ground: Use signboards, giving type and depth;

- Overhead: Use headroom markers.

Damage to services: If any results from execution of the Works:

- Immediately give notice and notify appropriate service authority/ statutory undertaker.

- Make arrangements for the work to be made good without delay to the satisfaction of

service authority/ statutory undertaker or other owner as appropriate.

- Any measures taken to deal with an emergency will not affect the extent of the Contractor's

liability.

Marker tapes or protective covers: Replace, if disturbed during site operations, to service

authority's/ statutory undertakers recommendations.

520  	Roads and footpaths

Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and

debris.

Damage caused by site traffic or otherwise consequent upon the Works: Make good to the

satisfaction of the Employer, Local Authority or other owner.

530  	Existing topsoil/ subsoil

Duty: Prevent over compaction of existing topsoil and subsoil in those areas which may be

damaged by construction traffic, parking of vehicles, temporary site accommodation or

storage of materials and which will require reinstatement prior to completion of the Works.

Protection: Before starting work submit proposals for protective measures.

540  	Retained trees/ shrubs/ grassed areas

Protection: Preserve and prevent damage, except those not required.

Replacement: Mature trees and shrubs if uprooted, destroyed, or damaged beyond

reasonable chance of survival in their original shape, as a consequence of the Contractor's

negligence, must be replaced with those of a similar type and age at the Contractor's

expense.

550  	Retained trees

Protected area: Unless agreed otherwise do not:

- Dump spoil or rubbish, excavate or disturb topsoil, park vehicles or plant, store materials or

place temporary accommodation within an area which is the larger of the branch spread of

the tree or an area with a radius of half the tree's height, measured from the trunk.

- Sever roots exceeding 25 mm in diameter. If unintentionally severed give notice and seek

advice.

- Change level of ground within an area 3 m beyond branch spread.

555  	Wildlife species and habitats

General: Safeguard the following:

Contractor to be vigilant for the potential presence of bats

Protected habitats and species: Upon discovery immediately advise. Do not proceed until

instruction is received.

Education: Ensure employees and visitors to the site receive suitable instruction and

awareness training.

560  	Existing features

Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas

and other site features, which are to remain in position during execution of the Works.

Special requirements:

Protect damage to adjacent residential properties

570  	Existing work

Protection: Prevent damage to existing work, structures or other property during the course

of the work.

Removal: Minimum amount necessary.

Replacement work: To match existing.

580  	Building interiors

Protection: Prevent damage from exposure to the environment, including weather, flora,

fauna, and other causes of material degradation during the course of the work.

620  	Adjoining property

Permission: Obtain as necessary from owners if requiring to erect scaffolding on or otherwise

use adjoining property.

625  	Adjoining property restrictions

Precautions:

- Prevent trespass of workpeople and take precautions to prevent damage to adjoining

property.

- Pay all charges.

- Remove and make good on completion or when directed.

Damage: Bear cost of repairing damage arising from execution of the Works.

630  	Existing structures

Duty: Check proposed methods of work for effects on adjacent structures inside and outside

the site boundary.

Supports: During execution of the Works:

- Provide and maintain all incidental shoring, strutting, needling and other supports as may

be necessary to preserve stability of existing structures on the site or adjoining, that may be

endangered or affected by the Works.

- Do not remove until new work is strong enough to support existing structure.

- Prevent overstressing of completed work when removing supports.

Adjacent structures: Monitor and immediately report excessive movement.

Standard: Comply with BS 5975 and BS EN 12812.

640  	Materials for recycling/ reuse

Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing

materials and other contaminants.

Storage: Stack neatly and protect until required by the Employer or for use in the Works as

instructed.

A35 SPECIFIC LIMITATIONS ON METHOD/  SEQUENCE/  TIMING

130 	Method/ sequence of work

Specific Limitations: Include the following in the programme:

________

160 	Use or disposal of materials

Specific limitations:

________

170 	Working hours

Specific limitations:

________

A36  FACILITIES/ TEMPORARY WORK/ SERVICES

GENERALLY

110  	Spoil heaps, temporary works and services

Location: Give notice and details of intended siting.

Maintenance: Alter, adapt and move as necessary. Remove when no longer required and

make good.

230  	Temporary accommodation

Proposals for temporary accommodation and storage for the Works: Submit two weeks prior

to starting on site.

Details to be included: Type of accommodation and storage, its siting and the programme for

site installation and removal.

340  	Name boards/ advertisements

Name boards/ advertisements: Not permitted.

410  	Lighting

Finishing work and inspection: Provide temporary lighting, the intensity and direction of which

closely resembles that delivered by the permanent installation.

420  	Lighting and power

Supply: Electricity from the Employer's mains may be used for the Works as follows:

- Metering:

Free of charge

- Point of supply:

Within property

- Available capacity:

230v

- Frequency: 50 Hz.

- Phase:

Single

- Current: Alternating.

Continuity: The Employer will not be responsible for the consequences of failure or restriction

in supply.

430  	Water

Supply: The Employer's mains may be used for the Works as follows:

- Metering:

Free of charge

- Source:

Within property

- Location of supply point:

Within property

- Conditions/ Restrictions:

None

Continuity: The Employer will not be responsible for the consequences of failure or restriction

in supply. Please note that the water supply is from a Private Water Supply and the

Contractor shall satisfy himself of the supply during the tender stage.

440  	Telephones

Direct communication: As soon as practicable after the Date of Possession provide the

Contractor's person in charge with a mobile telephone.

520  	Use of permanent heating system

Permanent heating installation: May be used for drying out the Works/ services and

controlling temperature and humidity levels.

Installation: If used:

- Take responsibility for operation, maintenance and remedial work.

- Arrange supervision by and indemnification of the appropriate Subcontractors.

- Pay costs arising.

530  	Beneficial use of installed systems

Permanent systems: Do not use for the Works.

540  	Meter readings

Charges for service supplies: Where to be apportioned ensure that:

- Meter readings are taken by relevant authority at possession and/ or completion as

appropriate.

- Copies of readings are supplied to interested parties.

570  	Personal protective equipment

General: Provide for the sole use of those acting on behalf of the Employer, in sizes to be

specified:

- Safety helmets to BS EN 397, neither damaged nor time expired. Number required:

1 (for Forestry Commission visits only)

- High visibility waistcoats to BS EN ISO 20471 Class 2. Number required:

1(for Forestry Commission visits only)

- Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required:

1(for Forestry Commission visits only)

- Disposable respirators to BS EN 149.FFP1S.

- Eye protection to BS EN 166.

- Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2

- Hand protection - to BS EN 388, 407, 420 or 511 as appropriate.

A37  OPERATION/ MAINTENANCE OF THE FINISHED WORKS

110  	The building manual

Responsibility:

The Contractor

Content: Obtain and provide comprehensive information for owners and users of the

completed Works. Include an overview of the main design principles and describe key

components and systems within the finished Works, so affording a complete understanding

of the Works, including all buildings and their systems to enable efficient and safe operation

and maintenance.

Specific requirements:

None

Format:

1 hardcopy and 1 electronic copy

Number of copies:

2

Delivery to:

Contract Administrator . by (date)

Two weeks after date for Practical Completion

155  	Content of the building manual

General: Details of the property, the parties, fire safety strategy, operational requirements

and constraints of a general nature.

Building fabric: Design criteria, maintenance details, product details, and environmental and

trafficking conditions.

Building services: Description and operation of systems, diagrammatic drawings, record

drawings, identification of services, product details, equipment settings, maintenance

schedules, consumable items, spares and emergency procedures.

Documentation: Guarantees, warranties, maintenance agreements, test certificates and

reports.

160  	Presentation of building manual

Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each

indexed, divided and appropriately cover titled.

Selected drawings needed to illustrate or locate items mentioned in the Manual: Where

larger than A4, to be folded and accommodated in the binders so that they may be unfolded

without being detached from the rings.

As-built drawings: The main sets may form annexes to the Manual.

A53  WORK BY STATUTORY AUTHORITIES/ UNDERTAKERS

120  	Work by statutory undertakers

Item:

TBC

Description of work:

TBC

Provisional Sum: Include

TBC

Allow for general attendance.

A54  PROVISIONAL WORK/ ITEMS

590  	Contingencies

Provisional sum: Include:

£2,500.00 (Two Thousand Five Hundred Pounds) to be expended in part or in full as directed

by the Contract Administrator.