CONTENTS

TERMS AND CONDITIONS

Part 1 – DEFENCE CONDITIONS

- Defence Conditions (DEFCON)

Part 2 -   SPECIAL CONDITIONS

- Interpretation

- Precedence of Documents

- Contractual Matters

- Entire Agreement

- Assignment

- Contractor Warranties and Representations

- Contractor Undertakings

- Contractor’s Obligations

- Contract Period

- Price

- Payment

- Options

- Integrated Project Management Plan (IPMP)

- Risk

- Tasking Procedure/Authorisation of Work

- Quality Assurance

- Quality – General Requirements

- Quality Management Plan

- Certificate of Conformity

- Quality Assurance Representative (QAR)

- Ships Safety and Environmental Protection

- Key Performance Indicators (KPIs)

- Continuous Improvement

- Authority’s Authorised Officer

- Government Furnished Equipment (GFE)

- Receipt of GFE

- Custody of GFE

- Government Furnished Information (GFI)

- Guarantee

- Sub-Contracts

- Matters to be Included in Sub-Contracts

- Indemnities

- Care and Protection of Boats

- Continuing Obligations

- Debt Factoring

- Health and Safety

- Attendance by Makers’ Representatives and Certification Authorities

- Certification and Classification

- Changes in Certification and Classification

- Changes to the Contract

- Commonality of Equipment and Systems

- Replacement of Obsolescent Parts and Equipment

- Liquidated Damages

- Permissible Delays

- Termination for a Permissible Delay

- Take Over/Tow-Out Option

- Financial Consequences of Termination

- Major Incident Inquiries

- Jigs and Tools

- Inspection, Tests and Trials

- Acceptance

- Import and Export of Boats and/or Associated Equipment or Spares

- Fuels, Lubes and Hydraulic Fluid

- Insurance

- Sustainable Procurement

- Compatibility with Authority Systems

- Transfer of Undertakings (Protection of Employment) (TUPE)

- PR and Publicity

- Exit

- Security Aspects Letter (SAL)

- IPR – Control of Material (Multi-Terrain Pattern (MTP))

Schedules to Terms and Conditions

Schedule 1 – Schedule of Requirements

Schedule 2 – Statement of Technical Requirements (SoTR)

Schedule 3 – Definitions and Interpretations

Schedule 4 – Pricing and Rates

Schedule 5 – Addresses and Other Information (DEFFORM 111)

Schedule 6 – Integrated Project Management Plan (IPMP)

Schedule 7 – Task Authorisation Form / Work Request Form

Schedule 8 – Key Performance Indicators (KPIs)

Schedule 9 – Information Reporting and Key Performance Indicators

Schedule 10 – Corrective Action Plan

Schedule 11 – Care and Custody Certificate

Schedule 12 – Sea Trial Form

Schedule 13 – Acceptance Form

Schedule 14 – Contract Data Requirements List (DEFFORM 315)

Schedule 15 – Government Furnished Information (DEFFORM 316)

Schedule 16 – Government Furnished Equipment (GFE)

Schedule 17 – On Demand Bond (DEFFORM 24a)

Schedule 18 – Transfer of Undertakings (Protection of Employment (TUPE)

Schedule 19 – Contract Change Proposal

Schedule 20 – Insurance

TERMS AND CONDITIONS

PART 1 – DEFENCE CONDITIONS

- Defence Conditions (DEFCON)

  - The following DEFCONs shall apply to the Contract:

| - No | - Edition | - Title |
| --- | --- | --- |
| - 5J | - (Edn. 08/11/16) | - Unique Identifiers |
| - 14 | - (Edn. 11/05) | - Inventions and Designs Crown Rights and Ownership of Patents and Registered Designs |
| - 16 | - (Edn. 10/04) | - Repair and Maintenance Information – See CDR No 001 attached at Schedule 15 (Contract Data Requirements List – DEFFORM 315) |
| - 21 | - (Edn. 10/04) | - Retention of Records - See CDR No 001 attached at Schedule 15 (Contract Data Requirements List – DEFFORM 315) |
| - 23 | - (Edn. 08/09) | - Special Jigs, Tooling and Test Equipment |
| - 68 | - (Edn. 02/17) | Supply of Data for Hazardous Articles, Materials and Substances |
| - 76 | - (Edn. 12/06) | - Contractor's Personnel at Government Establishments |
| - 82 | - (Edn. 11/16) | - Special Procedures for Initial Spares |
| - 113 | - (Edn. 02/17) | - Diversion Orders |
| - 117 | - (Edn. 10/13) | - Supply of Documentation for NATO Codification and Defence Inventory Introduction |
| - 126 | - (Edn. 11/06) | - International Collaboration |
| - 127 | - (Edn.12/14) | - Price Fixing Condition for Contracts of Lesser Value (this shall apply to amendments to contract and Ad hoc Tasks valued at less than £250,000) |
| - 129 | - (Edn. 18/11/16) | - Packaging (For Articles other than munitions) |
| - 129J | - (Edn. 18/11/16) | - The Use Of The Electronic Business Delivery Form |
| - 501 | - (Edn. 08/16) | - Definitions and Interpretations |
| - 502 | - (Edn. 06/14) | - Specification Changes |
| - 503 | - (Edn. 12/14) | - Formal Amendments to Contract |
| - 507 | - (Edn. 10/98) | - Delivery |
| - 513 | - (Edn. 11/16) | - Value Added Tax |
| - 514 | - (Edn. 08/15) | - Material Breach |
| - 515 | - (Edn. 02/17) | - Bankruptcy and Insolvency |
| - 516 | - (Edn. 04/12) | - Equality |
| - 518 | - (Edn. 02/17) | - Transfer |
| - 520 | - (Edn. 02/17) | - Corrupt Gifts and Payments of Commission |
| - 522 | - (Edn. 18/11/16) | - Payment and Recovery of Sums Due |
| - 524 | - (Edn. 10/98) | - Rejection |
| - 525 | - (Edn. 10/98) | - Acceptance |
| - 526 | - (Edn. 08/02) | - Notices |
| - 527 | - (Edn. 09/97) | - Waiver |
| - 528 | - (Edn. 05/12) | - Overseas Expenditure, Import and Export Licences |
| - 529 | - (Edn. 09/97) | - Law (English) |
| - 530 | - (Edn. 12/14) | - Dispute Resolution (English Law) (Any dispute concerning the Ship’s compliance or non-compliance with the rules, regulations and requirements of the Classification Society or other Regulatory Authorities shall be referred to the appropriate Classification Society or Regulatory Authority for a decision which shall be final and binding upon the Parties. All other disputes shall be dealt with in accordance with DEFCON 530) |
| - 531 | - (Edn. 11/14) | - Disclosure of Information |
| - 532A | - (Edn. 06/10) | - Protection Of Personal Data (Where Personal Data is not being processed on behalf of the Authority) |
| - 534 | - (Edn. 18/11/16) | - Prompt Payment (Sub-Contracts) |
| - 537 | - (Edn. 06/02) | - Rights of Third Parties |
| - 538 | - (Edn. 06/02) | - Severability |
| - 539 | - (Edn. 08/13) | - Transparency (Contractor Commercially Sensitive Information” shall mean the information listed in the Contractor Commercial Sensitive Information, Schedule 17 (Contractor Commercial Sensitive Information)) |
| - 550 | - (Edn. 02/14) | - Child Labour and Employment Law |
| - 566 | - (Edn. 10/16) | - Change of Control of Contractor |
| - 601 | (Edn. 04/14) | - Redundant Materiel (shall apply in respect of DEFCON 611 (Edn. 07/10), Issued Property and to the extent that the redundant materiel derives from the property owned by the Authority and issued to the Contractor) |
| - 602A | (Edn. 12/06) | Deliverable Quality Plan |
| - 604 | - (Edn. 06/14) | - Progress Reports (for the purposes of the Contract, the frequency of reports shall be as detailed in the Annex B to the Integrated Project Management Plan (Schedule 5) Key Performance Indicators at Schedules 9 (Key Performance Indicators) |
| - 606 | (Edn. 06/14) | Change and Configuration Control Procedure |
| - 607 | (Edn. 05/08) | Radio Transmissions |
| - 608 | - (Edn. 10/14) | - Access and Facilities to be Provided by the Contractor (for the purposes of this Contract the Contractor shall ensure that any Offices, Lay Apart Stores or facilities provided by the Contractor to the Authority are fitted with security locks on all doors and any windows that can be opened. The Contractor shall ensure access to keys is limited to authorised personnel only, in agreement with the Authority). |
| - 609 | - (Edn. 06/14) | Contractor's Records |
| - 611 | - (Edn. 02/16) | - Issued Property |
| - 612 | - (Edn. 10/98) | - Loss of or Damage to the Articles |
| - 619A | - (Edn. 09/97) | - Customs Duty Drawback |
| - 621A | - (Edn. 06/97) | - Transport (if Authority is responsible for transport). |
| - 621B | - (Edn. 10/04) | - Transport (if the Contractor is responsible for transport). For the purposes of this Contract the Contractor shall comply with Department for Transport Code of Practice, Safety Loads on Vehicles and BS EN 12195 (Load restraining on vehicles – safety). |
| - 624 | (Edn. 11/13) | Use of Asbestos in Arms, Munitions or War Materials |
| - 627 | (Edn. 12/10) | Quality Assurance - Requirement for a Certificate of Conformity |
| - 630 | (Edn. 03/15) | Framework Agreements – (for the purposes of this Contract this shall only apply to the In Service Support requirement) |
| - 632 | (Edn. 08/12) | Third Party Intellectual Property – Rights and Restrictions |
| - 637 | (Edn. 18/11/16) | Defect Investigation and Liability |
| - 642 | - (Edn. 06/14) | Progress Meetings |
| - 643 | - (Edn. 12/14) | - Price Fixing (Non-qualifying contracts) (this shall apply to amendments to contract and Ad hoc Tasks valued at more than £250,000). The period in Clause 4 of this DEFCON shall be 5 years. |
| - 644 | (Edn. 05/15) | Marking of Articles |
| - 646 | - (Edn. 10/98) | - Law and Jurisdiction (Foreign Suppliers) |
| - 647 | - (Edn. 09/13) | - Financial Management Information |
| - 649 | - (Edn. 12/16) | Vesting |
| - 656B | - (Edn. 08/16) | Break (for the purposes of this Contract condition 5 shall be amended as follows.: - Add the following words after “….Articles payable under the Contract” Add “or exceed the total amount stated as the limit of the Authority’s liability under a Task Authorisation Form.” |
| - 658 | - (Edn. 04/17) | Cyber Further to DEFCON 658 the Cyber Risk Level of the Contract is LOW, as defined in Def Stan 05-138. |
| - 660 | - (Edn. 12/15) | - Reportable Official and Official-Sensitive Security Requirements |
| - 670 | - (Edn. 02/17) | - Tax Compliance |
| - 681 | - (Edn. 06/02) | - Decoupling Clause – Subcontracting with the Crown |
| - 691 | - (Edn. 03/15) | - Timber and Wood-Containing Products Supplied under the Contract |
| - 694 | - (Edn. 03/16) | - Accounting For Property of the Authority |
| - 703 | (Edn. 08/13) | - Intellectual Property Rights - Vesting in the Authority - (This condition will only apply to PDS tasks that are fully funded by the Authority. For the avoidance of doubt DEFCON 703 does not apply to any other tasks/materials/deliveries under the Contract.) |

PART 2 – SPECIAL CONDITIONS

- Interpretation

  - In addition to the provisions of DEFCON 501 (Interpretation), the words and phrases set out in Schedule 3 (Definitions & Interpretations) shall have the meaning ascribed to them in those Schedules unless otherwise provided for in this Contract.

  - In this Contract, except where the context otherwise requires:

    - a reference in this Contract to any Clause, Paragraph, Schedule or Annex is, except where expressly stated to the contrary, a reference to such Clause, Paragraph, Schedule or Annex of this Contract;

    - any reference in this Contract to a range of Clauses, Paragraphs, Schedules or Annexes shall, except where expressly stated to the contrary, be inclusive of those Clauses, Paragraphs, Schedules or Annexes used to define the range;

    - any reference to this Contract or to any other document shall include any permitted variation, amendment or supplement to such document;

    - references to any documents being "in the agreed form" means such documents have been initialled by or on behalf of each of the parties for the purpose of identification;

    - reference to a person includes firms, partnerships and corporations and their successors and permitted assignees or transferees;

    - all covenants, agreements, undertakings, indemnities, representations and warranties by more than one person are entered into, given or made by such persons jointly and severally;

    - references to a public organisation (other than the Authority) shall be deemed to include a reference to any successor to such public organisation or any organisation or entity which has taken over either or both the functions and responsibilities of such public organisation. References to other persons (other than the Authority) shall include their successors and assignees;

    - reference to the phrase "agreed or determined" means agreed between the parties or determined pursuant to the resolution of any dispute under DEFCON 530 (Disputes);

  - The words and phrases “other”, “including” and “in particular” shall not limit the generality of any preceding words or be construed as being limited to the same class as any preceding words where a wider construction is possible.

  - Unless otherwise stated, the provisions of this Contract shall be read and construed as if separate and independent contracts had been entered into, in respect of each Boat and In Service Support for each Boat and not as one contract for all Boats and In Service Support for all Boats.

- Precedence of Documents

  - The documents constituting this Contract are intended to be consistent. In the event of any ambiguity, conflict or inconsistency between the Contract and any document referred to or cross-referenced in the Contract, or between documents referred to or cross-referenced in the Contract, the conflict shall be resolved according to the following descending order of priority:

    - Clauses 1 to 62 of this Contract and Schedule 3 (Definitions and Interpretations);

    - Schedule 2 (Statement of Technical Requirements) of this Contract;

    - Other Schedules;

    - any other document of this Contract;

    - any other document agreed between the Parties after the Commencement Date.

- Contractual Matters

  - All queries and correspondence relating to or affecting the Contract shall be addressed to the Authority’s Commercial Officer as specified in Box 1 to Schedule 5 (Appendix - Addresses and Other Information).

- Entire Agreement

  - This Contract constitutes the entire agreement between the Parties relating to the subject matter of this Contract. This Contract supersedes all prior negotiations, representations and undertakings, whether written or oral, except that this Clause shall not exclude liability in respect of any fraudulent misrepresentation.

- Assignment

  - Neither Party to the Contract shall give, bargain, sell, assign, or otherwise dispose of the Contract or any part thereof, or the benefit or advantage of the Contract or any part thereof, without the previous consent in writing of the other Party.

- Contractor Warranties and Representations

Contractor Warranties

  - The Contractor warrants and represents to the Authority that:

    - it is properly constituted and incorporated and has the corporate power to own its assets and to carry on its business as it is now being conducted;

    - it has the power to enter into and to exercise its rights and perform its obligations under this Contract;

    - all action necessary on the part of the Contractor to authorise the execution of and the performance of its obligations under this Contract has been taken or, in the case of any such document executed after the date of this Contract, shall be taken before such execution;

    - the obligations expressed to be assumed by the Contractor under this Contract are, or in the case of any such document executed after the date of this Contract shall be, legal, valid, binding and enforceable to the extent permitted by law and this Contract is or shall be in the proper form for enforcement in England;

    - the execution, delivery and performance by it of this Contract does not contravene any provision of:

      - any existing Legislation binding on the Contractor, including Legislation which has been enacted but is not yet in force;

      - the memorandum and articles of association of the Contractor;

      - any order or decree of any court or arbitrator which is binding on the Contractor;

      - any obligation which is binding upon the Contractor or upon any of its assets or revenues;

      - no claim is presently being assessed and no litigation, arbitration or administrative proceedings are presently in progress or, to the best of the knowledge of the Contractor (having made all due enquiry), pending or threatened against it or any of its assets which shall or might have a material adverse effect on the ability of the Contractor to perform its obligations under this Contract;

      - it is not the subject of any other obligation, compliance with which shall or is likely to have a material adverse effect on the ability of the Contractor to perform its obligations under this Contract;

      - no proceedings or other steps have been taken and not discharged (nor, to the best of the knowledge of the Contractor, having made all due enquiry, threatened) for its winding-up or dissolution or for the appointment of a receiver, administrative receiver, administrator, liquidator, trustee or similar officer in relation to any of its assets or revenues (or any equivalent procedure);

      - it shall not, and in entering into this Contract it has not, committed any Prohibited Act; and

      - there is not and nor has there been any infringement or alleged infringement of any third party's IPR in connection with this Contract (excluding any Government Furnished Information).

and the Authority relies upon such warranties and representations.

- Contractor Undertakings

  - The Contractor undertakes that for so long as this Contract remains in full force it shall:

    - provide notice of any Dispute Proceedings to the Authority that are likely to affect the Contractor’s ability to perform its obligations under the Contract or has the potential to cause reputational damage to the Authority, unless such notice is precluded by the rules of the court, arbitrator, administrator, adjudicator, mediator or any other relevant authority with jurisdiction over the Dispute Proceedings:

      - within twenty (20) Business Days of the Contractor becoming aware that Dispute Proceedings may be threatened or pending; and

      - immediately after the commencement of Dispute Proceedings;

      - not undertake the performance of its obligations under this Contract otherwise than:

        - at the Contractor’s Premises; and

        - through itself or a Sub-Contractor.

Status of Contractor Warranties and Undertakings

  - All warranties, representations, undertakings, indemnities and other obligations made, given or undertaken by the Contractor in this Contract are cumulative and none shall be given a limited construction by reference to any other.

- Contractor’s Obligations

  - The Contractor shall provide the Contractor Deliverables to the Authority, all in accordance with the Contract and Good Industry Practice and shall, inter alia, offer the Boat to the Authority fully in compliance with the Contract at the Contractor’s premises on the Required Delivery Date.

  - Without prejudice to the overriding obligation contained in Clause 9.1, the Contractor's responsibilities shall, unless provided otherwise in the terms of this Contract, include:

    - design, construction, launch, equipping, completing and delivering of the Boats to the Authority;

    - providing In Service Support;

    - satisfactory completion of all Tests, Trials and Inspections required to prove the quality of the Contractor Deliverables in accordance with the Integrated Test and Evaluation Plan at Annex K of Schedule 6 (Integrated Project Management Plan);

    - providing support during the Authority’s Acceptance Trials up to Acceptance off Contract in accordance with the Contract;

    - the provision and proper fitting in place of all material, equipment, fittings and deliverables necessary for the completion of the Boat as required by the Contract unless otherwise specified;

    - the provision of all labour, plant, machinery, freight and port services necessary for the proper performance of the Contract;

    - the provision of all necessary services, facilities for and assistance to the Authority’s Representatives and the Authority’s Contractors in accordance with the Contract;

    - the provision of all necessary access, facilities and drawings for any classification, certification, surveys or trials to the Classification Society or Regulatory Authorities in accordance with the Contract;

    - examination, testing, and if necessary retesting of Lifting Equipment; ensuring that, at Acceptance Off Contract of each Boat, there remains at least 80% of the total period between tests or surveys being completed and the next test or survey falling due;

    - provision of all fuels, lubricating oils, greases and hydraulic fluids required for setting to work and trials of the Boat up to Acceptance Off Contract;

    - compliance with local Statutory Duties And Obligations up to Acceptance Off Contract and shall ensure that the Contractor Deliverables and any activities of the Contractor within the UK shall comply with UK Statutory Duties And Obligations;

    - supply of documentation and data for NATO Codification purposes in accordance with DEFCON 117 (Supply of Information for NATO Codification and Defence Inventory Introduction);

    - not, by any act or omission at any time, placing the Authority in breach of its obligations as an employer;

    - the Boat and its equipment being designed and built in metric units.

    - meeting all the requirements set out in Schedule 2 (Statement of Technical Requirements)

  - The Contractor shall not deviate from the Contract nor introduce any contrivance unusual in the kind of work covered by the Contract save as provided for in Clause 41 (Changes to the Contract)

  - Save in respect of the Contractor’s Sea Trials or as expressly agreed in writing by the Authority, all work involved in providing the Contractor Deliverables shall be carried out at the Contractor’s Premises.

  - The Contractor is responsible for producing a design of Boat that is safe to operate and fit for purpose by demonstrating to the Authority that the design developed by the Contractor meets the requirements of the Contract.

  - No advice, comment or information proffered, given or omitted by, or on behalf of, the Authority on or in relation to the Contractor's work in accordance with the Contract shall, in any way, extinguish, diminish or reduce the Contractor's obligations and responsibilities under the Contract to provide the Contractor Deliverables. Neither shall the activities of the Authority or its representatives including that of scrutiny of the design produced by the Contractor under the Contract derogate from the Contractor's obligations and responsibilities under the Contract.

  - The Contractor acknowledges that any risk assessment, questionnaire or risk register which has, or may be undertaken or maintained in connection with this Contract is done so in a management capacity only. Such risk assessment activity does not affect the legal relationship between the Parties or in any way limit or exclude the Contractor’s obligations under this Contract.

- Contract Period

  - This Contract and the rights and obligations of the Parties to this Contract shall take effect on the date of this Contract and, except as set out in Clause 35 (Continuing Obligations), shall terminate on the earlier of:

    - the date on which the Contractor has discharged all of its obligations in respect of the Contractor Deliverables; or

    - the Termination Date.

  - Each Year will run for the following Financial Years (FY):

    - Year 1 (FY 18/19) – Contract Start Date to 31 March 2019

    - Year 2 (FY 19/20) – 01 April 2019 to 31 March 2020

    - Year 3 (FY 20/21) – 01 April 2020 to 31 March 2021

    - Year 4 (FY 21/22) – 01 April 2021 to 31 March 2022

    - Year 5 (FY 22/23) – 01 April 2022 to 31 March 2023

    - Year 6 (FY 23/24) – 01 April 2023 to 31 March 2024

- Price

  - The Contract contains a mix of Firm and Fixed prices as stated in Schedule 4 (Pricing and Rates). All prices quoted are exclusive of UK VAT in accordance with DEFCON 513 (Value Added Tax).

  - Prices recorded in Schedule 4 (Pricing and Rates) as FIRM are not subject to variation in any respect (including on account of fluctuations in wages, and/or cost of materials, interest rates or currency exchange rates) save as provided for in Clause 41 (Changes to the Contract).

  - Prices recorded in Schedule 4 (Pricing and Rates) as FIXED are at Financial Year (FY) 17/18 price levels. The prices do not include provision beyond this date for increases or decreases in the market price of the Articles being purchased. Any such variation shall be calculated in accordance with the following formula:

New Build, Spares

V = P (a+b (Oi/O0)) - P

Where:

V represents the variation of price

P represents the FIXED price as stated in the Schedule of Requirements

O represents the index K38B - Other Transport Equipment

O0 represents the average OUTPUT Price Index figure for the base period April 2017 to March 2018 (as above)

Oi represents the average OUTPUT Price Index figure for the period April 2020 to March 2021

a represents the Non Variable Element (NVE)

b represents the Variable Element

a+b=1

Upkeep, Repairs, Modifications, PDS

V = P (a+b (Oi/O0)) - P

Where:

V represents the variation of price

P represents the FIXED price as stated in the Schedule of Requirements

O represents the index K8ZU - Top Level Service Producer

O0 represents the average OUTPUT Price Index figure for the base period April 2017 to March 2018 (as above)

Oi represents the average OUTPUT Price Index figure for the period April 2020 to March 2021

a represents the Non Variable Element (NVE)

b represents the Variable Element

a+b=1

  - The Index referred to in Clause 11.3 above shall be taken from the following Tables:

OUTPUT Price Index - e.g. ONS Publication MM22 Table 2 'Price Indices of UK OUTPUT: All Manufacturing and Selected Industries', or, Table 4 'Price Indices of Products Manufactured in the UK'.

  - Indices published with a ‘B’ or ‘F’ marker, or a suppressed value, in the last 3 years are not valid for Variation of Price clauses and shall not be used. Where the price index has an ‘F’ marker or suppression applied to it during the term of the Contract, the Authority and the Contractor shall agree an appropriate replacement index or indices. The replacement index or indices shall cover, to the maximum extent possible, the same economic activities as the original index or indices.

  - In the event that any material changes are made to the indices (e.g. a revised statistical base date) during the period of the contract and before final adjustment of the final contract price, then the re-basing methodology outlined by the Office for National Statistics (ONS, the series providers) to match the original index to the new series shall be applied.

  - In the event the agreed index or indices cease to be published (e.g. because of a change in the Standard Industrial Classification) the Authority and the Contractor shall agree an appropriate replacement index or indices, which shall cover to the maximum extent possible the same economic activities as the original index or indices. The methodology outlined by the Office for National Statistics used for rebasing indices (as in Clause 11.4 above) shall then be applied.

  - Notwithstanding the above, any extant index / indices agreed in the Contract shall continue to be used as long as it is / they are available and subject to ONS revisions policy. Payments calculated using the extant index / indices during its / their currency shall not be amended retrospectively as a result of any change to the index or indices.

  - The Contractor shall notify the Authority of any significant changes in the purchasing / manufacturing plan on the basis of which these provisions were drawn up and agreed, or of any other factor having a material bearing on the operation of these provisions such as to cause a significant divergence from their intended purpose, in order that both parties may consider whether any change in this provision would be appropriate.

  - Prices shall be adjusted taking into account the effect of the above formula as soon as possible after publication of the relevant indices or at a later date if so agreed between the Authority and the Contractor. Where an index value is subsequently amended, the Authority and the Contractor shall agree a fair and reasonable adjustment to the price, as necessary.

  - Claims under this Condition shall be submitted to the Bill Paying Branch, certified to the effect that the “requirements of this Clause 11.11” have been met.

- Payment

  - Payments shall be in Pounds Sterling.

  - The Contractor shall submit their claim for payment, in accordance with DEFCON 522 (Payment and Recovery of Sums Due).

Items 1 and 1A of Schedule 1 (Schedule of Requirements)

  - The Contractor shall submit their claim for payment on acceptance of each Boat as per Clause 52 (Acceptance) below, in accordance with DEFCON 522 (Payment and Recovery of Sums Due), as follows:

    - following acceptance of the Boat, 90% of the agreed price;

    - twelve (12) months after acceptance of the Boat, 10% of the agreed price.

  - Payment of the retention at Clause 12.3.2 above shall be subject to there being no outstanding defects on the Boat.

In Service Support (Item 1B Schedule 1 (Schedule of Requirements)) (Except Codified and Un-Codified Spares)

  - The Contractor shall submit their claim for payment monthly in arrears on the Authority’s acceptance of all work listed in Schedule 9 (Information Reporting & Key Performance Indicators) in accordance with DEFCON 522 (Payment and Recovery of Sums Dues).

Training, Initial Provisioning Spares and Documentation (Item 2, 3 and 4 Schedule 1 (Schedule of Requirements))

  - The Contractor shall submit their claim for payment on completion of all work under this Statement of Technical Requirement Line Item per Boat, in accordance with DEFCON 522 (Payment and Recovery of Sums Due).

- Options

  - The Option prices detailed in Table 1 of Schedule 4 (Pricing and Rates) to this Contract are Firm and not subject to variation.

  - In addition to the quantity detailed at Item 1 of Schedule 1 (Schedule of Requirements) to this Contract, the Contractor hereby grants to the Authority the following irrevocable options to purchase the quantities of boats in accordance with the terms and conditions set out in this Contract or any such subsequent contract or contracts where such options are taken up, it being agreed that that Authority has no obligation to exercise such options.

    - Option 1: A quantity of five (5) Boats in addition to the twenty-nine (29) boats already ordered under Item 1 of Schedule 1 (Schedule of Requirements) to this Contract and at the Firm prices and in accordance with the delivery schedule set out at Table 2 of Schedule 4 - OPTION (FY 20/21) to this Contract provided that the Authority exercises such option by no later than 3 February 2020.

    - Option 2: A quantity of one (1) Boat in addition to the twenty-nine (29) boats already ordered under items 1 of Schedule 1 (Schedule of Requirements) to this Contract and at the Firm prices and in accordance with the delivery schedule set out at Table 2 of Schedule 4 – OPTION (FY 21/22) to this Contract provided that the Authority exercises such option by no later than the start of the Contract

  - The Authority shall have the right to exercise the options by the specified dates or within such further period as corresponds to the aggregate of any such period(s):

    - of delay in the delivery programme whether constituting any breach of the Contract or resulting from any force majeure event within Clause 45 (Permissible Delays); or

    - for the duration of which the Authority is prevented from exercising any such option by reason of any other breach of the Contract by the Contractor.

  - The Authority shall not be obliged to exercise the options.

  - For the avoidance of doubt, where the Authority exercises an option, the Firm/Fixed prices for the In Service Support of that craft as set out in the relevant section of Schedule 4 (Prices and Rates) shall apply.

- Integrated Project Management Plan (IPMP)

  - The Contractor shall demonstrate good project management practice in undertaking all activities under the Contract. The Authority and the Contractor shall adopt an open and honest approach at all times and ensure that potential risks to performance, cost and time are exposed at the earliest opportunity. The Contractor shall wherever practicable minimise the detrimental impact on the Authority so as to reduce costs and time and increase performance and shall identify any potential opportunities to the Authority.

  - The Integrated Project Management Plan (IPMP) (Schedule 6 to the Contract) shall define how the Contract activities shall be managed, outlining the processes, procedures and techniques to be used with details of how all activities, plans and programmes will be established, monitored, changed, controlled, integrated and communicated with the Authority.

  - The IPMP shall adopt a consistent and coherent approach to project management and establish procedures and reporting mechanisms. Implementation of the IPMP will provide the Authority with confidence in the Contractor’s ability to deliver to time, cost and performance in accordance with the Contract and provide early visibility of potential issues so that mitigating action can be taken.

  - No later than three (3) months from the date of this Contract, the Contractor shall update and finalise the draft Integrated Project Management Plan (IPMP) (Schedule 6 to the Contract) together with the associated Annexes and issue to the Authority to review. The updated IPMP shall address the scope of work as set out in the Contract.

  - The Authority will review the updated IPMP and associated Annexes and provide proposed amendments to the Contractor within ten (10) working days of receipt. Any such proposals shall be subject to agreement of the Contractor who shall incorporate all reasonable proposals from the Authority in to the IPMP within ten (10) working days of any discussion held between the parties as a result of the Authority’s comments. Within ten (10) working days thereafter the Contractor shall submit the IPMP and associated annexes at Revision 1 status to the Authority as Schedule 6 (Integrated Project Management Plan).

  - The IPMP shall cross reference to the Contract Clauses, the Statement of Technical Requirements (Schedule 2) and all associated Annexes within the IPMP as applicable.

  - The Contractor shall be responsible for the maintenance and updating of the IPMP throughout the life of the Contract.

  - The IPMP shall comprise of the following Annexes:

    - Annex A - Project Monitoring and Control Plan (including a Contract Set-Up Plan);

    - Annex B – Communication, Relationship Management and Reporting Plan;

    - Annex C - Risk Management Plan;

    - Annex D – Quality Management Plan;

    - Annex E – Safety and Environmental Management Plan;

    - Annex F – Exit Strategy Plan;

    - Annex G – Security Plan;

    - Annex H – Supply Chain Management Plan;

    - Annex I – Test, Evaluation and Acceptance Plan;

    - Annex J – Through Life Support Plan;

- Risk

  - The Contractor shall provide and maintain a Risk Management Plan which shall as detailed at Annex C of Schedule 6 (Integrated Project Management Plan):

  - The risk management process shall be underpinned by the production and maintenance of a formal Joint Risk Register, incorporating both the Contractor’s and the Authority’s identified risks. The register shall be managed by the Contractor and presented to the Authority within three (3) months of the award of the Contract. Each risk in the register shall have a nominated risk owner who shall be responsible for the day-to-day management of the risk including the recording of mitigation actions, current risk parameters and status.

  - The Contractor acknowledges that any risk assessment including, without limitation, the identification of (or failure to identify) particular risks and their impact or risk reduction measures, contingency plans and remedial actions shall not in any way limit or exclude the Contractor's obligations under this Contract and shall be entirely without prejudice to the Authority's rights, privileges and powers under this Contract. Where the Contractor identifies and notifies risks during the risk assessment process such risks shall remain the risks of the Contractor and are not assumed by the Authority.

- Tasking Procedure/Authorisation of Work – In respect of In Service Support

  - Tasks will be authorised by the Authority by issuing either;

    - A Task Authorisation Form (TAF) as detailed at Schedule 7 (Task Authorisation Form / Work Request Form);

    - A Work Request Form (WRF) as detailed at Schedule 7 (Task Authorisation Form / Work Request Form), for all requirements excluding Codified Spares; or

    - A demand order through Contracting, Purchasing and Finance (CP&F), for Codified Spares detailed at Table 4 (Through Life Spares) of Schedule 4 (Pricing and Rates).

  - All WRF’s authorised by the Authority before the end of a Task Authorisation Form period shall be priced in accordance with the agreed Firm Prices for that Year (Financial Year) in Clause 10 (Contract Period).

  - In the event that any authorised TAF or WRF with an Agreed Delivery Date before the Contract End Date, is due to exceed the Contract End Date the Contractor shall be required to complete the work scope contained within the Task Authorisation Form.

General – Task Authorisation Forms (Multi-TAF)

  - Before the placing of any tasks, the Authority will issue the Contractor with a completed Task Authorisation Form (TAF), as detailed at Schedule 7 (Task Authorisation Form / Work Request Form). This form will impart to the Contractor:

    - The period of time covered by the TAF, as detailed at Schedule 7 (Task Authorisation Form / Work Request Form).

    - The Limit of Liability. The price of all work performed during that period of time must be within this limit.

    - The assumptions in terms of Planned Maintenance, Unplanned Maintenance, Extra and Emergent Work and other requirements used to derive the Limit of Liability.

    - The technical, financial and commercial approval which authorises the Authority to place this commitment (Parts E, F and G of the TAF).

  - On receipt from the Authority, the Contractor shall sign Part B of the TAF, as detailed at Schedule 7 (Task Authorisation Form / Work Request Form) to confirm acceptance of the TAF and return to the Authority.

  - The Contractor shall immediately inform the Authority’s Project Officer detailed in Schedule 5 (Addresses and Other Information), either in writing or by e-mail, in the event that spend across all Work Request Forms in the period of time specified has reached 80% of the LoL identified in the TAF as detailed at Schedule 7 (Task Authorisation Form / Work Request Form).

General – Work Request Forms (WRF)

  - The Authority will issue a WRF, as detailed at Schedule 5A (Task Authorisation Form / Work Request Form) for each discrete task that the Contractor is to perform within a given Multi-TAF. The scope of work described in the WRF, as detailed at Schedule 5A (Task Authorisation Form / Work Request Form) shall be deemed to be a ‘task’ for the purposes of this contract.

  - The Contractor shall not undertake any work without the prior written authorisation of the Authority, which will be given by signing the appropriate part of WRF, as detailed at Schedule 5A (Task Authorisation Form / Work Request Form. The Authority will not be responsible in any way whatsoever for any work undertaken or costs incurred prior to receipt by the Contractor of written authorisation in accordance with this Clause 16.8.

  - The Contractor shall maintain a list of all WRFs and their progress in the format detailed at Schedule 9 (Information Reporting and Key Performance Indicators) Information Reporting Sheet and provide this electronically to the Authority’s Authorised Project Officer on a monthly basis. This information, together with the KPI data as detailed in Clause 23 and Schedule 9 (Information Reporting and Key Performance Indicators) will be agenda items at the monthly project review meetings. Where a change is required to the estimated price and / or the estimated delivery date, the Contractor shall approach the Authority with a reason for the change and a new estimate of price and / or delivery date. The Authority shall have the final decision on whether the changes are acceptable and therefore reflected in Schedule 6 (Key Performance Indicators and Information and Reporting).

  - In the event that any work authorised by the Authority under a WRF is not subsequently required and is not undertaken by the Contractor, or where it is agreed by the Parties post the authorisation of a WRF that the Authority will supply Government Furnished Equipment (GFE) in lieu of Contractor supplied items, the Contractor shall agree a rebate with the Authority. The agreed rebate shall be deducted from the price of the WRF.

  - The Contractor shall immediately inform the Authority’s Project Officer in the event that either:

    - The Contractor believes the work cannot be completed within the LoL specified in the WRF; or

    - Spend has reached 75% of the WRF LoL.

  - In such circumstances the Contractor shall provide the Authority’s Project Officer with the reasons for the potential overspend and an estimate for completing the outstanding work.

  - The Contractor shall maintain the information reporting spreadsheet at Schedule 9 (Information Reporting and Key Performance Indicators), detailing the monthly activity completed against the task and the price for each activity.

Tasking Process

Planned Upkeep, Extra and Emergent Work, Defects, Repair and Modification

  - Prior to commencement of any work, the Authority will raise a TAF for one or more Boat(s) which will define the package of work to be completed (Part A of the TAF) and detail the Firm Price, Required Delivery Date and, if appropriate, a LoL for Extra and Emergent Work. On receipt of the TAF the Contractor shall either:

    - confirm agreement by completing and signing Part B of the TAF or;

    - verify and agree with the Authority any changes which are required to the package of work. The Contractor shall submit a revised Firm Price by completing Parts B and C of the TAF and shall:

      - apply the Firm price(s) in respect of Planned Upkeep work as set out at Table 4 of Schedule 3 (Schedule of Pricing and Required Delivery Dates);

      - for repair and modifications, submit a breakdown of price, in accordance with DEFCONs 127 (Price Fixing Condition for Contracts of Lesser Value) or 643 (Price Fixing) as appropriate using the Firm Rates at Table 3 of Schedule 3 (Schedule of Pricing and Required Delivery Dates);

      - provide a revised Required Delivery Date for all work under the TAF.

Subject to the Contractor confirming agreement of the TAF in accordance with Clause 16.14.1 above or the Authority agreeing the revised Firm Price and Required Delivery Date in accordance with Clause 16.14.2 above the Authority’s Commercial Officer will authorise the Contractor to proceed with the TAF by completing and signing Part H. In respect of Clause 16.14.2 above, the Authority will review and if appropriate revise the LoL for Extra and Emergent Work prior to authorising the TAF.

Post Design Services, Non-Codified Spares, Extra and Emergent Tasks, Transport

  - The Authority will issue a TAF, setting out the scope of the task and detailing the Required Delivery Date (Part A of the TAF). On receipt of the TAF, the Contractor shall submit a Firm Price by completing Parts B, C and D of the TAF using the appropriate Firm Rates from Table 3 of Schedule 3 (Schedule of Pricing and Required Delivery Dates).

  - Subject to the Firm Price being considered as fair and reasonable by the Authority and sufficient funds being available, the Authority’s Commercial Officer will authorise the Contractor to proceed by completing Part H of the TAF.

Limit of Liability

  - Where a TAF authorised by the Authority includes a Limit of Liability (LoL) the Contractor shall immediately inform the Authority’s Project Officer detailed in Schedule 5 (Addresses and Other Information), either in writing or by e-mail, in the event that:

    - The Contractor believes the work cannot be completed within the LoL specified on the TAF. In such circumstances the Contractor shall provide the Authority’s Project Officer with the reasons for the potential overspend and an estimate for completing the outstanding work;

    - Spend has reached 75% of the LoL. In such circumstances the Contractor shall provide the Authority’s Project Officer with the reasons for the potential overspend and an estimate for completing the outstanding work;

    - The cost of any single Emergent Task is likely to exceed REDACTED

  - The total amount to be paid by the Authority for work which is subject of the LoL shall not, without the approval in writing of the Authority, exceed the LoL. Where the Authority agrees to an increase in the LoL this will be authorised by the Authority’s Commercial Officer via an updated TAF.

Ordering of Spares

  - The Authority will order codified spares as detailed at Table 4 (Through Life Spares) of Schedule 4 (Pricing and Rates) electronically via the CP&F system.

  - The Authority’s Authorised Demanders for ordering spares are:-

| REDACTED Tel: REDACTED e mail: REDACTED | REDACTED Tel: REDACTED e mail: REDACTED |
| --- | --- |

  - Delivery shall be Ex Works; the Contractor shall be responsible for arranging collection of the spares by the Authority’s Transport Branch as specified in Box 10 at Schedule 5 (Addresses and Other Information).

  - The delivery address will be notified through CP&F and will include, but not be limited to:

| REDACTED | REDACTED |
| --- | --- |
| REDACTED | REDACTED |

  - On some occasions, the Authority may request the Contractor to deliver spares direct to an Authority site. In such cases, the Authority will request the cost of transport and the Demand Order will be annotated accordingly.

  - The Contractor shall maintain a list of the spares ordered and keep a running total. This information will be an agenda item at the monthly project review meetings.

- Quality Assurance

  - The Contractor shall ensure that the quality of the Contractor Deliverables including those of Sub-Contractors conforms to the requirements of the Contract and the Specifications.

  - The Authority may reject any Contractor Deliverable that does not conform to the requirements of the Contract.

  - Non-Conformities shall be dealt with in accordance with Clause 41 (Changes to Contract).

  - The Contractor shall retain the quality control / inspection records for a period of ten (10) years after Acceptance Off Contract of each Boat, and shall make them accessible to the Authority on request.

- Quality - General Requirements

  - The Contractor shall be responsible for ensuring that the quality of the work performed, and of the articles and materials supplied or repaired by him and all his Sub-Contractors, conforms to the requirements of the Contract.

  - The Contractor shall maintain a quality management system and continually improve its effectiveness in accordance with the terms and conditions of this Contract, ISO 9001-2008, the AQAP 2100 series and Defence Standards, as detailed below:-

    - AQAP 2110 Edition 3 (NATO Quality Assurance Requirements for Design, Development & Production)

    - AQAP 2105 Edn 2 (NATO QA Requirements for Deliverable Quality Plans)

    - DEFSTAN 05-57 Issue 6 (Configuration Management of Defence Materiel)

    - DEFSTAN 05-61 Part 1 Issue 5 (Concessions)

    - DEFSTAN 05-61 Part 4 Issue 3 and Amendment 1 28/01/11 (Contractor Working Parties)

    - DEFSTAN 05-135 Issue 1 Avoidance of Counterfeit Material.

  - For the AQAP series, the following interpretations apply:

    - Where the Contract refers to the “Authority”, the AQAP series refers to the “Acquirer”

    - Where the Contract refers to the “Contractor”, the AQAP series refers to the “Supplier”

    - Where the Contract refers to the “Sub-Contractor”, the AQAP series refers to the “Sub-supplier”.

- Quality Management Plan

  - The Contractor shall implement and maintain for the duration of the Contract a Contract specific deliverable Quality Management Plan (QMP) (Annex D to Schedule 6 (Integrated Project Management Plan) compiled to meet the requirements of AQAP 2105.

  - The QMP shall address two complimentary roles;

    - Describe and document the ‘contract specific’ Quality Management System (QMS) requirements necessary to satisfy the contract requirements.

    - Describe and document the planning for product realisation in terms of the quality requirements of the product, including needed resources, required control activities (verification, validation, monitoring, inspection, testing and acceptance criteria).

  - Once the QMP has been agreed in accordance with Clause 14 (Integrated Project Management Plan), draft updates/amendments to the QMP shall be submitted to the Authority monthly except where the plan remains unchanged. All updates will be agreed with the Authority and issued within twenty (20) working days of submission to the Authority. The agreed Contract Quality Management Plan may be subject to QAR surveillance activity to ensure compliance with agreed contract requirements.

  - The Contractor shall throughout the duration of the Contract advise the Authority of any impact on product quality or on the process and controls detailed in the deliverable QMP resulting from revisions or changes to their QMS.

- Certificates of Conformity (CoC)

  - A Certificate of Conformity (CoC) meeting the requirements of DEFCON 627 (Quality Assurance - Requirement for a Certificate of Conformity), and in accordance with the Quality Management Plan detailed in Annex D to Schedule 6 (Integrated Project Management Plan), is to be provided on Acceptance Off Contract of each Boat.

- Quality Assurance Representative (QAR)

  - When called up in standards invoked by this Contract, Quality Assurance Representative (QAR) is to be read as Government Quality Assurance Representative (GQAR and/or Acquirer).

- Ship Safety and Environmental Protection

  - The Authority has dual responsibilities in relation to safety and environmental protection:

    - as the Safety Regulator (naval ships being excepted by IMO); and

    - as the owner of the Boat after Acceptance Off Contract.

  - The Contractor shall ensure that:

    - the Boat is safe to operate and maintain;

    - the requirements of Annex E of Schedule 6 (Integrated Project Management Plan) and Schedule 2 (Statement of Technical Requirements) are met;

    - in performing the Contract comply with all his Statutory Duties And Obligations relating to safety and environmental protection.

  - If, at any time after the Commencement Date, it becomes apparent to the Contractor that anything contained in Schedule 2 (Statement of Technical Requirements) renders the Boat non-compliant with, or the Contractor in breach of, any local or UK Statutory Duty or Obligation relating to safety the Contractor shall:

    - immediately draw that fact to the Authority's attention; and

    - vary Schedule 2 (Statement of Technical Requirements) (at the Contractor’s own expense) in a manner acceptable to the Authority so as not to render the Boat non-compliant with, or the Contractor in breach of, any local or UK Statutory Duty or Obligation relating to safety.

  - Any form of approval by the Authority of any plans, calculations or documents relating to boat safety and environmental protection submitted by the Contractor shall not be taken as transferring liability for boat safety and environmental protection to the Authority prior to Acceptance Off Contract.

- Key Performance Indicators

  - The Authority will monitor the Contractor’s performance in accordance with Schedule 8 (Key Performance Indicators) to this Contract.

- Continuous Improvement

  - As part of the Contractor’s programme of continuous improvement the Contractor shall work with the Authority to identify process improvement which will result in increased craft availability and/or reduced costs. In recognition of the partnering principles, any benefits derived will be equally shared between the Parties.

- Authority’s Authorised Officer

  - Notwithstanding Clause 9 (Contractor’s Obligations), the Authority will appoint an Authority’s Authorised Officer as identified in Schedule 5 (Appendix – Addresses and Other Information) to:

    - inspect the work being done under the Contract and/or any part thereof, including materials and articles used or to be used therein;

    - provide the Contractor with information and advice as required;

    - monitor the progress of work on the Boat(s);

    - implement procedures for the authorisation of Extra and/or Emergent work or reductions (rebates) to a TAF;

    - co-ordinate all visits by Authority staff in connection with this Contract to the Contractor's premises;

    - arrange for the attendance of Authority inspection, tests and teams as required.

  - The Authority’s Authorised Officer will have the right to inspect all work being carried out under the Contract including at sub-contractors premises and to conduct product surveillance audits at any reasonable time. Any deficiencies or defects found during these inspections or audits shall be rectified by the Contractor at no additional cost to the Authority.

  - To enable the Authority’s Authorised Officer to carry out his duties, the Contractor shall:

    - permit full access at all times to the work in progress and to all drawings, models, samples and articles or things of any kind pertaining to the Contract; maintain full co-operation and provide all such drawings, information and assistance as may reasonably be required;

    - provide shore side office and equipment including but not limited to desk, chair, telephone, internet facilities; mains power, facsimile and access to a photocopier;

    - provide access to basic catering facilities (kitchen sink, running hot and cold water, water boiler, refrigerator and microwave);

    - submit all condition survey reports, dimension reports and readings from machinery in a timely manner;

    - submit Extra and Emergent work or reductions (rebates) to a TAF in accordance with the Contract.

  - The Authority’s Authorised Officer will have the right to:

    - reject any workmanship, article or material, which does not conform with the requirements of the Contract;

    - stop any test or trial or any other activity being carried out by the Contractor on the Boat(s) at any time if, in his opinion, the safety of the Boat(s), its equipment or personnel on board is compromised.

In respect of Clauses 25.4.1 and 25.4.2 above, the Contractor shall have a right of appeal to the Authority whose decision will be final and conclusive.

  - In the event of appeal by the Contractor against an Authority rejection of any	 workmanship, article or material;

    - notice of appeal shall be given to the Authority within seven (7) working days of receipt by the Contractor of notification of rejection;

    - workmanship shall not be made good nor the article or material removed until directed by the Authority.

  - Successful Appeal - Should an appeal by the Contractor prove successful then the Contractor will be entitled to request an extension of time, in accordance with Clause 45 (Permissible Delays) or KPI no. 1, Schedule 8 (Key Performance Indicators) for a period which is equivalent time of the Authority’s action under clause 25.4.1 and/or 25.4.1 up to and including the date on which the appeal is determined. The Authority shall have the absolute right to determine whether or not to grant such an extension of time.

  - The Contractor shall make good or replace at his own expense and to the satisfaction of Authority’s Authorised Officer, any workmanship, article or material rejected by the Authority. The Contractor shall also, if so required by the Authority, mark any rejected article or material, in a manner acceptable to the Authority’s Authorised Officer.

  - The Contractor shall not use surplus or used stores without the Authority's prior written approval. Where the Contractor proposes to use surplus or used stores, they shall submit their detailed proposals, including the effects on agreed prices or programme, to the Authority’s Authorised Officer for consideration and, if appropriate, approval.

  - The Contractor shall be liable for all costs and expenses incurred in the provision and proper use of the accommodation and facilities provided in accordance with Clause 25.3 above.

  - The Authority shall indemnify the Contractor in respect of:

    - damage occurring at the Contractor’s Premises; and

    - any third party claims; and

    - Injury or death to the Contractor’s employees caused by the acts or omissions of the Authority’s Representatives.

  - The Contractor shall indemnify the Authority in respect of injury or death to Authority Representatives caused by the acts or omissions of the Contractor’s Representatives.

  - Clause 25.10 and Clause 25.11 do not apply to the extent that a Party is able to show that any such damage, injury or death was caused or contributed to by circumstances beyond the reasonable control of the Authority’s Representatives or Contractor’s Representatives as appropriate.

- Government Furnished Equipment

  - The Government Furnished Equipment listed in Schedule 16 shall be issued, free of charge to the Contractor for embarkation and embodiment or fitting to the Boat.

  - Embarkation, embodiment or fitting of the Government Furnished Equipment to the Boat shall be at the expense of the Contractor unless otherwise specified in writing by the Authority.

  - The Contractor shall provide:

    - storage space at his premises or their Sub-Contractor for the Government Furnished Equipment which shall be secure, of adequate volume and have a controlled environment suitable for the Government Furnished Equipment;

    - lifting equipment, racking and shelving;

    - goods inwards inspection, stores accounting to include receipt recording, notification of receipts to the Authority, storage recording, issue to the Boat and filing of supporting vouchers in a dedicated file for periodic inspection by the Authority, stowage and simple maintenance tasks.

  - The Contractor hereby acknowledges that the Government Furnished Equipment may include pyrotechnics associated with the lifesaving equipment.

  - The delivery dates of Government Furnished Equipment shall be agreed between the Authority and the Contractor and shall be recorded in Schedule 16 (Government Furnished Equipment) after the Commencement Date.

  - The Required Delivery Date of each Boat is based on the assumption that all items of Government Furnished Equipment shall be delivered on the dates stated in Schedule 16 (Government Furnished Equipment). In the event that the Required Delivery Date of each Boat is revised, the Parties may agree to amend the delivery dates in Schedule 16 (Government Furnished Equipment) to accord with the changed Required Delivery Date.

  - The Authority shall be liable for the costs of:

    - removing and/or replacing defective Government Furnished Equipment;

    - repairing or replacing any part of the Boat damaged by defective Government Furnished Equipment;

    - repeat trials occasioned solely by faulty design of, or defects in, Government Furnished Equipment;

    - any delay to the Required Delivery Date of the Boat caused by late delivery of the Government Furnished Equipment and where the Authority has agreed an extension of time in accordance with Clause 45 (Permissible Delays).

provided that such costs are not due to error, default, breach, omission or negligence on the part of the Contractor.

  - All Government Furnished Equipment shall remain the property of the Authority. It shall be used in the execution of the Contract and for no other purpose, without the prior approval in writing of the Authority.

  - Neither the Contractor, nor any Sub-Contractor, nor any other person, shall have a lien on Government Furnished Equipment, for any sum due to the Contractor, Sub-Contractor or other person, and the Contractor shall take all such steps as may be necessary to ensure that the title of the Authority, and the exclusion of any such lien, are brought to the notice of all Sub-Contractors and other persons dealing with any Government Furnished Equipment.

  - The equipment will be serviced by the OEM(s) and delivered to the Contractors premises in accordance with the dates in Schedule 16 (Government Furnished Equipment);

  - The Contractor shall be responsible for the installation of the GFE in the Boat in accordance with SOTR ID number 5.13 of Schedule 2 (Statement of Technical Requirements).

- Receipt of Government Furnished Equipment

  - Subject to Clauses 27.2 to 27.4 below, the Contractor shall promptly and no later than ten (10) Days of receipt of Government Furnished Equipment:

    - check that the Government Furnished Equipment corresponds with the Government Furnished Equipment specified in the Contract;

    - conduct a reasonable visual inspection; and

    - notify the Authority’s Authorised Officer of any defects, deficiencies or discrepancies discovered.

  - Where Government Furnished Equipment is packaged it shall not be unpacked earlier than is necessary. The period identified at Clause 27.1 above shall count from the date on which packages are opened.

  - The Authority shall within a reasonable time after receipt of any notice under Clause 27.1 replace, re-issue or arrange for the repair of the defective or deficient Government Furnished Equipment. If appropriate, it shall also issue written instructions for the return or disposal of the defective or deficient Government Furnished Equipment.

  - The proceeds of the sale of defective or deficient Government Furnished Equipment shall be credited to the Authority in accordance with arrangements made between the Contractor and the Authority. A list of the Government Furnished Equipment sold by the Contractor shall be sent to the Commercial Officer specified in the Schedule 5 (Appendix - Addresses and Other Information) together with a statement of the proceeds of sale.

  - In the event that the Authority fails to provide, replace, or arrange for the repair of the defective or deficient Government Furnished Equipment within a reasonable time of receipt of a notice in accordance with Clause 27.1, the Parties shall agree appropriate changes to the Contract in accordance with Clause 41 (Changes to the Contract) provided that the Contractor has taken all reasonable measures to mitigate the consequences of any such delay.

- Custody of Government Furnished Equipment

  - The Contractor shall be responsible for:

    - safe custody and return to the Authority of;

    - calibration and maintenance of;

    - loss or damage to;

the Government Furnished Equipment as set out in Schedule 16 (Government Furnished Equipment)

from the expiry of the period specified in Clause 27.1 until the earlier of Acceptance Off Contract or re-delivery of the Government Furnished Equipment to the Authority in accordance with the Authority's instructions.

  - If requested, the Authority shall, within a reasonable time and where practicable before delivery of the Government Furnished Equipment, notify the Contractor of the value of the Government Furnished Equipment.

  - The Contractor shall not be liable to the Authority in respect of:

    - defects or deficiencies notified to the Authority in accordance with Clause 27.1 above or latent defects which the Contractor can show could not reasonably have been discovered by means of the activities described at Clause 27.1;

    - fair wear and tear of Government Furnished Equipment resulting from its normal and proper use in the execution of the Contract save where the deterioration is contributed to by any misuse, lack of care or maintenance by the Contractor;

  - At Acceptance Off Contract of each Boat the Contractor shall forward a list of Government Furnished Equipment still held by the Contractor to the Authority's Commercial Officer named in Schedule 5 (Appendix - Addressees and Other Information) and shall return or dispose of the Government Furnished Equipment in accordance with the Authority’s instructions.

- Government Furnished Information

General

  - All Government Furnished Information disclosed by the Authority pursuant to this Contact is set out in Schedule 16 (Government Furnished Information). All drawings, documents, design information and details of arrangements, models, mock-ups and samples provided by the Authority in connection with the Contract shall remain the property of the Authority.

  - Subject to Clause 32.1 the Contractor shall not in any way be relieved from any obligation under this Contract nor shall it be entitled to claim against the Authority on grounds that the Government Furnished Information is insufficient, and shall make its own enquiries as to the adequacy of that information.

  - In the event the Contractor discovers that the Government Furnished Information supplied by the Authority is inaccurate, the Contractor shall immediately notify the Authority of such inaccuracy and any impact on the Contract including any requirement for a change in the Contract under Clause 41 (Changes to the Contract) or extension of time in accordance with Clause 45 (Permissible Delays).

  - Nothing in this Clause 29 shall exclude any liability which the Authority or any of its agents or employees would otherwise have to the Contractor in respect of any statements made fraudulently or fraudulent omissions to make statements prior to the date of this Contract.

Drawings, documents and information

  - Where the Contract states that the Authority will supply any drawings, documents or information to the Contractor they will be provided free of charge.

  - On completion of the Contract, the Authority’s Authorised Officer will advise the Contractor of the method of disposal of all drawings, documents and other information supplied to him in accordance with Clause 29 above.

Review of Documents provided by the Contractor

  - During the course of the Contract where documents are delivered to the Authority for review, unless specified otherwise, the Contractor shall allow no less than ten (10) working days for the Authority to respond. The Authority’s comments on the documents will be supplied in writing. In cases where the Authority’s comments are extensive, a separate review meeting will be held with the Contractor to discuss the changes required to the document.

Supply of Support Documentation by the Contractor

  - The Contractor shall provide the Authority with technical handbooks, maintenance schedules, operating instructions, spare parts lists and/or any other documentation in accordance with Schedule 2 (Statement of Technical Requirements) or a Task Authorisation Form.

- Guarantee

  - The Contractor shall guarantee all work undertaken under the Contract, including fitness for purpose and compliance with all current Health and Safety Legislation, and shall be responsible for the rectification of defects discovered within the guarantee periods stated below.

| Type of Work | Guarantee Period from each Boat’s Acceptance Date |
| --- | --- |
| New build | Two (2) years |
| In Service Support (including but not limited to Planned Refit / Repair / Upgrade / Modifications) | Six (6) months |
| Post Design Services | One (1) year from acceptance of the deliverable |
| Spares | One (1) year from delivery |

  - The Authority will notify the Contractor in writing of any guarantee issues as soon as practicable, specifying the nature and extent of the guarantee issue, the date of its discovery and the location where the Authority requires the Contractor to undertake corrective action.

  - If during the guarantee period specified in Clause 30.1 above, any item or material or part thereof is found to be defective or show signs of weakness due to faulty materials or workmanship the Authority will have the right to either:

    - require the Contractor at his own expense to remove, repair and/or replace such defective materials and/or parts;

    - take such corrective action itself and to recover from the Contractor its expenses in so doing.

  - The Contractor shall be liable for all costs, expenses and liabilities incurred or suffered by the Authority as a consequence of the defects.

  - Notwithstanding anything contained in this Clause 30, the Contractor shall not be required to remedy or pay the cost of remedying any deficiency arising:

    - from fair wear and tear, or;

    - from negligence on the part of any person in the service of the Authority.

  - Where the Authority has supplied Government Furnished Equipment (GFE) the Contractor's guarantee shall only apply to the work undertaken by the Contractor to install the GFE in the Boat and not to the GFE itself. For the avoidance of doubt nothing in this Clause 30.6 shall reduce or limit the Contractor's guarantee obligations under the remainder of this Clause 30.

  - The Contractor shall assign to the Authority all guarantees or warranties given by Sub-Contractors or suppliers of any of the materials or equipment supplied under this Contract which exceed the guarantee periods specified in Clause 30.1 above.

  - In the event of any rectification work being required during the guarantee period(s) specified at Clause 30.1 above, the guarantee period for the remedial work shall be the later of:

    - three (3) months from the date of completion of the remedial work; or

    - the end of the guarantee period.

  - The Contractor shall proceed with due diligence in all corrective action under this Clause 30.

  - The Contractor shall be responsible for all aspects of Guarantee management including but not limited to:

    - progressing the rectification of all Defects,

    - the management of Sub-Contract guarantees including the transfer of any rights in Sub-Contract guarantees to the Authority in accordance with Clause 30.7;

    - the production and distribution of Defect status reports; and

    - attendance at meetings with the Authority and/or Sub-Contractors to review Defects.

  - Save as provided for in Clause 30.5, the Contractor shall make any necessary repairs or replacements to rectify any Defects or damage to the Boat caused as a direct consequence of such Defects. Such repairs and replacements shall be made at the Contractor’s Premises (or at the sub-contractors premises where boat build has been sub-contracted) at the Contractor’s cost and expense.

  - The Authority shall have the right to arrange for the rectification of any Defect, or damage to the Boat caused as a direct consequence of a Defect, to be undertaken at a location of the Authority’s choice and obtain any necessary replacement parts and materials where:

    - it is impractical to bring the Boat to the Contractor’s Premises or at the sub-contractors premises where boat build has been sub-contracted ; or

    - the Contractor cannot supply necessary replacement parts and materials without impairing or delaying the operation or working of the Boat ; or

    - the Contractor is in default of Clause 30.11.

  - In the event that the Authority proposes to rectify Defects at any premises other than the Contractor’s Premises or at the sub-contractors premises where boat build has been sub-contracted in accordance with Clause 30.12, the Authority shall notify the Contractor of the time and place proposed to rectify the Defect. The Contractor shall be given a reasonable opportunity to inspect the nature and extent of the Defect and promptly advise the Authority whether or not he accepts that the Defect is covered by the Guarantee but such advice to the Authority shall not be conclusive.

  - The Contractor shall pay the Authority the reasonable cost and expenses of rectifying a Defect in accordance with Clause 30.13 above which shall be:

    - set off against a payment; or

    - paid within thirty (30) Days of receipt of a written demand for payment from the Authority where:

      - all payments in accordance with the Contract have been made by the Authority; or

      - the amount payable by the Contractor exceeds those sums which have been set off by the Authority in accordance with Clause 30.14.2.1 above.

  - At any time prior to rectification in accordance with Clause 30.12 above the Contractor shall be entitled to request that the Authority return any parts replaced to the Contractor. The Authority shall make reasonable endeavours to comply with the Contractors request and any parts returned shall be at the Contractor’s cost.

  - In the event that any replaced parts returned to the Contractor in accordance with Clause 30.15 are the subject of a dispute under DEFCON 530 (Disputes), the Contractor shall make available the replaced parts for inspection by the Authority.

Post Design Services Deliverables

  - Where in the opinion of the Authority the deliverables associated with PDS tasks are found to be inaccurate so as to be unfit for purpose, the Contractor shall rectify, at his own expense, any incorrect information or deliverables and the Authority will also have the right to recover from the Contractor any costs incurred by the Authority in implementing any corrective action associated with the incorrect information provided by the Contractor.

- Sub-Contracts

  - No Sub-Contracting by the Contractor shall in any way extinguish, diminish or reduce the Contractor’s obligations under the Contract and the Contractor shall be fully responsible for acts, errors, defaults, breaches, omissions or negligence of any Sub-Contractor.

  - The Contractor shall perform its obligations under and observe all the terms of any Sub-Contracts.

  - Nothing in this Contract shall prohibit or prevent any Sub-Contractor employed by the Contractor from being employed by the Authority at any establishments of the Authority.

  - Where the Contractor enters into a Sub-Contract with a supplier or contractor for the purpose of performing the Contract, he shall cause a term to be included in such Sub-Contract which requires payment to be made by the Contractor to the supplier or contractor within a specified period not exceeding thirty (30) days from receipt of a valid invoice and the requirements for a valid invoice shall be defined by the Sub-Contract.

  - The Contractor shall not place any Sub-Contract or order involving the design or development of Articles required under this Contract without the prior approval of the Authority.

  - The Contractor shall not enter into any commitment in relation to the design or development of equipment until such time as the Contractor has entered into an agreement with the Authority in the form set out at Schedule 19 (Design Rights and Patents (Sub-Contractors Agreement – DEFFORM 177). Wherever possible the request for approval should be accompanied by two copies of the agreement signed by the Sub-Contractor. If, in any case the Contractor is unable to comply with this Clause he shall report the matter to the Authority’s Commercial Officer and await further instructions before placing the Sub-Contractor or order.

  - The Contractor shall retain, for a period of at least ten (10) years after Acceptance Off Contract of the final Boat under the Contract or Termination Date, a copy of the Sub-Contracts (or the relevant parts thereof) sufficient to demonstrate the Authority’s rights with respect to Intellectual Property Rights and shall provide certified copies of such records to the Authority upon request.

  - The Authority shall have a right of direct access to any Sub Contractor for the purpose of monitoring the progress of work under the Contract, technical liaison and discussion with the Sub-Contractor provided that his presence at the site shall not hinder progress of the work. The Authority shall give prior notification to the Contractor of any proposed visits and the Contractor shall have a right to be present at any site visit by the Authority to a Sub Contractor. This right of direct access under this Clause shall also include the Authority's right to discuss, at any time, with Lloyd's Register or any relevant maritime and coastguard agency, or agency having similar jurisdiction, any aspects relating to the Contract.

Change of Sub-Contractors

  - The Contractor shall assign any guarantees or warranties provided by its Sub-Contractors to the Authority which exceed the Guarantee Period.

- Matters To Be Included In Sub-Contracts

  - The Contractor shall ensure that all Sub-Contracts shall at all times include:

    - provisions such that the Sub-Contract shall not be rescinded, or varied in such a way as to alter or extinguish any rights granted to the Authority without the prior written consent of the Authority;

    - provisions that the Authority's rights referred to in this Clause 32, which are otherwise enforceable under the Contracts (Rights of Third Parties) Act 1999, are not rendered unenforceable; and

    - a requirement that either party to the Sub-Contract may release to the Authority any of those parts of the Sub-Contract as are necessary to be sufficient to demonstrate compliance with the provisions of this clause and that any such release shall not amount to a breach of any provision of confidentiality contained within the Sub-Contract.

    - provisions enabling the Contractor to terminate the Sub-Contract (on similar terms to those which apply to any termination by the Authority of this Contract under the Terms and Conditions of the Contract), and shall terminate such Sub-Contract where reasonably directed by the Authority to do so.

    - provisions enabling the Contractor to secure the dismissal of an employee of the Sub-Contractor, so as to enable implementation of any Authority requirement of the Contractor to secure such dismissal, due to a breach of DEFCON 520 (Corrupt Gifts and Payments of Omission) by that employee, include a provision enabling the Contractor to determine such Sub-Contracts in the event that the Authority exercises its rights under DEFCON 656 (Break) to terminate this Contract upon written notice;

    - include the power to determine the Sub-Contract on substantially the same terms as those which apply to any termination of this Contract pursuant to DEFCON 656B (Break), provided that references in the provisions DEFCON 656B (Break) to "Authority", "Contractor" and "Contract" shall be construed (as appropriate) as references to "Contractor, "Sub-Contractor" and "Sub-Contract" (respectively) for the purposes of the corresponding Sub-Contract provisions.

    - a requirement for any further Sub-Contracts of lower tiers to contain provisions capable of giving effect to all of the provisions of Clauses 31 (Sub-Contracts) and 32 (Matters to be Included in Sub-Contracts), to the extent reasonably required by the Authority.

  - When placing subcontracts, the Contractor is asked to give consideration, as far as possible, to placing work on a competitive basis with Subcontractors that are Supported Businesses. The Contractor can find details of Supported Businesses in the United Kingdom on the Supported Business Directory that is British Association for Supported Employment at Unit 4, 200 Bury Road, Tottington, Lancashire BL8 3DX (Telephone : 01204 880733) or http://business.base-uk.org/procurement.

- Indemnities

  - The Contractor shall be responsible for, and shall release and indemnify the Authority, its employees, agents and contractors on demand from and against, all liability for:

    - death or personal injury;

    - loss of or damage to property (including property belonging to the Authority or for which it is responsible ("Authority Property");

    - breach of statutory duty; and

    - actions, claims, demands, costs, charges and expenses (including legal expenses on an indemnity basis);

which may arise out of, or in consequence of the performance or non-performance by the Contractor, its Sub-Contractors, their employees or agents.

  - The Contractor shall not be responsible or be obliged to indemnify the Authority for:

    - any of the matters referred to in Clauses 33.1.2 to 33.1.4 above which arises as a direct result of the Contractor acting on the instruction of the Authority;

    - any injury, loss, damage, cost and expense caused by the negligence or wilful misconduct of the Authority, its employees, agents or contractors or by the breach by the Authority of its obligations under this Contract; or

    - an indemnity by either the Authority or the Contractor under any provision of this Contract shall be without limitation to any indemnity by the Authority or the Contractor under any other provision of this Contract.

- Care and Protection of the Boat(s)

General

  - The Contractor shall be responsible for the care, protection, physical security, loss and damage of the Authority’s Boats, their equipment and other equipment and materials whilst in their custody from the point of either:

    - collection by the Contractor in accordance with DEFCON 621B (Transport (if the Contractor is responsible for Transport)): or

    - delivery by the Authority to the Contractor’s premises in accordance with DEFCON 621A (Transport (if the Authority is responsible for Transport)):

to the point of either:

    - delivery by the Contractor in accordance with DEFCON 621B (Transport (if the Contractor is responsible for Transport)): or

    - collection by the Authority from the Contractor’s premises in accordance with DEFCON 621A (Transport (if the Authority is responsible for Transport))

  - The Authority when handing over custody of a Boat will present the Contractor with a signed Care and Custody Certificate form at Schedule 12 (Care and Custody Certificate). The Contractor shall sign the certificate accepting custody of a Boat and shall complete the inventory of loose items and engine serial number and hours before and after the refit or repair work has been undertaken. When returning custody of a Boat the Contractor shall sign and return the completed certificate to the Authority.

Berthing/Slipping

  - The Boat(s) whilst in the care and protection of the Contractor shall be docked and undocked and slipped and unslipped in accordance with the requirements of the TAF/ WRF and as required to complete the work. At all other times the Contractor shall place the Boat(s) in a suitable berth approved by the Authority. Except as may otherwise be approved by the Authority, the Contractor shall ensure the Boat(s) is fully afloat at all states of the tide.

Stability

  - The Contractor shall be responsible for ensuring the Boat’s stability is, at all times, satisfactory whilst in their care and protection. The Authority will have the right to require the Contractor, at the Contractor’s expense, to check the stability of a Boat at any time.

Clean Boat and Protection of Equipment

  - The Contractor shall maintain high standards of cleanliness to decks, Boat compartments and passageways, Boat structure, dock bottom and steps (where applicable) and dock side.

  - The Contractor shall ensure there is no contamination of equipment or installation by any means including dirt, condensation, paint, shipyard arisings, corrosive products of grit blasting, lagging and kindred operations. Arisings shall be removed on a daily basis, whenever the nature of the work permits and debris shall not be allowed to accumulate. In places where equipment may be subject to heavy wear or knocks from passing traffic it must be boxed in. All deck coverings shall be protected from dirt and damage.

  - The Contractor shall be responsible for making good damage to paint-work and fittings arising from Work in Way.

  - The Contractor shall remain responsible for the condition and cleanliness until acceptance of the Boat by the Authority.

  - The Contractor shall ensure compartments in which switchboards are located are kept clear of stores, tools and clothing.

  - The Contractor shall ensure all work which may have an adverse effect on electronic and/or environmentally sensitive equipment is completed before any such equipment is moved aboard and/or fitted.

Fire Precautions

  - The Contractor shall be responsible for fire fighting arrangements whilst a Boat is in their care and protection. The Contractor shall:

    - provide access and action by the local Fire Authority to meet applicable legislation;

    - provide fire watcher and fire-fighters at all times during working hours and up to one hour after any hot work is complete in accordance with hot work procedures and for security rounds at cessation of the working day;

    - ensure clearance of fire hazards;

    - ensure availability of alarms, extinguishers and appliances;

    - provide equipment and training and exercising of personnel.

  - Without prejudice to the Contractor's responsibility under Shipbuilding and Ship Repairing Regulations (1960), supplemented by the Health and Safety at Work Act and the Shipyard Auditable Health and Safety Policy Document and all applicable legislation, the Contractor shall as and when requested by the Authority:

    - allow access to the Contractor’s facilitates to enable the Authority to check that the efficacy of the Contractor's precautions at Clause 34.11 above is to the entire satisfaction of the Authority; and

    - provide evidence of their compliance with this 34.12.

- Continuing Obligations

  - Save as otherwise expressly provided in this Contract or as already taken into account in the calculation of any payment on termination pursuant to this Contract:

    - termination of this Contract shall be without prejudice to any accrued rights or obligations under this Contract prior to termination; and

    - termination of this Contract shall not affect the continuing rights and obligations of the Contractor and the Authority under:

      - Clauses 3 (Precedence of Documents), 9 (Contractor’s Obligations), DEFCON 527 (Waiver), DEFCON 529 (Law (English)), DEFCON 530 (Disputes), DEFCON 531 (Disclosure of Information), and DEFCON 538 (Severability); or:

      - any other Clause or any provision of this Contract which is expressed or implied to survive termination or which is required to give effect to such termination or the consequences of such termination.

- Debt Factoring

  - Subject to the Contractor obtaining the prior written consent of the Authority in accordance with DEFCON 518 (Transfer) the Contractor may assign to a third party (“the Assignee”) the right to receive payment of the Contract Price or any part thereof due to the Contractor under this Contract (including any interest incurred by the Authority under any Contract clause concerning the late payment of debts).

  - Any assignment of the right to receive payment of the Contract Price (or any part thereof) under DEFCON 518 (Transfer) shall be subject to:

    - reduction of any sums in respect of which the Authority exercises its right of recovery under DEFCON 522 (Payment and Recovery of Sums Due), or any narrative clause concerning recovery of sums due;

    - all related rights of the Authority under the Contract in relation to the recovery of sums due but unpaid; and

    - the Authority receiving notification under both Clause 36.3 and sub-Clause 36.4.2 below.

  - In the event that the Contractor obtains from the Authority the consent to assign the right to receive the Contract Price (or any part thereof) under Clause 36.1 above, the Contractor shall notify the Authority in writing of the assignment and the date upon which the assignment becomes effective.

  - The Contractor shall ensure that the Assignee:

    - is made aware of the Authority’s continuing rights under sub-Clauses 36.2.1 and 36.2.2 of this Clause 36; and

    - Notifies the Authority of the Assignee’s contact information and bank account details, to which the Authority shall make payment, subject to any reduction made by the Authority in accordance with sub-Clauses 36.2.1 and 36.2.2 above.

  - The provisions of the Contract, including any clauses concerning payment, shall continue to apply in all other respects after the assignment and shall not be amended without the prior approval of the Authority.

- Health and Safety

  - Notwithstanding and without prejudice to the provisions detailed elsewhere in the Contract, the Contractor shall be entirely responsible for the safety, whilst on his premises, of all personnel in connection with the Contract, whether or not in his employ.

  - Save as may otherwise be specifically defined in the Contract, the Contractor shall be in charge of, and entirely responsible for, the care, protection and security of the Boat(s) and all Authority property whilst in their possession.

  - Where the Authority engages an Independent Safety Advisor/Auditor/Assessor the Contractor shall provide access to records, including Sub-Contractor records to enable the Authority to carry out safety audits and other assessment activities. This shall include the provision of access to the Contractor and Sub-Contractors premises if required.

- Attendance by Makers' Representatives and Certification Authorities

  - The Contractor shall be responsible for co-ordinating and arranging all attendance to execute or oversee work in connection with delivery, installation on board, setting to work, acceptance, maintenance, trials and repair or examination of machinery, systems and equipment, under the Contract.

  - The Contractor shall make all arrangements for, and provide all necessary drawings, access and facilities for any work in connection with registration, classification, certification, surveys or trials.

  - The Contractor shall be responsible for co-ordinating and arranging attendance by all surveyors necessary for any certification required by the Contract.

  - The Contractor is encouraged to bring to the attention of the Authority any measures which might promote sustainable procurement from a social, economic and environmental point of view.

  - The Contractor shall take all reasonable steps to ensure that all activities under this Contract shall comply with certified environmental management standards based on ISO14001 or equivalent.

- Certification and Classification

  - The Boat shall be designed, constructed, surveyed, tested and delivered in compliance with the applicable laws, rules, regulations and requirements of the Classification Society, the Regulatory Authorities (including the Authority whose requirements are specified in this Contract):

    - in force as of the date of this Contract, or

    - if not in force as of the date of this Contract, which are ratified and promulgated on or before the date of this Contract and which will be compulsory for the Boat on or before the delivery of the Boat.

  - All such laws, rules, regulations and requirements of the Classification Society and the Regulatory Authorities shall be complied with without qualification.

  - Any subsequent Change in Certification and Classification shall be dealt with in accordance with Clause 40 (Changes in Certification and Classification).

  - The final decisions of the Classification Society or Regulatory Authorities shall be binding on the Parties as to the Boat’s compliance with their respective applicable laws, rules, regulations and requirements.

  - Subject to Clause 39.1 all costs, fees and charges in respect of compliance with the applicable laws, rules, regulations and requirements of the Classification Society or Regulatory Authorities referred to above (as well as the fees and costs payable to the Classification Society or Regulatory Authorities) shall be for the Contractor’s cost and expense.

- Changes in Certification and Classification

  - Subject to Condition 39 (Certification and Classification) above, the Clauses 40.2 to 40.7 below shall apply to any Change in Certification and Classification.

  - The Parties shall promptly notify the other Party of the change as soon as possible after becoming aware of the Change in Certification and Classification.

  - The Contractor shall at his own expense provide to the Authority a written statement detailing the consequences of implementing the Change in Certification and Classification, including but not limited to, any changes to:

    - Contract price in accordance with Clause

    - Delivery Date;

    - Speed of the Boat;

    - Lifting weight.

  - If the Authority obtains an exemption from the Change in Certification and Classification he shall notify the Contractor of such and the Contractor shall take no further action in relation to the Change in Certification and Classification.

  - If the Authority has not sought or obtained an exemption from the Change in Certification and Classification the Contractor shall incorporate such Change in Certification and Classification into the construction of the Boat.

  - The Parties shall agree any adjustments to the Contract resulting from the incorporation into the construction of the Boat of any Change in Certification and Classification.

  - If the Parties fail to agree the adjustments, the Contractor shall proceed with required changes and the consequences of its implementation shall be decided in accordance with DEFCON 530 (Dispute Resolution).

- Changes to the Contract

Categorisation of Changes

  - Each proposal for a change to the Contract shall be categorised as follows:

    - Priority changes.

    - Routine changes.

  - The category shall be determined by the Authority’s Authorised Officer following the procedure set out at Clause 41.3 below.

Contract Change Proposal Procedure

  - The procedure set out in the following Table shall be followed by the Authority and the Contractor for all Changes to this Contract except as otherwise provided for under this Contract.

|  | Changes Initiated by the Authority | Changes Initiated by the Contractor |
| --- | --- | --- |
| Step 1 | A Change Number shall be allocated by the Authority’s Authorised Office using Contract Change Proposal Form (CCPF) 2. Change category assigned by the Authority’s Authorised Officer. Written request for a formal proposal shall be issued to the Contractor by the Authority. | The Contractor shall gain internal Contractor approval to submit a Contract Change Proposal. |
| Step 2 | The Contractor shall respond to the Authority within ten Business Days (five Business Days for priority changes) of receiving the written request advising the date by which the Contract Change Proposal Form (CCPF1) shall be submitted. | Initially an outline CCPF 1 shall be tabled by the Contractor with a Rough Order of Magnitude price to cover the change and advising the date by which the Contract Change Proposal Form (CCPF1) shall be submitted. The proposal shall be given a Change Proposal Number and registered on the Index of Contract Change Proposals (Form CCPF 2) by the Authority’s Authorised Officer who shall advise the Contractor whether to proceed with the following steps or that the change proposal is rejected. |
| Step 3 | Within fifteen Business Days (ten Business Days for priority changes) of receiving the written request the Contractor shall provide an outline CCPF 1 with an indication of the price to cover the change. The Authority’s Authorised Officer will advise the Contractor whether to proceed with the following steps or that the change proposal is rejected. | NOT USED |
| Step 4 | The Contractor shall determine, in conjunction with the Authority, whether sub-Contract competition is required |  |
| Step 5 | The Contractor shall provide formal completed CCPF1 including proposed Firm prices (including a price breakdown) in accordance with Schedule 1 (Schedule of Requirements) to this Contract. The CCPF 1 shall be submitted in accordance with Step 2. |  |
| Step 6 | If required, the Authority and the Contractor shall meet within five business days from receipt of CCPF1 to agree and approve the Change. The Authority’s Authorised Officer shall make the necessary arrangements to convene the meetings. |  |
| Step 7 | Subject to agreement of a Firm Price, any other changes to the Contract and approval of funding the Authority’s nominated Commercial Officer shall issue a serially numbered Contract Amendment in writing to the Contractor’s nominated Commercial Manager within ten Business Days of agreement of the change proposal. The provisions of DEFCON 503 shall apply. |  |
| Step 8 | The Contract Amendment shall be signed by the Contractor’s nominated Commercial Manager and such confirmation of acceptance returned to the Authority |  |

  - The Authority shall maintain configuration control of CCPF 1 forms and the CCPF 2 and shall issue copies to the Contractor’s nominated Project and Commercial Managers as requested.

  - Once the CCPF 1 has been agreed and authorised by the Authority the signed original CCPF 1 and all its attachments, including the Contractor’s quotation, shall be retained by the Authority’s nominated Commercial Officer who shall raise a Contract Amendment in accordance with Step 7 of the procedure set out at Clause 41.3 above indicating formal approval for the Contractor to implement the change. A copy of the CCPF1 shall be retained by the Contractor.

  - The Contractor’s cost for supporting in the Contract Change Proposal Procedures specified at Clause 41.5 above are included in the Contract Price detailed at Schedule 4 (Pricing and Rates).

Pricing Of Contract Change Proposals

  - Contract amendment(s) resulting from a CCPF 1 submission shall not be issued until Firm prices have been agreed by the Authority’s nominated Commercial Officer. Such prices shall be based upon the Contract Rates set out to Schedule 4 to this Contract.

  - In exceptional circumstances, where the Authority requires urgent action to be taken provisional prices for change may be set in accordance with DEFCON 643 (Price Fixing). Such provisional prices shall be based upon the Contract rates set out to Schedule 4 (Pricing and Rates) to this Contract.

  - Where the change has a sub-Contract element the Firm price proposed for that element on the CCPF 1 shall be equal to the sum of the quotation from the sub-Contractor plus the agreed Contractor’s rates detailed at Schedule 4 (Pricing and Rates) to this Contract.

Gainshare Proposals

  - Should either the Authority or the Contractor propose a Change to the Contract which shall result in a benefit to the Authority, the CCPF1 shall be completed with full details of the proposed benefit that would accrue to the Authority in approving the implementation of such a change. The CCPF 1 shall also include the Contractor’s proposal for sharing of any resultant financial benefit or increase in Contract price based on the net effect of such a change.

  - In such cases the Contract Change Procedure detailed at Clause 41.3 shall be followed and the Parties shall consider whether the proposed change should be implemented. If approved, the sharing arrangements and method of payment shall be agreed on a case by case basis.

General

  - The Authority shall not accept liability for any costs or charges incurred other than in accordance with this Contract including tasks properly raised and authorised in accordance with the procedures herein. This Contract may only be changed by the Contractor’s acceptance of a written amendment issued after a change has been proposed and evaluated by following the procedures of the Contract Change Proposal (CCP) Form, Schedule 22 to the Contract.

- Commonality of Equipment and Systems

  - The Contractor shall ensure that all Boats ordered under this Contract are fitted with the same equipment and systems, unless such equipment and/or systems are no longer available. In the event that commonality of equipment and/or systems is not possible the Contractor shall immediately notify and seek approval from the Authority, providing details of the proposed replacement equipment and/or systems. Notwithstanding approval by the Authority, the Contractor shall ensure that any such replacement equipment and/or system is of the same (or better) quality and performance levels as required under this Contract.

- Replacement of Obsolescent Parts and Equipment

  - The Contractor shall be responsible for correctly specifying all material to be incorporated into the Boat, including the replacement of obsolescent parts and equipment and maintaining up-to-date records of equipment variants fitted in each Boat. The Contractor shall be required to provide assurance to the Authority that replacement parts and equipment where different from those originally fitted will not affect the Boats fitness for purpose in its intended role. The Contractor shall also obtain certification from the relevant certification society for replacement parts or equipment where required.

- Liquidated Damages

  - This Clause shall apply to the Acceptance of the Boat off Contract. For the avoidance of doubt, this Clause 44 shall not apply to deliveries of the In Service Support requirements.

  - It is recognised by the Parties that if the Contractor fails to deliver any of the Articles by the date(s) specified in the delivery schedule at Table 2 of Schedule 4 (Pricing and Rates), the Authority will suffer loss and damage.

  - Accordingly, for each day’s delay (including bank holidays and weekends) the Contractor shall pay the Authority REDACTED up to a maximum of REDACTED as Liquidated Damages. The Parties confirm that this sum represents a genuine pre-estimate of the Authority’s loss.

  - The provisions of this Clause are without prejudice to any other rights of the Authority under the Contract, including but not limited to those under DEFCON 514 (Material Breach). Accordingly, in the event that the Authority terminates the Contract, Liquidated Damages shall be payable under Clause44.3 above until the date of such termination.

  - Unless expressly stated by the Authority in writing, the provisions of DEFCON 527 (Waiver) shall apply to the Authority’s right to recover Liquidated Damages under this Clause.

- Permissible Delays

  - The Contractor shall notify the Authority in writing within five (5) Days of the occurrence of a Force Majeure Event or Delay Event and may request in writing an extension to the Required Delivery Date in accordance with Clause 45.2 provided that:

    - any Delay Event:

      - was not caused by the error, neglect, act or omission of the Contractor or its Sub-Contractors; and

      - could not reasonably have been, foreseen by the Contractor at the date of the Contract; and

      - the Contractor shall have made all reasonable efforts to avoid and mitigate the effects such Force Majeure Event or Delay Event has on the delivery of the Boat.

  - A request for an extension of time to the Required Delivery Date shall be submitted by the Contractor to the Authority within ten (10) Days of the occurrence of the Force Majeure Event or Delay Event and shall include:

    - the cause and extent of the delay;

    - a statement on the effect the event has, or will have on the critical programme path of the Boat has or will be delayed;

    - those contractual obligations which have been affected by the delay;

    - proposals for mitigating the delay, including alternative arrangements.

  - A failure of the Contractor to notify the Authority in accordance with Clauses 45.1 and 45.2 shall prevent the Contractor from claiming an extension to the Required Delivery Date.

  - The Contractor shall:

    - advise the Authority immediately in writing that the Force Majeure Event or Delay Event has ended; and

    - as soon as reasonably practicable thereafter, and no later than fifteen (15) Days after the end of the Force Majeure Event or Delay Event, submit in writing details of the length of extension to the Required Delivery Date claimed including evidence that the critical path of the Boat has been delayed.

  - Any extension of time granted or rejected by the Authority pursuant to this Clause 45 shall be fair and reasonable. For the avoidance of doubt the Authority shall have a right to grant an extension to the Required Delivery Date irrespective of any claim by the Contractor.

  - For the avoidance of doubt, any act or omission of the Authority causing a Delay Event to a Boat shall not necessarily be a Delay Event in respect of any subsequent Boats.

- Termination For A Permissible Delay

  - If a Permissible Delay is continuing, or its consequence remains such that the affected Party is unable to comply with its obligations under this Contract, for a period of more than one hundred and twenty (120) Days, then either Party may (subject to Clause 46.2 below) terminate this Contract or part thereof by serving upon the other Party a Termination Notice stating that:

    - It is terminating the Contract pursuant to Clause 46 and

    - The Contract shall terminate on the day falling fifteen (15) days after the date of the Termination Notice.

  - If the Termination Notice has been served by the Contractor the Authority may elect to require the Contract or part thereof to continue by serving the Contractor with written notice of such and the Parties shall agree a fair and reasonable adjustment in accordance with Clause 41 (Changes to the Contract) - Changes Initiated by the Authority. The Contract or part thereof shall not terminate until the earlier of:

    - any applicable date for the termination or expiry of this Contract set out in Clause 10 (Contract Period); and

    - the expiry of any subsequent written notice (of at least thirty (30) Days) from the Authority to the Contractor that it wishes this Contract to terminate.

  - Subject to Clause 46.2 above the Contract shall terminate upon the expiry of fifteen (15) Days from the date of the Termination Notice.

- Take Over/Tow-Out Option

  - The Authority shall, within fifteen (15) days after termination of this Contract in accordance with DEFCON 514 (Material Breach) or Clause 46 (Termination for a Permissible Delay), have the right to elect to take possession of the Boat, documentation and other deliverables in their current state and to:

    - complete such work as be necessary in order to remove the Boat, documentation and other deliverables from the Contractors Premises or the premises of a sub-contractor, using the premises, labour, plant, machinery and equipment of the Contractor or sub-contractor (at the Contractor’s risk); and

    - remove the Boat, documentation and other deliverables from the Contractors Premises or the premises of a sub-contractor in order to complete the Boat elsewhere in accordance with this Contract.

    - upon giving prior written notice of such to the Contractor.

  - In the event that the Contract is terminated in accordance with DEFCON 514 (Material Breach) all reasonable costs and expenses incurred by the Authority in exercising its rights in accordance with Clause 47.1 and completing the Boat elsewhere shall be deducted from any outstanding payments to be made to the Contractor if the same be sufficient and if the same is not sufficient shall be made good by the Contractor on demand.

  - This Clause shall not apply if the Contractor has commenced action under DEFCON 530 (Dispute Resolution) at any time prior to the Authority exercising its rights in accordance with Clause 47.1.

- Financial Consequences of Termination

Termination for Contractor Default

  - Where the Authority has terminated this Contract pursuant to DEFCON 514 (Material Breach) the Contractor shall, in respect of any Boats that have not been Accepted Off Contract, but terminated by the Authority, promptly refund to the Authority the full amount of sums paid by the Authority to the Contractor under Clause 12 (Payment).

  - Where the Authority has exercised its right to Take Over/Tow-Out Option in accordance with Clause 47, the Authority shall not be entitled to a refund in accordance with Clause 48.1 and the financial consequences shall be dealt with in accordance with Clause 48.

  - Notwithstanding the refund of instalment payments in accordance with Clause 48.1, the Authority may elect to pay the Contractor for some or all of the Contractor Deliverables at prices to be agreed by the Parties.

  - Where the Authority is entitled to terminate this Contract pursuant to DEFCON 520 (Corrupt Gifts and Payments of Commission), the Authority shall, in addition to its rights set out in Clause 48.1 above (but without any double-counting) be entitled to:

    - recover from the Contractor the amount of any loss resulting from such termination;

    - where this Clause 48.4 applies but this Contract has not been terminated, to recover from the Contractor any other loss sustained as a result of such breach,

and any recovery action taken against any UK Government employee shall be without prejudice to any recovery action taken against the Contractor pursuant to this Clause.

Break

  - Where this Contract is terminated pursuant to DEFCON 656B (Break), then in addition to the provisions of DEFCON 656B, the provisions of Clause 48.6 below shall also apply.

  - The Authority shall not be liable under DEFCON 656B (Break) to pay any sum which;

    - would be claimable under any insurance held (or required to be held) by the Contractor, but for the fact that the Contractor has failed to make a claim on its insurance, or has failed to make a claim in accordance with the procedural requirements of the insurance policy, or has failed to take out or maintain any insurance that it is required to take out and/or maintain; or

    - When added to any sums already paid or due to the Contractor under this Contract, exceeds the total sum that would have been payable to the Contractor if this Contract had not been terminated pursuant to DEFCON 656B (Break).

Termination for a Permissible Delay

  - Where this Contract is terminated pursuant to Clause 46 (Termination for a Permissible Delay), the provisions of Clauses 48.8 to 48.10 below shall apply.

  - Subject to Clause 48.9 below, where the Contract has been determined in accordance with Clause 46 (Termination for a Permissible Delay) the Contractor shall promptly refund to the Authority the full amount of sums paid by the Authority to the Contractor under Clause 12 (Payment).

  - The Contractor shall only be entitled to be paid from the sums refunded to the Authority in accordance with Clause 48.8 for any aspect of the Contractor Deliverables that it has, as at the Termination Date, delivered to the Authority in accordance with the Contract (subject to any other provisions of this Contract affecting the level of such payment).

  - The Authority shall not be entitled to a refund under Clause 48.8 above where:

    - the permissible delay is caused entirely by an act or omission of the Authority; or

    - the Authority has exercised its right to Take Over/Tow-Out in accordance with Clause 47.1 above.

Miscellaneous Provisions

  - Each Party shall pay to the other any amounts payable pursuant to Clause 48 within twenty (20) Business Days of the Termination Date (or, if later, within twenty (20) Business Days of the amount being identified by both Parties as being payable, where it was not possible to determine on the Termination Date that such amount was payable).

  - Any payment made by the Authority to the Contractor or by the Contractor to the Authority, pursuant to this Clause 48 shall be in full satisfaction of the liability of the paying Party and shall be the sole remedy of the receiving Party in relation to this Clause 48.

- Major Incident Inquiries

  - If any Major Incident occurs the Contractor shall, as soon as possible and upon notice to the Authority, convene and conduct a formal enquiry under the chairmanship of a director of the Contractor to establish the causes of the incident and, where appropriate, recommend remedial action to prevent any recurrence of the Major Incident.

  - The requirement of Clause 49.1 shall be without prejudice to any inquiry by the relevant national health and safety regulatory body, as required by law, and in the event that any such Inquiry is convened the Contractor shall:

    - give notice of the inquiry to the Authority as soon as reasonably practicable;

    - to the extent lawful and practicable secure for the Authority the right to attend and to be represented at the inquiry;

  - The Authority shall have the right to appoint representatives to attend the Major Incident Inquiry in any of the following capacities:

    - as members of the Major Incident Inquiry board;

    - in an advisory capacity;

    - to question witnesses.

  - The presence of such representatives of the Authority shall be without prejudice to the Authority's right to accept or reject the findings and recommendations of the Major Incident Inquiry board.

  - A full report of the Major Incident Inquiry signed by all members of the board shall be forwarded to the Authority and shall include:

    - a summary of the proceedings;

    - evidence of any witnesses, together with copies of any sketches or diagrams which may have been produced;

    - details of any difference of opinion between the board members on any material point;

    - the conclusions and recommendations of the board.

  - Any Major Incident Inquiry shall not deliberate on adjustments to the Contract and shall be without prejudice to the rights and remedies of the Parties, under the Contract or otherwise, in respect of any loss or damage arising from any such incident.

  - Notwithstanding anything in this Clause 49, in certain circumstances the Authority may wish to conduct an inquiry itself; in which case the Authority shall have the right to require the Contractor, or any person in his employ, to attend the inquiry in any capacity.

  - If the Contractor proposes to call representatives of the Authority to the Major Incident Inquiry either to give evidence or for any other purpose, prior approval shall be sought from the Authority’s Authorised Representative.

- Jigs and Tools

  - The Contractor shall provide Jigs and Tools.

  - The Contractor shall advise the Authority in writing within three (3) Months of Contract award of any Special Jigs and Tools required for the purposes of this Contract.

  - Save as provided in Clause 50.8, the cost of all Jigs and Tools and Special Jigs and Tools including the cost of maintenance and calibration is included in the Contract Price. The Contractor shall not claim assistance from other UK Government funds towards the cost of any Special Jigs and Tools.

  - Special Jigs and Tools shall be the absolute property of the Authority.

  - Neither the Contractor, nor a Sub-Contractor, nor any other person shall have a lien on the Special Jigs and Tools for any sum due to the Contractor, Sub-Contractor or any other person. The Contractor shall take all reasonable steps necessary to ensure that the provisions of this clause are brought to the notice of all Sub-Contractors and other persons dealing with any Special Jigs and Tools.

  - Save as provided in this Clause 50, Special Jigs and Tools shall be treated as Government Furnished Equipment in accordance with Clause 26 (GFE).

  - The Contractor shall be free to modify the Special Jigs and Tools as he may deem to be necessary in order to perform the Contract and the Authority's approval of such modifications shall not be required.

  - In the event that any Special Jigs and Tools are required by the Contractor for installation of Government Furnished Equipment, the Authority shall provide these to the Contractor free of charge. The Contractor shall be responsible for the cost of maintenance and calibration of Special Jigs and Tools provided under this Clause 50.8.

  - The Contractor shall not use the Special Jigs and Tools for any purposes other than those of the Authority without first obtaining the written approval of the Authority which may be conditional upon the Parties agreeing terms for commercial exploitation of the Special Jigs and Tools.

- Inspection, Tests and Trials

General

  - The Contractor shall undertake inspections, tests and trials in accordance with the requirements specified in Annex I of Schedule 6 (Integrated Project Management Plan). All inspection, tests, trials and rectification of defects arising must be completed prior to the Contractor offering up the Boat for Acceptance by the Authority.

  - The programme for undertaking such inspections, tests and trials shall be agreed between the Contractor and the Authority and the Contractor shall ensure that inspections, tests and trials are not fragmented.

  - The Contractor shall be solely responsible for conducting all inspections, tests and trials and for co-ordinating their requirements and those of his Sub-Contractors.

  - The Contractor shall confirm in writing to the Authority’s Authorised Officer five (5) working days before an inspection test or trial is to take place, or such other period if specified in the Contract, that:

    - the Boat or equipment or system will be ready; and

    - all pre-requisites for the trial will be met.

  - The Authority’s Authorised Officer will arrange for the attendance of the Authority’s inspection, test and trials team as required and will also advise the Contractor where he considers that all pre-requisites are not being met. In the event that written confirmation is not received by the Authority five (5) working days, or such other period as agreed between the Parties, prior to an inspection, test or trial taking place or where the Authority is not satisfied that all pre-requisites are being met, the Authority’s personnel will not attend the inspection, test or trial. In these circumstances the Contractor shall be liable for all costs.

  - The Authority will, at its discretion, have the right to:

    - postpone any or all inspections, tests or trials;

    - keep the Boat at sea for such periods as necessary;

    - require the Boat to proceed to sea for extra trials or for any other purpose not specified in the Contract;

    - and will reimburse the Contractor for any reasonable costs thereby incurred, except where the events in Clauses 51.6.1 to 51.6.3 above is due to error, breach, omission or negligence on part of the Contractor.

Additional Contractor Inspections, Tests and Trials

  - Any additional inspections, tests and trials which the Contractor wishes to carry out prior to the Contractor offering up the Boat for Acceptance by the Authority, shall be the responsibility and liability of the Contractor.

Inspection and Trials Teams

  - Where the Authority appoints personnel to attend inspections, tests and trials on behalf of the Authority, the presence of these personnel shall not in any way relieve the Contractor of his responsibilities under the Contract.

  - In the event that any inspection, test or trial or part thereof, undertaken by the Contractor has to be repeated for any reason, including but not limited to all pre-requisites or requirements not being met, and for which the Contractor is responsible, the Contractor shall re-programme or re-run the inspection, test or trial. In these circumstances the Contractor shall be liable for all costs, including reimbursement of the Authority’s reasonable costs.

  - Without prejudice to the Contractor's responsibilities, the Authority will, if so requested and subject to availability, provide staff to carry out under the Contractor's orders, and acting as unpaid servants of the Contractor, duties for which specialised knowledge is required. Nothing in this Clause 51 shall extinguish, diminish or reduce the Contractor's responsibilities for inspections, tests or trials in accordance with the Contract.

Sea Trials

  - Unless otherwise agreed between the Authority and the Contractor, the Contractor shall take command of the Boat(s) for sea trials. During all sea trials, whether Boat(s) are under the control of the Contractor or the Authority, the Contractor shall be fully responsible for the care and custody of the Boat(s). The Contractor shall liaise with the Authority’s Authorised Officer on matters of Boat(s) safety.

  - Arrangements for Contractor's and Sub-Contractors' representatives attending sea trials shall be agreed between the Contractor and the Authority’s Authorised Officer whose decision on numbers attending shall be final.

  - On satisfactory completion of sea trials, the Contractor shall complete Schedule 15 (Boat Sea Trial Form) and present to the Authority with all other deliverables required on Acceptance Off Contract.

- Acceptance

New Build

  - Acceptance of the Boat Off Contract shall be in accordance with the provisions set out in Annex I (Test, Evaluation & Acceptance Plan) of Schedule 6 (Integrated Project Management Plan).

  - Immediately prior to Acceptance Off Contract the Contractor shall complete and present to the Authority for review the Acceptance Form (Schedule 13a for First of Class, and Schedule 13b for subsequent Boats) together with all other deliverables required prior to acceptance in accordance with Schedule 2 (Statement of Technical Requirements). The Contractor shall record on Schedule 13 all outstanding items which shall be completed/rectified at the Contractors expense within five (5) days of the Boat being presented for Acceptance Off Contract.

  - Subject to the Authority being satisfied that the Boat has met the condition for Acceptance Off Contract, the Authority will sign the Acceptance Form (Schedule 13a for First of Class, and Schedule 13b for subsequent Boats).

  - Following Acceptance Off Contract, the Authority reserves the right to retain the Boat at the Contractor’s Premises for a period of up to thirty (30) Calendar days at the Contractor’s expense. Whilst the Boat is at the Contractor’s Premises following Acceptance Off Contract the Contractor shall be responsible for Care and Protection of the Boat in accordance with Clause 34 (Care and Protection).

In-Service

  - The Contractor shall, on completion of all work specified in the applicable TAF (including but not limited to authorised Emergent and Additional Tasks, Harbour Acceptance or Sea Acceptance Trials and final cleaning) detail the work completed by completing Part H of the applicable TAF.

  - The Contractor shall give the Authority a minimum five (5) working days’ notice to attend and/or be represented at the Sea Acceptance Trial and/or final inspection and acceptance. Any attendance at these events will be at the Authority’s discretion.

  - If the Authority is satisfied that the work is complete in all respects, the Authority will accept the Boat by signing Part [insert Part No] of the Acceptance Form (Schedule 13c).

  - In the event that the Authority is not satisfied that the work is complete in all respects, the Authority will advise the Contractor of the reasons for the rejection. The Contractor shall advise the Authority of the date when the Boats will be re-presented to the Authority for acceptance in accordance with Clause 52.5 above.

  - Notwithstanding the provisions of Clause 30 (Guarantee), the Authority’s signature of acceptance on Part [insert Part No] of the Acceptance Form (Schedule 14c) will be without prejudice to the Authority’s rights in respect of any defects in the work which in the reasonable opinion of the Authority:

    - were not apparent to the Authority during tests or trials or when the Boat was presented by the Contractor to the Authority for acceptance; or

    - only became apparent following acceptance by the Authority.

- Import and Export of Boats and/or any Associated Equipment or Spares

  - In the event the Contractor, with the agreement of the Authority, takes the decision to transport a Boat, and/or any associated equipment or spares into or out of the UK the Contractor shall be responsible for all the relevant custom formalities. In these circumstances the Contractor shall be liable for all costs.

- Fuels, Lubricants and Hydraulic Fluids (In Service Support Only)

  - Where specified in a TAF the Authority will provide the Contractor, on a free issue basis, with fuels, lubricating oils and hydraulic fluids (but not greases) required for the purposes of setting to work and trials. In such circumstances the Contractor shall provide early notification to the Authority of his requirements for fuels, lubricating oils and hydraulic fluids (but not greases) to enable the Authority to make delivery and for the Contractor to complete all work required under the TAF by the Authority’s Required Delivery Date.

  - Upon receipt of the fuels, lubricating oils and hydraulic fluids from the Authority the Contractor shall ensure suitable and safe storage.

  - In the event that it is necessary for the Contractor to undertake repetition of any tests or trials, due to a failure of the Contractor, the Contractor shall be liable for the cost of the fuels, lubricating oils and hydraulic fluids consumed during such additional tests and trials. Where the Authority provides fuels, lubricating oils and hydraulic fluids, the costs will be charged to the Contractor by the Authority at the rates current at the date of consumption.

- Insurance

  - Without prejudice to its liability to indemnify or otherwise be liable to the Authority under this Contract, the Contractor shall for the periods specified in Schedule 20 (Insurance) take out and maintain, or procure the taking out and maintenance of, the insurances described in Schedule 20 (Insurance) and any other insurances as may be required by law or relevant regulation (together the “Required Insurances”). The Contractor shall ensure that each of the Required Insurances is effective in each case not later than the date on which the relevant risk commences.

  - The Required Insurances shall be maintained from time to time (as far as is reasonably practicable) on terms no less favourable to those generally available to a prudent contractor in respect of risks insured in the international insurance market from time to time.

  - The Required Insurances shall be taken out and maintained with insurers who are of good financial standing and of good repute in the international insurance market.

  - Where specified in Schedule 20 (Insurance) the Contractor shall ensure that the relevant policy of insurance:

    - shall contain an indemnity to principals clause under which the Authority shall be indemnified in respect of claims made against the Authority arising from death or bodily injury or third party property damage, and for which the Contractor is legally liable in the provision of the services under this Contract;

    - names the Authority as an insured party in respect of its separate interests.

  - Without limiting the other provisions of this Contract, the Contractor shall take or procure the taking of all reasonable risk management and risk control measures in relation to the requirements of this Contract as it would be reasonable to expect of a prudent Contractor acting in accordance with good industry practice including, but not limited to, the investigation and reporting of claims to insurers.

  - No party shall take any action or fail to take any action or, insofar as is reasonably within its power, permit anything to occur in relation to it which would entitle any insurer to refuse to pay any claim under any of the Required Insurances.

  - If the Contractor is in breach of Clause 55.1 the Authority may elect, but shall not be obliged, to purchase any insurance which the Contractor is required to maintain pursuant to this Contract but has failed to maintain in full force and effect, and the Authority shall be entitled to recover the premium and other reasonable costs incurred in connection therewith as a debt due from the Contractor.

  - The Contractor shall, from the date of this Contract and within fifteen (15) days after the renewal of any of the Required Insurances, provide evidence, in a form satisfactory to the Authority, that the Required Insurances meet in full the requirements of this Clause 55 (Insurance) and Schedule 20 (Insurance). The supply to the Authority of any evidence of insurance cover in compliance with the requirements of this Clause 55 shall not imply acceptance by the Authority that the extent of insurance cover is sufficient or that the terms and conditions thereof are satisfactory, in either case, for the purposes of this Contract.

  - The Contractor shall hold all policies in respect of the Required Insurances and cause any insurance broker effecting the Required Insurances to hold any insurance slips and other evidence of placing cover representing any of the Required Insurances to which it is a part and for which it is responsible under this Contract.

  - The Contractor shall promptly notify to insurers any matter arising from, or in relation to, this Contract for which it may be entitled to claim under any of the Required Insurances. In the event that the Authority receives a claim relating to this Contract, the Contractor shall co-operate with the Authority and assist it in dealing with such claims including without limitation providing information and documentation in a timely manner.

  - Except where the Authority is the claimant party, the Contractor shall give the Authority notice within twenty (20) days after any insurance claim in excess of REDACTED relating to this Contract on any of the Required Insurances or which, but for the application of the applicable policy excess, would be made on any of the Required Insurances and (if required by the Authority) full details of the incident giving rise to the claim.

  - Where any Required Insurance requires payment of a premium, the Contractor shall be liable for such premium, including any increase in premium.

  - Where any Required Insurance referred to in Schedule 20 (Insurance) is subject to an excess or deductible, below which the indemnity from insurers is excluded, the Contractor shall be liable for such excess or deductible which would otherwise be insured but for the excess or deductible. The Contractor shall not be entitled to recover from the Authority any sum paid by way of excess or deductible under the Required Insurances whether under the terms of this Contract or otherwise.

  - Neither failure to comply nor full compliance with the insurance provisions of this Contract shall limit or relieve the Contractor of its liabilities and obligations under this Contract.

- Sustainable Procurement

  - The Contractor shall take all reasonable steps to procure the observance of the economic, social and environmental legislation related to the subject matter or the execution of the Contract by any servants, employees or agents of the Contractor and any Sub-Contractors engaged in the performance of the Contract.

  - If the Contractor becomes aware of any potential or actual prosecution or proceedings, for criminal breaches of the economic, social and environmental legislation related to the subject matter or the execution of the Contract, against the Contractor, any servants, employees or agents of the Contractor and any Sub-Contractors engaged in performance of the Contract, the Contractor shall immediately notify the Authority at the address specified in the Contract.

  - Any convictions during the period of the Contract for criminal breaches of the economic, social and environmental legislation related to the subject matter or the execution of the Contract by the Contractor or any of the Contractor’s directors/partners or senior management who have powers of representation, decision or control, shall be regarded as a material breach of this Contract.

  - A sustainable procurement plan is not required for the purposes of this Contract.

- Compatibility With Authority Systems

  - The Contractor shall ensure that all documents required for this Contract including but not limited to plans, drawings, report, forms and logs are supplied in the English Language (UK) using both the Oxford English Dictionary and the principles of the Simplified Technical English (STE) Dictionary.

  - The Contractor shall ensure that all Notices and Deliverable Drawings and Documents are provided in, or shall be fully compatible with, the following applications:

    - MS Office 2010 applications (MS Word, MS Excel, MS PowerPoint, MS Outlook, MS Project)

    - Microsoft Office SharePoint portal Server 2007

    - Adobe Acrobat Reader vXI

    - Drawings (both formats to be provided for all drawings)

    - Autodesk AutoCAD Drawing (*dwg), DWF (available on AutoCAD v2004+);

    - PDF format that permits a word-based search function.

    - Active Risk Manager 5.1 by Strategic Thought Ltd, Release 5.1.1606 update 07 (or an alternative agreed with the Authority)

    - Telelogic DOORS® 9.5 (or an alternative agreed with the Authority)

  - In transferring information to the Authority, the Contractor shall:

    - ensure that all information is marked/classified in accordance with the Contract terms and conditions for data security and the security aspects letter.

    - ensure that all electronic information is free from viruses and malware.

    - ensure that e-mails do not exceed 8Mb in size (electronic files larger than 8Mb or MS Access files shall be sent to the Authority on CD or DVD).

    - not use memory sticks.

- Transfer Regulations – (Transfer of Undertakings (Protection of Employment) Regulations)

  - The Contractor shall comply with the provisions of Schedule 21 (Transfer Regulations)

- Public Relations and Publicity

  - The Contractor shall not by itself, its employees or agents, and shall procure that its Sub-Contractors shall not:

    - communicate with representatives of the press, television, radio or other communications media or members of the public on any matter concerning this Contract;

    - photograph or film in or upon any Authority Sites;

    - erect or exhibit on any part of the Authority Sites any signs or trade boards; or exhibit or attach to any part of the Authority Sites any notice or advertisement, unless the Authority has given its prior written consent or as otherwise required to comply with Legislation.

- Exit

  - On termination of the Contract or a TAF, and at any time and for whatever reason, the Authority shall not be liable for any additional costs, other than where the Authority is liable under the Contract, for the hand-over by the Contractor to any successor Contractor or to the Authority of all data as may exist in the Contractor’s possession at the time of termination of the Contract or TAF, and as relevant to the performance of the work by that successor Contractor or the Authority.

  - To provide for the possible hand-over to another Contractor on termination of the Contract, or transfer back of responsibility for the work to the Authority, throughout the duration of the Contract, the Contractor shall maintain records, including an IPR register, in a manner suitable to facilitate such a hand-over.

  - The Authority’s minimum requirement is that, subject to the ownership of the hardware and Intellectual Property Rights/Free User Rights vesting with the Authority, the records required by the Authority are as set out in Annex G to the Integrated Project Management Plan (Schedule 6). The records shall be maintained by the Contractor in a manner that the Contractor would expect them to be maintained in were the Contractor to be a successor Contractor unfamiliar with the requirements.

- OFFICIAL and OFFICIAL- SENSITIVE Security Condition for UK Contracts

Definitions

  - The term "Authority" means a Ministry of Defence (MOD) official acting on behalf of the Secretary of State for Defence.

Security Grading

  - REDACTED

Official Secrets Acts

  - The Contractor's attention is drawn to the provisions of the Official Secrets Acts 1911-1989 in general, and to the provisions of Section 2 of the Official Secrets Act 1911 (as amended by the Act of 1989) in particular. The Contractor shall take all reasonable steps to make sure that all individuals employed on any work in connection with the Contract (including sub-contractors) have notice that these statutory provisions, or any others provided by the Authority, apply to them and shall continue so to apply after the completion or earlier termination of the Contract.

Protection of OFFICIAL and OFFICIAL- SENSITIVE Information

  - The Contractor shall protect OFFICIAL and OFFICIAL-SENSITIVE information provided to it or generated by it in accordance with the requirements detailed in this Security Condition and any other conditions that may be specified by the Authority. The Contractor shall take all reasonable steps to prevent the loss or compromise of the information or from deliberate or opportunist attack.

  - The contractor shall apply Industry Security Notice (ISN) 2017/01 requirements to every industry owned IT and communication system used to store, process or generate MOD information including those systems containing OFFICIAL and/or OFFICIAL-SENSITIVE information. ISN 2017/01 details Defence Assurance and Risk Tool (DART) registration, IT security accreditation processes, risk assessment and risk management requirements. The ISN is available at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/594320/DART_ISN_-_V2_3.pdf

  - OFFICIAL and OFFICIAL-SENSITIVE information shall be protected in a manner to avoid unauthorised access. The Contractor shall take all reasonable steps to prevent the loss, compromise or inappropriate access of the information or from deliberate or opportunist attack.

  - All OFFICIAL and OFFICIAL-SENSITIVE material including documents, media and other material shall be physically secured to prevent unauthorised access. When not in use OFFICIAL and OFFICIAL- SENSITIVE documents/material shall be handled with care. As a minimum, when not in use, OFFICIAL-SENSITIVE material shall be stored under lock and key and in a lockable room, cabinets, drawers or safe and the keys/combinations are themselves to be subject to a level of physical security and control.

  - Disclosure of OFFICIAL and OFFICIAL-SENSITIVE information shall be strictly in accordance with the "need to know" principle. Except with the written consent of the Authority, the Contractor shall not disclose any of the classified aspects of the Contract detailed in the Security Aspects Letter other than to a person directly employed by the Contractor or sub-Contractor, or Service Provider.

  - Any samples, patterns, specifications, plans, drawings or any other documents issued by or on behalf of the Authority for the purposes of the Contract remain the property of the Authority and shall be returned on completion of the Contract or, if directed by the Authority, destroyed in accordance with paragraph 32.

Access

  - Access to OFFICIAL and OFFICIAL-SENSITIVE information shall be confined to those individuals who have a “need-to-know”, have been made aware of the requirement to protect the information and whose access is essential for the purpose of his or her duties.

  - The Contractor shall ensure that all individuals having access to OFFICIAL-SENSITIVE information have undergone basic recruitment checks. Contractors shall apply the requirements of HMG Baseline Personnel Security Standard (BPSS) for all individuals having access to OFFICIAL-SENSITIVE information. Further details and the full requirements of the BPSS can be found at the Gov.UK website at:

https://www.gov.uk/government/publications/government-baseline-personnel-security-standard.

Hard Copy Distribution

  - OFFICIAL and OFFICIAL-SENSITIVE documents shall be distributed, both within and outside company premises in such a way as to make sure that no unauthorised person has access. It may be sent by ordinary post or Commercial Couriers in a single envelope. The words OFFICIAL or OFFICIAL-SENSITIVE shall not appear on the envelope. The envelope should bear a stamp or details that clearly indicates the full address of the office from which it was sent.

  - Advice on the distribution of OFFICIAL-SENSITIVE documents abroad or any other general advice including the distribution of OFFICIAL-SENSITIVE hardware shall be sought from the Authority.

Electronic Communication, Telephony and Facsimile Services

  - OFFICIAL information may be emailed unencrypted over the internet. OFFICIAL-SENSITIVE information shall normally only be transmitted over the internet encrypted using either a CESG Commercial Product Assurance (CPA) cryptographic product or a MOD approved cryptographic technique such as Transmission Layer Security (TLS). In the case of TLS both the sender and recipient organisations must have TLS enabled. Details of the required TLS implementation are available at:

https://www.ncsc.gov.uk/guidance/tls-external-facing-services

Details of the CPA scheme are available at:

https://www.ncsc.gov.uk/scheme/commercial-product-assurance-cpa

Exceptionally, in urgent cases, OFFICIAL-SENSITIVE information may be emailed unencrypted over the internet where there is a strong business need to do so and only with the prior approval of the Authority.

  - OFFICIAL-SENSITIVE information shall only be sent when it is known that the recipient has been made aware of and can comply with the requirements of these Security Conditions and subject to any explicit limitations that the authority shall require. Such limitations, including any regarding publication, further circulation or other handling instructions shall be clearly identified in the email sent with the material.

  - OFFICIAL information may be discussed on fixed and mobile telephones with persons located both within the UK and overseas. OFFICIAL-SENSITIVE information may be discussed on fixed and mobile types of telephone within the UK, but not within earshot of unauthorised persons.

  - OFFICIAL information may be faxed to recipients located both within the UK and overseas, however OFFICIAL-SENSITIVE information may be faxed only to UK recipients.

Use of Information Systems

  - The detailed functions that must be provided by an IT system to satisfy the minimum requirements cannot all be described here; it is for the implementers to identify possible means of attack and ensure proportionate security mitigations are applied to prevent a successful attack.

  - The contractor shall ensure 10 Steps to Cyber Security is applied in a proportionate manner for each IT and communications system storing, processing or generating MOD UK OFFICIAL or OFFICIAL-SENSITIVE information. 10 Steps to Cyber Security is available at:

https://www.ncsc.gov.uk/guidance/10-steps-cyber-security

The contractor shall ensure competent personnel apply 10 Steps to Cyber Security.

  - As a general rule, any communication path between an unauthorised user and the data can be used to carry out an attack on the system or be used to compromise or ex-filtrate data.

  - Within the framework of the 10 Steps to Cyber Security, the following describes the minimum security requirements for processing and accessing OFFICIAL-SENSITIVE information on IT systems.

    - Access Physical access to all hardware elements of the IT system is to be strictly controlled. The principle of “least privilege” will be applied to System Administrators. Users of the IT System -Administrators should not conduct ‘standard’ User functions using their privileged accounts.

    - Identification and Authentication (ID&A). All systems shall have the following functionality:

      - Up-to-date lists of authorised users.

      - Positive identification of all users at the start of each processing session.

    - Passwords. Passwords are part of most ID&A, Security Measures. Passwords shall be ‘strong’ using an appropriate method to achieve this, for example including numeric and “special” characters (if permitted by the system) as well as alphabetic characters.

    - Internal Access Control. All systems shall have internal Access Controls to prevent unauthorised users from accessing or modifying the data.

    - Data Transmission. Unless the Authority authorises otherwise, OFFICIAL- SENSITIVE information shall be transmitted or accessed electronically (e.g. point to point computer links) via a public network like the Internet, using a CPA product or equivalent as described in paragraph 13 above,

    - Security Accounting and Audit. Security relevant events fall into two categories, namely legitimate events and violations.

      - The following events shall always be recorded:

        - All log on attempts whether successful or failed,

        - Log off (including time out where applicable),

        - The creation, deletion or alteration of access rights and privileges,

        - The creation, deletion or alteration of passwords,

      - For each of the events listed above, the following information is to be recorded:

        - Type of event,

        - User ID,

        - Date & Time,

        - Device ID, The accounting records shall have a facility to provide the System Manager with a hard copy of all or selected activity. There shall also be a facility for the records to be printed in an easily readable form. All security records are to be inaccessible to users without a need to know. If the operating system is unable to provide this then the equipment shall be protected by physical means when not in use i.e. locked away or the hard drive removed and locked away.

    - Integrity & Availability. The following supporting measures shall be implemented:

      - Provide general protection against normally foreseeable accidents/mishaps and known recurrent problems (e.g. viruses and power supply variations),

      - Defined Business Contingency Plan,

      - Data backup with local storage,

      - Anti-Virus Software (Implementation, with updates, of an acceptable industry standard Anti-virus software),

      - Operating systems, applications and firmware should be supported,

      - Patching of Operating Systems and Applications used shall be in line with the manufacturers recommended schedule. If patches cannot be applied an understanding of the resulting risk will be documented,

    - Logon Banners Wherever possible, a “Logon Banner” shall be provided to summarise the requirements for access to a system which may be needed to institute legal action in case of any breach occurring. A suggested format for the text (depending on national legal requirements) could be:

“Unauthorised access to this computer system may constitute a criminal offence”

    - Unattended Terminals. Users are to be automatically logged off the system if their terminals have been inactive for some predetermined period of time, or systems must activate a password protected screen saver after 15 minutes of inactivity, to prevent an attacker making use of an unattended terminal.

    - Internet Connections. Computer systems shall not be connected direct to the Internet or ‘untrusted’ systems unless protected by a firewall (a software based personal firewall is the minimum but risk assessment and management must be used to identify whether this is sufficient).

    - Disposal Before IT storage media (e.g. disks) are disposed of, an erasure product shall be used to overwrite the data. This is a more thorough process than deletion of files, which does not remove the data.

Laptops

  - Laptops holding any MOD supplied or contractor generated OFFICIAL-SENSITIVE information are to be encrypted using a CPA product or equivalent as described in paragraph 14 above.

  - Unencrypted laptops not on a secure site are to be recalled and only used or stored in an appropriately secure location until further notice or until approved full encryption is installed. Where the encryption policy cannot be met, a Risk Balance Case that fully explains why the policy cannot be complied with and the mitigation plan, which should explain any limitations on the use of the system, is to be submitted to the Authority for consideration. Unencrypted laptops and drives containing personal data are not to be taken outside of secure sites. For the avoidance of doubt the term “drives” includes all removable, recordable media (e.g. memory sticks, compact flash, recordable optical media e.g. CDs and DVDs), floppy discs and external hard drives.

  - Any token, touch memory device or password(s) associated with the encryption package is to be kept separate from the machine whenever the machine is not in use, left unattended or in transit.

  - Portable CIS devices are not to be left unattended in any public location. They are not to be left unattended in any motor vehicles either in view or in the boot or luggage compartment at any time. When the vehicle is being driven the CIS is to be secured out of sight in the glove compartment, boot or luggage compartment as appropriate to deter opportunist theft.

Loss and Incident Reporting

  - The contractor shall immediately report any loss or otherwise compromise of any OFFICIAL or OFFICIAL-SENSITIVE information to the Authority.

  - Accordingly, in accordance with Industry Security Notice 2014/02 as may be subsequently updated at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/293480/ISN 2014_02_Incident_Reporting.pdf

any security incident involving any MOD owned, processed, or Contractor generated OFFICIAL or OFFICIAL-SENSITIVE information defined in the contract Security Aspects Letter shall be immediately reported to the MOD Defence Industry Warning, Advice and Reporting Point (WARP), within the Joint Security Co-ordination Centre (JSyCC). This will assist the JSyCC in formulating a formal information security reporting process and the management of any associated risks, impact analysis and upward reporting to the MOD’s Chief Information Officer (CIO) and, as appropriate, the company concerned. The MOD WARP will also advise the contractor what further action is required to be undertaken.

JSyCC WARP Contact Details

Email: For those with access to the RLI: REDACTED

Email: For those without access to the RLI: REDACTED

Telephone: Working Hours: REDACTED

Out of Hours/Duty Officer Phone: REDACTED

Fax: REDACTED

Mail: REDACTED

Sub-Contracts

  - The Contractor may Sub-contract any elements of this Contract to Sub-contractors within the United Kingdom notifying the Authority. When sub-contracting to a Sub-contractor located in the UK the Contractor shall ensure that these Security Conditions shall be incorporated within the Sub-contract document. The prior approval of the Authority shall be obtained should the Contractor wish to Sub-contract any OFFICIALSENSITIVE elements of the Contract to a Sub-contractor located in another country. The first page of Appendix 5 (MOD Form 1686 (F1686)) of the Security Policy Framework Contractual Process chapter is to be used for seeking such approval. The MOD Form 1686 can be found at Appendix 5 at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/367494/Contractual_Process_-_Appendix_5_form.doc.

If the Sub-contract is approved, the Authority shall provide the Contractor with the security conditions that shall be incorporated within the Sub-contract document. Chapter 2: Contract Security – Annex N

Publicity Material

  - Contractors wishing to release any publicity material or display hardware that arises from this contract shall seek the prior approval of the Authority. Publicity material includes open publication in the contractor’s publicity literature or website or through the media; displays at exhibitions in any country; lectures or symposia; scientific or technical papers, or any other occasion where members of the general public may have access to the information even if organised or sponsored by the MOD, Services or any other government department.

Private Venture

  - Any defence related Private Venture derived from the activities of this Contract are to be formally assessed by the Authority for determination of its appropriate classification. Contractors are to submit a definitive product specification for PV Security Grading in accordance with the requirement detailed at:

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/414857/20150310_PV_Ex_Guidance_Document.pdf

Promotions and Potential Export Sales

  - Contractors wishing to promote, demonstrate, sell or export any material that may lead to the release of information or equipment classified OFFICIAL-SENSITIVE (including classified tactics, training or doctrine related to an OFFICIAL-SENSITIVE equipment) are to obtain the prior approval of the Authority utilising the MOD Form 680 process, as identified at:

https://www.gov.uk/mod-f680-applications.

Destruction

  - As soon as no longer required, OFFICIAL and OFFICIAL-SENSITIVE information/material shall be destroyed in such a way as to make reconstitution unlikely, for example, by burning, shredding or tearing into small pieces. Advice shall be sought from the Authority when information/material cannot be destroyed or, unless already authorised by the Authority, when its retention is considered by the Contractor to be necessary or desirable. Unwanted OFFICIAL-SENSITIVE information/material which cannot be destroyed in such a way shall be returned to the Authority.

Interpretation/Guidance

  - Advice regarding the interpretation of the above requirements should be sought from the Authority.

  - Further requirements, advice and guidance for the protection of MOD information at the level of OFFICIAL-SENSITIVE may be found in Industry Security Notices at:

https://www.gov.uk/government/publications/industry-security-notices-isns.

Audit

  - Where considered necessary by the Authority, the Contractor shall provide evidence of compliance with this Security Condition and/or permit the inspection of the Contractors processes and facilities by representatives of the Authority to ensure compliance with these requirements.

- Intellectual Property Rights – Control of Material (Multi-Terrain Pattern)

  - The intellectual property (The Information) in the UK Multi-Terrain Pattern (MTP) camouflage design is owned by the Secretary of State for Defence of the United Kingdom of Great Britain and Northern Ireland who holds the Design Registration RCD 001627035-0001. The Contractor is not authorised to dispose of products, partial products or material incorporating the UK MTP that are not delivered to the Authority whether by sale, gift or free issue. All such products, partial products or material incorporating the UK MTP and not delivered to the Authority, other than those required by the Contractor for meeting its on-going obligations under the Contract, shall be destroyed and a record provided to the Authority on a quarterly basis.

  - The Contractor shall impose upon and procure of its supply chain the same conditions and obligations set out in Clause 62.1. above.

  - All Articles produced under this contract which incorporate the UK MTP design shall incorporate on the Article label the following wording “Camouflage Pattern Registered Design No. RCD 001627035-0001.”

  - Notwithstanding the provisions of DEFCON 531 (Edn 11/14) Disclosure of Information, Paragraph 2b, ‘The Information’ pertaining to MTP shall not be used for any purpose other than the delivery of any product made using MTP under this contract. For the avoidance of doubt the provisions of DEFCON 531 (Edn 11/14) Disclosure of Information, Paragraph 5 shall not apply to the MTP information.

  - The Contractor shall procure that any subcontractor to which it is required to release ‘The Information’ for the purpose of this contract shall sign the Confidentiality Agreement. This shall be returned by the Contractor to the Authority prior to release of ‘The Information’. The Contractor shall also comply with the obligations of Clause 62.6. in the event that any change in the subcontractor is agreed by the Authority during the period of the contract.

  - Should a change to the place of manufacture be agreed by the Authority, the Contractor shall procure that any subcontractor to which it is required to release the MTP specification and pattern (the Information) for the purpose of this contract enters into a confidentiality agreement with the Authority. To effect this, the Confidentiality Agreement shall be completed and signed by any subcontractor with full company name and address inserted where indicated. ‘The Information’ must not be released to any subcontractor prior to signature and return of the Confidentiality Agreement to the Authority by the Contractor who will be responsible for ensuring this obligation is in place.

  - This approval is granted for the duration of contract CSS/0103 between (INSERT CONTRACTOR NAME) and the Secretary of State for Defence dated (INSERT DATE).

- Bank or Parent Company Guarantee

Not Applicable