## Detailed
St Mungo's Broadway Implementation Plan - TST - North |  |  |  |  | PRE-MOBILISATION PHASE |  |  |  | MOBILISATION PHASE | [11 empty] | 1st Qtr | [11 empty] | 2nd Qtr
[5 empty] | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-12-01
| Task |  | Responsible Officer | KEY MILESTONE | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4
Transition & Implementation Management | A1 | Notification of proposed appointment | Implementation Manager | bar: 2015-12-01 wk3; 2016-01-01 wk1
| A2 | Establish Implementation Group & set up weekly/monthly meetings | Implementation Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk2
| A3 | Circulate Implementation Plan to relevant internal management and commissioners | Implementation Manager | bar: 2016-01-01 wk2 to 2016-01-01 wk3
| A4 | Set Key Milestones for Project Implementation timeline | Implementation Manager | KEY MILESTONE | bar: 2015-12-01 wk3 to 2015-12-01 wk4
| A5 | Meet with relevant internal departments - IT, HR, Comms, Facilities, Outside In | Implementation Manager | bar: 2016-01-01 wk3; 2016-02-01 wk1; 2016-02-01 wk3; 2016-03-01 wk1; 2016-03-01 wk3 to 2016-03-01 wk4
| A6 | Confirm and agree contigency plan for transition with comissioners | Implementation Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk4
| A7 | Agree and set any outstanding KPI's & Performance Targets with Commissioner | Implementation Manager | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| A8 | Review Risk Log & Contingency planning | Implementation Manager | bar: 2015-12-01 wk3; 2016-01-01 wk4; 2016-02-01 wk4; 2016-03-01 wk4
Office Accommodation | B1 | Re-specify existing offices(furniture, amenities, etc) | Regional Head | bar: 2016-01-01 wk1 to 2016-01-01 wk2
| B2 | Confirm Hub Locations | Regional Head | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| B3 | Fix office plan | Regional Head | bar: 2016-01-01 wk4
| B4 | Negotiate agreements with co-located services - where needed | Regional Head | bar: 2016-01-01 wk4 to 2016-02-01 wk2
| B5 | Full Health & Safety checks / review of the offices completed and logged | Regional Head | KEY MILESTONE | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| B6 | Formal contract agreed and lease signed - where needed | Regional Head | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| B7 | Read meters and set up / Handover utility suppliers - where needed | Regional Head | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| B8 | Confirm IT / telecommunications requirements with IT Manager | Regional Head | bar: 2016-02-01 wk3 to 2016-03-01 wk1
| B9 | Office equipment items (e.g. photocopiers) supplied | Regional Head | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| B10 | Stationary including headed paper in place | Regional Head | bar: 2016-03-01 wk3 to 2016-03-01 wk4
Finance & Purchasing | D1 | Confirm Budget | Implementation Manager | KEY MILESTONE | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| D4 | Establish Cost Code for service/s | Implementation Manager | bar: 2016-02-01 wk1 to 2016-02-01 wk2
| D5 | Set up project on Ebis (Electronic Purchasing System) | Implementation Manager | bar: 2016-02-01 wk1
| D6 | Liaise with Finance re: raising invoices for purchases | Implementation Manager | bar: 2016-01-01 wk4 to 2016-02-01 wk1
| D7 | Send new supplier's forms to local suppliers for entry to Ebis | Implementation Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
IT | E1 | Set up OPAL (service user Data Monitoring) system & request service user data | Implementation Manager | KEY MILESTONE | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| E2 | Seek view only access to CHAIN | Implementation Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| E3 | Develop information sharing protocols with partner agencies | bar: 2016-03-01 wk1 to 2016-03-01 wk3
| E4 | Information sharing protocols with partner agencies in place | Implementation Manager | KEY MILESTONE
Communications |  | Clients
| F1 | Inform clients and carers of service changes that may affect them, with tailored communications to active and non active client groups | Comms team | KEY MILESTONE | bar: 2016-02-01 wk1; 2016-03-01 wk1
| F2 | Distribute new service leaflets to service users | Comms team | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| F3 | Engage with key partners and relevant statutory providers re changes | Comms team | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| F4 | Set up and advertise service user involvement opportunities throughout transition | Comms team | bar: 2016-03-01 wk2 to 2016-03-01 wk4
| F5 | Conduct Client Survey into service improvement suggestions | Comms team
Internal Departments
| G1 | Inform all central services | Implementation Manager | KEY MILESTONE | bar: 2016-01-01 wk3 to 2016-02-01 wk2
| G2 | Prepare new service leaflets | Implementation Manager | bar: 2016-02-01 wk1 to 2016-02-01 wk3
| G3 | Ensure coverage of the project opening in Core Brief | Implementation Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk2
External Stakeholders
| H1 | Agree Communications Plan with GLA | Regional Head | KEY MILESTONE | bar: 2016-02-01 wk1 to 2016-02-01 wk2
| H2 | Agree standard operating procedures and reporting obligations with landlords | Regional Head | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| H3 | Arrange meetings with leads from key identified agencies | Regional Head | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H4 | Information sharing at relevant forums | Regional Head | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H5 | Inform key partners of provider change and model changes | Regional Head | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H6 | Ensure coverage of Service Opening in The Saint (St Mungo's Broadway Supporter Magazine) | Regional Head
| H7 | Meet with Local Borough Leads | Regional Director | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| H8 | Discussions with Police, and relevant enforcement agencies. | Regional Head | bar: 2016-02-01 wk4 to 2016-03-01 wk1
| H9 | Identify any additional possible partners and join existing forums | Regional Head | KEY MILESTONE | bar: 2016-02-01 wk1 to 2016-02-01 wk2
| H10 | Preparation of community asset maps | Regional Head / Service Manager/PAL | bar: 2016-03-01 wk4
| H11 | Contact all other services such as required | Regional Head | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| H12 | Conduct initial stakeholder satisfaction review | Regional Head
Clients | I1 | Inform Outside In (Client Involvement Group) and consolidate Outside In's role in service marketing | Regional Head, Implementation Manager | bar: 2016-01-01 wk2 to 2016-01-01 wk4; 2016-02-01 wk2 to 2016-02-01 wk4
| I2 | Area Manager to write to and set up open meetings with current clients and carers | Regional Head, Implementation Manager | KEY MILESTONE | bar: 2016-02-01 wk3 to 2016-03-01 wk2
| I3 | Outside in (CI Group) to meet with current service users | Regional Head, Implementation Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| I4 | Implement Client Involvement Toolkit | Regional Head, Client Involvement lead
| I5 | Promote apprenticeships scheme | Regional Head, Client Involvement lead
| I6 | Review risk levels of all transferring clients | Implementation Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk2
| I7 | Initial Keywork Meetings with clients and set up forward plan | TST Staff
| I8 | Introduce Support Planning & Outcomes Star as agreed with GLA | Service Manager | bar: 2016-03-01 wk4
| I9 | Map Recovery Networks | Regional Head, Service Manager | bar: 2016-03-01 wk4
| I10 | Seek consent from clients via existing provider regarding data transfer | Regional Head, Implementation Manager | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| I11 | Handover of any current safeguarding issues | Regional Head, Implementation Manager | bar: 2016-03-01 wk2 to 2016-03-01 wk4
Equality & Diversity | J1 | Review recruitment plan in line with equality policy | Head of Equality and Diversity | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| J2 | Introduce and promote St Mungo's Broadway Diversity Groups to new clients | Head of Equality and Diversity
| J3 | Ensure communication materials are translated into appropriate languages | Head of Equality and Diversity | bar: 2016-02-01 wk1 to 2016-02-01 wk3
| J4 | Ensure new staff undertake equality and diversity training | Head of Equality and Diversity | KEY MILESTONE
| J5 | Appraise property/accommodation sites for accessibility and make suitable adjustments | Head of Equality and Diversity | bar: 2016-02-01 wk1 to 2016-02-01 wk4
TUPE Transition Plan | K1 | Final TUPE information received | HR / Regional Head | bar: 2016-03-01 wk1
| K2 | Contact with exiting providers | HR / Regional Head | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| K3 | TUPE applicability determined & measures letter issued | HR / Regional Head | KEY MILESTONE | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| K4 | Welcome meetings with TUPE eligible staff | HR / Regional Head | bar: 2016-02-01 wk2; 2016-03-01 wk2
| K5 | Liaise with Trade Unions or recognised representatives | HR / Regional Head | bar: 2016-01-01 wk4 to 2016-02-01 wk1; 2016-03-01 wk1 to 2016-03-01 wk4
| K6 | New starter process implemented | HR / Regional Head | KEY MILESTONE
| K7 | HR database – CIPHR updated & skills audit completed | HR / Regional Head | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| K8 | Staff skills audit completed | HR / Regional Head
| K9 | Set up new staff on payroll system | HR / Regional Head
| K10 | Complete safe recruitment of new staff if required (incl DBS and reference security checks) | HR / Regional Head | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| K11 | Induct staff | HR / Regional Head
| K12 | Prepare service structure document for TUPE’d staff | HR / Regional Head | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| K13 | Instigate formal restructuring process | HR / Regional Head
| K14 | Ongoing service management structure confirmed | HR / Regional Head
| K15 | Ongoing service delivery structure confirmed | HR / Regional Head
| K16 | Ongoing service delivery structure fully bedded in | HR / Regional Head
Other Staffing Plans | L1 | Identify staffing gaps e.g. Apprentice roles and recruit to fill | HR / Regional Head / Implementation Manager | KEY MILESTONE | bar: 2016-03-01 wk2 to 2016-03-01 wk3
| L2 | IT and email accounts set up | HR / Regional Head / Implementation Manager
| L3 | Plan local and central induction training | HR / Regional Head / Implementation Manager | bar: 2015-12-01 wk4; 2016-01-01 wk4; 2016-03-01 wk1 to 2016-03-01 wk2
| L4 | Deliver local and central induction training | Regional Head / Learning and Development
| L5 | Client Involvement training | HR / Head of Client Involvement
| L6 | Implement on-call and Crysis Lone Working systems | HR / Health and Safety Coordinator | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| L7 | Localise quality manuals | Quality and Continuous Improvement Team | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| L8 | Prepare and issue new ID Badges | HR / Facilities
| L9 | Diarise staff meetings | Service Manager | bar: 2016-03-01 wk4
| L10 | Away days to review performance and smooth transition | Regional Head / Service Manager / Head of Business Excellence | KEY MILESTONE