CONTRACT FOR: The development of an assessment and accreditation system for three new statuses in child and family social work

THIS CONTRACT IS DATED  26th March 2015

Parties

1)	The Secretary of State for Education whose Head Office is at Sanctuary Buildings, Great Smith Street, London, SW1P 3BT acting as part of the Crown (“the Department”); and

2)	KPMG LLP, a limited liability partnership registered in England & Wales with registered number OC301540, whose registered office is at  15 Canada Square, London, E15 5GL (“the Contractor”)

Recitals

The Contractor has agreed to development of an assessment and accreditation system for three new statuses in child and family social work on the terms and conditions set out in this Contract.

The Department's reference number for this Contract is SWR01260315

1	Interpretation

1.1	In this Contract the following words shall mean:-

| “the Services”" | the services to be performed by the Contractor as described in Schedule 1; |
| --- | --- |
| “Central Government Body” “the Contract Manager” | means a body listed in one of the following sub-categories of the Central Government classification of the Public Sector Classification Guide, as published and amended from time to time by the Office for National Statistics: (a) Government Department; (b) Non-Departmental Public Body or Assembly Sponsored Public Body (advisory, executive, or tribunal); (c) Non-Ministerial Department; or (d) Executive Agency; Thomasin Miller, SWRU, 1st Floor, Sanctuary Buildings, Great Smith Street, SW1P 3BT |
| “the Contractors Contract Manager | Andrew Hine, 15 Canada Square, London, E14 5GL |
| “Confidential Information” | the Department's Confidential Information and/or the Contractor's Confidential Information; |
| "Contracting Department" | any contracting Department as defined in Regulation 5(2) of the Public Contracts (Works, Services and Supply) (Amendment) Regulations 2000 other than the Department; |
| "Contractor Personnel" | all employees, agents, consultants and contractors of the Contractor and/or of any Sub-contractor; |
| “Crown” | means Queen Elizabeth II and any successor |
| "Crown Body" | any department, office or agency of the Crown; |
| "Department’s Confidential Information" | all Personal Data and any information, however it is conveyed, that relates to the business, affairs, developments, trade secrets, know-how, personnel, and suppliers of the Department, including all IPRs, together with all information derived from any of the above, and any other information clearly designated as being confidential (whether or not it is marked "confidential") or which ought reasonably be considered to be confidential; |
| “Different Contractor Person(s)” | means, collectively or individually, Contractor Personnel who are not members of the Engagement Team; |
| “Engagement Team” | means, collectively or individually, Contractor Personnel who is or are involved in delivering the Services; |
| "Environmental Information Regulations" | the Environmental Information Regulations 2004 together with any guidance and/or codes of practice issues by the Information Commissioner or relevant Government Department in relation to such regulations; |
| "FOIA" | the Freedom of Information Act 2000 and any subordinate legislation made under this Act from time to time together with any guidance and/or codes of practice issued by the Information Commissioner or relevant Government Department in relation to such legislation; |
| “Her Majesty's Government” | means the duly elected Government for the time being during the reign of Her Majesty and/or any department, committee, office, servant or officer of such Government |
| "Information" | has the meaning given under section 84 of the Freedom of Information Act 2000; |
| "Personal Data" | shall have the same meaning as set out in the Data Protection Act 1998; |
| “Property” | means the property, other than real property, issued or made available to the Contractor by the Client in connection with the Contract. |
| "Request for Information" | a request for information or an apparent request under the Code of Practice on Access to Government Information, FOIA or the Environmental Information Regulations; |
| "SME" | means a micro, small or medium-sized enterprise defined in accordance with the European Commission Recommendation 2003/361/EC and any subsequent revisions. |
| "Working Day" | any day other than a Saturday, Sunday or public holiday in England and Wales. |

1.2 	References to “Contract” mean this contract (and include the Schedules).  References to “Clauses” and “Schedules” mean clauses of and schedules to this Contract.  The provisions of the Schedules shall be binding on the parties as if set out in full in this Contract.

1.3	Reference to the singular include the plural and vice versa and references to any gender include both genders.  References to a person include any individual, firm, unincorporated association or body corporate.

2	Commencement and Continuation

The Contractor shall commence the Services on 26th March 2015 and, subject to Clause 10.1 shall complete the Services on or before 31st March 2016. The contract is to be for a period of 1 year with a possible extension of 1 year dependent on funding availability and a track record of successful performance of the contract.

3	Contractor's Obligations

3.1	The Contractor shall promptly and efficiently complete the Services in accordance with the provisions set out in Schedule 1

3.2	The Contractor shall comply with the accounting and information provisions of Schedule 2.

3.3	The Contractor shall comply with all statutory provisions including all prior and subsequent enactments, amendments and substitutions relating to that provision and to any regulations made under it.

4	Departments Obligations

The Department will comply with the payment provisions of Schedule 2 provided that the Department has received full and accurate information and documentation as required by Schedule 2 to be submitted by the Contractor for work completed to the satisfaction of the Department.

5	Changes to the Department's Requirements

5.1	The Department shall notify the Contractor of any material change to the Department's requirement under this Contract.

5.2	The Contractor shall use its best endeavours to accommodate any changes to the needs and requirements of the Department provided that it shall be entitled to payment for any additional costs it incurs as a result of any such changes.  The amount of such additional costs to be agreed between the parties in writing.

6	Management

6.1	The Contractor shall promptly comply with all reasonable requests or directions of the Contract Manager in respect of the Services.

6.2	The Contractor shall address any enquiries about procedural or contractual matters in writing to the Contract Manager.  Any correspondence relating to this Contract shall quote the reference number set out in the Recitals to this Contract.

7	Contractor's Employees and Sub-Contractors

7.1	Where the Contractor enters into a contract with a supplier or contractor for the purpose of performing its obligations under the Contract (the “Sub-contractor”) it shall ensure prompt payment in accordance with this clause 7.1. Unless otherwise agreed by the Department in writing, the Contractor shall ensure that any contract requiring payment to a Sub-contractor shall provide for undisputed sums due to the Sub-contractor to be made within a specified period from the receipt of a valid invoice not exceeding:

7.1.1	10 days, where the Sub-contractor is an SME; or

7.1.2	30 days either, where the sub-contractor is not an SME, or both the Contractor and the Sub-contractor are SMEs,

The Contractor shall comply with such terms and shall provide, at the Department’s request, sufficient evidence to demonstrate compliance.

7.2	The Department shall be entitled to withhold payment due under clause 7.1 for so long as the Contractor, in the Department’s reasonable opinion, has failed to comply with its obligations to pay any Sub-contractors promptly in accordance with clause 7.1.  For the avoidance of doubt the Department shall not be liable to pay any interest or penalty in withholding such payment.  .

7.3	The Contractor shall take all reasonable steps to satisfy itself that its employees or sub-contractors (or their employees) are suitable in all respects to perform the Services.

7.4	The Contractor shall immediately notify the Department if they have any concerns regarding the propriety of any of its sub-contractors in respect of work/services rendered in connection with this Contract.

7.5	The Contractor, its employees and sub-contractors (or their employees), whilst on Departmental premises, shall comply with such rules, regulations and requirements (including those relating to security arrangements) as may be in force from time to time.

7.6 	The Contractor shall ensure the security of all the Property whilst in its possession, during the supply of the Services, in accordance with the Department’s reasonable security requirements as required from time to time.

8	Copyright

Copyright in all reports and other documents and materials arising out of the performance by the Contractor of their duties under this Contract are to be assigned to and shall vest in the Crown absolutely.  This condition shall apply during the continuance of this Contract and after its termination howsoever arising.  The Department shall not require the Contractor and the Contractor shall not be obliged to transfer or assign a) copyright in any part of a product of the Services that may be owned by a third party and which has been identified as such in the product or b) the Contractor's name or trade-marks, the association of these with any product of the services being confidential or c) the Contractor's copyright in its methods of work, working papers, computer programmes, methodologies, skills, experience, expertise and any associated or related information maintained by the Contractor in any form (whether oral, written, visual, electronic or other), all intellectual property rights therein remaining vested in the Contractor.  To the extent that the matters excluded in item (c) above are comprised in or incorporated in or required in connection with a product of the Services, the Contractor shall grant to the Department a non-exclusive royalty free licence to use the same solely for the purposes contemplated by the Contract.  For the purposes of delivering services to the Department or other clients, the Contractor, the Engagement Team and Different Contractor Persons shall be entitled to use, develop or share knowledge, experience and skills of general application gained through performing the Services.

9	Warranty and Indemnity

9.1	The Contractor warrants to the Department that the obligations of the Contractor under this Contract will be performed by appropriately qualified and trained personnel with reasonable skill, care and diligence and to such high standards of quality as it is reasonable for the Department to expect in all the circumstances.  The Department will be relying upon the Contractor's skill, expertise and experience in the performance of the Services and also upon the accuracy of all representations or statements made and the advice given by the Contractor in connection with the performance of the Services and the accuracy of any documents conceived, originated, made or developed by the Contractor as part of this Contract.  The Contractor warrants that any goods supplied by the Contractor forming a part of the Services will be of satisfactory quality and fit for their purpose and will be free from defects in design, material and workmanship.

9.2	Without prejudice to any other remedy, if any part of the Services is not performed in accordance with this Contract then the Department shall be entitled, where appropriate to:

9.2.1	The Contractor has stated that the whole of the contract value is at risk on the basis that all deliverables shall be subject to content, quality and fitness for purpose clearance by the Chief Social Worker, exercising her professional judgement, or delegated to Department for Education officials acting on her behalf, where this is explicitly notified in writing to the Contractor. Where the deliverables are reasonably judged to be in need of re-performance or replacement the Contractor shall act reasonably and promptly in taking any remedial action at no additional cost to the Department

9.2.2	Assess the cost of remedying the failure (“the assessed cost”) and to deduct from any sums due to the Contractor the Assessed Cost for the period that such failure continues.

9.3	The Contractor shall be liable for and shall, subject to clause 9.7, indemnify the Department in full against any expense, liability, loss, claim or proceedings arising under statute or at common law in respect of personal injury to or death of any person whomsoever or loss of or damage to property whether belonging to the Department or otherwise arising out of or in the course of or caused by the provision of the Services.

9.4	The Contractor shall be liable for and shall, subject to clause 9.7, indemnify the Department against any expense, liability, loss, claim or proceedings arising as a result of or in connection with any breach of the terms of this Contract or otherwise through the default of the Contractor

9.5	All property of the Contractor whilst on the Department's premises shall be there at the risk of the Contractor and the Department shall accept no liability for any loss or damage howsoever occurring to it.

9.6	The Contractor shall ensure that it has adequate insurance cover with an insurer of good repute to cover claims under this Contract or any other claims or demands which may be brought or made against it by any person suffering any injury damage or loss in connection with this Contract (to include Professional Indemnity Insurance policies sufficient to provide £5,000,000 (five million pounds) cover in respect of any one claim or series of related claims).  The Contractor shall upon request produce to the Department, a broker’s confirmation of its policy or policies of insurance, also confirming payment of the last premium in respect of each policy.  On request, the Contractor shall provide further broker’s confirmations of renewed insurance cover after the date on which any previously evidenced insurance has expired.

9.7     All other terms of this Contract shall be subject to this clause.  The liability of the Contractor to the Department, in contract or tort or under statute or otherwise, for any loss or damage (including but not limited to any liability under any indemnity provision in the Contract) suffered by the Department arising from or in connection with any services provided under the Contract, shall be subject to a court of competent and final jurisdiction holding that the Contractor had breached its duties to the Department and that the breach has caused such loss or damage in such amount as is assessed by the court applying principles of recoverability (or otherwise) of damages under the laws of England & Wales after taking into account the responsibilities (if any) of others.

10	Termination

10.1	This Contract may be terminated by either party giving to the other party at least 3 months’ notice in writing.

10.2	In the event of any breach of this Contract by either party, the other party may serve a notice on the party in breach requiring the breach to be remedied within a period specified in the notice which shall be reasonable in all the circumstances.  If the breach has not been remedied by the expiry of the specified period, the party not in breach may terminate this Contract with immediate effect by notice in writing.

10.3	In the event of a material breach of this Contract by either party, the other party may terminate this Contract with immediate effect by notice in writing.

10.4	This Contract may be terminated by the Department with immediate effect by notice in writing if at any time:-

10.4.1	the Contractor passes a resolution that it be wound-up or that an application be made for an administration order or the Contractor applies to enter into a voluntary arrangement with its creditors; or

10.4.2	a receiver, liquidator, administrator, supervisor or administrative receiver be appointed in respect of the Contractor's property, assets or any part thereof; or

10.4.3	the court orders that the Contractor be wound-up or a receiver of all or any part of the Contractor's assets be appointed; or

10.4.4	the Contractor is unable to pay its debts in accordance with Section 123 of the Insolvency Act 1986.

10.4.5	there is a change in the legal or beneficial ownership of 50% or more of the Contractor's share capital issued at the date of this Contract or there is a change in the control of the Contractor, unless the Contractor has previously notified the Department in writing.  For the purpose of this Sub-Clause 10.4.5 “control” means the power of a person to secure that the affairs of the Contractor are conducted in accordance with the wishes of that person by means of the holding of shares or the possession of voting power.

10.4.6		the Contractor is convicted (or being a company, any officers or representatives of the Contractor are convicted) of a criminal offence related to the business or professional conduct

10.4.7		the Contractor commits (or being a company, any officers or representatives of the Contractor commit) an act of grave misconduct in the course of the business;

10.4.8		the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to the payment of Social Security contributions;

10.4.9	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to fulfil his/their obligations relating to payment of taxes;

10.4.10	the Contractor fails (or being a company, any officers or representatives of the Contractor fail) to disclose any serious misrepresentation in supplying information required by the Department in or pursuant to this Contract.

10.5	Nothing in this Clause 10 shall affect the coming into, or continuance in force of any provision of this Contract which is expressly or by implication intended to come into force or continue in force upon termination of this Contract.

11	Status of Contractor

11.1	In carrying out its obligations under this Contract the Contractor agrees that it will be acting as principal and not as the agent of the Department.

11.2	The Contractor shall not say or do anything that may lead any other person to believe that the Contractor is acting as the agent of the Department.

12	Confidentiality

12.1	Except to the extent set out in this clause or where disclosure is expressly permitted elsewhere in this Contract, each party shall:

12.1.1	treat the other party's Confidential Information as confidential and safeguard it accordingly; and

12.1.2	 not disclose the other party's Confidential Information to any other person without the owner's prior written consent; information relating to the Department, to the Contractor’s relationship with the Department, and to the Services, including Confidential Information, may be shared by the Contractor with Different Contractor Persons and with other member firms of KPMG International Cooperative for the purposes of maintaining quality and standards in the Contractor’s work.  Furthermore, the Contractor engages service providers who facilitate the administration of the Contractor’s business or support its infrastructure, who may have access to Confidential Information whilst supporting the Contractor.  The other member firms and service providers referred to in this Clause have no direct involvement with the performance of the Services (so are not sub-contractors) and are subject to conditions of confidentiality with a least the effect of those set out in the Contract.  The Contractor shall remain responsible for preserving confidentiality if Confidential Information is shared with other member firms or accessed by such service providers.

12.2	Clause 12 shall not apply to the extent that:

12.2.1		such disclosure is a requirement of Law placed upon the party making the disclosure, including any requirements for disclosure under the FOIA, Code of Practice on Access to Government Information or the Environmental Information Regulations pursuant to Clause 13 (Freedom of Information);

12.2.2		such information was in the possession of the party making the disclosure without obligation of confidentiality prior to its disclosure by the information owner;

12.2.3		such information was obtained from a third party without obligation of confidentiality;

12.2.4		such information was already in the public domain at the time of disclosure otherwise than by a breach of this Contract; or

12.2.5		it is independently developed without access to the other party's Confidential Information.

12.3	The Contractor may only disclose the Department's Confidential Information to the Contractor Personnel who are directly involved in the provision of the Project and who need to know the information, and shall ensure that such Contractor Personnel are aware of and shall comply with these obligations as to confidentiality.

12.4	The Contractor shall not, and shall procure that the Contractor Personnel do not, use any of the Department's Confidential Information received otherwise than for the purposes of this Contract.

12.5	The Contractor shall ensure that their employees, servants or such professional advisors or consultants are aware of the Contractor’s obligations under this Contract.

12.6	Nothing in this Contract shall prevent the Department from disclosing the Contractor's Confidential Information:

12.6.1		on a confidential basis to any Central Government Body for any proper purpose of the Department or of the relevant Central Government Body;

12.6.2		to Parliament and Parliamentary Committees or if required by any Parliamentary reporting requirement;

12.6.3		to the extent that the Department (acting reasonably) deems disclosure necessary or appropriate in the course of carrying out its public functions;

12.6.4		on a confidential basis to a professional adviser, consultant, supplier or other person engaged by any of the entities described in Clause 12.6.1 (including any benchmarking organisation) for any purpose relating to or connected with this Contract;

12.6.5		on a confidential basis for the purpose of the exercise of its rights under this Contract, including audit rights, step-in rights and exit management rights; or

12.6.6		on a confidential basis to a proposed successor body in connection with any assignment, novation or disposal of any of its rights, obligations or liabilities under this Contract.

12.7	The Department shall use all reasonable endeavours to ensure that any Central Government Body, Contracting Department, employee, third party or Sub-contractor to whom the Contractor's Confidential Information is disclosed pursuant to clause 12 is made aware of the Department's obligations of confidentiality.

12.8	Nothing in this clause 12 shall prevent either party from using any techniques, ideas or know-how gained during the performance of the Contract in the course of its normal business to the extent that this use does not result in a disclosure of the other party's Confidential Information or an infringement of Intellectual Property Rights.

12.9	The parties acknowledge that, except for any information which is exempt from disclosure in accordance with the provisions of the FOIA, the content of this Contract is not Confidential Information.  The Department shall be responsible for determining in its absolute discretion whether any of the content of the Contract is exempt from disclosure in accordance with the provisions of the FOIA.

12.10	Subject to Clause 12.9, the Contractor hereby gives his consent for the Department to publish the Contract in its entirety, including from time to time agreed changes to the Contract, to the general public.

12.11	The Department may consult with the Contractor to inform its decision regarding any redactions but the Department shall have the final decision in its absolute discretion.

12.12	The Contractor shall assist and cooperate with the Department to enable the Department to publish this Contract.

13	Freedom of Information

13.1	The Contractor acknowledges that the Department is subject to the requirements of the FOIA and the Environmental Information Regulations and shall assist and cooperate with the Department to enable the Department to comply with its information disclosure obligations.

13.2	The Contractor shall and shall procure that its Sub-contractors shall (in respect of the Information referred to in Clause 13.1):

13.2.1	transfer to the Department all Requests for Information that it receives as soon as practicable and in any event within two Working Days of receiving a Request for Information;

13.2.2	provide the Department with a copy of all Information in its possession, or power in the form that the Department requires within five Working Days (or such other period as the Department may specify) of the Department's request; and

13.2.3	provide all necessary assistance as reasonably requested by the Department to enable the Department to respond to the Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations.

13.3	The Department shall be responsible for determining in its absolute discretion and notwithstanding any other provision in this Contract or any other agreement whether any Information is exempt from disclosure in accordance with the provisions of the FOIA or the Environmental Information Regulations.

13.4	In no event shall the Contractor respond directly to a Request for Information unless expressly authorised to do so by the Department.

13.5	The Contractor acknowledges that (notwithstanding the provisions of Clause 13) the Department may, acting in accordance with the Ministry of Justice’s Code of Practice on the Discharge of the Functions of Public Authorities under Part 1 of the Freedom of Information Act 2000 (“the Code”), be obliged under the FOIA, or the Environmental Information Regulations to disclose information concerning the Contractor or the Project:

13.5.1	in certain circumstances without consulting the Contractor; or

13.5.2	following consultation with the Contractor and having taken their views into account;

provided always that where 13.5.1 applies the Department shall, in accordance with any recommendations of the Code, take reasonable steps, where appropriate, to give the Contractor advanced notice, or failing that, to draw the disclosure to the Contractor’s attention after any such disclosure.

13.6	The Contractor shall ensure that all Information is retained for disclosure and shall permit the Department to inspect such records as requested from time to time.

14	Access and Information

The Contractor shall (subject to the Contractor maintaining the confidentiality of information relating to its other clients and its own non-relevant information) provide access at all reasonable times to the Department's internal auditors or other duly authorised staff or agents to inspect such documents as the Department considers necessary in connection with this Contract and where appropriate speak to the Contractor’s employees.

15	Transfer of Responsibility on Expiry or Termination

15.1	The Contractor shall, at no cost to the Department, promptly provide such assistance and comply with such timetable as the Department may reasonably require for the purpose of ensuring an orderly transfer of responsibility upon the expiry or other termination of this Contract.  The Department shall be entitled to require the provision of such assistance both prior to and, for a reasonable period of time after the expiry or other termination of this Contract.

15.2	Such assistance may include (without limitation) the delivery of documents and data in the possession or control of the Contractor which relate to this Contract, including the documents and data, if any, referred to in the Schedule.

15.3	The Contractor undertakes that it shall not knowingly do or omit to do anything which may adversely affect the ability of the Department to ensure an orderly transfer of responsibility.

16	Tax Indemnity

- 16.1	Where the Contractor is liable to be taxed in the UK in respect of consideration received under this contract, it shall at all times comply with the Income Tax (Earnings and Pensions) Act 2003 (ITEPA) and all other statutes and regulations relating to income tax in respect of that consideration.

- 16.2	Where the Contractor is liable to National Insurance Contributions (NICs) in respect of consideration received under this contract, it shall at all times comply with the Social Security Contributions and Benefits Act 1992 (SSCBA) and all other statutes and regulations relating to NICs in respect of that consideration.

- 16.3	The Department may, at any time during the term of this contract, ask the Contractor to provide information which demonstrates how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it.

- 16.4	A request under Clause 16.3 above may specify the information which the Contractor must provide and the period within which that information must be provided.

- 16.5	The Department may terminate this contract if-

- (a)	in the case of a request mentioned in Clause 16.3 above if the Contractor:

- (i)	fails to provide information in response to the request within a reasonable time, or

- (ii)	provides information which is inadequate to demonstrate either how the Contractor complies with Clauses 16.1 and 16.2 above or why those Clauses do not apply to it;

- (b)	in the case of a request mentioned in Clause 16.4 above, the Contractor fails to provide the specified information within the specified period, or

- (c)	it receives information which demonstrates that, at any time when Clauses 16.1 and 16.2 apply, the Contractor is not complying with those Clauses.

- 16.6	The Department may supply any information which it receives under Clause 16.3 to the Commissioners of Her Majesty’s Revenue and Customs for the purpose of the collection and management of revenue for which they are responsible.

- 16.7	The Contractor warrants and represents to the Department that it is an independent contractor and, as such, bears sole responsibility for the payment of tax and national insurance contributions which may be found due from it in relation to any payments or arrangements made under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

- 16.8	The Contractor will account to the appropriate authorities for any income tax, national insurance, VAT and all other taxes, liabilities, charges and duties relating to any payments made to the Contractor under this Contract or in relation to any payments made by the Contractor to its officers or employees in connection with this Contract.

- 16.9	The Contractor shall indemnify Department against any liability, assessment or claim made by the HM Revenue and Customs or any other relevant authority arising out of the performance by the parties of their obligations under this Contract (other than in respect of employer's secondary national insurance contributions) and any costs, expenses, penalty fine or interest incurred or payable by Department in connection with any such assessment or claim.

- 16.10	The Contractor authorises the Department to provide the HM Revenue and Customs and all other departments or agencies of the Government with any information which they may request as to fees and/or expenses paid or due to be paid under this Contract whether or not Department is obliged as a matter of law to comply with such request.

17	Amendment and variation

No amendment or variation to this Contract shall be effective unless it is in writing and signed by or on behalf of each of the parties hereto.  The Contractor shall comply with any formal procedures for amending or varying contracts which the Department may have in place from time to time.

18	Assignment and Sub-contracting

The benefit and burden of this Contract may not be assigned or sub-contracted in whole or in part by the Contractor without the prior written consent of the Department.  Such consent may be given subject to any conditions which the Department considers necessary.  The Department may withdraw its consent to any sub-contractor where it no longer has reasonable grounds to approve of the sub-contractor or the sub-contracting arrangement and where these grounds have been presented in writing to the Contractor.

19	The Contract (Rights of Third Parties) Act 1999

This Contract is not intended to create any benefit, claim or rights of any kind whatsoever enforceable by any person not a party to the Contract.

20	Waiver

No delay by or omission by either Party in exercising any right, power, privilege or remedy under this Contract shall operate to impair such right, power, privilege or remedy or be construed as a waiver thereof.  Any single or partial exercise of any such right, power, privilege or remedy shall not preclude any other or further exercise thereof or the exercise of any other right, power, privilege or remedy.

21	Notices

Any notices to be given under this Contract shall be delivered personally or sent by post or by facsimile transmission to the Contract Manager (in the case of the Department) or to the address set out in this Contract (in the case of the Contractor).  Any such notice shall be deemed to be served, if delivered personally, at the time of delivery, if sent by post, 48 hours after posting or, if sent by facsimile transmission, 12 hours after proper transmission.

21	Dispute resolution

22.1	The Parties shall use all reasonable endeavours to negotiate in good faith and settle amicably any dispute that arises during the continuance of this Contract.

22.2	Any dispute not capable of resolution by the parties in accordance with the terms of Clause 22 shall be settled as far as possible by mediation in accordance with the Centre for Dispute Resolution (CEDR) Model Mediation Procedure.

22.3	No party may commence any court proceedings/arbitration in relation to any dispute arising out of this Contract until they have attempted to settle it by mediation, but any such mediation may be terminated by either party at any time of such party wishing to commence court proceedings/arbitration.

23	Discrimination

23.1	The Contractor shall not unlawfully discriminate within the meaning and scope of any law, enactment, order, or regulation relating to discrimination (whether in race, gender, religion, disability, sexual orientation or otherwise) in employment.

23.2	The Contractor shall take all reasonable steps to secure the observance of Clause 23.1 by all servants, employees or agents of the Contractor and all suppliers and sub-contractors employed in the execution of the Contract.

Professional advice

24.1	The Contractor aspires to embed in its culture the attributes that the Contractor feels distinguish its brand and contribute to the difference that the Department experiences when engaging KPMG.  The Contractor may invite the Department to provide feedback on the Contractor’s performance so that the Contractor can measure to what extent the Contractor meets its goals.  If the Department wishes to discuss the Services or complain about them, the Department is invited to contact any partner or director named in the Statement of Work.  If the Department’s problem is not resolved, the Department should contact David Matthews, the Contractor’s UK Head of Quality & Risk Management, by e-mail to david.matthews@kpmg.co.uk or by writing to him at 15 Canada Square, London E14 5GL or through the Contractor’s website at http://www.kpmg.co.uk/clientcare where the Department can also find details of information about the Contractor that the Contractor is required by regulations to make available to the Department.  The Contractor investigates any complaints promptly and does what the Contractor can to resolve difficulties.  If the Department is still not satisfied, the Department can refer the matter to the ICAEW and (in respect of “regulated activities” and ancillary services) to the Financial Ombudsman Service and to the Legal Ombudsman in respect of activity that is “reserved legal activity” or “legal activity” under the Legal Services Act 2007, or any complaint that the Legal Ombudsman considers to be about a legal service.

24.2	The Contractor may supply written advice or confirm oral advice in writing or deliver a final written report or make an oral presentation on completion of the Services.  Prior to completion of the Services the Contractor may supply oral, draft or interim advice or reports or presentations but in such circumstances the Contractor's written advice or final written report shall take precedence.  No reliance shall be placed by the Department on any draft or interim advice or report or any draft or interim presentation.  Where the Department wishes to rely on oral advice or on an oral presentation made on completion of the Services, the Department shall inform the Contractor and the Contractor shall supply documentary confirmation of the advice concerned.

24.3	The Contractor shall not be under any obligation in any circumstances, unless agreed as part of the Services, to update any advice, report or any product of the Services, oral or written, for events occurring after the advice, report or product concerned has been issued in final form.

24.4	Any advice, opinion, statement of expectation, forecast or recommendation supplied by the Contractor as part of the Services shall not amount to any form of guarantee that the Contractor has determined or predicted future events or circumstances.

24.5	Notwithstanding the Contractor’s duties and responsibilities in relation to the Services, the Department shall retain responsibility and accountability for managing its affairs, deciding on what to do after receiving any product of the Services, implementing any advice or recommendations provided by the Contractor, and realising any benefits requiring activity by the Department.

24.6	To enable the Contractor to perform the Services, the Department shall supply promptly all information and assistance and all access to documentation in its possession, custody or under its control and to personnel under its control where required by the Contractor (and shall use reasonable endeavours to procure these supplies where not in the Department’s possession or custody or control).  The Department shall inform the Contractor of any information or developments which may come to the Department’s notice and which might have a bearing on the Services.

24.7	The Contractor may receive information from the Department or from other sources in the course of delivering the Services.  To the fullest extent permitted by law, the Contractor shall not be liable to the Department for any loss or damage suffered by the Department arising from fraud, misrepresentation, withholding of information material to the Services or other default relating to such material information, whether on the Department’s part or that of the other information sources, unless such fraud, misrepresentation, withholding or such other default is evident to the Contractor without further enquiry.  This provision shall not apply to the extent that the agreed scope of the Services states that the Contractor is to verify information.

24.8	The Contractor may rely on any instructions or requests made or notices given or information supplied, whether orally or in writing, by any person whom the Contractor knows to be or reasonably believes to be authorised by the Department to communicate with the Contractor for such purposes.  The Contractor may communicate with the Department by electronic mail where any such person wishes the Contractor to do so, on the basis that in consenting to this method of communication the Department accepts the inherent risks (including the security risks of interception of or unauthorised access to such communications, the risks of corruption of such communications and the risks of viruses or other harmful devices), that to the extent permitted by law the Contractor may intercept such communications in order to monitor them for internal compliance or other statutory purposes, and that the Department shall perform virus checks.  The Contractor may at the Department’s request send documents to an electronic storage facility hosted or controlled by the Department or at the Department’s direction, in which event the Department shall be responsible for security and confidentiality at such facility.

24.9	On termination of the Contract, for the purposes of complying with policies reflecting the guidance of its regulators, the Contractor may retain sufficient copy documentation that it reasonably requires to support any advice, reports or opinions the Contractor may provide to the Department.

25.	Knowledge and conflicts

25.1	The Engagement Team shall not be required, expected or deemed to have knowledge of any information known to Different Contractor Persons which is not known to the Engagement Team.  The Engagement Team shall not be required to make use of nor to disclose to the Department any information, whether known to them personally or known to Different Contractor Persons, which is confidential to another customer of the Contractor.  The Contractor is entitled to protect the confidentiality of information relating to its other customers.

25.2	The Contractor shall, where appropriate, establish Ethical Dividers (safeguards designed to facilitate the protection of each of the Contractor’s customers’ interests and may include (for example): separate teams, their geographical and operational separation and/or access controls over data, computer servers and electronic mail systems).  Contractor Persons may be delivering services to, or be approached to deliver services to, another party or parties who has or have interests which compete or conflict with the Department’s (a “Conflicting Party” or “Conflicting Parties”).  Contractor Persons are and shall remain free to deliver services to a Conflicting Party but where the interests of the Conflicting Party conflict with the Department’s specifically and directly in relation to the subject matter of the Services provided to the Department: a) members of the Engagement Team shall not deliver services to the Conflicting Party; and b) Different Contractor Persons may only deliver services to the Conflicting Party where appropriate Ethical Dividers are put in place.  In these circumstances, the effective operation of those Ethical Dividers shall constitute sufficient steps to avoid any real risk of a breach of the Contractor’s duty of confidence to the Department.

25.3	The Contractor seeks to identify Conflicting Parties in the circumstances set out in clause 25.1.   If the Department knows or becomes aware that the Contractor is (or may be) advising a Conflicting Party then the Department shall inform the Contractor promptly.

26	Law and Jurisdiction

This Contract shall be governed by and interpreted in accordance with English Law and the parties submit to the jurisdiction of the English courts.

As witness the hands of the parties

Authorised to sign for and on		Authorised to sign for and on

behalf of the Secretary of		behalf of KPMG

State for Education

Signature		Signature

Name: ALMUDENA LARA		Name: ANDREW HINE

Position in Organisation:		Position in Organisation: Partner

Head of Children’s Social Care Reform,

Innovation and Analysis

Address in full:		Address in full:

Department for Education

Sanctuary Buildings

Great Smith Street

London

SW1P 3BT		KPMG LLP, 15 Canada Square,

London, E14 5GL

Date		Date 26th March 2015

Schedule 1

1	Background

1.1	In recognition of the need to have absolute public confidence in the quality of practice undertaken by social workers working with our most at-risk children - children in need (Children Act 1989), children in need of protection and children in public care - the Secretary of State for Education, Nicky Morgan, announced in October that the government intends to develop three levels of practice:

i.	Approved Child and Family Practitioner: for those social workers working with children and families identified above.

ii.	Practice Supervision: for social workers who have a role in educating, developing and supervising social workers.

iii.	Practice Leadership: for social workers with responsibility for leading social work organisations, and creating and sustaining optimum practice conditions for frontline social work practice.

These new accreditations will provide for the first time a national, practice focused, career pathway based on the highest levels of skill and knowledge. This will provide clarity for commissioners, employers and the public about the quality of practice that can be expected from those who hold these accreditations. This new kite-mark of expertise and practice authority will position child and family social work as a leadership profession in the developing landscape of multi-disciplinary and integrated responses to vulnerable children and families.

We expect the Contractor to set out plans for the design, development and testing of all three assessments and accreditations of the social work workforce.  Methodology for testing these should address bias issues and must be robust enough to provide sufficient assurances that they are fit for purpose.

The Contractor will also be expected to work closely with the Office of the Chief Social Worker and officials in the Social Work Reform Unit in the Department throughout the contract. The Chief Social Worker will review and approve all interim and final products.

An expert reference group will be convened and chaired by the Chief Social Worker to provide support and challenge to the Contractor throughout the delivery of the contract.

2	Aim

2.1	The Contractor shall use all reasonable endeavours to achieve the following aims:

- Design a single transparent, evidence based, rigorous pass / fail process for social workers to achieve Approved Child and Family Practitioner (ACFP) status against the published knowledge and skills statement.

- Develop a knowledge and skills statement for Practice Supervision, and a knowledge and skills statement for Practice Leadership.

- Design a single transparent, evidence based, rigorous pass / fail process to achieve practice supervision status, and a single transparent, evidence based, rigorous pass / fail process to achieve practice leadership status.

- Critically review how direct observation methods can be used to assess and accredit the three social work statuses, alongside a digital solution, and make recommendations for future development – working through an independent expert, and collaborating with a range of other organisations which have experience with practice observation.

- Devise processes to test the ACFP assessment with social workers undertaking ASYE (Assessed and Supported Year in Employment) and more experienced social workers at different grades in a range of settings.

- Devise processes to test the Practice Supervision, and Practice Leadership assessments with social workers who hold a range of leadership, supervisory, and practice education and development responsibilities in a range of settings.

- Set out in detail how the developed assessment process will be scalable to a workforce of employers with responsibility for statutory social work functions.

Reporting Requirements:

- Fortnightly reporting meetings will take place between KPMG and the Department to monitor whether the aims and objectives of the contract are being met in relation to the tasks detailed in Schedule 1.

- Meetings as proposed in the Schedule 1 with the Chief Social Worker to review and approve all interim and final products.

- Meetings as proposed in the Schedule 1 with the expert reference group.

- It is the responsibility of KPMG to keep a robust risk and issues log throughout the contract and to escalate any risk that may impact on the success of the contract with the Department at the earliest opportunity, even if this is in between reporting meetings.

- This contract has strong interdependencies with the Support for ASYE contract and any associated evaluation contract for the programme. We will therefore expect there to be strong on-going communication and information sharing schedules agreed by the awarded organisations for each contact and joint contractor meetings at regular intervals to make sure the three contracts are working together to meet the wider programme objectives.

3	Outputs

3.1	The Contractor shall use all reasonable endeavours to achieve the following outputs:

| Description of outputs | Proposed measure |
| --- | --- |
| Development of Knowledge and Skills statements and competencies for Practice Supervisor and Practice Leadership | Progress against agreed milestones Deliverables aligned with DfE quarterly reports and billing schedule Chief Social Worker approval and sign off |
| Design of the assessment processes for each of the three social work statuses (ACFP, Practice Supervisor and Practice Leadership) | Progress against agreed milestones Deliverables aligned with DfE quarterly reports and billing schedule Chief Social Worker approval and sign off |
| Provide an independent report which critically reviews, and makes recommendations about, how direct observation can be used alongside a digital solution (across the three social work statuses). | KPMG propose and appoint independent person following discussions with DfE and CSW Progress against agreed milestones Deliverables aligned with DfE quarterly reports and billing schedule Involvement of a range of other organisations who have experience in practice observation. Final report completed by date as specified in Schedule 1 Chief Social Worker approval and sign off |
| Development of the assessment test approach for ACFP, Practice Supervisor and Practice Leadership | Progress against agreed milestones Deliverables aligned with DfE quarterly reports and billing schedule Chief Social Worker approval and sign off |
| Conduct the assessment tests and reviewing results | Progress against agreed milestones Deliverables aligned with DfE quarterly reports and billing schedule Chief Social Worker approval and sign off |
| Social worker feedback | Satisfaction rating of test participants with the management and administration of the process (but not the content of the assessment system itself) |
| Client Satisfaction | DfE satisfaction with KPMG work, obtained independently including mid-programme feedback discussions (“in-flight review”) |

4	Methodology

The Contractor shall perform the tasks detailed in the Schedule of Work.

SCHEDULE OF WORK

| Task | Detailed activity | Timescale |
| --- | --- | --- |
| Project set-up and the establishment of project governance | This includes: - Agreeing roles and responsibilities with the DfE team. - Agreeing the sign off process for deliverables with the DfE. - Setting up a risk log and issues log. - Agreeing the project’s governance arrangements. - Agreeing the project’s reporting approach. - Agreeing the project’s branding and identity. | March 2015 |
| Stakeholder Communication launch | This includes: - Developing the stakeholder consultation policy and procedure. - Developing the Consortium Consultation Panel terms of reference | March 2015 |
| Design of the assessment process | This includes for each of the three levels of social work practice: - Listing of different assessment tools and approaches. - Develop a long list – pros and cons - Agree shortlist | March 2015 |
| Appraisal of direct observation methods | This includes: - Undertaking a critical review of direct observation (with recommendations for the future), which reviews the methods of direct observation, alongside the development of a digital solution. - Collaborating with a range of other organisations who have experience with practice observation. - The critical review will look at how direct observation could/should be used, alongside a digital solution, across the three social work statuses (practitioner, supervisor, leader). It will address questions including: to what extent direct observation is needed alongside the digital solution; how much direct observation is needed; and what type of direct observation (or combination of methods)? - A written report to the DfE, with recommendations. - An independent person will be appointed by KPMG in consultation with the DfE to conduct the appraisal in order bring independence to this element of the work. - The DfE will have intellectual property rights over the critical review. | March – June 2015 |
| Stakeholder Communication and Consultation | A full review and sign off process for the stakeholder consultation policy and procedure and the Consortium Consultation Panel terms of reference This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers The frequency of consultation with each group of stakeholders will need to be determined. Communication and consultation will be on-going throughout the project. | April to June 2015 |
| Development of knowledge and skills statements and competences | This includes: - Developing the competences for ACFP. - Developing the knowledge and skills statements for PS. - Developing the knowledge and skills statements for PL. - Developing the competences for PS. - Developing the competences for PL. - A full review and sign off process for the above. | April – June 2015 |
| Design of the assessment process | This includes in relation to each of the three levels of social work practice: - Analysis of assessment options for each level to indicate a preferred approach(es). - Appraisal and selection of additional assessment methods incorporating practice observation to support the digital solution. - Research / visit example sites and research best approaches to conducting practice observation - Consult CCP / ERG regarding perceived applicability of assessment methods - Sampling and testing strategy - Devise testing solution with sample employers - Agree final approach to practice observation with the Chief Social Worker | April – June 2015 |
| Development of the assessment Test Approach | This includes: - Agreeing which competences will be covered in each test item for each of the 3 levels. - Agreeing a sampling approach and a sample size with the DfE which will be large enough to produce valid results that can be applied across the population. | April – June 2015 |
| Technical development of the assessment tool | This includes: - Specification of the IT platform. - Defining the user acceptance criteria. | April – June 2015 |
| Design of the assessment process | This includes for each of the three levels of practice: - Develop and implement agreed approach to practice observation and the digital solution in line with an agreed resourcing plan | July – September 2015 |
| Development of the assessment Test Approach | This includes: - Producing a detailed development and review schedule for the ACFP, PS and PL tests. - Identifying and booking test locations. - Identifying and inviting test participants. - Agreeing the review and change control process. | July – September 2015 |
| Technical development of the assessment tool | This includes: - Specification of the IT platform. - Defining the user acceptance criteria. - Building the test environment. - User acceptance testing. Following the tests by ACFP, PS and PL, there may be some further technical development. | July – September 2015 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers | July – September 2015 |
| Conducting the assessment tests and reviewing results | This includes: - Conducting all ACFP, PS and PL tests. - Analysis of candidate feedback and test results. | October – December 2015 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers | October – December 2015 |
| Re-testing the assessments | This includes: - Arrange re-testing sessions for ACFP, PS and PL. - Analysis of candidate feedback and test results. - Sign off of all test results. | January – March 2016 |
| Technical development of the assessment tool | This include: - Final updates following retest – to be agreed with relevant change control process. | January – March 2016 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers | January – March 2016 |
| Handover and project close down | This includes: - Handover of all documentation - IT transfer - An end of project report, with a narrative explaining how the platform works within the social work system and what needs to be done to make it work as part of workforce development; and with recommendations about scaling the work up across the three levels. | January – March 2016 |

Please note that the timescale of these tasks may change and will be monitored at progress meetings every two weeks between DfE and the Consortium.  They may also change due to the mutual agreement of both parties.  The relationship between these tasks may mean that they are mutually dependent.

End of schedule 1

Schedule 2

- Table

| Workstream | Task | Cost | Invoice Date |
| --- | --- | --- | --- |
| Project set and up and the establishment of project governance | This includes: - Agreeing roles and responsibilities with the DfE team. - Agreeing the sign off process for deliverables with the DfE. - Setting up a risk log and issues log. - Agreeing the project’s governance arrangements. - Agreeing the project’s reporting approach. - Agreeing the project’s branding and identity. |  | March 2015 |
| Stakeholder Communication launch | This includes: - Developing the stakeholder consultation policy and procedure. - Developing the Consortium Consultation Panel terms of reference |  | March 2015 |
| Design of the assessment process | This includes: - Listing of different assessment tools and approaches. - Develop a long list – pros and cons - Agree shortlist |  | March 2015 |
| Appraisal of direct observation methods | This includes: - Undertaking a critical review of direct observation (with recommendations for the future), which reviews the methods of direct observation, alongside the development of a digital solution. - Collaborating with a range of other organisations who have experience with practice observation. - The critical review will look at how direct observation could/should be used, alongside a digital solution, across the three social work statuses (practitioner, supervisor, leader). It will address questions including: to what extent direct observation is needed alongside the digital solution; how much direct observation is needed; and what type of direct observation (or combination of methods)? - A written report to the DfE, with recommendations. - An independent person will be appointed by KPMG in consultation with the DfE to conduct the appraisal in order bring independence to this element of the work. - The DfE will have intellectual property rights over the critical review. |  | June 2015 |
| Stakeholder Communication and Consultation | A full review and sign off process for the stakeholder consultation policy and procedure and the Consortium Consultation Panel terms of reference This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers The frequency of consultation with each group of stakeholders will need to be determined. Communication and consultation will be on-going throughout the project. |  | June 2015 |
| Development of knowledge and skills statements and competencies | This includes: - Developing the competences for ACFP. - Developing the knowledge and skills statements for PS. - Developing the knowledge and skills statements for PL. - Developing the competences for PS. - Developing the competences for PL. - A full review and sign off process for the above. |  | June 2015 |
| Design of the assessment process | This includes: - Analysis of assessment options for each level to indicate a preferred approach(es). - Appraisal and selection of additional assessment methods incorporating practice observation to support the digital solution. - Research / visit example sites and research best approaches to conducting practice observation - Consult CCP / ERG regarding perceived applicability of assessment methods - Sampling and testing strategy - Devise testing solution with sample employers - Agree final approach to practice observation with the Chief Social Worker |  | June 2015 |
| Development of the assessment Test Approach | This includes: - Agreeing which competences will be covered in each test item for each of the 3 levels. - Agreeing a sampling approach and a sample size. |  | June 2015 |
| Technical development of the assessment tool | This includes: - Specification of the IT platform. - Defining the user acceptance criteria. |  | June 2015 |
| Design of the assessment process | This includes: - Develop and implement agreed approach to practice observation and the digital solution in line with an agreed resourcing plan |  | September 2015 |
| Development of the assessment Test Approach | This includes: - Producing a detailed development and review schedule for the ACFP, PS and PL tests. - Identifying and booking test locations. - Identifying and inviting test participants. - Agreeing the review and change control process. |  | September 2015 |
| Technical development of the assessment tool | This includes: - Specification of the IT platform. - Defining the user acceptance criteria. - Building the test environment. - User acceptance testing. Following the tests by ACFP, PS and PL, there may be some further technical development. |  | September 2015 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Families - Local authorities and other employers |  | September 2015 |
| Conducting the assessment tests and reviewing results | This includes: - Conducting all ACFP, PS and PL tests. - Analysis of candidate feedback and test results. |  | December 2015 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Family - LA and Employers |  | December 2015 |
| Re-testing the assessments | This includes: - Arrange re-testing sessions for ACFP, PS and PL. - Analysis of candidate feedback and test results. - Sign off of all test results. |  | March 2016 |
| Technical development of the assessment tool | This includes: - Final updates following retest – to be agreed with relevant change control process. |  | March 2016 |
| Stakeholder Communication and Consultation | This includes meetings/ forums/ discussions with: - Consortium Consultation Panel - Social Workers - Children and Family - LA and Employers |  | March 2016 |
| Handover and project close down | This includes: - Handover of all documentation - IT transfer - An end of project report, with a narrative explaining how the platform works within the social work system and what needs to be done to make it work as part of workforce development; and with recommendations about scaling the work up across the three levels. |  | March 2016 |
| Total Travel and Subsistence |  | £84,854 |  |
| Total Professional Fees |  | £2,055,534 |  |

Notes1) Travel and subsistence costs will be charged as incurred up to the agreed limit of£84,854. They have been proportioned across the invoice schedule for illustrative purposes only.

2) The costs are shown to the nearest £1. Any differences are due to rounding of the blended rate.

2	Funds allocated to a particular expenditure heading in the table at paragraph 1 ("the Table") are available for that expenditure heading only.  Funds allocated to a particular accounting year are available for that accounting year only.  The allocation of funds in the Table may not be altered except with the prior written consent of the Department.

3	The Contractor shall maintain full and accurate accounts for the Service against the expenditure headings in the Table.  Such accounts shall be retained for at least 6 years after the end of the financial year in which the last payment was made under this Contract.  Input and output VAT shall be included as separate items in such accounts.

4  	The Contractor shall permit duly authorised staff or agents of the Department or the National Audit Office to examine the accounts at any reasonable time and shall furnish oral or written explanations of the account if required.  The Department reserves the right to have such staff or agents carry out examinations into the economy, efficiency and effectiveness with which the Contractor has used the Department's resources in the performance of this Contract.

5	Invoices shall be prepared by the Contractor Quarterly on the invoice dates specified in the Schedule 2 in arrears and shall be detailed against the expenditure headings set out in the Table.  The Contractor or his or her nominated representative or accountant shall certify on the invoice that the amounts claimed were expended wholly and necessarily by the Contractor on the Service in accordance with the Contract and that the invoice does not include any costs being claimed from any other body or individual or from the Department within the terms of another contract.

6	Invoices shall be sent, within 30 days of the end of the relevant Quarter to SSCL Accounts Payable Team, Room 6124, Tomlinson House, Norcross, Blackpool FY5 3TA, quoting the Contract reference number.   The Department undertakes to pay correctly submitted invoices within 10 days of receipt. The Department is obliged to pay invoices within 30 days of receipt from the day of physical or electronic arrival at the nominated address of the Department.  Any correctly submitted invoices that are not paid within 30 days may be subject to the provisions of the Late Payment of Commercial Debt (Interest) Act 1998.  A correct invoice is one that: is delivered in timing in accordance with the contract; is for the correct sum; in respect of goods/services supplied or delivered to the required quality (or are expected to be at the required quality); includes the date, supplier name, contact details and bank details; quotes the relevant purchase order/contract reference and has been delivered to the nominated address.  If any problems arise, contact the Department's Contract Manager.  The Department aims to reply to complaints within 10 working days.  The Department shall not be responsible for any delay in payment caused by incomplete or illegible invoices.

7	The Contractor shall have regard to the need for economy in all expenditure.  Where any expenditure in an invoice, in the Department's reasonable opinion, is excessive having due regard to the purpose for which it was incurred, the Department shall only be liable to reimburse so much (if any) of the expenditure disallowed as, in the Department's reasonable opinion after consultation with the Contractor, would reasonably have been required for that purpose.

8 	If this Contract is terminated by the Department due to the Contractors insolvency or default at any time before completion of the Service, the Department shall only be liable under paragraph 1 to reimburse eligible payments made by, or due to, the Contractor before the date of termination.

9	On completion of the Service or on termination of this Contract, the Contractor shall promptly draw-up a final invoice, which shall cover all outstanding expenditure incurred for the Service.  The final invoice shall be submitted not later than 30 days after the date of completion of the Service.

10	The Department shall not be obliged to pay the final invoice until the Contractor has carried out all the elements of the Service specified as in Schedule 1.

11	It shall be the responsibility of the Contractor to ensure that the final invoice covers all outstanding expenditure for which reimbursement may be claimed.  Provided that all previous invoices have been duly paid, on due payment of the final invoice by the Department all amounts due to be reimbursed under this Contract shall be deemed to have been paid and the Department shall have no further liability to make reimbursement of any kind.

# End of Schedule 2