Call-Off Schedule 25 (Billable Works and Projects)

- Introduction

  - This schedule prescribes the procedure, calculations and rates to be used by the Buyer and Supplier when assessing the Charges for Billable Works and Projects.

  - For the avoidance of doubt, nothing in this Schedule shall give the Supplier exclusive rights over Billable Works and Projects and the Buyer shall not be required to order Billable Works or Projects from the Supplier and shall be entitled to order Billable Works and Projects from other Suppliers.

  - The Buyer reserves the right to vary or amend this Schedule as part of a Call Off Award Procedure

- Billable Works

  - The Billable Works Management Uplift Percentage shall be applied against the cost of the Billable Works.

  - The Billable Works Management Uplift Percentage shall include the costs of:

    - processing and managing the quotation/tenders within each tier as per the Buyers process;

    - management of works;

    - management of subcontractors (where applicable); and

    - day to day administration.

    - Where the Buyer requests, the Supplier will provide weekly progress reports and attend meetings, to include;

      - Overall status of project

      - KPIs for H&S, Time, Cost, Quality, Risk, Scope and Benefits

      - Performance against Milestone dates

      - Exceptions to milestones

      - List of early warnings (Change Control items)

      - Commercial overview

      - Request for Information (RFIs)

  - The Billable Works Management Uplift Percentage shall exclude any service delivery costs which are expected to be included in the pricing of the works.

  - All Billable Works shall be authorised in accordance with the Billable Works and Approvals Process.  The Buyer may at its discretion require Billable Works to be:

    - managed and executed by the Supplier;

    - managed by a third party nominated by the Buyer and executed by the Supplier;

    - managed by the Supplier and executed by any third party nominated by the Buyer.

  - Any estimate/quotation for Billable Works shall breakdown the costs in the categories below:

    - labour;

    - parts;

    - replacement Assets;

    - materials;

    - such other applicable cost categories as the Buyer may notify to the Supplier from time to time.

    - relevant Billable Works Management Uplift Percentage (which includes Overhead); and

    - profit;

  - Where Billable Works are delivered directly via the Supplier’s appointed Subcontractor the estimate/quotation shall breakdown the cost categories as per 2.5.1 – 2.5.7 and shall also include:

    - Subcontractor name

    - Subcontractor total cost (including Subcontractors profit and overhead)

  - The application of the Billable Works Management Uplift Percentage and Profit percentages shall be as follows:

    - Calculate sum total of costs defined in paragraph 2.5.1 – 2.5.5

    - Apply Billable Works Management Uplift Percentage as per 2.5.6

    - Apply profit as per 2.5.7

- Quotations and Tenders for Billable Works

  - Where the Buyer gives instructions to the Supplier to manage and/or execute Billable Works according to the estimated value ranges, unless otherwise stated at Call Off within the Order Form.

    - Tier One Billable Works shall be managed and executed by the Supplier. Where the Billable Works are to be delivered directly by the Supplier, the Supplier shall provide an estimate of costs in accordance with the rates set out in Call Off Schedule 5 (Pricing Details) or other schedule of rates as requested by the Buyer at Call Off. Where Works are to be undertaken by other Supplier appointed third parties, the Supplier shall provide at least [one] written quotation. The Supplier shall not commence any Tier One Billable Works until approval has been granted by the Buyer to proceed to completion.

    - Tier Two Billable Works shall be managed and/or executed by the Supplier. Where instructed by the Buyer, the Supplier shall obtain at least [two] written quotations. The Supplier shall not commence any Tier Two Billable Works until approval has been granted by the Buyer to proceed to completion.

    - Tier Three Billable Works shall be managed and/or executed by the Supplier.  Where instructed by the Buyer, the Supplier shall obtain at least [three] formal tenders under the defined procurement process as agreed between the Supplier and the Buyer from time to time. The Supplier shall not commence any Tier Three Billable Works until approval has been granted by the Buyer to proceed to completion.

    - Tier Four Billable Works shall be managed and/or executed by the Supplier. Where instructed by the Buyer, the Supplier shall obtain up to [five] formal tenders under the Supplier’s defined procurement process. The Supplier shall not commence any Tier Four Billable Works until approval has been granted by the Buyer to proceed to completion.

    - Where the Buyer allows the Supplier to both manage the tender process and tender for the Billable Works, the Supplier shall ensure appropriate Ethical Wall arrangements are in place to prevent conflicts of interest and that the Public Contract Regulations (2015) are adhered to.

    - The terms and conditions for Billable Works will be as per those in the PSC unless otherwise specified by the Buyer under their defined procurement process.

  - The Supplier shall seek prior written approval from the Buyer prior to proceeding to provide any Billable Works except for:

    - Billable Works up to the value specified in the Order Form (Billable Works not requiring approval); or

    - Billable Works required as a consequence of a Business Critical Event, and the Buyer shall not unreasonably withhold approval to the costs associated with such Billable Works; however the Supplier shall retrospectively commence the relevant approval process set out in paragraph 3.1 by the next Working Day and complete such process as soon as reasonably practicable.

  - Where Billable Works arise because of any:

    - Reactive Maintenance Works where the costs exceed the Inclusive Repair Threshold;

    - Works that are Small Works; or

    - Works arising from Planned Maintenance

the Billable Works shall not proceed until an instruction is received from the Buyer in writing or via the CAFM System.

  - Quotations for Billable Works may include the Billable Works Management Uplift Percentage (if applicable) as per the rates submitted in the Pricing Matrix.

  - If Billable Works are aborted by the Buyer prior to completion, any claim for costs up to the point of it being aborted shall be limited to actual costs, reasonably and properly incurred and they shall be evidenced as part of any quote for the Buyer to consider.

    - On receipt of the Suppliers breakdown and evidence, the Buyer shall either:

      - Notify the Supplier in writing of acceptance of the costs;

      - Request further information/evidence; and/or

      - Request a meeting to discuss/clarify the evidence provided.

  - Where the costs are agreed following the receipt of further information/evidence or following a meeting, the Buyer shall notify the Supplier in writing and confirm the costs are to apply.

  - If the Parties are unable to agree the costs the Parties shall follow the Dispute Resolution Procedure.

- Major Projects

  - If the Buyer decides at its sole discretion that the scope of any Billable Works is such that they require a defined management approach such that the RIBA “Plan of Work” management principles shall apply, then the Billable Works will be deemed to be a Major Project and not a Billable Work.

  - The buyer will appoint the Supplier as Principal Contractor under the provisions of CDM and the Building Safety Act.

  - The Major Projects Project Stage Uplift Percentage shall include the costs of:

    - processing and managing the quotation/tenders within each tier as per the Buyers process;

    - working with and providing timely information to the Client-Side Design Team, appointed separately by the Buyer;

    - management of works via a dedicated project manager;

    - management of subcontractors (where applicable); and

    - day to day administration.

    - Providing weekly progress reports and attending meetings, to include;

      - Overall status of project

      - KPIs for H&S, Time, Cost, Quality, Risk, Scope and Benefits

      - Performance against Milestone dates

      - Exceptions to milestones

      - List of early warnings (Change Control items)

      - Commercial overview

      - Request for Information (RFIs)

    - Bringing new assets into service.

    - Updating the Buyers BIM model.

    - Update the Buyers evacuation plans (Tag Evac).

  - The Supplier shall work in accordance with the details within the Buyers RACI document, unless otherwise agreed in writing before commencement of RIBA Stage 2.

  - The Supplier will propose to the Buyer a process such that each Major Project is adopted into service by both the Suppliers and Buyers Facilities Management (FM) teams, satisfactory completion of which is mandatory before final payments against the Major Project are made. This process must include agreeing any variations to the Contract due to the installation of new assets.

  - The Supplier shall review any Forward Maintenance Register (FMR) with the Supplier and Buyers FM teams to identify any assets that should be considered for replacement as part of the works, in any case, before RIBA Stage 3 is completed. Failure to do so will mean the Buyer is liable to the cost of 50% of the asset replacement cost only.

  - Any other duty required as Principal Contractor under CDM and the Building Safety Act (BSA).

  - If it is deemed as a Major Project, the Project Stage Uplift will apply as stated in the Pricing Matrix.

  - The Supplier will obtain three quotations for individual packages of works exceeding £25,000 in value. The Supplier will confirm who the tendering parties are and why they are being considered for each Major Project. Agreement for using specific sub-contractors will not be withheld unless performance against Health & Safety, Quality or Cost have been raised previously.

  - If the Buyer raises any concerns regarding Health & Safety, Quality or Cost more than twice in any 12-month period, the Subcontractor will not be permitted to work on the contract, unless written approval is received from the Head of Property.

  - The Supplier will provide a tender analysis of each received tender including a recommendation based on both cost and quality. The Suppliers Tender process may be reviewed at any time.

  - It is agreed that the Project Stage Uplift shall always be applied to the value of a Major Project prior to any profit.

  - Major Project Key Performance Indicators (KPIs) will be reviewed on a project-by-project basis, as a minimum at the end of RIBA stage 4 and 6. The Supplier is expected to achieve a score of 70% across each section of the KPI.

  - Failure to achieve 70% at any Stage, will incur a reduction of the Major Projects Project Stage Uplift Percentage as follows;

    - Below 40% will incur a reduction of 50%

    - Below 70% will incur a reduction of 20%

  - The Supplier will submit costs to the Buyer for each project as defined in [4.3], these costs will be deemed to be Target Costs, with the Buyer and Supplier undertaking a Pain/Gain share of 50% for any differences in the actual costs, where;

    - The Target Cost will be increased if the Buyer requests any changes to the agreed scope of works, the Supplier must provide a cost for those works within 5 days from the Buyers request and must not proceed with the works until instruction is received from the Buyer. If it is expected to take longer than 5 days, then the Supplier must inform the ONS PM of how long it will take to provide a cost for that Instruction and the impact that delay may have on the delivery schedule.

    - The Supplier provides Target Costs no less than 10 working days before the Buyer must commit to the project in the form of a Purchase Order to achieve the desired Start and End dates of the Major Project work, providing enough time for the Buyer to review all proposed costs submitted by the Supplier.

    - Examples.

      - Agreed Target Cost of £100,000

      - Client led change orders of £10,000

      - New Target Cost of £110,000

      - Actual Costs submitted in Final Account of £100,000

        - Supplier is due payment of £105,000 (Actual costs plus 50% of cost under-run of £10,000 (£110,000 less £100,000 Actual Costs)

      - Actual Costs submitted in Final Account of £120,000

        - Supplier is due payment of £115,000 (Target Cost plus 50% of cost over-run of £10,000 (£120,000 Actual Costs less £110,000 Target Costs)

  - If a Major Project is aborted by the Buyer prior to completion, if applicable, the relevant Project Stage Uplift will be applied up to the point at which it is aborted based on the agreed estimated cost of the Project.

  - The Supplier shall provide evidence of the resource allocation required to provide any Project at the time of quotation or tender and such associated costs must be agreed as acceptable by the Buyer prior to any Works which are part of a Project commencing.

  - If professional services are required, then a separate appointment will be made, using the Major Works fee model and will cover the services of;

    - Design Team

    - Principal Designer (CDM)

    - Principal Designer (BSA)

    - Cost Manager

    - Project Management

    - Feasibility

  - This separate Major Works Fee Model will be deemed to include all Overheads and Profit and as such will not be liable to any additional uplifts.

- General Projects (Non-RIBA)

  - If the Buyer decides at its sole discretion that the scope of any Billable Works are such that they require a defined management approach other than the RIBA plan of works, this will be deemed to be a General Project and not a Billable Work and the management approach will be defined by the Buyer at Further Competition.

  - The Supplier shall provide evidence of the resource allocation required to provide any Project at the time of quotation or tender and such associated costs must be agreed as acceptable by the Buyer prior to any Works which are part of a Project commencing.

  - If the Buyer aborts General Projects at any stage, the Supplier may provide a full breakdown and evidence of the resource allocation utilised and associated costs to date on notification of the Buyer.  Such associated costs must be agreed as acceptable by the Buyer prior to raising the invoice

    - On receipt of the Suppliers breakdown and evidence, the Buyer shall either:

      - Notify the Supplier in writing of acceptance of the costs;

      - Request further information/evidence; and/or

      - Request a meeting to discuss/clarify the evidence provided.

    - Where the costs are agreed following the receipt of further information/evidence or following a meeting, the Buyer shall notify the Supplier in writing and confirm the costs are to apply.

    - If the Parties are unable to agree the costs the Parties shall follow the Dispute Resolution Procedure.

- Inclusive Repair Threshold

  - The Supplier shall note that except for emergencies or Business Critical Events, no activity with a value more than the agreed Inclusive Repair Threshold shall be undertaken without a Work Order.

  - Where the costs of Reactive Maintenance Works exceed the Inclusive Repair Threshold, only the cost above this value shall be billed to the Buyer through the approval process as detailed in the Billable Works and Approvals Process.

  - The Supplier shall supply and install all parts associated with Reactive Maintenance Works at its own cost. The Supplier shall note that, for the avoidance of doubt, this requirement includes the replacement of entire Assets as well as component part of Assets where replacement is deemed appropriate.

  - The Supplier shall maximise the benefits of its own buying power by being granted access to and exploring other CCS frameworks and benchmarking against these before looking to their own supply agreements to offer the most advantageous commercial position to the Buyer to ensure value for money. Any negotiated discounts applied against current trade price levels shall be passed to the Buyer in full. Where appropriate the Supplier shall utilise the Buyer’s parts agreements, where any such agreements exist.

  - The Supplier shall source parts at the most cost-effective terms having regard to quality and delivery time requirements. The Supplier and the Buyer shall agree in advance the use of refurbished parts where they are deemed to be cost beneficial without any loss of service or as required in order to achieve required return to full operational service.

  - In the event of emergencies or Business Critical Events, the Supplier may proceed with remedial action without prior approval from the Buyer. The Supplier shall seek formal approval from the Buyer by email and/or telephone as soon as is operationally possible and shall keep the Buyer always advised on the technical and financial status of the task. The Buyer shall not unreasonably withhold approval of costs arising from emergencies and Business Critical Events; however, the Supplier shall retrospectively commence the relevant approval process set out in paragraph 6.1 by the next Working Day and complete such process as soon as reasonably practicable

  - Where works fall into the following categories, they are exclusions to Inclusive Repair Threshold and charges will be subject to review and agreement between the Supplier and the Buyer during Monthly contract performance meetings. Where charges apply, they will be considered via the Billable Works and Approvals Process. This will include but not be limited to unless otherwise stated at Call Off:

    - equipment Beyond Economic Repair, where costs, excluding management overhead and profit, exceed the Inclusive Repair Threshold;

    - misuse of an Asset and/or abuse of an Asset where this can be proven by the Supplier;

    - vandalism;

    - damage or failure if due to continued use by the Buyer or building user after fault has been diagnosed and the Supplier has advised the Buyer not to use the Asset;

    - the building user not following the Buyer or manufacturer’s operating procedural standards;

    - other unapproved suppliers repairing Assets;

    - water or cleaning fluid damage due to incorrect cleaning procedures by building users;

    - damage or failure due to electrical supplies being interrupted or altered by others;

    - access denied to the Supplier where access had been agreed and prearranged;

    - buyer specifies a price variation;

    - fire, leaks, act of God, storm damage, floods or similar force majeure; unless caused by an act or failure of the Supplier;

    - Billable Works;

    - that part of the cost of the Reactive Maintenance Works for an 	event which exceeds the Inclusive Repair Threshold; and

    - operator error by a building user, where this can be proven by the Supplier.

The above listed works include works arising from Planned Maintenance.

  - A schedule of works arising from events listed in paragraph 6.6 above shall be provided to the Buyer on a monthly basis and payment will be made through the defined approval process as agreed between the Buyer and the Supplier.

- Annual Look Ahead

  - During September of each contract year, the Supplier will present to the Buyer a list of investments representing the next 5-year investment plan, these will consider items from the;

    - Forward Maintenance Register (FMR);

    - Accessibility Audits;

    - Fire Risk Assessments;

    - Condition surveys; and

    - Health & Safety Audits.

  - The Supplier shall have engaged with the Facilities Management and Health & Safety teams in the Buyers Property Services Division, to assess when these investments need to be made and the priority for each investment.

  - For the purposes of modelling and transparency, the actions from 7.1.2, 7.1.3 and 7.1.4 shall be captured in the FMR where the following fields are mandatory:

    - Asset ID

    - Criticality of Asset

    - Cost of replacement (in this case, desired action).

  - The review should be made using DynamicAim or other system used by the Buyer to manage their assets and their performance. The Supplier may provide data in an alternative format if the FMR data set is maintained before and after this annual review.

  - The Supplier is responsible for maintaining the accuracy of the FMR at all times and for loading a copy of the FMR into DynamicAim, no less than every 3 months.