## FOO Template
|  |  | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | [5 empty] | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
Current Period | Jul'21
Firm Price
Forecast/Actuals of work complete (% of milestone)
FY21/22
Milestone | Description | Value (£) | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total | Work completed to date (As at Jul'21) | Evidence to support work done to date
1 | Delivery of Progress Reporting | 20000 | FY21/22 Apr: 25%; FY21/22 May: 25%; FY21/22 Jun: 50% | 100% | 100% | Progress report delivered to PM on 20/03/21
2 | Delivery of final PYRAMID Component (Baseline) | 200000 | FY21/22 Jul: 50%; FY21/22 Nov: 50% | 100% | 50%
4a | Delivery of final Lessons Learned Report Version 1 | 95000 | FY21/22 Sep: 20%; FY21/22 Oct: 20%; FY21/22 Nov: 20%; FY21/22 Dec: 20%; FY21/22 Jan: 20% | 100% | 0%
4b | Delivery of final Lessons Learned Report Version 2 | 10000 | FY21/22 Oct: 20%; FY21/22 Nov: 20%; FY21/22 Dec: 20%; FY21/22 Jan: 20%; FY21/22 Feb: 20% | 100% | 0%
325000
Cost Plus
Forecast/Actuals of hours worked
|  | Labour Rate (per hr) | FY21/22 Apr: FY21/22
Milestone | Description |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total hrs
3a | Delivery of draft PYRAMID Component (Amended) | 54.6 | FY21/22 Jul: 325 | 325
3b | Delivery of draft PYRAMID Component (Amended) | 25 | [12 empty] | 0
3c | Delivery of final PYRAMID Component (Amended) | 75.6 | [12 empty] | 0
Firm Price Hourly Rate
Forecast/Actuals of hours worked
|  | Labour Rate (per hr) | FY21/22 Apr: FY21/22
Milestone | Description |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total hrs
5 | Delivery of 100 hours of support to System Integration | 10 | FY21/22 Nov: 15; FY21/22 Dec: 20; FY21/22 Jan: 5; FY21/22 Feb: 5; FY21/22 Mar: 5 | 50
CALCULATED AUTOMATICALLY (USING DATA ABOVE)
Total Forecast (£)
FY21/22
Milestone |  | Description | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Total |  | Work completed to date (As at Jul'21 | Invoices Paid to date | DE&S Accrual for Jul'21
1 | Delivery of Progress Reporting |  | 5000 | 5000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  | 20000 |  | 20000
2b | Delivery of final PYRAMID Component (Baseline) |  | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 200000 |  | 100000 |  | 100000
3a | Delivery of draft PYRAMID Component (Amended) |  | 0 | 0 | 0 | 17745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17745 |  | 17745 |  | 17745
3b | Delivery of draft PYRAMID Component (Amended) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
3c | Delivery of final PYRAMID Component (Amended) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0
4a | Delivery of final Lessons Learned Report Version 1 |  | 0 | 0 | 0 | 0 | 0 | 19000 | 19000 | 19000 | 19000 | 19000 | 0 | 0 | 95000 |  | 0 |  | 0
4d | Delivery of final Lessons Learned Report Version 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000 | 2000 | 0 | 10000 |  | 0 |  | 0
5 | Delivery of 1-- hours of support to System Integration |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 200 | 50 | 50 | 50 | 500 |  | 0 |  | 0
[15 empty] | 343245 |  | 137745 | 0 | 137745

## Notes for completion
ONLY CELLS THIS COLOUR WILL REQUIRE INPUT
Select current reporting period in Cell B2. This will automatically highlight what periods are now actuals and what are forecast
Milestone | Description | Type | Price | Basis
1 | Delivery of Progress Reporting | Firm Price | Value of Milestone will be agreed beforehand | Cells D7:O7 For months of when it is highlighed as actual, reflect the % of work completed For future forecasting months estimate how much % of the milestone will be completed for each month When complete, Cell P7 should be green and show actuals/forecast that 100% of the milestone will be completed
2 | Delivery of draft PYRAMID Component (Baseline) | Firm Price | Value of Milestone will be agreed beforehand | Cells D8:O8 as above for milestone 1
3a | Delivery of draft PYRAMID Component (Amended) | Cost Plus | Rates agreed before hand and added into Cell C20:C22 Costed at no. of hrs x hourly rate | Cells D17:O19 For months of when it is highlighted as actual, reflect the number of hours of work completed For future forecasting months estimate how many hours will be completed for each month Forecast is then calculated based on the agreed rates X the no. of hours applied
3b | Delivery of draft PYRAMID Component (Amended) | Cost Plus
3c | Delivery of final PYRAMID Component (Amended) | Cost Plus
4a | Delivery of final Lessons Learned Report Version 1 | Firm Price | Value of Milestone will be agreed beforehand | Cells D9:O9 as above for milestone 1
4b | Delivery of final Lessons Learned Report Version 2 | Firm Price | Value of Milestone will be agreed beforehand | Cells D10:O10 as above for milestone 1
5 | Delivery of 50 hours of support to System Integration | Firm Price | Rates agreed before hand and added into Cell C28. Costed at 50hrs x hourly rate | Cells D25:P25 For months of when it is highlighted as actual, reflect the number of hours of work completed For future forecasting months estimate how many hours will be completed for each month When complete, Cell P28 should be green and show actuals/forecast of the 50hrs available
FORECAST (£)
Cells A30:O38
Uses all the information above to calculate the forecast in £
Used by DE&S for corporate reporting and calculation of monthly accruals

## Sheet2 (hidden)
Actual/Forecast
Apr'21 | Apr | 1 | Actual
May'21 | May | 2 | Actual
Jun'21 | Jun | 3 | Actual
Jul'21 | Jul | 4 | Actual
Aug'21 | Aug | 5 | Forecast
Sep'21 | Sep | 6 | Forecast
Oct'21 | Oct | 7 | Forecast
Nov'21 | Nov | 8 | Forecast
Dec'21 | Dec | 9 | Forecast
Jan'22 | Jan | 10 | Forecast
Feb'22 | Feb | 11 | Forecast
Mar'22 | Mar | 12 | Forecast