Area 3 Asset Support Contract

Service Information

Annex 19

Reports

SERVICE INFORMATION FOR AREA 3 ASC

ANNEX 19

CONTENTS AMENDMENT SHEET

| Amend. No. | Issue Date | Amendments | Initials | Date |
| --- | --- | --- | --- | --- |
| 0 | August 2012 | First Issue | SOS | 21/08/12 |
| 1 | October 2012 | New entries added in Table 19.1 to include Category Management Plan, Asset Data Gap Analysis report and Information/Records Gap Analysis report | SOS | 05/10/12 |
| 2 | October 2012 | New entry added in table 19.1 to include Safety Incident Reporting requirement. | SOS | 24/10/12 |

LIST OF CONTENTS

19	REPORTS	4

19.1	Introduction	4

19.2	Monthly Review Progress Report Framework	14

19.3	Maintenance and Making Better Use Guides Reports	16

19.4	SfM Reports	17

19.5	NRSWA Reports	22

19.6	Nonconformity and Corrective Action Reports	24

19.7	Cost Capture	25

APPENDIX A: NDD Out-turn data

APPENDIX B: Activity Benchmark Sheet

APPENDIX C: Annual Commercial Plan and Guidance Note

# REPORTS

## Introduction

    - Table 19.1 identifies reports which are to be submitted by the Provider to the Employer and includes the Monthly Review Progress Report. Other reports as set out in Table 19.1 are made available to the Employer as appropriate, or as required by the Employer, and may be appended to the Monthly Review Progress Report.

    - Tables 19.2 to 19.7 provide further details of reports to be provided by the Provider on particular topics.

    - All reports are to be submitted by in electronic format unless otherwise stated or as required by the Employer.

    - All reports with a frequency of “as required” or “as required by the Employer” shall be requested through the Service Manager.

Table 19.1

| Ref No. | Title | Contract Reference / Document Source | Description / Remarks | Frequency |
| --- | --- | --- | --- | --- |
|  | Monthly Review Progress Report | Annex 19 Table 19.2 | The Provider shall prepare a Monthly Review Progress Report the framework for which is outlined in Table 19.2 | Monthly (7 working days after the end of month) |
|  | Annual Commercial Plan and Guidance Note | Service Information Chapter 2.2 and Appendix C | Plan to be prepared during mobilisation in the first year and prior to the commencement of each subsequent financial year. | Annual |
|  | Reports to Network Board | Service Information Chapter 1.1.2 (4) | Various reporting requirements. | Quarterly or as required |
|  | Performance and Continual Improvement | Conditions of Contract Clause 53 | The Provider reviews and reports on performance levels and costs incurred compared to the Annual Commercial Plan. | Annually (not later than two months before the end of each financial year) |
|  | Strategies & Plans |  | Reviews, updates and maintains Employer’s strategies and plans. | As required |
|  | SfM | Annex 21 & Annex 19 Table 19.4 | Financial and Output Reports in accordance with Table 19.4 of this Annex. | As required by the Employer |
|  | SfM | Annex 19 Table 19.4(a) & 19.4(b) | Outturn cost data and Activity Benchmark sheets. | At scheme final account |
|  | Cost Capture | Service Information Chapter 2.4 & Annex 5 | Reports using Cost Report in accordance with Table 19.7. | Monthly |
|  | NRSWA | Annex 19 Table 19.5 AMOR Part 2 - Managing Network Occupancy Requirement and Annex | Report to the Employer as outlined in Table 19.5 attached. Monitor compliance with legislation in Annual report and identify areas of non-compliance and action plan for improvement. | Annually |
|  | Winter Service - operator’s daily diary of decisions and actions taken | AMOR Part 4 - Severe Weather Requirement and Appendix | Provide operator’s daily diary of decisions made and actions taken during the winter service period in order to record decisions made and provide confirmation of winter service treatment actions. | ”Live” reporting during Winter Period (Web based system) |
|  | Weather Conditions | AMOR Part 4 - Severe Weather Requirement and Appendix | Report on the weather conditions (actual and forecast site conditions for each 24 hour period) during the winter service period. Monitor changes of weather condition on the Area Network: a. Liaise with media team where necessary; b. Inform senior management where appropriate. | Daily during Winter Period (Web based) |
|  | Weather Forecasting Analysis | AMOR Part 4 - Severe Weather Requirement and Appendix | Report detailing end-of-season analysis of the accuracy of weather forecasts, for each forecast site, based on information contained in the Road Weather Information System. The Forecasting Organisation prepares the report for the Provider. | Annually (As required) |
|  | Winter Service – thermal mapping- | Severe Weather Plan AMOR Part 4 - Severe Weather Requirement and Appendix | Report on any changes adjacent to and on the Area Network which will affect the Employer’s thermal mapping information. Review coverage of thermal maps as part of winter service and identify areas of improvement. | As required |
|  | Winter and Business Continuity | AMOR Part 4 - Severe Weather Requirement and Appendix | Report on the winter and business continuity throughout the Winter Period. Monitor adequate salt stock level, to ensure salt stock is above capability threshold level, reserve fleet levels and fuel stocks (as appropriate) throughout the Winter Period. | Daily reporting during Winter Period (Web based system) |
|  | Winter Service Operational Assessment Report | AMOR Part 4 - Severe Weather Requirement and Appendix | Report on the performance of all aspects of the winter service at the end of the winter period. Include any recommendations for further actions to improve the operations as appropriate. Present the report to the Employer during the first week of June each year throughout the Contract Period to enable the Employer to review the effectiveness of the winter service. | Annually |
|  | Watchman Role / General | AMOR Part 1 Watchman Role | Report on all matters performed by the Provider in relation to the watchman role. | Quarterly |
|  | Contract (Managed Works) | Annex 9 Contract Management Duties | Report in accordance with the requirements of each Managed Works services contract; including but not limited to: - Tender assessments (financial and quality) competitive and framework evaluation; - monthly valuations; - completion/ maintenance/ other certificates; - site inspections and test work; - financial reports; - procurement schedules; - Scheme design and construction programmes; - action plans; - Engineer or Project Manager and Supervisor monthly progress reports; - reports on claims to identify any potential overspend, compensation events (including estimates and altering drawings, specifications and other details) and any financial risks; - Maintains such records of the Contractor’s performance necessary to complete Motivating Success - A Toolkit for Performance Measurement or provide objective and detailed reports to the Service Manager. | Monthly or as required by the Employer |
|  | Close down meeting lessons learnt and innovation | Annex 9 Contract Management Duties | - The Provider shall chair a close down meeting on completion of the Scheme. Any lessons learnt or innovations from the Scheme are to be reported to the Service Manager in an agreed format. | On completion of each Scheme. |
|  | Programme Development | Table 19.3 & Annex 18 Reference documents: Annex 25 | Report in accordance with the requirements of the Programme Development Management Manual | As stated in Table 19.3 |
|  | Energy Procurement Strategy (EPS) | Annex 18 Reference documents: & Annex 6 Information Systems | Report to the EPS Administrator providing a copy of the complete EPS formatted half hourly lighting inventory updated to include all amendments/additions to road lighting and illuminated signs. | Monthly on the first working day each month |
|  | Communications & Media Relations | Service Information Chapter 1.8 & Annex 3 | The Provider will monitor contact with stakeholders (inc. media and customers) – and report to Service Manager and HA Communications Group. The Provider shall also include a section on communications in its monthly report to the Service Manager. This includes a review of all agreed proactive and reactive media contact and coverage; any agreed publicity and advertising; and, community liaison work. (Ref. Annex 3 section 3.5.2) | On each occasion immediately following contact |
|  | Management of Employer’s Stocks | Service Information Chapter 1.13 | Report on inventory of Employer’s Stocks in terms of serviceability, movement, usage and disposal. Monitor utilisation of Employer’s Stocks. Ensure Employer’s Stocks are effectively utilised. | Bi-annually |
|  | Design (including road safety audits and exception reports) | Annex 20 | Undertake when instructed by the Employer an assessment of designs submitted by others and report findings to the Employer. Report on design progress, departures from standard, liaison with statutory undertakers and other statutory organisations, land acquisition requirements, statutory procedures and orders and road safety audits. | As required by the Employer |
|  | Various Provider’s Plans and Reports as detailed in AMOR and Appendices | AMOR Part 0 - All sections | Provide all the forward plans as required in AMOR to demonstrate the management of the Asset Maintenance and Operations. A non-exhaustive list of these plans includes: - Environmental Management Plan - Incident Response Plan - Lighting Asset Management Plan - Maintenance Requirements Plan (MRP) - Manage Network Occupancy Plan - Salt Restocking Plan - Severe Weather Plan - Strategic Lighting Asset Management Plan. | Annual |
|  | ADMM Reports | ADMM | Report in accordance with the reporting requirements of ADMM for various systems and services including HAPMS, geotechnics, drainage, environmental, winter services, etc. | As required by ADMM and the Employer |
| 26a. | Accidents & Incidents / Emergencies | AMOR – Part 3 - Incident Response and Appendix Part 4 - Severe Weather Requirement and Appendix | Provide the reports in relation to accidents and incidents. - Tactical Incident Response Plan (TIRP) (undertaken for each incident notified of) - Incident Data Capture sheet (completed for each incident attended) (NB. there is a parallel procedure under which the police also report certain major accidents direct to the Employer). - Accidents / incidents involving Providers winter service vehicle. | - As required. - As required - As stipulated in Severe Weather Plan |
| 26b. | Supply Chain Health and Safety Incident Reporting | IAN 128/12 | In accordance with IAN 128/12 | As required |
| 27. | Collection of Fees | Service Information Chapter 2.5 | Report to the Employer all fees recovered on his behalf. | Monthly |
| 28. | Third Party Claims handled by the Provider | Service Information Chapter 1.9 & Annex 23 | Report detailing, for each claim, the amount of repair costs calculated on the basis of Defined Cost plus Fee, the amount claimed from third parties, the amount recovered and an explanation of any differences between any of these amounts. | As required by the Employer |
| 29. | Development control | Service Information Chapter 6.5 | Report on advice on effect of proposed development/re-development on Area Network. | As per development proposal |
| 30. | Employer’s Vehicles | Annex 7 | - Vehicle condition, status and defect reports including any repairs or modifications carried out (refer Annex 7.3.6). - Joint Inspection reports (report submitted within 14 days of inspection) (refer Annex 7.2.7). - Accident reports (refer Annex 7.2.5). - Pre winter checks (report submitted within 3 days of checks) (refer Annex 7.3.7). - Roadside Repair (refer Annex 7.6.1). | a. Within 1 week of the access date and following any change / action & at Monthly intervals with summaries at Sept and March each year b. within 28 days of the access date and within 28 days before the end of the Contract Period c. Immediate d. September each year e. As soon as possible |
| 31. | Scheme development | Annex 20 | Develop Forward programme; produced PAR; report variance cost estimate/budget; report variance of design during construction; and post project reviews. | As required in Annex 20 |
| 32. | Tourist Signs | Service Information Chapter 6.11 | When instructed by the Employer undertake an assessment, for a particular applicant, of the feasibility of provision of tourist signs, inclusive of preliminary estimated costs, in accordance with the principles in Circular Roads 3/95 and report findings with recommendations to the Employer. Study and LNMS scheme development. | As required by Employer |
| 33. | Demobilisation duties | Service Information Chapter 1.10.2 | A report on all designs in progress, outstanding defects, work in progress and the Provider’s assessment of all duties that would appropriately be performed by the Provider after the end of the Contract Period. | A draft of the information is provided 3 months before the expiry of the Contract Period and is finalised 1 week before the expiry of the Contract Period or at a time agreed with the Service Manager. |
| 34. | Non-conformity and Corrective Action Reports | Table 19.6 | Report as outlined in Table 19.6. | As required by Table 19.6 |
| 35. | Lean “Planned & Realised” Benefits Report | Annex 14 Lean Benefits Realisation Guide | Report using data from the Benefits Realisation Capture Form (BCRF) structured around “Planned Benefits” and “Realised Benefits”. | Annually |
| 36. | Category Management Plan | Annex 29 | Plan proposing Provider’s approach to category management as detailed in Annex 29. | Prior to access date and updated quarterly |
| 37. | Information/ Records Gap Analysis report | Service Information Chapter 3.1 | Submits an Information/Records Gap Analysis report to the Service Manager detailing gaps listed in Annexes 17 & 19. | Within 2 months of the access date |
| 38. | Asset Data Gap Analysis Report | Annex 25 (Section 25.4.2) | A report detailing deficiencies in the completeness, currency and correctness of the asset data. | As required in Annex 25 |

Notes to Table 19.1: -

- All reports shall include where appropriate recommendations for further actions.

- References to documents, forms, appendices or similar may be amended at any time by the Employer.

## Monthly Review Progress Report Framework

    - The purpose of the Framework is to monitor the Provider’s performance to meet contract requirements in order to deliver the Employer’s objectives.

    - The schedule below forms a general framework for the Monthly Review Progress Report (MRPR).

    - The exact format of the MRPR and any subsequent amendments to the format required shall be agreed with the Employer.

    - The MRPR shall be a brief report of each item below using exception reporting whenever practicable.

Table 19.2

| Ref | Item | Item Coverage |
| --- | --- | --- |
|  | Financial Monitoring | Comparison of actual and forecasted expenditure against budget for all works carried out on the Area Network, together with analysis and reason for variances. Budget allocation reviews and updates. Programme development in accordance with the Maintenance and Making Better Use Guides. |
|  | Annual Plan | Report on progress made in achieving Annual Plan targets or requirements. Annual Plan issues. |
|  | Report of Performance Management (Annex 15) | Record performance scores for each output performance indicator in the Employer’s Performance Management Framework in accordance with Annex 15. |
|  | Development Control | Summary of progress of all development control issues. |
|  | Customer Service | Provide customer service reports to the Employer, including the following: No of complaints/enquiries, received, responses given and actions taken. Response times, number and type should correspond with CRS/HAIL customer categories and the media reporting categories given in the Appendix to this Table (as abstracted from the HAIL categorisations) of complaints received and actions taken. |
|  | Publicity and Public Relations | a. Prepare a programme of activity to help inform future HA communications plans including identifying all works affecting the Area Network that require advance publicity or could generate media or public interest. Details would typically include scheme information; programme dates; times of operation; proposed lane closures; traffic safety and management measures; alternative routes as applicable; the impact to the road user; and, benefit to the Employer’s customers. b. Report back on local issues and how local communications activity has been received. This should include any agreed contact with the media, and any proposed publicity agreed with the Employer. The Employer already has separate media monitoring arrangements in place and the Provider should discuss with the HA Communications Group any instances of contentious media reporting including that which may require a response. |
|  | Any Other Issues | Any other issues considered necessary to report and or as required by the Employer, for example Partnering issues. |
|  | Appendices | Append any detailed reports as appropriate and as required by the Employer as outlined in Table 19.1 of this Annex. |

## Maintenance and Making Better Use Guides Reports

    - The following is an indicative summary of the main reporting requirements of the Maintenance and Making Better Use Guides.

| Table 19.3Ref | Description | Remarks | Frequency |
| --- | --- | --- | --- |
| 1 | Project Appraisal Reports (PAR) | Project appraisals for programme development proposals in accordance with the Maintenance and Making Better Use Guides. | As required by the Employer. |
| 2 | Value management workshops | Report information as outlined in the Maintenance and Making Better Use Guides to Value Management Workshops. | As required by the Employer. |
| 3 | Software for Whole-life Economic Evaluation of Pavements (SWEEP) | Report on the SWEEP Analysis of regional roads projects by applying whole life costing in accordance with the Maintenance and Making Better Use Guides and Scheme Appraisal System. | As required by the Employer. |
| 4 | Programme development | Report on the development of the regional structures programme in accordance with the Programme Development Management Manual | As required by the Employer. |

## SfM Reports

    - The Employer operates a computer-based management information system (SfM). In addition to information provided through the business planning and financial procedures, it will be necessary for the Provider to provide regular reports, generally monthly.

    - Typical information requirements are outlined below but these may vary as further performance indicators are developed.

    - Physical and financial progress reporting is aimed to assist the Employer and the Provider in management of the Work. Emphasis will be placed on monitoring progress against predicted expenditure profiles, for all Work and associated preparatory activities, and the Provider shall assist in producing the reports.

    - The Provider shall provide the data in an agreed format and content, using software provided by the Employer. Until such time as data transfer is made by means of the Business Information Gateway Interface the Provider shall provide the necessary data in electronic format to the Employer by other means to be agreed.

    - The Employer will provide details of the timing and content of the required reports.

    - Reporting requirements are outlined in Table 19.4 below. For the current year, reporting will be monthly and cumulative completion of each output unit as recorded in SfM.

Table 19.4

| Data Item | Output Unit | Frequency |
| --- | --- | --- |
| Contracted cost | scheme £ 0.1k, month. | At acceptance, at revision. |
| Forecast period costs to the completion of the project. | scheme £1k, month. | Monthly as per agreed timetable or at agreed milestones. |
| Dates when key milestones achieved | scheme, agreed events. | As achieved. |
| If a scheme is expected to start next month | y/n. | When occurs. |
| If a scheme is expected to end next month | y/n. | When occurs. |
| Reconstruction | scheme, number of lane kms. | Monthly |
| Surface overlay | scheme, number of lane kms. | Monthly |
| Surfacing inlay | lane kms. | Monthly |
| Resurfacing | lane kms. | Monthly |
| Quiet surfacing | lane kms. | Monthly |
| Surface dressing | lane kms. | Monthly |
| Structures strengthened | scheme, number. | Monthly |
| Structures inspected | number | Monthly |
| Structures assessed | scheme, number. | Monthly |
| Structures renewal schemes – strengthening | Number | Monthly |
| Structures renewal -safeguard | Number | Monthly |
| Structures renewal – upgrade piers/supports | Number | Monthly |
| Routine maintenance structural surveys | lane kms | Monthly |
| Routine maintenance – skid resistance surveys | lane kms | Monthly |
| Routine maintenance – inspection of surfacings | carriageway kms. | Monthly |
| Emergency phones tested to target | number, 1%. | Monthly |
| Emergency phones repaired to target | number, 1%. | Monthly |
| Salting within 2 hours of forecast | number of events, 1%. | Monthly |
| Advance warning given of roadworks | y/n | On event. |
| Numbers of emergency phones installed | number | Monthly |
| Lighting installed/replaced | km | Monthly |
| Signage cleaned to standard | y/n | Monthly |
| Litter cleared to standard | y/n | Monthly |
| Projects / Schemes | Number | Monthly |
| General inspections | Number | Monthly |
| Principal inspections | Number | Monthly |
| Special inspections | Number | Monthly |
| Post tensioned inspections | Number | Monthly |
| LMNS – toolkit (pilots) | Number | Monthly |
| LMNS – safety | Number | Monthly |
| LNMS – accessibility | Number | Monthly |
| LNMS – environment | Number | Monthly |
| LNMS – integration | Number | Monthly |
| LNMS – multi-modal studies | Number | Monthly |
| LNMS – road based studies | Number | Monthly |
| LNMS – TCC milestones | Number | Monthly |
| LNMS – economy | Number | Monthly |
| Network communications schemes – renewals | Number | Monthly |
| Section 274/278 schemes | Number | Monthly |

    - In order for the Employer to capture further analysis of specific project Works expenditure, the Provider will be required to capture all Defined Costs including actual costs where the defined cost is deemed to be zero and a breakdown of payments in respect of work which is subcontracted, against the Schedule of Cost Components headings. The Provider is to report these Defined Costs, excluding fee on the document “NDD Out-turn data” contained in Appendix A. “Other” to include Charges and Insurance costs.

    - Each Defined Cost recorded in the out-turn, must in addition, be allocated against appropriate activities in the Activity Benchmark Sheet (ABS) as part of cost reporting in accordance with Table 19.4(a). The Activity Benchmark Sheet data is to include fee to reflect the total works cost excluding pain/gain. The Activity Benchmark Sheet is contained in Appendix B.

Table 19.4 (a)

| Works expenditure should be summated to these Activities and Defined Cost including actual costs where the defined cost is deemed to be zero captured and allocated to these Reference nos |  |  |
| --- | --- | --- |
| Series subheading | Activity | NDD Out-turn Reference No. |
| 100 | Preliminaries (Excluding TM) | 100 (all) |
|  |  | 101 (all) |
|  |  | 102 (all) |
|  |  | 103 (all) |
|  |  | 104 (all) |
|  |  | 105 (all) |
|  |  | 113 (all) |
|  |  | 114 (all) |
|  |  | S1 100 (all) |
| 100 A | Traffic Management | 115 (all) |
| 200 | Site Clearance | 200 (all) |
|  |  | S1 200 (all) |
| 300 | Fencing | 300 (all) |
| 400 | Vehicle Restraint (Concrete) | 400.5 |
|  | Vehicle Restraint (Non-Concrete) | 400 |
|  |  | 400.05 |
|  |  | 400.1 |
|  |  | 400.15 |
|  |  | 400.2 |
|  |  | 400.4 |
|  | Pedestrian Guardrail | 400.3 |
|  | Parapet Non Concrete N1 | S1 400.1 |
|  |  | S1 400.15 |
|  | Parapet Non Concrete N2 | S1 400.11 |
|  |  | S1 400.16 |
|  | Parapet Concrete | S1 400.12 |
| 1800 | Structural Steelwork | S1 1800 (all) |
| 5000/1900/1700 | Protection of Steel work against corrosion (includes maintenance painting and concrete finish) | 5000 (all) |
|  |  | S1 1900 (all) |
| 2000 | Waterproofing | S1 2000 (all) |
| 2100 | Bridge Bearings | S1 2100 |
| 2300 | Bridge Joints (Asphaltic plug) | S1 2100.2 |
|  | Bridge Joints (Metal/rubber) | S1 2100.3 |
|  | Bridge Joints (Mechanical and other) | S1 2100.4 |
| 2400 | Brickwork, Blockwork and Stonework | 2400 (all) |
|  |  | S1 2400 (all) |
| 2500 | Special Structures | S1 2500 (all) |
| 2700 | Other Works (Service Utilities, Noise Insulation, Accommodation works etc) | W 2700 (all) |
|  |  | S1 2600 (all) |
| 3000 | Landscape and Ecology | 3000 (all) |

    - The Provider submits an ABS with Target quantities and costs prior to Stage 3 (Construction, as per Annex 20) for all Schemes. At financial completion, ABS will be completed in full and submitted to CommercialCentral@highways.gsi.gov.uk. These will be in relation to the breakdown of the cost and the Unit of Measure as per the categories detailed in Table 19.4(b) below.

    - The Provider is responsible for maintaining all records of quantity changes which result from any potential or agreed compensation events which change the Prices.

Table 19.4 (b)

| Task | Description | Target Quantity | Changes | Initial Target Value | Changes | PSPD | Unit of Measure |
| --- | --- | --- | --- | --- | --- | --- | --- |
| N4.1 | Preliminaries |  |  |  |  |  | Weeks |
| N4.2 | Traffic Management |  |  |  |  |  | Weeks |
| N4.3 | Site Clearance |  |  |  |  |  | Hectares |
| N4.4 | Fencing |  |  |  |  |  | Linear Metres |
| N4.5 | Vehicle Restraint Systems (Concrete) |  |  |  |  |  | Linear Metres |
| N4.6 | Vehicle Restraint Systems (Non-Concrete) |  |  |  |  |  | Linear Metres |
| N4.7 | Pedestrian Guardrail |  |  |  |  |  | Linear Metres |
| N4.8 | Parapet Non Concrete N1 |  |  |  |  |  | Linear Metres |
| N4.9 | Parapet Non Concrete N2 |  |  |  |  |  | Linear Metres |
| N4.10 | Parapet Concrete |  |  |  |  |  | Linear Metres |
| N4.11 | Drainage & Service Ducts |  |  |  |  |  | Linear Metres |
| N4.12 | Filter Drain Recycling |  |  |  |  |  | Cubic Metres |
| N4.13 | Filter Drain Removal/ Renewal |  |  |  |  |  | Cubic Metres |
| N4.14 | Earthworks |  |  |  |  |  | Cubic Metres |
| N4.15 | Pavements - Sub Base |  |  |  |  |  | Cubic Metres |
| N4.16 | Pavements - Road Base |  |  |  |  |  | Cubic Metres |
| N4.17 | Pavements - Binder Course |  |  |  |  |  | Cubic Metres |
| N4.18 | Pavements - Surface Course |  |  |  |  |  | Cubic Metres |
| N4.19 | Pavements - Planning |  |  |  |  |  | Cubic Metres |
| N4.20 | Kerbs, Footways and Paved Areas |  |  |  |  |  | Square Metres |
| N4.21 | Traffic Signs |  |  |  |  |  | Number |
| N4.22 | Road Markings |  |  |  |  |  | Linear Metres |
| N4.23 | Road Lighting Columns and Masts |  |  |  |  |  | Number |
| N4.24 | Electrical Work for Road Lighting and Traffic Signs |  |  |  |  |  | Linear Metres |
| N4.25 | Motorway Commun- ications |  |  |  |  |  | Item |
| N4.26 | Piling & Embedded Retaining Walls |  |  |  |  |  | Item |
| N4.27 | Structural Concrete |  |  |  |  |  | Cubic Metres |
| N4.28 | Structural Steelwork |  |  |  |  |  | Tonnage |
| N4.29 | Protection of Steelwork against Corrosion |  |  |  |  |  | Item |
| N4.30 | Waterproof- -ing for Concrete Structures |  |  |  |  |  | Square Metres |
| N4.31 | Bridge Bearings |  |  |  |  |  | Number |
| N4.32 | Bridge Expansion Joints (Asphaltic plug) |  |  |  |  |  | Number |
| N4.33 | Bridge Expansion Joints (metal/ rubber) |  |  |  |  |  | Number |
| N4.34 | Bridge Expansion Joints (mechanical and other) |  |  |  |  |  | Number |
| N4.35 | Brickwork, Blockwork and Stonework |  |  |  |  |  | Square Metres |
| N4.36 | Special Structures |  |  |  |  |  | Item |
| N4.37 | Other Works (SUs, Noise Insulation, Acc Works etc) |  |  |  |  |  | Item |
| N4.38 | Landscape & Ecology |  |  |  |  |  | Hectares |
| N4.39 | Contractors Share |  |  |  |  |  | NA |

## NRSWA Reports

    - Report to the Employer on the number of notices, inspections and fees received in the preceding 12 months for those items listed in Table 19.5 below.

    - The annual report will identify changes from the previous annual report and a trend analysis based on as many of the previous five years records that are available.

Table 19.5

| NRSWA Section | Record | Reporting Requirement |
| --- | --- | --- |
| 50 | Income received Street Works Licences | Total fee from each Undertaker per month |
| 72 (2) (3) | Income received from inspections fees. | Total fee from each Undertaker per month |
| 74(5) | Overrun charges issued | Total fee from each Undertaker per month |
| 76 | Traffic orders introduced. Emergency orders introduced. Fees recovered. | Totals. |

## Nonconformity and Corrective Action Reports

    - The purpose of this section is to describe the minimum requirements to be fulfilled by the Provider when submitting reports in connection with Nonconformities and corrective actions.

    - The reporting of Nonconformities shall comprise an initial statement and the keeping of an up to date register.

    - Corrective actions require a specific report.

    - The requirements stated in Table 19.6 below are the minimum requirements. The Provider or the Employer may add to these from time to time.

Table 19.6

| Ref | Item | Item Coverage |
| --- | --- | --- |
| 1 | Nonconformities |  |
| 1.1 | Report | Within three working days from the identification of a Nonconformity the Provider prepares a brief report covering as a minimum: - Unique reference for the Nonconformity - A brief description stating which requirement is not being fulfilled and in what way - The effect both current and potential - The likely cause i.e. what aspect of the Quality Plan is not functioning properly |
| 1.2 | Register | The Provider keeps an up to date register of Nonconformities covering as a minimum: - Unique reference, - Date of Identification, - Identification Method for example by operation of the Performance Management Manual or by Audit etc., - Date of corrective action report, - Date Nonconformity corrected (i.e. confirmed as such by the Service Manager), - Traffic light type notation, - Red – indicates Nonconformity identified but no corrective action report prepared – also where corrective action not complete by planned date, - Amber – Correction action report prepared and action in progress and within planned parameters, - Green – Corrective action complete and accepted by the Service Manager. The Provider enters the Nonconformity on to the register within three working days from its identification. |
| 2 | Corrective Action |  |
| 2.1 | Corrective Action Report | Within seven working days from the identification of a Nonconformity the Provider issues a corrective action report covering as a minimum: - Unique reference of the Nonconformity - Description – this could be as per the Nonconformity report or expanded - Details of the corrective action to be taken - Categorisation of corrective action into high, medium or low risk - For high and medium risk an analysis of the root cause(s) of the Nonconformity commensurate with risk i.e. what is the evidence based underlying truth about what is causing the Nonconformity to occur - What aspect of the Quality Plan needs to be addressed i.e. which of the Provider’s processes is not performing as required - What the corrective action will address, for example is it a process design that needs changing or is it an execution issue (i.e. that requires additional training, tools etc.) - For high and medium risk a detailed action plan, commensurate with risk, with planned correction date and milestones – the plan should contain named individuals for the actions and for high risk the plan should nominate the relevant executive process owner from the Provider to take overall accountability for the plan. A brief action plan is required for low risk. - Method of reporting progress to the Service Manager - The method to be used to signify successful correction of the Nonconformity to allow that to be recorded on the register. Any envisaged circumstance that will allow the Service Manger to confirm the correction. - Adjustments to be made to the Quality Plan in order to prevent reoccurrence of the Nonconformity. |

## Cost Capture

    - The Provider is required to maintain and submit a report showing the Provider’s cumulative cost for each current year tied back to value. This report should provide a summary of the Provider’s Works activity and cost breakdown as outlined in Annex 5 Tables 5.1.1, 5.1.2. and 5.1.3.

    - All overhead costs should be reported against the appropriate overhead activity.

    - In addition the Provider is required to maintain and report by activity the values outlined in Table 19.7 below. This information will be used by the Employer to benchmark cost across contracts.

    - The Provider is required to submit reports electronically using the “Provider Works Cost Report” supplied separately for this purpose. In order to maintain confidentiality reports should only be sent to Highways Agency mailbox: CostCaptureMailbox@highways.gsi.gov.uk

    - Costs captured for winter maintenance are required to be maintained for all the agreed treatment route locations and allocated to prescribed route locations.

    - The level of reporting the Provider will be required to report at sub-activity level to the Employer. Sub-activities for the Provider’s Works are outlined in Annex 5 Table 5.1.2. For activities identified for benchmarking, the Provider is required to populate the “Activity Benchmark Sheet” (as per table19.4b) supplied by the Employer for this purpose. The Provider is required to maintain a database of this for all completed schemes in accordance with the Service Information.

    - The Employer must be given open access to the Provider’s costing system as is necessary for the Employer to verify the accuracy of the data being reported.

    - For Works Constructed by Other Contractors the Provider is required to maintain cost data and submit “Con Forms for other types of projects” to support payment certificates. A spreadsheet is supplied separately for this purpose. These reports should be submitted electronically to the Highways Agency mailbox: Managed frameworks@highways.gsi.gov.uk.

Table 19.7

| Header | Value |
| --- | --- |
| Percentage of Total Value. | Cumulative cost for each current year for each activity as a percentage of total value. |
| Remaining Current Year Forecast | The remaining forecast for each current year for each activity. |
| Current Year Total (CYT) | Cumulative cost for each current year for each activity plus the remaining forecast for each current year for each activity. |
| Current Year Full Year Total (CYFYT) | CYT cost for each activity divided by contract duration in year multiplied by 12 months. |
| £’s/lanekm | CYFYT as a cost per lane kilometre for each activity. |
| £’s/cwkm | CYFYT as a cost per carriageway kilometre for each activity. |
| Alternative Attributes | CYFYT as additional unit rates for specific activities: - Paved Areas as a rate per 1000 square metres of paved area. - Gully/ Catchpit Cleaning as a rate per number of gullies and catchpits. - Structures as a rate per number of structures. - Road Restraint Systems as a rate per kilometre of road restraint systems. - Road Traffic Signs as a rate per number of road traffic signs. - Lighting as a rate per number of road lighting units and number of lit signs. - Other Soft Estate Works as a rate per hector of soft estate works. |
| Total Value | Overall costs to be tied back to total value. This should include the value of the application to the Employer plus other related value for example income from third party damage. |

## APPENDIX A – NDD Out-turn data

See separate Microsoft Excel Worksheet

Area 3 ASC S I Annex 19 Appendix A - NDD Out-Turn Data Rev 0.xls

## APPENDIX B – Activity Bench Mark Sheet

See separate Microsoft Excel Worksheet

Area 3 ASC S I Annex 19 Appendix B - Activity Benchmark Sheet Rev 0.xls

## APPENDIX C – Annual Commercial Plan and Guidance Note

See separate Microsoft Excel Worksheet

Area 3 ASC S I Annex 19 Appendix C - ASC Annual Commercial Plan Rev 0.xls