DEF STAN 00-970 Compliance Review Statement of Requirements (SOR)

Purpose: Ensure that compliance sentencing of Def Stan 00-970 requirements pertinent to MLSP is complete before initial RTS date.

Scope: Table 1 is an extract of the DHels/MAA endorsed Merlin Mk4 TCB illustrating the systems that are being modified and the standards against which they will be certified. The Design Organisation shall provide compliance statements against the relevant requirements of Def Stan 00-970 Part 7 issue 2/3. The task is to assess these statements and where applicable justify the non-compliances and obtain the necessary agreement in accordance with MAA regulations. For the purposes of scoping the task it is estimated that the systems in Table 1 will be non-compliant against 10-15% of the individual requirements in the relevant leaflets.

WP 1: Task Management

- Develop a project and technical risk register that details any risk to task completion.

- Raise, monitor and (where delegated) manage 00-970 compliance risks in consultation with key stakeholders (AgustaWestland, Merlin PT, Commodity PTs and other external agencies such as QinetiQ).

WP Outputs:

- WP1.1	Deliver a project management plan for the task including project plan and risk register.

- WP1.2	Deliver monthly progress reports.

WP 2: Compile and technically review the Def Stan compliance spreadsheet.

- Identify each mandatory requirement in Def Stan 00-970.

- Collate these requirements into a standard search and filter capable document that is compatible with DII.

- For each Mandatory Requirement:

  - Determine if the requirement is applicable to MLSP

  - Technically review any previously detailed compliance and attach to the relevant requirement.

  - Determine if the requirement is Safety or Airworthiness related.

  - In conjunction with AgustaWestland identify those Def Stan 00-970 requirements for which AW cannot provide the necessary evidence (for example items provided as GFE).

WP Outputs:

- WP2.1	Formally present the outcome of WP2 to Merlin PT. This is to include highlighting any requirement considered not applicable to MLSP or outside the scope of AW responsibility.

WP 3: Technical review of each Def Stan Compliance evidence submission from Design Organisation (AW).

- AW shall provide compliance evidence for each mandatory requirement detailed in the output of WP2.

- Technically assess compliance evidence as presented by the Design Organisation (DO – AgustaWestland), to propose to the Type Airworthiness Authority (TAA - Merlin PT Leader) whether MLSP is Compliant, Partially Compliant or Non-Compliant, together with the scope of any partial/non-compliance and any risk presented.

- For those requirements that are compliant, record evidence for review by the TAA.

WP Outputs:

- WP3.1	Include a summary of WP3 progress in monthly report.

- WP3.2	Collate and formally present the outcome of WP3 to the Merlin PT and DHels Safety staff. Coordinate and minute compliance acceptance meetings with TAA. Assist Merlin TAA in presentation of partial/non-compliance assessments to DHels.

WP 4: Staffing of non-compliant requirements

- For those requirements that are non or partially compliant, generate a non/partial compliance briefing sheet and mitigation argument for submission to the TAA. This should detail the alternative means of compliance claim or risk acceptance argument made by the Design Organisation with supporting evidence, including a statement detailing the effect on platform airworthiness through analysis of the aircraft safety case, with the relevant cross references to the Aircraft Safety Assessment Model/Report as required.

WP Outputs:

- WP4.1	Presentation of evidence and mitigation argument supporting non-compliant requirements for acceptance by senior stakeholders.

Task Schedule:

Assumed Contract Effective Date (CED):  January 2017

WP1.1	CED + 2wk

WP1.2	CED + 4wk and then monthly

WP2.1	CED + 6wk

WP3.1	CED + 4wk and then monthly

WP3.2	As required, assuming at least monthly

WP4.1	As required, assuming four sessions with senior management

Contract Completion Date: 31 December 2017

Skill, Competencies, Experience

The skills required for these tasks are detailed below and recent evidence for each is to be provided in support of any response:

- Systems based knowledge of Merlin Mk3/3a and MLSP

- Detailed knowledge of MRP including certification of rotary wing aircraft in accordance with MAA RA1500.

- Experience of the Military Aircraft Certification Process (MACP), including experience of writing Type Certification Expositions.

- Comprehensive evidence of Rotary Wing Def Stan 00-970 review work at a platform and system level.

- Detailed knowledge and experience of platform certification.

- Experience of DOORS (location of AW compliance data).

- Detailed knowledge of safety management and Merlin ASAM and ASAR.

Assumptions

- It is estimated that the systems in Table 1 will be non-compliant against 10-15% of the individual Def Stan 00-970requirements in the relevant leaflets

- Attendance at four TAA, 1-Star and 2-Star reviews.

- The task is primarily based at AW Yeovil, but attendance at Abbey Wood may be required.

- Presentation of compliance claims to senior management will be at Abbey Wood or Yeovil.

- Personnel shall have a valid security clearance to enable attendance at AW Yeovil and MOD Abbey Wood.

GFX

- Access to DII and AW Shared Data Environment shall be provided.

- Compliance evidence from AW should start to be available from October 2016. All evidence should have been provided by AW by May 2017.

Certification Basis for Merlin Mk4 based upon Merlin Mk4 TCB MLSP1051 issue 4 dated 31 Jul 15

| Sys No | System or Attribute Heading | Change | Requirement | Aspect of Design |
| --- | --- | --- | --- | --- |
| 09 | Air Vehicle Handling | Folding Head and tail fold joint | AvP970 Vol 3 |  |
| 15 | Air vehicle Performance | Folding Head and tail fold joint | AvP970 Vol 3 |  |
|  |  | 3rd Pitot/Static system | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 101, 716 |  |
| 16 | Role Equipment | Steel lashing rings (8 off) | AvP970 Vol 3 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 101, 200, 201, 206 | Steel rings Fuselage strengthening |
|  |  | Fast roping beam | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 101, 200, 201, 206, Section 4 |  |
| 18 | Vibration and Noise Analysis and Attenuation | Revised and new equipment locations. | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 108 Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Leaflets 501 |  |
|  |  | New avionics cooling fans | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 108 Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Leaflets 501 |  |
| 21 | Avionics Cooling System | Changes to Avionics Cooling System to suit revised avionics and displays | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 101, 731 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 101, 731 | Mk2-derived designs New MLSP designs |
| 22 | Auto Flight/Pilot (AFCS) | Removal of Dynamic Sensor Unit (DSU) | Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Leaflets 604 DO-178A |  |
| 23 | Common Communications | Communications system based on MCSP | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178B DO-254 | Mk2-derived designs New MLSP designs |
|  |  | V/UHF R&S MR6000A (x2) | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178B DO-254 | Mk2-derived designs New MLSP designs |
|  |  | HF Selex RT/170/DR | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178B DO-254 | Mk2-derived designs New MLSP designs |
| 24 | Electrical Power | Based on MCSP to service new controls and displays | AvP970 Vol 3 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 706 | Mk3-derived designs New MLSP designs |
| 25 | Equipment and Furnishings | Personal stowages | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 105, 200, Section 4 |  |
| 29 | Hydraulic Power | System modified for tail fold joint | AvP970 Vol 3 |  |
| 30 | Ice and Rain Protection | Introduce Mk3a Rotor Icing Protection Unit (RIPU) | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 101, 706, 711 DO-178B |  |
| 31 | Indicating/ Recording Systems (including EIS, AMS, Air Data System) | Emergency Aircraft Recording and Location System (EARLS) including CV/FDR and ELT | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 724, 725 DO-178B |  |
| 32 | Landing Gear | Addition of gagging valves, heavyweight wheels and heavy duty gas heads | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 300, 301, 302, 304, 306, 307, 308, 310 |  |
|  |  | Increased oleo pressure | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 310 |  |
|  |  | Requalification for ship operations | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Section 3 |  |
| 33 | Lights | Internal lights based on MCSP | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106, 107, 706 |  |
|  |  | External lights based on MCSP | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98)) Chapters 105, 106, 107, 110, 706 |  |
| 34 | Navigation (including ILS, EGI, DVS, AHRS, ADS, Rad Alt, GPS,DF/PLS Homing) | Honeywell 764G EGI | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708, 725 DO-178B |  |
|  |  | Attitude Heading Reference System (AHRS) | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 708, 713, 725 DO-178B DO-254 |  |
|  |  | DADS / ADU | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 708, 725 DO-178B DO-254 |  |
|  |  | Doppler Velocity Sensor (DVS) | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708, 725 DO-178A |  |
|  |  | DME | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708, 725 DO-178B |  |
|  |  | GPS 2nd system | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708, 725 DO-178B DO-254 |  |
|  |  | Direction Finder (DF) | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 707, 708, 725 DO-178B |  |
| 43 | Tactical Communications | Communications system based on MCSP | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178B DO-254 | Mk2-derived designs New MLSP designs |
|  |  | Separate crypto | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 DO-178A DO-254 |  |
|  |  | ARC-231 | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178A DO-254 | Mk2-derived designs New MLSP designs |
|  |  | TETRA | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 DO-178B DO-254 | Mk2-derived designs New MLSP designs |
|  |  | Iridium Satcom (UOR fittings) | Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 707, 708 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 707, 708 | Mk2-derived designs New MLSP designs |
| 46 | Systems Integration and Display (including Cockpit/ Displays/ Cabin Controls) | IDU screens | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflet 107, 724 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapter 107, 724 DO-178B DO-254 | New MLSP designs Mk2-derived designs |
|  |  | Integrated Standby Instrument System (ISIS) | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflet 107, 724 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapter 107, 724 DO-178B DO-254 | New MLSP designs Mk2-derived designs |
|  |  | Touch Screen Unit (TSU) | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 105, 106, 724 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106, 724 DO-178B DO-254 | New MLSP designs Mk2-derived designs |
|  |  | Consoles | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 105, 106 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106 | New MLSP designs Mk2-derived designs |
|  |  | AMMC | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 105, 106, 725 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106, 725 DO-178B DO-254 | New MLSP designs Mk2-derived designs |
|  |  | Data Transfer Unit (DTU) | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 105, 106, 725 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106, 725 | New MLSP designs Mk2 derived designs |
|  |  | Additional TSU in cabin | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 105, 106, 724 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapters 105, 106, 724 DO-178B DO-254 | New MLSP designs Mk2-derived designs |
|  |  | AMS software | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 leaflets 728, 729 DO-178B |  |
| 53 | Fuselage (including Main Load Path and Underslung Load Hook) | Tail fold joint | AvP970 Vol 3 Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Section 4 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Section 2, Leaflet 722 | Mk1-derived designs New MLSP designs |
|  |  | Addition of folding MRH | AvP970 Vol 3 Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Section 4 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Section 2, Leaflet 722 | Mk1-derived designs New MLSP designs |
|  |  | Rear fuselage | Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Section 4 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Section 2, Leaflet 722 |  |
| 62 | Main Rotors | BERP III on folding MRH | AvP970 Vol 3 |  |
| 63 | Main Rotor Drive(s) | Common MLSP Torque ratings | Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 07 |  |
| 65 | Tail Rotor Drive | Modified for tail fold joint | AvP970 Vol 3 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 722 | Mk1-derived designs New MLSP designs |
| 66 | Folding Blades/Pylons | Fold Management Unit (FMU) | AvP970 Vol 3 DO-178A |  |
| 67 | Rotor Flight Controls | Modified for tail fold joint | AvP970 Vol 3 |  |
| 72 | Engine | Common rating structure | Def Stan 00-970 Part 11 Issue 4 dated 20 July 12 DO-178A |  |
| 93 | Surveillance | I-Band transponder | AvP970 Vol 3 DO-178A DO-254 |  |
| 94 | Weapon Systems | Additional chaff dispensers | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 710, 718 DO-178A |  |
|  |  | DAS controller | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 706, 708, 725 DO-178B |  |
| 98 | Meteorological and Atmospheric Research (EMC) | New/modified equipment rewired as MCSP using best practices | Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 Leaflet 1011 Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflet 706, 717 Def Stan 00-970 Issue 1 Vol 2 Amdt 12 (Mar 98) Chapter 706, 717, 726, 1011 | New MLSP designs Mk2-derived designs |
| 99 | Tactical Electronic Warfare | Tactical Processor | Def Stan 00-970 Part 7 Issue 3 dated 29 Jan 2010 Leaflets 105, 706, 708, 725 DO-178B DO-254 |  |

The DHels/MAA endorsed TCB is based upon Def Stan 00-970 Part 7 Issue 2 dated 31 Jan 2007 for all sections (1-10). The contract with AW has since been amended to issue 3 dated 29 Jan 2010 for sections 1, 2, 3 & 7. This document reflects this change.