## TM
TM Scope
Mobilisation and Site Set-up
TM Design | Enabling works drawings, Tm drawings including contraflow and stepped speed limit. Phasing drawing 1 - 4, AIPCAT 1 check for the cameras and CCTV
Phase 0 | Install enabling phase inconjunction with constructing the crossovers at each end of the bridge
Install Speed camera system, CCTV & VMS systems
Phase 1 Westbound Hard Shoulder & Lane 1 works - Construction | Install VRS and contraflow system & Swap TM to Phase 2 Install temporary white lines
Phase 2 Westbound Lane 2 & 3 works - Construction | Install VRS and contraflow system & Swap TM to Phase 3 Install temporary white lines
Phase 3 Eastbound Hard Shoulder & Lane 1 works - Construction | Install VRS and contraflow system & Swap TM to Phase 3 Install temporary white lines
Phase 4 Eastbound Lane 2 & 3 works - Construction | Install VRS and contraflow system & Swap TM to Phase 3 Install temporary white lines
Phase 5 | Remove Contraflow and install pemanent lane for the crossover removal
Recovery | Provide 2 crews one east and one west
Crossovers | VRS removal and installation
Maintenance | Provide 24hr maintenance cover and TSO
Road Markings | Install permanent road marking and road studs once all works are complete
Site Clearance and Project Closeout

## Surfacing
Surfacing Scope
Mobilisation and Site Set-up
All Phase | Remove existing road studs before the planing out
Topographical survey of Cable Stay Bridge deck every 10m via trail hole in each lane to discover the depth of black
Plane off the first 45mm layer of black
Plane off the second layer to within 10mm of the bridge deck
Surfacing | Install the regulating to the underside surface working 24hr shifts
Install the asphalt and chips on night shifts
Testing | Sand patch test and rolling straight edge
Site Clearance and Project Closeout

## Concrete and Waterproofing
Concrete Repairs and Waterproofing Scope
Mobilisation and Site Set-up
All Phase | Remove the final 10mm of surfacings and waterproofing to expose the deck
Captive blast the bridge deck
Testing | Concrete inspection and testing to exposed deck areas – Visual, tap hammer and cover only
Concrete inspection and testing to exposed deck areas – Half-cell, chloride ion content, concrete resistivity, and cement content only.
Cube testing and results 1,3,7 and 28 days
Pull off tests for the waterproofing
Concrete repairs | Hydrodem the concrete repair identified following visual inspection
Waterproofing | Waterproof the deck allowing for 150mm lap
Central Res | Allow material to concrete infill the gap between the surfacing and central res
Site Clearance and Project Closeout