## Summary Price schedule
SCHEDULE 1 - PRICE
NOTES:
A | The University will directly appoint and accept invoices from only the lead consultant. It is for the lead consultant to ensure that fees for any sub-consultants required to complete the commission are included in the submitted Total Fee (Table A)
B | Fees to include for all disciplines required to fulfil the listed tasks, Scope of Service and Client Requirements
C | The submitted fees are to be inclusive of Disbursements – travel, printing, telephony, electronic communication etc
D | The Total Fee is to include the General Contingency sum and any contingency sums shown in Table A
E | The contingency sums are only to be expended on the express instruction of the University
F | Fees will be paid upon satisfactory completion of the stated Activity at Stages A and B
G | Stage C which will be paid in equal monthly instalments in arrears during the works contract period (as originally signed).
H | 80% of the Stage D fee will be paid upon issue of the agreed Final Account Figure. The remaining 20% will be paid upon issue of the Certificate of Making Goods defects at the end of the Defects Period
J | The fee inserted for Stage D must be a minimum of 5% of the total of the fees inserted for Stages A, B and C i.e. ((A+B+C)*5%)). If the minimum 5% figure is not included with the submitted fee the fee will be adjusted accordingly and the revised Total Fee figure used in the assessment of the tender
K | An hourly rate is to be included for the employment of a Clerk of Works during the construction period (Table A item (a)). The number of hours shown in the Table is to allow for an assessment of this Tender. The number of hours shown (500) is NOT to be altered by the tenderer. The hourly rate inserted will be used irrespective of the number of hours ultimately worked. The Clerk of Works fees will be paid monthly in arrears during the construction contract period based on the agreed number of hours worked in the preceding month
L | Table B is to be completed and submitted as part of the bid process, however it will not be used in the assessment. It should be completed listing all disciplines and categories/levels of staff which will be involved in the project. These rates will be used to establish the cost of services which are deemed to be additional to those detailed in Appendix A.
M | Table B should replicate the information provided in Appendix D - Contract Data (Part 2)
N | The appointment will be confirmed progressively by work stage, with the commission only progressing beyond each work stage following instruction from the Client to do so. If the commission has to be terminated no further payment will be due to the selected consultant other than the fees due to the completion of that work stage.
P | Fees to be inserted exclusive of VAT (except as shown)
Q | The University will only accept invoices from the lead consultant
R | Fees included in the Schedule are to exclude any Search or Application fees etc for Statutory or Utilities consents. These will be paid by the University
S | Fees included in the Schedule are to exclude purchase of Contract documents (Professional Services and Construction works etc). These will be purchased by the University
T | Fees to be inclusive of general correspondence and video and in-person meetings as required for a commission of this nature
TABLE A
|  | Activity |  |  | Cost
£
| 1 | Stage A – Initial Design
| 2 | Stage B – Outline Design, Detailed Design and Tendering
| 3 | Stage C – Contract
| 4 | Stage D – Commissioning and Handover
| a | Clerk of Works | 500 | 0 | 0
| b | General Contingency sum |  |  | 35000
|  | Sub-Total (Items 1-4 Inclusive and a & b) (excluding VAT) |  |  | 35000
|  | VAT (at 20%) |  |  | 7000
|  | TOTAL FEE (including VAT) |  |  | 42000
TABLE B
The consultant is to insert hourly rates for all of the disciplines and grades of staff that will be involved in the project. This should include for in-house staff and those of other disciplines/sub-consultants. These rates will be used to agree fees for any work deemed to be outside the stated Scope of Service.
|  | Profession /Discipline | Grade | £/hour
Table can be added to as necessary
Table B should replicate the information provided in Appendix D Contract Data (Part 2)
Note on E30: Number of hours. Will be used to assess tenders but does not indicate actual number of hours that will be required
Note on F30: Insert hourly rate, which will remain fixed for the duration of the contract
Note on G31: This is a fixed sum and is NOT to be altered by the tenderer