Draft Procurement and Mobilisation timetable

NHS Medway Clinical Commissioning Group
APMS Primary Care
2nd July 2018

Draft timetable

The below indicative timetable is to inform respondents to the Market Sounding Questionnaire. The timetable is draft and does not commit the Commissioner to any future procurement process and is subject to change.

| No. | Stage | Dates |
| --- | --- | --- |
| 1 | First Tender Stage released to Bidders | 03/09/2018 |
| 2 | First Tender Stage Clarification Deadline | 14/09/2018 |
| 3 | First Tender Stage submission closing date | 21/09/2018 |
| 4 | First Tender Stage Evaluation commencement | 24/09/2018 |
| 5 | First Tender Stage Evaluation shortlisting | 05/10/2018 |
| 6 | Second Tender Stage released to shortlisted Bidders | 15/10/2018 |
| 7 | Second Tender Stage Clarification Deadline | 26/10/2018 |
| 8 | Second Tender Stage submission closing date | 02/11/2018 |
| 9 | Second Tender Stage Evaluation commencement | 05/11/2018 |
| 10 | Commissioner Primary Care Committee ratification | 28/11/2018 |
| 11 | Formal award decision made and award decision notices issued to unsuccessful Bidders | 29/11/2018 |
| 12 | 10 day standstill period | 29/11/2018 – 10/12/2018 |
| 13 | Mobilisation Period | 11/12/2018 – 31/3/2019 |
| 14 | Services commencement date | 01/04/2019 |

The Procurement process will split from a traditional “single stage” and be split into two stages, each with a tendering period of 3 weeks for bidder response.

Draft questions for the second stage will be provided at advert (3rd Sept) to help bidders prepare for the second stage. Any changes at release of the second stage will be clearly indicated.