# DRAFT

# Scope

# DWP Estates Contractor Framework

# Project No.19502

# August 2017

Contents

1.	Introduction	6

1.1	DWP Projects Contractor Framework	6

1.2	DWP Integrator	6

1.4	Packaging of the Work into Project Programmes	7

2.	General Requirements	9

2.1	DWP Design standards	9

2.2	Furniture	10

2.3	Space planning	10

2.4	IT Requirements	11

2.5	Smart Working	11

2.6	Building Information Modelling	11

2.7	Design Drawings (all Projects where Contractor provides design)	12

2.8	Construction drawings	12

2.9	Responsibility for dimensions	13

2.10	Co-ordination	13

2.11	Design submission procedure	13

2.12	Design approvals	14

3.	General constraints on how the Contractor Provides the Works: Site related matters	15

3.1	Inspections and investigations by Contractor prior to allocation of Work	15

3.2	Access to Site	15

3.3	Working Hours	16

3.4	Other Works on Site	16

3.5	Car Parking	17

4.	General constraints on how the Contractor Provides the Works: Permissions/Agreements	18

4.1	Contractor System	18

4.2	Permissions/Agreements	18

4.3	Licences	18

4.4	Permit to Work	18

5.	Contractor’s Personnel	19

5.1	Key Roles	19

5.2	Personnel recruitment	19

5.3	Personnel policies	19

6.	Regulatory and Policy Compliance	20

6.1	Planning Conditions	20

6.2	Building Regulation Approval	20

6.3	Fire Officer’s Requirements	20

6.4	Work by Statutory Authorities	20

6.5	Statutory Obligations	20

6.6	Environment	21

7.	Management of the Works	22

7.1	General Requirements	22

7.2	Specifications and quantities	22

7.3	Supervision and co-ordination of the works	22

7.4	Security and protection of the site	23

7.5	Security and Identification of People	23

7.6	Protection of existing structures and services	23

7.7	Control of site personnel	24

7.8	Prevention of Dumping	24

7.9	Protection of the works	25

7.10	Traffic management	25

7.11	Condition survey	25

7.12	Consideration of others	25

7.13	Progress meetings	26

7.14	Progress Meeting and Reports	26

7.15	Risk Management Process	27

8.	Quality Assurance	28

8.1	Quality Plans and Systems	28

8.2	Additional information	28

8.3	Quality Manager	28

8.4	Quality monitoring	28

8.5	Quality control	28

8.6	Codes of Practice for Contractors	28

8.7	Document formats	29

8.8	Site records	29

8.9	Sufficient Stocks	29

8.10	Storage	29

8.11	Covered up work	29

8.12	Drying out the works	29

9.	Tests and Inspections	30

9.1	Tests and Inspections	30

9.2	Commissioning of Engineering Services	30

9.3	Inspections and tests at manufacturer’s works	30

9.4	Use of Engineering Services Installations by Contractor	30

9.5	Notice before Covering Work that is to be Inspected or Measured	31

9.6	Covering up Completed Work	31

9.7	Arrangements for opening up and remedying Defective Work	31

10.	Works Control Measures	32

10.1	Noise control	32

10.2	Dust control	32

10.3	Existing services, cables and drains, etc.	32

10.4	Hoardings	33

10.5	Existing trees	33

10.6	Openings into existing buildings	33

10.7	Rodent infestation precautions	33

10.8	Fire precautions	33

10.9	Personal Protective Equipment (PPE)	33

10.10	Drinking/drugs	34

10.11	Clearance of fuel/oil leakages or spillages	34

10.12	Protection of work in all sections	34

11.	Materials and Workmanship	35

11.1	Quality	35

11.2	Manufacturer’s recommendation	35

11.3	British Standards	35

11.4	Sustainability	35

11.5	Products	35

11.6	Single sources	36

11.7	Old materials	36

11.8	General quality of workmanship	36

11.9	Accuracy/Setting Out Generally	36

11.9.1	Tolerances	36

11.9.2	Appearance and fit	36

11.9.3	Non compliance	37

11.9.4	Setting out	37

11.10	Fixing/Fastening/Adhesives Generally	37

11.10.1	Fixing generally	37

11.11	Fastenings for materials and components	38

11.11.1	Fixing through finishes	38

11.11.2	Adhesives	38

11.12	Scaffolding	38

11.12.1	Provision	38

11.12.2	British Standards	38

11.12.3	Scaffold erection	38

11.12.4	Fittings	38

11.12.5	Approvals and consents	39

11.12.6	Protection	39

11.12.7	Windows	39

11.12.8	Ladders	39

11.12.9	Lighting	39

11.12.10	Projections	39

11.12.11	Inspection	39

11.12.12	Striking scaffold	39

12.	Programmes	40

12.1	General	40

12.2	The Overall Construction Programme	40

12.3	Detailed Critical Path Programme	40

12.4	Programme Support Information	41

12.5	Programme revisions	41

12.6	Method Statement	41

13.	Facilities, Temporary Works and Services	43

13.1	Mechanical Plant	43

13.2	Temporary Works	43

13.3	Use of permanent electrical and cold water installations and sanitary facilities	43

13.3.1	Electricity supply from the Client's mains	44

13.3.2	Water for the Works	44

13.4	Use of lifts	44

13.5	Sanitary facilities	44

13.6	Use of permanent telephone installations	45

13.7	Site accommodation	45

13.8	Charges	45

13.9	Advertisements	45

13.10	Site name-boards	46

13.11	Route signs	46

13.12	Wayleaves	46

13.13	Services and other things to be provided by the Contractor	46

13.13.1	Contractors Requirements	46

14.	Health & Safety, Asbestos and CDM 2015	47

14.1	Health & Safety	47

14.2	Construction Phase Plan	49

14.3	Health and Safety File	49

Where the Contractor is the Principal Contractor, completion of an Order is subject to the submission by the Contractor to the CDM Co-ordinator of all the required information so that the Health and Safety File can be updated in compliance with the CDM Regulations 2015.	49

14.4	Asbestos	49

15.	Subcontracting	51

15.1	Sub-Contractors	51

16.	Completion	52

16.1	Pre-Completion arrangements	52

16.1.1	General	52

16.2	Work At Completion/Making Good Defects	52

16.2.1	Making good	52

16.2.2	Cleaning	52

16.2.3	Security at completion	52

16.2.4	Completion Deliverables	53

16.2.5	Completion Deliverables Schedule	53

16.3	Handover Procedure	56

16.4	Operation and maintenance manuals	56

16.5	Record documents and As Built Information	56

16.6	Training	57

16.7	Defects	57

16.8	Defects Protocol	57

# Introduction

## DWP Projects Contractor Framework

    - This document will form the basis of Scope for the purpose of Call-Off Contracts let under the framework (the Framework) established by the Department of Works and Pensions (DWP) for estate projects fit out and refurbishment works.  The framework is open to DWP, other government departments and wider public sector organisations (as stated in the Contract Notice [ref…] and collectively referred to as Participating Bodies).  It is anticipated that any other Participating Bodies making use of the Framework will adapt this Scope for the purpose of their estate requirements.

Words and phrases used in this document have (unless otherwise stated) the meaning given to them in the Framework Agreement and/or the Template Call Off Contracts under the Framework.  The term "works" means services (Lot 1) or works (Lots 2 and 3), as appropriate and "Site" means Affected Property (Lot 1) or Site (Lots 2 and 3), as appropriate.

The Framework supports DWP's estate (DWP Estate) consisting of:

- a national network of Job Centre Plus Offices, which are similar in nature to a retail shop with 'over the counter' style service provision; and

- regional Corporate Centre offices

- Call Centres

DWP Estate requires periodic works of refurbishment and renewal.

## DWP Integrator

DWP has engaged and authorised a third party service provider referred to in the Template Call Off Contracts as the Integrator to perform certain DWP Estate related DWP duties and obligations.  This includes allocation of specific project works to Projects and Programmes (as defined to in Framework Agreements) and the role of the Client under Call-Off Contracts..

DWP has also established a central Programme Management Office (PMO) responsible for day to day management of the framework. The PMO appointment is one part of the services to be provided by the Integrator. Other Participating Bodies will provide their own governance process and procedures to how their specific project work is allocated to suppliers on the framework.

Notwithstanding the role of the Integrator, final accountability remains with the DWP Estate Business Partner Organisation (BPO). DWP Estate BPO will provide assurance to the DWP business units that the work being undertaken by the Integrator in the day to day management of DWP’s directly appointed members of the supply chain complies with the department’s policies and procedures and meets all relevant service standards. As such, DWP Estate BPO shall hold ultimate responsibility for approving all estate related matters upon which the Integrator will be required to obtain authorisation prior to implementation eg. Proposed project work allocations, procurement strategies etc. The DWP Estate BPO will carry out audits of the Integrator’s work function.The Integrator will –

- Provide a "Programme Management System" and function to govern, control, manage and co-ordinate all project work undertaken.

- Be responsible for all required project planning, work scheduling and coordination with other DWP Estates supply chain members (DWP Estate Supply Chain) to ensure efficient and effective delivery of life cycle replacement works (Life Cycle Plan Projects) and other DWP Estate logistical projects (Moves and Changes)

- Bundle projects into programmes (Programmes of Work) based on estate type, project / trade type or region to benefit from economies of scale

- Provide prioritisation of Project allocation  ensuring specific projects are appropriately allocated across the DWP Estates Supply Chain

- Provide day to day management of professional services consultants, Project Contractors including Lot 3 National Contractors, Lot 1 and Lot 2 Regional Contractors, the FM Provider and their specialist domestic sub-contractors.

- Oversee the professional services team in the procurement of high value Projects

- Provide Projects risk management including providing a risk register

- provide and manage an electronic 
Permit to Work system to  ensure all DWP Estates Supply Chain members have pre-authorised access to DWP properties

- Audit Projects

- Provide Performance Reporting of Projects

Day to day contract administration will be provided by the Service Manager (Lot 1) and the Project Manager (Lots 2 and 3) but the Contractor will be expected to liaise with the Integrator as part of the Client's organisation.  In particular, the Contractor will be required, at regular intervals, to provide Management Information to the Integrator including data related to a series of Performance Measurement Indicators to be uploaded via the Integrator Performance Management System.

  - Description of the services and works

    - DWP’s on-going strategic management of the DWP Estate will generate a regular pipeline of Projects.  and Programmes which will vary in scale and type but will generally consist of one or a combination of the following :

- Life Cycle Work Projects: to support the general up-keep of the buildings, ensuring statutory compliance with safe and effective places for staff to work and clients to visit to receive the required high level of services from DWP. Typically these projects cover:

• Office Refurbishments, carpet, ceilings etc.

• Redecorations

• Replacement of end-of-life mechanical and electrical assets.

• Fabric Refurbishments

• Upgrades of existing space

• Replacement of obsolete or end of life Furniture, Fixtures & Equipment

- Capital Work Projects: business unit elected expenditure in support of the overall estates strategy where DWP will be required at on-going regular intervals to relocate office functions, within and to new buildings and carry out dilapidation work on buildings being vacated and disposed of. Typically these projects cover:

• Moves & Changes (Churn)

• Divestments - Disposal of Space / Dilapidations work (where applicable)

• Relocation / New Office

• Rebranding (Universal Credit)

• Expansion into New Space

• Reconfiguration work, general layouts, meeting rooms etc.

## Packaging of the Work into Project Programmes

The Integrator will package individual work requirements into either individual Projects or grouped into Programmes of work. The approach will vary depending on estate type, project / trade discipline type; regional location; and when the works need to be completed.  The Integrator will identify Programmes to optimise cost benefits through economies of scale and to minimise business disruption to DWP.

For business convenience, the Integrator may award some of the Projects and/or Programmes to contractors outside of the Framework, including to DWP's Facilities Management Contractor (FM Contractor).  It is intended that Projects undertaken by the FM Contractor will be of low value.

Work activities to be undertaken by the Contractor in undertaking Projects and Programmes under Lots 1 and 2 will be those activities priced in the PSA schedules of rates and DWP's composite schedule of rates for specific components within the JPEG – Job Centre Plus Environment Guide (the Price List and Activity Schedule in the Lot 1 and Lot 2 contracts).  DWP's design standards for Jobcentre Plus service delivery sites will apply to Projects and Programmes and cover customer facing areas and back of house offices set out in the Jobcentre Plus Environment Guide (JPEG) components directory and specifications (detailed elsewhere in this document).

Project specific requirements will reflect the activities set out in the Price List/the Activity Schedule (Lots 1 and 2) and the JPEG design guidance (all Lots).  The following activities will not be included in Projects or Programmes:

  - supply and Installation of audio visual equipment; and

  - supply and installation of all IT equipment including telephone.

# General Requirements

## DWP Design standards

The Contractor may be required from time to time to provide design by a Task Order (Lot 1) or a Call-Off Contract (Lots 2 and 3).

The Jobcentre Plus Environment Guide (JPEG) provides Contractors with the required DWP design standards for Jobcentre Plus service delivery sites covering customer facing areas and Jobcentre back of house offices. The JPEG design standard shall be updated from time to time to reflect changes in the Client's operational requirements and preferences such as the introduction of new or altered branding.  Any Call off Contract or Task Order (as the case may be) shall be issued by reference to the JPEG design standard current at the date of issue.

Contractors can access the DWP JPEG design standards via the UK Government Web Archive at the following URL web address –

http://webarchive.nationalarchives.gov.uk/20130128102031/http://dwp.gov.uk/jpeg/

DWP will through the Integrator directly appoint design consultants (the Design Team) to provide other additional design services that may be required for a Project or a Programme and /or specify in the Task Order and/or Contract Data (as the case may be)  the extent of design to be provided by the Contractor.

The Contractor is expected to engage fully with the Design Team and DWP's other consultants, as may be required, to carry out any specific project or Task Order.

It is anticipated that all DWP construction consultants (other than the Integrator) shall be appointed from the Crown Commercial Service's Project Management & Full Design Team Services framework RM3741.

JPEG is the main reference document to be used when designing, providing, altering and maintaining offices. It is the reference point for:

- commissioning Jobcentre Plus projects

- designing and managing Jobcentre Plus projects and

- specialist services and delivering the end product

JPEG provides details of the design elements to ensure that all offices meet the requirements of the Jobcentre Plus ‘brand identity’ and present a uniform ‘look and feel’ across the business. The following service delivery Sites are covered by the design standard –

- Job Centres

- Client Suites

- Standalone Screening Services

- Assessment Centres

- NINO Allocation Offices

- Benefit Centres

- Contact Centres

JPEG also provides guidance on the design concept of our Sites, space planning, implementation and best practice, as well as details of the range of components and finishes and their correct usage. With a few minor exceptions, all current Job Centres have been designed and built in accordance with the JPEG design standard. The Contractor must be familiar with and comply with the JPEG design.

The JPEG design may, from time to time require amendment to ensure compliance with relevant legislation, regulations, British Standards and Government policies. Amendments to the design standards are managed through the Jobcentre Plus Environment Design Assurance (EDA) team. EDA recognises the need for the relaxation of certain design standards during change in those Sites where the full JPEG standard has not been delivered during Rollout.

The design standards cover the following key components –

  - Banners

  - Ceilings specifications

  - Wall Finishes

  - Doors and Partitioning systems

  - Flooring specifications

  - Induction loops

  - Information Display screens

  - Internet Access Kiosks

  - Lighting

  - Power poles

  - Signage

  - Furniture, Tables Desk and storage systems

  - Window Film

  - Window Blinds

## Furniture

## Other contractors will usually provide all furniture through a DWP approved furniture catalogue direct agreement with a furniture supplier. The Contractor may sometimes be required to include for the provision of some or all furniture for the project.

## Space planning

Space Planning guidelines are part of the design standards with specific requirements for both Front of House and Back of House areas. Back of House (BoH) areas are not open to the public.

The areas, components and finishes for BoH areas will be [instructed on a Project or Programme specific basis]. JPEG only has guidance notes on the decoration of, and components used in, areas that maintain the Jobcentre Plus brand identity.  For example, it specifies mess rooms, but not toilets. Staff welfare facilities will be required to be in accordance with the law of the Contract and Good Industry Practice.

Office areas are generally open-plan.  Some cellular accommodation will be required.

When considering support functions, the exact requirements of the Site will depend on staff numbers, type of office etc. However, the BoH will usually include some or all of:

- Conference/Meeting Room

- Finance Room

- First Aid Room

- IT Equipment Room

- Manager’s office(s)

- Mess facilities

- Personal Assessment Room(s)

- Security/CCTV office

- Tea Point

- Trades Union office

- Training Rooms.

The design standard includes an Environment Schedule which lists the detailed specifications for all relevant surfaces and areas – for example, construction, finishes and colour.

## IT Requirements

There are very specific requirements for the design and construction of IT Equipment Rooms, but these are not covered within the scope of JPEG. With support and guidance from DWP IT Dept. the Contractor will need to procure specialist contractors to provide technical specifications and they will describe ideal sizes and locations within a building for specific IT requirements.

As broad guidance to designers:

- the IT Equipment Room must be a secure room, sited away from glazed external walls and south facing elevations, in order to minimise solar heat gain

- in new buildings, the location should be considered in relation to IT cabling runs and mechanical services requirements

- in existing buildings these rooms will most likely be existing facilities. They should not be relocated, as the associated changes to equipment layouts and data cabling would be prohibitive. For this reason the room is considered to be one of the fixed elements in the planning strategy.

## Smart Working

In addition to the JPEG Design Standards, DWP has, in response to the Cabinet Office-led The Way we Work (TW3) programme, developed a set of new design guidelines to support Corporate Centres.

The Contractor should refer to the ‘DWP Workplace Design Guideline Final version.pdf’ for further information. The design guide provides high level principles on the look and feel of workplace designs to establish a level of consistency upon which workplace design is based. These design guides are linked to the governments hub programme promoting co-location of Government departments all working to similar design principles linked to ‘smart working’ covering improved utilisation of space and help drive a move towards a more flexible, modern and empowered work culture.

The guidance for implementing workplace Projects and Programmes that include the adoption of smart working is contained in a Code of Practice PAS3000 issued by the British Standards Institute. This Code of Practice has been adopted as part of the Government’s policy for Hubs, which is reflected in DWP’s Estate strategy.

## Building Information Modelling

Capital Works allocated under Lot 3: Major Projects, may further require the Contractor to create and manage a BIM model to include BIM Level 2 information requirements as defined in PAS 1192-2:2013 and Project specific Scope.  In such cases the Contractor must allow for a BIM Manager and associated support staff.

The Contractor will manage the BIM processes and environment including the integration of suppliers and Sub-contractors through to Completion.

No more than two weeks after starting date, the Contractor shall provide the Service Manager/Project Manager and Design Team with a schedule of the drawings to be produced which will also show the dates by which the drawing will be submitted and comments are required.  The dates shall take due note of the periods stated above which shall be allowed for the commenting process.

All drawings, specifications, information or other like details shall be fully co-ordinated with one another to ensure that the design, manufacture, construction and installation of the works may be properly completed in accordance with the Scope.

Accepted drawings shall not be departed from except with the written approval of the Service Manager/Project Manager.

Drawings shall be produced on a BIM system that is compatible with the requirements set out in the Scope and in accordance with the [CIC?] BIM Protocol.  The quality of drawing work (e.g. clarity etc.) shall be to a good standard and the recommended procedure of “working drawing production” shall be in accordance with the Application Guide 1/76 by the Building Services Research and Information Association.  Layering convention shall be in accordance with BS 1192, Part 5.

The drawings shall be produced to suit the Accepted Programme.  Allowance shall be made for the necessary approval period required by the Project Manager and for the incorporation of any amendments caused by such comments.

## Design Drawings (all Projects where Contractor provides design)

All drawings shall conform to the file naming and ‘data structure asset’ conventions stipulated in the Scope.

The Contractor shall produce all necessary drawings for the design and construction of the Project.

The Contractor shall take ownership of the design detailed in Scope, develop his own design drawings / models and complete the design in such detail as necessary to fully comply with the Scope.

The general arrangement and layouts shall be at a scale of not less than 1:50 with plant rooms, details and sections at not less than 1:20 scale.

Drawings should be provided in PDF and DWG, with all submission, written / commercial to be an editable format.

The Integrator or the Project Manager may at any time impose standard document styles / formats for contractor submissions.

Room wall elevations of suitable scale (not less than 1:50) of every room shall be produced showing dimensioned locations of all services outlets and terminals.

Each item of plant/equipment shall be referenced against a schedule of equipment giving full details of the equipment to be utilised.  Schematic layouts shall also be produced indicating the general arrangement of plant and ancillaries and their relationship within the system, along with sizes, flow rates, etc.

## Construction drawings

The Contractor shall produce drawings to demonstrate proposed routes for installing equipment and to indicate any areas of the building fabric to be left incomplete so that large items can be correctly positioned.

In addition to the detailed installation drawings the Contractor shall also provide fully detailed plans, sections and elevations showing all required builders work at such time that the Contractor can construct the Project in accordance with the Accepted Programme.

Drawings shall be fully dimensioned, including structural loadings where necessary, and to the required scales and shall give details of:

- cutting or forming of holes, pockets, openings chases and the like through walls, floors, ceilings, partitions, roofs, false ceilings etc., making good and fire proofing.

- building or forming of services ducts including where necessary, the provision of metal proprietary ducts, frames and covers.

- formation of bases, plinths, piers etc., for supporting all items of plant and equipment.

- building of manholes, pits, etc.

- excavating of trenches for underground mains etc., and the filling in of same after the mains etc., is laid.

- building in of brackets, straps, rag bolts or other form of suspension or fixing;

- ducts and floor trenches including pockets for pipe bearers; and

- position of access panels in false ceilings and vertical ducts for access to services.

The Contractor shall co-ordinate the preparation of builders work drawings to avoid conflict between respective services requirements.

Installation drawings shall be based on the detailed design drawings and shall show dimensioned layouts of all services installations, their support systems and their fixings; supplier’s general arrangements, wiring diagrams and detailed fabrications drawings and the like and shall reflect their relationships with the building structure and all building services.

Layouts shall be at a scale of not less than:

- 1:50 for general arrangement and layouts

- 1:20 for plant rooms details and sections

Drawings shall be obtained from the manufacturers’ of all plant and equipment, including ductwork systems.  The Drawings shall be fully dimensioned and shall show and describe all components, wiring diagrams, etc.

The Contractor shall keep a complete set of the design documents on site including the Scope, design drawings, installation and builders work drawings.

The installation and builders work drawings shall be amended on site with any variations as they occur.  These drawings will form the basis of the record drawings which shall be provided in the format required by the Scope.

## Responsibility for dimensions

All drawing dimensions supplied by the Project Manager or the Design Team are for information only and are to be verified by the Contractor by site survey or production of working drawings.

## Co-ordination

The Contractor shall be responsible for co-ordination, supervision and administration of the works, including the work of Sub-contractors, local authorities and statutory undertakers.

The Contractor shall hold co-ordination meetings which all Sub-contractors shall attend. The Contractor shall notify the Integrator, the Project Manager, the Design Team and any other of the Client's consultants when they need to attend. .

The purpose of the co-ordination meetings is to monitor progress, co-ordinate the execution of the works and clarify such matters as difficult access routes and services, conflict between trades and to ensure that all works and services are coordinated and installed safely and in the correct sequence.

## Design submission procedure

Drawings shall be fully dimensioned and to the required scales and shall give details of:

- all equipment and systems;

- shop and installation drawings of all ventilation ductwork, pipework, gas flues and associated sleeves and all fabricated sheet metal, brackets and supports;

- fabricated supports and brackets for tanks, pipework, ductwork and any equipment to be provided, including all structural loadings where necessary;

- wiring diagrams showing internal and external wiring between manufacturer’s equipment and electrical distribution boards etc.  All drawings shall clearly indicate all components and their respective terminal block references;

- any Site working drawings that the Mechanical/Electrical Services Contractor(s) intends to issue

The Contractor shall issue copies of all design and construction documents at the times stipulated in the Accepted Programme in accordance with the following:

Documents are to be issued direct to the Design Team.  Electronic copies should be distributed either via email, internet storage portals or on CD.

The Contractor shall ensure that all information produced is complete in order that a proper inspection of information may be carried out.  Information must be submitted in co-ordinated packages relating to the various activities during construction.

Documents must be stamped with the Contractor’s name, dated with the submitted date, signed by the Contractor and must be submitted to the Project Manager and the Design Team for comment and consideration prior to the fabrication, manufacture or construction of any work.

## Design approvals

Documents and samples submitted for comment will be dealt with as follows:

- Status A - Documents so marked means that fabrication, manufacture or construction may proceed in accordance with the submitted documents.

- Status B- Documents so marked means that fabrication, manufacture or construction may proceed in accordance with the documents submitted subject to the Contractor taking necessary action based on the Design Team’s comments and all notations added to the returned documents.  The Contractor shall submit the required number of amended documents to the Client's Advisory Team within 14 days.

- Status C - Documents so marked by the Design Team means that no work shall be fabricated, manufactured or constructed.  The Contractor shall re-submit new drawings to the Design Team for review until re-submission is no longer required.  Any submission marked ‘C’ will not be permitted on site.

Final comment upon documents (Status A) will be conditional upon submission of all necessary calculations, certificates, samples, mock-ups etc. as required in the Scope.

The Design Team will return the drawings with relevant comments within 14 working days of issue.

The Contractor shall separately identify any changes to drawn information by use of bubble clouds and legend notes.

The Contractor shall provide a programme indicating the proposed dates for release and quantities of design documents for comment, and shall maintain a schedule which clearly identifies the planned and actual flow of information with respect to all design drawings issued by themselves or their sub-contractors.

The Contractor is to incorporate in the Accepted Programme for the works, a period of no less than 14 days for initial inspection and comment by the Design Team.  Resubmission of design documents shall not be considered grounds for a compensation event.

Consideration by the Design Team of design and production information, calculations, etc., and the samples specified, will not relieve the Contractor of its responsibility for carrying out the works in accordance with the performance and quality standards specified herein.

The Contractor shall not alter the approved design without further approval from the Service Manager/Project Manager who in turn will need to ensure the relevant stakeholder and business unit approvals have been granted as required specific to the projects requirements.

The Contractor shall procure that its mechanical and electrical Sub-contractor:

- is provided with the dimensional information required for the preparation of the all drawings;

- prepares the base layout for working drawings to reflect the current architectural and structural and services information that is available to the mechanical and/or electrical contractor(s);

- issues to the Service Manager/Project Manager the required number of drawings as instructed whether working or builder’s work drawings for comment;

- issues fully co-ordinated drawings, including shop installation drawings;

- issues all drawings whether working or builder’s work drawings to the Service Manager/Project Manager for comment in good time to allow:

- the Service Manager/Project Manager at least two weeks for comments; and

- sufficient time for the incorporation by the Contractor of any comments made without affecting the Contract programme.

# General constraints on how the Contractor Provides the Works: Site related matters

## Inspections and investigations by Contractor prior to allocation of Work

Specific Site Information / Surveys will be provided with each Task Order, Call Off Contract and/or mini tender as applicable.

Prior to the issue of a Lot 1 Task Order the Contractor may not be afforded the opportunity to visit and inspect the Affected Property.

For Lot 2 and 3 Projects, the Contractor is deemed to have visited the Site prior to the commencement of the works and to have consulted all appropriate and relevant authorities and to have satisfied himself as to the means of communication, access to the Site, the extent of the works, the nature of the Site and the conditions under which the works will be carried out, together with conditions affecting the supply of labour and materials, and all other matters affecting the price for completion of the works.

The Contractor shall analyse the site information available to it and satisfy itself as to the quality, accuracy and completeness of any such data and to ensure that he has sufficient information to undertake the works in accordance with the terms and conditions of the Contract.

The Contractor will be responsible for carrying out all necessary investigations and research concerning the construction of any existing buildings or structures on the Sites to determine Site conditions.

The Contractor is to take into consideration the proximity and construction of adjoining buildings and their usage.

The Client accepts no responsibility for the accuracy or completeness of any information made available at tender stage. The information will be deemed to have been checked and approved by the Contractor who will have the same liability as if he had prepared the information or caused it to be prepared himself.

## Access to Site

Access to Sites and egress for inspection or for carrying out works, will be by agreement with the Service Manager/Project Manager for each Site and confirmed within each Call-off Contract.

The Contractor shall note, and make due allowance for any sharing of access with other contractors or users.

The Contractor shall comply with any specific regulations affecting individual Sites.

DWP’s office opening hours vary across the estate. With differing opening arrangements for corporate offices; medical centres; benefit centres and call centres. There are 8 Sites that operate 24 hours a day.

The Contractor should refer to DWP’s Property Matrix (in the Site Information) for details of individual Sites operating hours. Some Sites current published operating hours will be subject to further change in April 2018 when Saturday opening for all Jobcentres comes into force.

The majority of Sites open from 07:00-19:00 but no later than 20:30; so 07:00-20:30 Monday to Friday is a fair capture of the whole estate. In addition to this there are a small number of key back office corporate function buildings operate 24 hours however currently the majority of back office buildings operating hours are -

Mon – Fri	Open between 07.00hrs – 19.00hrs

Closed between 18.00hrs – 20.30hrs

Sat – Sun	Closed

The Contractor shall at all times observe all Police Regulations including those regarding the loading and unloading of vehicles on the public highway or any other road.

All disturbance and nuisance to building users and neighbours must be kept to an absolute minimum.

Similarly, access and egress from the works that are in close proximity to the building on which the Site is located and other buildings which will remain operational during the works, must not be disturbed.

Existing/adjacent buildings may be sensitive to noise and dust.

If, for any reason, access is required to adjacent property before any work beyond the boundary of the Site is commenced, the Contractor shall make all arrangements and give all necessary notices to the Client and any other interested parties, and pay all fees, expenses, charges and compensation in connection therewith.

Access will be by prior agreement with the Service Manager/Project Manager at least two weeks in advance;.

All services to existing buildings are to be maintained including the provision of temporary services where services have to be shut down. Planned shut downs must be scheduled and agreed with the Service Manager/Project Manager and reconfirmed with two weeks written notice to the Service Manager/Project Manager for each shut down. Temporary Services shall be provided for planned shut-downs prior to commencing the works where likely to last more than 4 hours.

## Working Hours

The Contractor and his sub-contractors must generally confine their work on Site, including deliveries to within the hours of 08:00 to 18:00 Mondays to Fridays, and 08:00 to 13:00 Saturdays with no works undertaken on Sundays or Bank Holidays.

The Contractor will be required to agree delivery times to Sites to and avoid peak traffic ingress and egress times of 08:30 – 09:30 and 16:00 – 17:30; and subject to planning restrictions and adjacent occupiers/users/owners.

The Contractor is to note that no noisy works will be carried out on Saturdays.

They will only be permitted to work outside these hours if prior written application has been made to the  Service Manager/Project Manager not less than seven working days in advance, and if such application has not been rejected by the  Service Manager/Project Manager in writing before the additional hours commence.

Approval of additional working hours is at the discretion of the  Service Manager/Project Manager and refusal or subsequent withdrawal of approval will not entitle the Contractor to a compensation event or any relief or remedy under the Contract.

## Other Works on Site

The Contractor shall note that access to and use of the Site will usually be shared with and/or access will be required by Others including the Client's staff and customers and other building users.

The Contractor shall ensure the necessary access to each Site in order to carry out work in accordance with the law of the Contract and/or any right of Others.  Whenever consistent with such requirements, such access shall be limited so as not to unnecessarily impede or restrict Others.

Other works and/or services may occur on the Sites, which may affect the access, proximity to the works and cause other inconvenience; the Contractor must ensure this is allowed for in its programme(s).

## Car Parking

Vehicle parking will only be allowed within the Contractor’s own working areas designated for Contractor’s parking (if any), as described within the Task Order or specific Project Call-off Contract, or on adjacent public highways, etc., where legally permitted. No extra costs will be considered for the Contractor’s failure to comply with this requirement.

The Contractor shall note that clear access to the Sites must be maintained at all times to allow free passage of firefighting appliances, the Clients and other vehicles. Entrances / exits to Sites shall not be obstructed or obscured at any time.

# General constraints on how the Contractor Provides the Works: Permissions/Agreements

## Contractor System

The Contractor, via the Contractor System or otherwise, shall ensure that systems and processes are in place to receive and process work requests from the Integrator. The Contractor is required to ensure the Contractor System maintains primacy of data and provides complete and accurate details, documents and updates of both an operational and commercial nature.

## Permissions/Agreements

The Contractor shall allow for obtaining permissions / agreements before erecting any hoardings, gantries, scaffolding etc., on or above property adjoining the works or erecting cranes which may overhang or swing over adjoining property. The Contractor shall allow all costs in complying with the foregoing and shall indemnify the Client from any claim or action for damages arising from any failure to obtain any permissions / agreements.

Details of the permissions obtained with supporting documentation are to be provided to the Service Manager/Project Manager.

## Licences

In relation to Licences which it is the Client's responsibility to obtain, the Contractor (without taking the risk that such Licences are not obtained, save to the extent that this is caused by the Contractor's failure to provide the support required by this contract) shall provide such support as the Scope states the Contractor is to provide to the Client in applying for and obtaining such Licences

## Permit to Work

The Contractor is required to have a permit to work system in place and provide to the Integrator the appropriate access and reports to enable the Integrator to audit, monitor and report on the systems adherence to all process, procedures and controls.  During the term of the framework, the Integrator may introduce a Permit to Work System. The Contractor is required to adhere to all process, procedures and controls as set out by the Integrator’s Permit To Work System and ensure the Contractor’s inputs into the system along with all supporting documentation is fully up to date and compliant to meet the required permissions prior to the relevant work commencing on Site.

# Contractor’s Personnel

## Key Roles

The Contractor shall ensure that all persons engaged in the carrying out of the works are competent and capable to undertake the work they are engaged in and have the relevant qualifications and skill with level of resources that is suitably commensurate with the project requirements and programme.

The Contractor shall ensure that all persons engaged in the carrying out of the works are at all times properly trained with regard to their respective tasks, meet to the extent the Contractor has been notified by the Client of the same the Client's specific educational or training requirements, attend induction and orientation courses and are trained with regard to all rules and procedures concerning health and safety at work, mandatory requirements and in particular asbestos containing materials, fire risks, precautions and procedures.

The Contractor shall ensure there are resource contingency plans in place to cover potential absenteeism of previously appointed key roles.

## Personnel recruitment

The Contractor shall ensure that no persons are employed or engaged in connection with the provision of the works unless satisfactory references including appropriate checks on criminal convictions in documentary form are obtained prior to the employment or engagement of such person.

The Contractor shall ensure at all times that sufficient personnel is engaged in relation to the carrying out of the works including all relevant grades of supervisory personnel.  For the avoidance of doubt this obligation shall include ensuring that there is sufficient staff to cover periods of holiday, sickness, other absence, and reasonable foreseeable peaks in demand for the works.

The Contractor shall ensure and where necessary shall obtain appropriate registration or notifications under any laws relating to data protection that the Client, the Client and the Service Manager/Project Manager shall at all reasonable times have access to the following details in respect of all employees of the Contractor, Subcontractors and suppliers engaged in the works:

- terms and condition of employment and length of service;

- any recognition agreements signed with independent trade unions; and

- any employment records.

All screening shall be undertaken in full adherence to DWP’s Security Policies and Standards.

## Personnel policies

The Contractor shall have suitable mechanisms in place to ensure that all persons engaged in the carrying out of the works are kept informed of essential information regarding the Client which affect or may affect the carrying out of the works, to the extent that the Client has notified the Contractor of the same.

The Contractor shall, to the extent it has been notified by the Client of the same, ensure that all management and supervisory staff engaged on the works are made aware of the Client's policies and procedures concerning emergency procedures, polices, security matters and health and safety matters.

The Contractor shall set up and maintain appropriate personnel policies and procedures covering all relevant matters, including discipline, grievance, equal opportunities, and health and safety in accordance with the law of the Contract and Good Industry Practice and shall issue all such relevant information to the Client upon request.

The Contractor shall and shall procure that all Sub-Contractors comply with the Client's operational policies including without limitation those relating to security.

The Contractor shall ensure that the Client and the Service Manager/Project Manager have access to all relevant information that demonstrates the Contractor’s compliance with this paragraph 5,3

The Client or their appointed representative shall be entitled to conduct upon reasonable notice an audit of the Contractor’s personnel and management policies at no extra cost to the Client.

# Regulatory and Policy Compliance

## Planning Conditions

The Contractor shall agree with the Service Manager/Project Manager such matters as may affect provisions of any planning conditions noted in the planning permission as being for the building contractor to discharge.

All relevant conditions must be satisfied and agreed in writing by the Contractor with the relevant planning authority in a timely manner so as not to jeopardise progress.  The Contractor must allow for all costs and fees in connection with such conditions. In the event that the Contractor's proposals for the discharge of planning conditions require resubmission to the planning authority, such costs and delays incurred shall be at the Contractor’s expense.

The Contractor shall provide to the  Service Manager/Project Manager originals of all approvals of planning conditions obtained from the Planning Authority.

## Building Regulation Approval

The Contractor shall obtain approval for the works under the Building Regulations and to pay all fees in connection therewith and shall comply in every respect with the Building Regulations.

The Contractor shall provide the Service Manager/Project Manager with originals of all formal approvals under the Building Regulations.

## Fire Officer’s Requirements

The Contractor shall ensure that the works are constructed in every respect to the satisfaction of the local fire authority and the Client's fire safety adviser.

## Work by Statutory Authorities

The Contractor shall give all notices and pay all fees and charges required and comply with the requirements of the any statutory authority including, the electricity, gas and water utilities and local authorities.

## Statutory Obligations

Working Rule Agreement

The Contractor shall allow as necessary for all obligations under the Working Rule Agreement for Building Trades Operatives in accordance with the rules, including sick pay, of the National Joint Council for the Building Industry, or, in the case of the workpeople so engaged whose rates of wages and other emoluments and expenses are governed by the rules of somebody other than the National Joint Council for the Building Industry, in accordance with the rules of such other body, applicable to the works and to meet the requirements and conditions in the area in which the Site is situated, for bonus payments and all expenses in connection therewith, for any extra cost of wages paid for any higher standard time rates that those authorised by the authorised wage fixing body and for all costs incurred in transporting workpeople to and from the Site. He shall also allow for all expenses in connection with the Annual Holiday and Death Benefit Scheme or any amendments or revisions thereto.

## Environment

The Contractor shall ensure that:

- all records are fully auditable and all information is freely available to support ISO 14001;

- all wood used as part of any works (temporary or permanent) or installed within any Site is from an independently verified sustainable source;

- no peat is used at any Site;

- all spent fluorescent tubes and rechargeable batteries are recycled or disposed of safely;

- all activities are monitored to ensure legal compliance with all applicable Laws for all waste streams;

- there is no venting of recoverable ozone-depleting or global-warming substances from any equipment, and that these substances are recovered for recycling or destruction using appropriate technology;

- at all times the Client's notified policies of resource conservation, pollution reduction, bio-diversity protection, and sustainable development are supported; and

- an energy profile in respect of all occupied Client Properties providing information concerning effective energy management is provided.

The Contractor is required to consider and submit with each Task Order or specific Project Call-off contract any further measures together with any cost implication which could be incorporated to improve the Environmental standard of the building. He is to offer with his proposals the costs including all additional preliminaries, overheads and profit required for incorporation of the stated measures.

# Management of the Works

## General Requirements

- The Prices and the Fee include for ensuring that the works are at all times carried out:

- in an effective and efficient manner and in accordance with Good Industry Practice;

- in a manner that is not likely to be injurious to health and safety or to cause damage to property;

- in compliance with the law of the Contract;

- in compliance with the Contractor's method statements and Quality Plans;

- minimise, so far as is reasonably practicable:

  - consumption of energy;

  - emissions of pollutants, harmful radiation, electromagnetic interference and chemicals which deplete the ozone layer;

  - the use if noxious substances; and

  - consumption of products associated with the destruction of tropical rainforests or threatened animal species.

- The Contractor shall submit to the Client a method statement including a programme and the Quality Plan for the Site in the content and format requested by the Service Manager/Project Manager and at least fourteen (14) days prior to the commencement of the works on the Site, failing which the Client may propose a method statement including a Quality Plan for that Site and the Contractor shall comply with the same.

- The Contractor shall have in place its Site organisational structure.

- The Contractor is to provide all necessary head office management support personnel and facilities and on site management and supervision.

- The Contractor shall ensure that all Sub-contractors undertaking elements or parts of elements of the works, are provided with copies of drawings or other instructions issued by the  Service Manager/Project Manager which relate to or affect the respective elements of the works and with copies of any subsequent revisions to such drawings or instructions.

The Contractor shall co-ordinate, supervise and provide administration of the works. He shall arrange and monitor a programme with any Sub-contractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for co-ordination of the work including commissioning and proving.

## Specifications and quantities

When ordering materials, the Contractor shall not rely solely on the description size and quantities contained in the documents but shall refer to the drawings, specifications and instructions issued by the Service Manager/Project Manager and satisfy itself as to quantities required.

## Supervision and co-ordination of the works

The Prices include for the costs of its personnel including all disbursements arising from the employment of all necessary management and supervisory staff, including without limitation the following:

- working foreman - at all times during the carrying out of the works, the Contractor shall ensure that a competent person is present who combines his Site work duties with the co-ordination, supervision and administration of the works, including work carried out by sub-contractors and suppliers;

- trade supervisors - in addition to the working foreman all significant items of work shall be under the supervision of a competent trade supervisor; and

- co-ordination of engineering services- the Site organisation staff shall include one or more persons with appropriate level of knowledge and experience of mechanical and electrical engineering services and the works generally

## Security and protection of the site

The Contractor shall submit prior to entering into contract, a method statement indicating his proposals for site and security establishment for the works.

The Contractor shall provide a secure compound which is to be used for the Contractor’s accommodation; mess; drying out facilities; storage of materials; tools and equipment as agreed with the Service Manager/Project Manager.  At the end of each day, all ladders, tools, equipment etc. shall be stored within this secure area. The compound shall be locked during hours which the Site is not occupied.

The proposed siting of all temporary offices, huts, latrines and compounds shall be submitted to the Service Manager/Project Manager for approval and approved before erection, but in any event shall be confined to the site compound.

Adequately safeguard the Site, the works, products, materials and plant from damage and theft. The Contractor shall make all reasonable precautions to prevent unauthorised access to the Site, the works and adjoining property and shall indemnify the Client against any claim resulting from injury or damage to any person whomsoever arising, or resulting from any incident occurring, during the contract period whether the person’s presence within the Site boundaries is authorised or not.

Provide temporary fences; hoardings; fans; planked footways; guard rails; gantries and the like together with lighting as may be necessary for protecting the public for the proper execution of the works and for meeting the requirements of the Local Authorities and the like. Obtain all licences and pay all fees legally demandable.

Take all necessary precautions to prevent personal injury, death, and damage to the works or other property from fire.

## Security and Identification of People

All permanent staff are to be registered with the Site Security and issued with security passes which shall be carried at all times on site.

All visitors, company representatives, etc. shall report to the security office  and obtain a pass before going on site, and shall at all times whilst on site be escorted by the Contractor’s representative.

## Protection of existing structures and services

The Contractor shall be responsible for taking all necessary precautions and protecting underground services, for making good any damage which does occur and for maintaining services while works are being undertaken.

The Contractor shall allow for all services required to carry out the works and shall make good any temporary connections to services upon completion.

The Contractor is responsible for ascertaining the exact location of all mains and services likely to affect the construction of the works.

Any damage to the mains or services that do not form part of the works shall be notified immediately to the Service Manager/Project Manager and be made good at the Contractor’s expense.

The Contractor shall not cut, isolate or otherwise interrupt any existing live services without prior approval.

The Contractor will be required to make good any damage to highways and services underneath, whether public or private, both inside and outside the Site, if caused by or attributable in any way to the execution of the works and indemnify the Client against loss and damage or claims by the local Client or others for damage to roads, paths and services by reason of extraordinary traffic.

For the purpose of this paragraph the term “Highways” shall be deemed to include any road, footpath or bridleway on or off the Site, used by the public, together with any verges, gullies, sewers, street lighting, public utility services or tree planting associated therewith.

The Contractor will be required to take all necessary and sufficient precautions to prevent the deposition of mud, dirt, rubbish or any deleterious matter on any footpaths, roads, or highways adjacent to the Site. Immediately remove any such matter which may be deposited in spite of such precautions, and pay all fines and charges incurred as a result of failure to observe the requirement. Comply with any Police requirements concerning the provision and use of wheel cleaning devices.

## Control of site personnel

The Contractor at all times ensures that there is no trespass by the Contractor, its servants, agents, sub-contractors or suppliers on or over any other part of the building at which the Site is located and any adjoining or neighbouring property arising out of, or in the course of, or caused by the carrying out of the works and the Contractor takes all reasonable safety and other measures to prevent damage or injury to any persons (including, but without limitation, the adjoining or neighbouring property and members of the public.

The Contractor is only permitted access to the designated working area, as defined in the Scope. A system of booking in must be maintained by the Contractor to ensure accurate records of people on Site are kept.

The Contractor complies with the following:

- No smoking is allowed on the Site.

- No radios other than two way communication radios with agreed frequencies shall be allowed on Site.  No cd/dvd/mp3 or cassette players are allowed on Site.

- No access onto the Site other than via designated routes.

- Wearing of PPE at all items

- No ladders and step ladders to be used as working platform

- No operation of any plant or equipment by untrained persons

- No altering/removing/adapting or changing any scaffold on Site other than by an approved scaffolder.

- No placing of materials in walkways and escape route or keeping areas untidy /debris not placed in the bins provided.

- No eating in undesignated areas is allowed on Site.  No food or drink is to be taken onto Site.

- Personnel found not using the designated toilets shall be removed from Site.

- Removal of rubbish and debris

The Contractor shall be responsible for disposal of all Site waste.

Remove rubbish, debris, surplus material and spoil regularly and keep the Site and works clean and tidy.

Remove all rubbish, dirt and residues from voids and cavities in the construction before closing in.

Ensure that unwanted non-hazardous material, spoil and rubbish is disposed of at a tip approved by a Waste Regulation Authority.

Remove all surplus hazardous materials and their containers regularly for disposal off site in a safe and competent manner as approved by a Waste Regulation Authority and in accordance with relevant regulations.

Retain all waste transfer documents on Site.

## Prevention of Dumping

The Contractor shall take all practicable steps to prevent spoil, rubbish, surplus materials etc., arising from the works being dumped on an area other than a recognised tipping area.  Without prejudice to the generality of the foregoing the Contractor shall:-

- subcontract carting away only to bona fide carriers;

- obtain from such carriers the locations of the proposed tipping area or areas;

If and when required by the Service Manager/Project Manager, obtain and submit written evidence that all loads of spoil, rubbish, surplus materials, etc., have been deposited at a recognised tipping area or areas.

In the event of the Service Manager/Project Manager being satisfied that any spoil, rubbish, surplus materials etc., have been deposited elsewhere than at a recognised tipping area, the Contractor shall bear all costs of clearing away such deposits and ensure that they are deposited at a recognised tipping area

## Protection of the works

The Contractor shall be responsible for adequately protecting the works against damage arising from weather conditions, or other environmental conditions, which would have an adverse effect upon the works. He shall anticipate all possible damage problems; take all necessary steps to protect, including altering protection as necessary.

## Traffic management

The Contractor is to co-ordinate vehicular movements so as to cause the minimum inconvenience to the adjoining properties and other users. All roads and areas outside of the Site boundaries must be kept clean and clear of all materials, equipment and vehicles at all times.

## Condition survey

Before work commences, the Contractor in the presence of the Service Manager/Project Manager or their designated representatives shall inspect all areas of the site and adjoining site boundaries and prepare a Schedule of Conditions.

The Schedule of Conditions shall fully describe the condition of all items likely to be affected by the works and should include photographs and/or video film taken by the Contractor. The Schedule shall be dated and signed by the Service Manager/Project Manager and the Contractor and deposited with the Service Manager/Project Manager. At the completion of the Contract the Contractor shall make good any damage directly attribute to the carrying out of the works.

## Consideration of others

The surrounding highways will be in constant use and the building on which the Site is located and adjoining buildings will remain fully occupied during the duration of the works. Fire access routes and exits of buildings are to remain free from obstruction at all times.

The Contractor shall protect and shall ensure the safety and continued operation of adjacent buildings / structures, paved surfaces and roadways adjacent to the works and shall make good immediately any damage resulting directly or indirectly from his operations.

The Contractor shall ensure that safe passage is maintained for pedestrians near works; particular attention being paid to the safety of disabled persons, blind persons, and children and that all works have prescribed warning signs, clearly visible at all times.

The Contractor must ensure that all of his staff, employees and workpeople and sub-contractors’ workpeople do not make any remarks, noises, gestures, movements or other that could be considered to be racially or sexually offensive, or offensive to people with disabilities.

The Contractor shall not display pin up material of either sex in any place on the works.

## Progress meetings

The following progress meetings will be held and are to be attended by the Contractor's Representative and, where requested by the Service Manager/Project Manager, representatives of any Subcontractor or other supplier:

- monthly regional project meetings for each regional Lot;

- pre-start meetings at each Site;

- project meetings at each Site as often as it is reasonably required no less frequently than monthly; and

- a meeting at each Site on Completion of the works (a Handover Meeting).

## Progress Meeting and Reports

For Task Orders and Call Off Contracts of sufficient size and value,  the Service Manager/Project Manager will hold meetings on Site at regular intervals during the course of the works, to review the progress of the construction of the works.

At these meetings the Contractor is required to submit a Progress Report which is to be submitted to the Service Manager/Project Manager five days before the meeting.  A sample of the report is to be submitted to the Service Manager/Project Manager within 21 days from appointment.

Periodic reporting from the Contractor will be required. These reports are in order to fulfil Contractors and Integrators Performance Management System in addition to capturing all elements of contractor delivery. Contractor Reports to include, though not limited to –

- Programme

- Risk & Compliance

- H&S / Incident reporting

- Commercial

- Quality

A typical structure for Contractor Reports would be as follows:

- Programme

- Summary of all Task Orders in progress

- Individual Project Progress Reports

- Project Programme Forecasts including critical path

- Current or anticipated delays and mitigation measures

- Risk & Compliance

- Individual Project Risk Register

- Risk Register at a Programme level (where applicable)

- Notices and Licences applied for and obtained in period

- Outstanding approvals

- BIM reports – (Lot 3 Contractors)

- H&S / Incident reporting

- Incidents including near misses

- Tool box talks undertaken in the period

- Commercial

- Variations status report

- Payment Applications status report

- Quality

- Snagging status report

- Defects status reports

- Performance

- Performance reports via the Integrator Performance Management System

## Risk Management Process

Contractors must adhere to the Client's risk management processes that will be managed by the Integrator.

# Quality Assurance

## Quality Plans and Systems

The Contractor shall ensure that all aspects of the work are the subject of quality management systems applicable to the Contractor and its Sub-Contractors,

The quality management systems shall be reflected in appropriate Quality Plans and shall comply with:

- BS EN ISO 9001/9002 or equivalent externally certificated quality assurance procedures;

- the Contract Documents.

The Contractor shall comply with the Quality Plans and shall ensure its Sub-Contractors comply with the Quality Plans.

## Additional information

The Contractor shall provide the Service Manager/Project Manager  with or procure the provision of such information as the Service Manager/Project Manager may reasonably require demonstrating compliance with this paragraph.

## Quality Manager

The Contractor shall appoint as soon as is reasonably practicable the Quality Manager, who shall be independent of the Contractor’s personnel who are directly involved in the day-to-day management of the works.  Without limitation, the terms and conditions of engagement of the Quality Manager shall require him to:

- ensure the effective operation of the quality system defined herein;

- audit the quality system at regular intervals and report the findings of such audits to the Service Manager/Project Manager;

- review all quality systems at intervals agreed with the Service Manager/Project Manager  to ensure their continued suitability and effectiveness;

- liaise with the Service Manager/Project Manager on all matters relating to quality management.

## Quality monitoring

The Service Manager/Project Manager may carry out periodic monitoring, spot checks and audits to the Contractor’s quality system including without limitation all Quality Plans and any quality system.

The Contractor shall:

- procure that the Service Manager/Project Manager shall have like rights set out above in respect of its Sub-Contractors;

- bear the costs of the audits, monitoring or spot checks carried out by the Service Manager/Project Manager; and

- procure that its Sub-Contractors, shall, co-operate and provide all necessary information and documentation to the Client in connection with such audits, monitoring or spot checks.

## Quality control

The Contractor and Sub-Contractors shall have in place and maintain accredited certification from an approved assessment body pursuant to BS EN ISO 9001/9002 (or equivalent) or any modification or replacement of these standards.

## Codes of Practice for Contractors

Where instructed by the Service Manager/Project Manager, the Contractor shall register a specific project with the Considerate Constructor’s Scheme and shall use its best endeavours to comply with the Scheme’s Code for Considerate Practice (see Considerate Contractors Scheme).

## Document formats

The Contractor shall provide all information, documents, records and the like in connection with this Contract in any form as may be requested by the Client and/or the Service Manager/Project Manager from time to time including without limitation progress reports, information about its staff and other information required to monitor compliance by the Contractor  with the provisions of this Contract.

## Site records

The Contractor shall keep daily records of the weather, maximum and minimum temperatures, hours lost due to inclement weather, number of trade operatives including Sub-Contractors working on Site, together with details of materials and goods delivered to Site. Such records shall be summarised weekly in an agreed manner and produced for inspection by the Service Manager/Project Manager when requested, where required, provide monthly progress photographs to record the monthly progress of the works, allowing for 10 photographs for each works Order taken from viewpoints agreed with the Service Manager/Project Manager. Digital photographs and/or two sets of colour prints size 215 x 150 mm shall be supplied, as agreed, by the Service Manager/Project Manager at least a week before the monthly project meetings.

## Sufficient Stocks

The Contractor shall ensure that sufficient stocks of goods, consumables, equipment and materials are held in order to carry out the works in accordance with the Task Order/Call-off contract.

## Storage

The Contractor shall ensure that all hazardous materials or equipment used or stored on Site shall be kept in accordance with good industry practice, properly and securely labelled and stored, under appropriate supervision, and used only by appropriately trained and competent staff.

## Covered up work

Where any element of the works is to be covered up by subsequent operations the Contractor shall give the Service Manager/Project Manager  at least two working days-notice of when such element of the works will be available to be measured prior to being covered up.

## Drying out the works

The Contractor shall be responsible for drying out the works and controlling temperature and humidity levels commensurate with the nature of the works.

The Contractor shall comply with British Codes of Practice which call for special methods of curing, laying and maintenance of materials in particular conditions or at a certain moisture content or temperature range and to conditions adopted by the Association of Flooring Contractors and similar bodies.

Prior to fixing any internal joinery, the Contractor shall provide, where necessary, a slow build-up of heat until 13C is achieved and thereafter maintain a minimum temperature of 13C until Completion.  The Contractor shall maintain a sufficient supply of fresh air throughout the building.

# Tests and Inspections

## Tests and Inspections

It shall be a condition precedent to achieving Completion that the Contractor shall have fully tested and balanced the engineering services Installations and the Contractor shall produce test certificates and records of commissioning to verify the successful working of these installations and receive the Service Manager/Project Manager’s acceptance.

Agree dates and times of tests and inspections with the Service Manager/Project Manager at least one week in advance, to enable the affected parties to be present. On the previous working day to each test or inspection confirm that the works or sample in question will be ready or, if not ready, agree a new date and time.

The Contractor shall allow for returning to Site to carry out seasonal commissioning of service installations.

## Commissioning of Engineering Services

The requirements for commissioning are, prior to Handover and Seasonal Commissioning.

It is a requirement that the Contractor  allows within his programme to ensure that the services engineering design performance is being achieved and provide for the Design Team subsequently to witness all tests and receive all certificates.

The Contractor is to develop an effective and logical commissioning programme with the agreement of the Service Manager/Project Manager.  The Contractor  is to allow for periodic return visits during the defect correction period to check and adjust the engineering services in the building taking account of seasonal climatic changes.

Allow for all continuous running tests required by the Scope.

The Contractor shall employ an independent commissioning company to carry out the commissioning works which shall be in accordance with the C.I.B.S.E codes.

In the event of an on-site or off-site test being unsuccessful no extra charges will be allowable for any subsequent delays or re-testing and the Contractor shall be liable for any costs associated with re-testing.

The Contractor shall allow periodic visits during the construction of the building to allow the Client's maintenance staff to familiarise themselves with the installed services.

## Inspections and tests at manufacturer’s works

At the Service Manager/Project Manager’s request the Contractor shall make arrangements for the Service Manager/Project Manager or his delegated representative to witness the inspection of the quality of workmanship and/or witness tests during manufacture of any materials/equipment being supplied as part of the works.  The Contractor shall also be present at any such test.

The Service Manager/Project Manager shall be given ten days clear notice of any test.

Three copies of test certificates shall be sent to the Service Manager/Project Manager on completion of a satisfactory test.

## Use of Engineering Services Installations by Contractor

The Contractor shall be allowed to use the services installations for testing, proving, commissioning and applying thermal insulation only, and when the following requirements have been fulfilled:

- The Contractor has given written advice of the date of testing, proving and commissioning etc., to the Service Manager/Project Manager.

- The Contractor has undertaken full responsibility and adequate insurance cover for the period of said operation.

- The Contractor has arranged for a qualified and competent engineer to be in attendance during period of operation.

- The Contractor has given written confirmation that the running of the plant prior to handing over shall in no way affect or invalidate the Contractor’s guarantees,.

- The Contractor shall provide water, power, fuel etc., for temporary operation of the plant and shall include for all temporary supplies for testing and commissioning.

## Notice before Covering Work that is to be Inspected or Measured

The Service Manager/Project Manager may, at his discretion, give notice to the Contractor that he requires to inspect or measure any part of the works prior to it being covered or hidden. In this case, the Contractor is to give reasonable notice in writing to the Service Manager/Project Manager before covering or hiding such work. In default of this requirement, the Contractor will be responsible for uncovering the work and carrying out all subsequent making good at his own expense whether the work was found to be satisfactory or otherwise. The Contractor is to give the Service Manager/Project Manager not less than one week’s notice before removing scaffolding or other facilities for access.

The Contractor shall allow the Service Manager/Project Manager or his representatives’ facilities for the inspection and testing of the quality of the work, materials, exposed surfaces and spoils from the works. Access shall be arranged as necessary to any place of manufacture off-site. Similar access shall be arranged for Sub-contractors’ works.

Any work found to be defective and not in accordance with the Scope will be dealt with in accordance with the terms of the Contract.

Inspection / test certificates are to be produced in accordance with the specifications within the Scope and appropriate standards.

## Covering up Completed Work

The Contractor shall agree dates for inspections of works to be covered up with the Service Manager/Project Manager or his representatives five days in advance. On the previous working day to each such arranged inspection confirm that the Work in question will be complete and ready for inspection, or that it will not be ready, in which case agree a new date.

The Contractor will not cover up such work until authorised to do so.

## Arrangements for opening up and remedying Defective Work

As soon as possible after any part(s) of the work or any materials or goods are known or appear to be not in accordance with the Scope, the Contractor shall submit proposals to the Service Manager/Project Manager and the Building Control Officer where appropriate for opening up, inspection, testing, making good or removal and re-execution.

The Contractor shall allow for the possibility that such proposals may be unacceptable to the Service Manager/Project Manager or his representatives and that the Service Manager/Project Manager may issue contrary instructions.

# Works Control Measures

## Noise control

The following applies:

- the Contractor shall carry out the works causing the least possible of noise and inconvenience to the occupants of the property at which the Site is located and to other adjoining and neighbouring buildings by the use of appropriate plant and equipment incorporating up to date methods of sound reduction;

- the Contractor shall comply with the Control of Pollution Act 1974 Part III Noise and BS 5228, and allow in its rates for any costs arising from such compliance;

- the Service Manager/Project Manager’s approval is required for the positioning of all fixed plant and equipment before its installation on Site;

- the use of portable radios and tape/cassette players, etc. is not be permitted on Site;

- the Contractor shall comply with Control of Noise at Work Regulations 2005.

## Dust control

The Contractor shall take all reasonable measures to limit and control dust nuisance caused by building work, including:

- providing screens, dust sheets and other Equipment to minimise the generation, disturbance and dispersal of dust;

- providing dust dampening and capture equipment (such as spraying water from hoses having fine rose-headed jets);

- not undertaking any work where ITC and other installations of DWP staff are not adequately protected from dust and debris at all times during the carrying out of the works and providing such protection where necessary.

## Existing services, cables and drains, etc.

The following applies (see also paragraph 7.6 above):

- prior to commencing operations on Site, the Contractor shall notify all the public undertakings concerned that work will be commencing on Site and shall ascertain the position of all electric power cables, telephone cables, gas mains, water mains and sewers, which may be under or over the Site or the approaches thereto;

- the Contractor shall take all the necessary precautions to support, maintain and protect any existing pipes, ducts, drains, sewers, services, overhead or buried cables, etc. during the execution of the works, to the satisfaction of the Service Manager/Project Manager. In the event of damage the Contractor shall make good any damage and/or pay the cost and/or charges for the making good of the same.  The Contractor shall notify the Service Manager/Project Manager immediately of any damage caused to any service, cables, etc.;

- during the progress of the works, the Contractor shall not interfere with the operation of existing services such as electricity, gas, water, telephone, buried cables, sewers, drains and ditches both on the Site and adjoining premises without the agreement of the Service Manager/Project Manager, and in the case of works of statutory authorities and private owners, without their permission.

- no diversion of any of the existing services, etc., other than as shown on the drawings, or described elsewhere shall be carried out without the Service Manager/Project Manager’s consent.  Any temporary disconnection of the services, etc., which may be necessary in connection with the works shall be carried out at such times instructed by the Service Manager/Project Manager.  The Contractor shall be responsible for maintaining close liaison with the public undertakings so as to avoid any disruption of the existing services;

- the Contractor shall make provision in its rates for the cost of taking all reasonable precautions to ensure the efficient protection of all streams and waterways against pollution arising out of, or by reason of, the execution of the works.

## Hoardings

The Contractor shall obtain all necessary approvals and provide and erect hoardings, planked footways, guardrails etc. as instructed by the Service Manager/Project Manager, together with the necessary temporary warning lights.  On completion of the works, the Contractor shall remove any temporary structures and make good any damage to kerbs, footpaths and roadways, etc. to reinstate them as necessary.

## Existing trees

All trees on Site including trees within any adjacent public footpaths, shall be carefully preserved and protected from damage during the execution of the works. Chemicals and petroleum products shall not be stored within five metres from the base of trees.

## Openings into existing buildings

When work ceases at the end of each working session, all access points and/or openings into the working area shall be sealed as instructed by the Service Manager/Project Manager before the Site is vacated, to ensure that the premises are secure and prevent unauthorised access.

## Rodent infestation precautions

The following applies:

- all necessary precautions shall be taken to avoid animal/rodent infestation of the Site;

- without prejudice to the generality of this paragraph the Contractor shall put into place and enforce as required rules to prevent the indiscriminate scattering of food scraps and other litter by all persons working on Site including all sub-contractors and persons working on behalf of public service companies for the whole duration that it has access to the Site.  Covered metal refuse bins shall be provided for the disposal of food scraps and litter and such bins shall be emptied at frequent intervals as instructed by the Service Manager/Project Manager;

- the Contractor shall take precautions as necessary to avoid the entry of rodents when drains are being laid including, providing temporary stoppers to pipe ends and setting manhole covers in positions as the work proceeds.  Pipes and cables passing through the foundation walls shall be properly built in.

## Fire precautions

The Contractor shall comply with Joint Code of Practice entitled Fire Prevention on Construction Sites and shall take all reasonable precautions to avoid the outbreak of fire particularly during the carrying out of work involving the use of naked flames.  The Contractor shall ensure that persons working on Site are made aware and are continually reminded of the dangers involved in the accumulation of rubbish on the Site. The Contractor shall comply with the relevant provisions of the Construction Phase Plan for the approval, control and supervision of all activities that may involve the use of naked flame and/or may cause a fire incident on Site.

The Contractor is to take all reasonable precautions to avoid the outbreak of fire particularly in work involving the use of naked flames. Such work should be examined at short intervals immediately following its completion. He must impress on his workmen the dangers involved in the careless use of naked flame in proximity to combustible material, and the accumulation of rubbish on the Site.

Burning on site of materials arising from the works will not be permitted.

## Personal Protective Equipment (PPE)

The Contractor shall provide and ensure the appropriate use of all necessary personal protective clothing and other equipment as is necessary for the protection of health and safety of the persons carrying out the works.

The Contractor shall provide industrial safety helmets in accordance with BS 5240 for the use of all persons on Site, including all sub-contractors’ staff and authorised visitors, who may be at risk of head injury.  The Contractor shall use its best endeavours to ensure that all personnel on the Site wear helmets when necessary.

## Drinking/drugs

The Contractor shall ensure at all times that no alcohol consumption or usage of drugs is carried out on Site by any person whether employed directly by the Contractor or a Named Sub-Contractor, other approved sub-contractor or any other person working or visiting the Site under any capacity.

## Clearance of fuel/oil leakages or spillages

Where the Contractor has caused or allowed to be caused any oil and/or fuel leakage or spillage the Contractor shall procure the removal and/or clearing or the same by the Client's cleaning service provider as instructed by the Service Manager/Project Manager and shall reimburse all related costs.

## Protection of work in all sections

The Contractor shall cover up and protect all work and materials including but not limited to work and materials of Sub-Contractors and all furniture and equipment liable to damage from traffic, weather or any other cause and provide, install and afterwards remove, all necessary temporary boarding, fillets, casings and other coverings and leave the works and the Client furniture and equipment clean and free from dust.  The Contractor shall exhibit in conspicuous position, notices emphasising to all persons working on Site the importance of protecting finished work, furniture and equipment.

# Materials and Workmanship

## Quality

Where and to the extent that materials, products and/or workmanship are not fully specified under the Contract Documents they shall be, as a minimum:

a)	the best of their respective kind or of a reasonable quality for the works as stated in or can reasonably be inferred from the Contract Documents; and

b)	in accordance with the PSA schedules of rates, and DWP's composite schedule of rates for specific components within the JPEG – Job Centre Plus Environment Guide (the Price List and Activity Schedule in the Lot 1 and Lot 2 contracts);

c)	in accordance with good building practice, current British Standards and/or Agrément Certificates.

## Manufacturer’s recommendation

The following applies:

a)	the Contractor shall handle, store, prepare, use or fix each product in accordance with the manufacturer’s printed/written recommendations and/or instructions.  The Contractor shall inform the Service Manager/Project Manager in the event of a discrepancy between the manufacturer’s recommendations and/or instructions and any specified requirements under the Contract;

b)	the manufacturer’s recommendations and/or instructions are those current at the time of carrying out the works;

c)	at the request of the Service Manager/Project Manager the Contractor shall submit copies of the manufacturer’s recommendations and/or instructions.

## British Standards

Compliance to the relevant British Standards refers to the most updated version as listed in the edition of British Standard Yearbook current at the time of executing the works.

At the request of the Service Manager/Project Manager the Contractor shall obtain British Standard Certificates, for products and materials specified to British Standard.

## Sustainability

Only FSC timber from sustainable/renewable sources shall be used. Evidence shall be provided by the Contractor of compliance with FSC accreditation of all timber incorporated into the works, used for temporary works and used on the Site for scaffold boards or any other use.

## Products

Products are to be new unless otherwise specified.  The Contractor must ensure that the quantities of each product and material required to complete the work are adequate and consistent in kind, size, quality and overall appearance.  The Contractor shall handle, store, and fix products with care to ensure that they are not damaged when incorporated into the works.

## Single sources

Where the Service Manager/Project Manager has approved a manufacturer or a source of supply for any particular product and/or material, the Contractor shall ensure that the whole quantity required to complete the works shall be of the same type, manufacturer, and/or source.  At the Service Manager/Project Managers request the Contractor shall produce written evidence of the source of supply of any product and/or material. The Contractor shall not change the source without the prior written consent of the Service Manager/Project Manager.

## Old materials

No old or used materials are to be used in the works without the prior written approval of the Service Manager/Project Manager.

## General quality of workmanship

The Contractor shall ensure that:

a)	its operatives shall be appropriately skilled and experienced for the type and quality of work;

b)	all necessary precautions are taken to prevent damage to the work from frost, rain and other hazards;

c)	components and products are inspected carefully before fixing or using and reject any which are defective;

d)	its operatives shall fix or lay securely, accurately and in alignment;

e)	its operatives, where not specified otherwise, shall select suitable fixing and joining methods and types, sized and spacing of fastenings;

f)	suitable packings are used at screwed and bolted fixings to take up tolerances and prevent distortion and they are not over tightened;

g)	adjusting location and fixing of components and products are carried out in such manner that joints which are open to view are even and regular;

h)	all moving parts operate properly and freely;

i)	its operatives do not cut, grind or plane pre-finished components and products to remedy binding or poor fit without the Service Manager/Project Manager’s prior written approval.

## Accuracy/Setting Out Generally

### Tolerances

Where not specified otherwise the Contractor shall carry out the works to such accuracy that all final sizes fall within the permissible deviations, and approximately two thirds of achieved size fall within one third of the permissible deviations of the British Standard 5606, Tables 2 and 3.

### Appearance and fit

The Contractor shall set out, erect, juxtapose components and applications of finishes (working within the practical limits of the design and specification) ensuring satisfactory fitting at junctions and that the finish has a well aligned, true and regular appearance.

Wherever satisfactory accuracy, fit and/or appearance of the work are likely to be critical or difficult to achieve the Contractor shall obtain the Service Manager/Project Manager’s approval of the methods in which he proposes to use and/or of the appearance of the relevant aspects of the work in progress as early as possible.

### Non compliance

Work which fails to meet the specified levels of accuracy, appearance and fit shall not be rectified without the Service Manager/Project Manager’s prior written approval of the methods in which it proposes to use for rectification. The Contractor shall pay for all costs arising from such rectification work including the cost for other work that is affected.  In the event that the Contractor is not granted rectification approval it will remove and replace the unsatisfactory work and shall pay for all costs arising from such removal and replacement including the cost related to other work that is affected.

### Setting out

The Contractor shall:

- be responsible for setting out the works using methods and measuring instruments described in BS 5606: section 5 and accuracy within the limits stipulated in table 4 of that Standard and within permissible deviations;

- submit details of methods and equipment to be used in setting out the works;

- obtain the Service Manager/Project Manager’s prior written approval of the detailed methods and equipment that it proposes to use in setting out the works;

- check the levels and dimensions of the Site against those shown on the drawings, and record the results on a copy of the drawings.  Notify the Service Manager/Project Manager in writing of any discrepancies identified and obtain instructions before proceeding;

- prepare setting out and construction details to be submitted to the Service Manager/Project Manager for acceptance prior to construction;

- inform the Service Manager/Project Manager when overall setting out is complete and before carrying out the works;

- be cognisant with the following for which he is responsible:

- recording information on a drawing and 2nr copies submitted to the Service Manager/Project Manager.

- for verification on site of all dimensions. Where these vary from theoretical dimensions the Service Manager/Project Manager or his representatives are to be informed.

## Fixing/Fastening/Adhesives Generally

### Fixing generally

The Contractor shall use fixing and joining methods and types, sizes and spacing of fastening which are suitable having regard to the following:

a)	Nature of and compatibility with product/material being fixed and fixed to;

b)	Recommendation of manufacturers of fastenings, and manufacturers of component, product or material being fixed and fixed to;

c)	Materials and loads to be supported;

d)	Conditions of expected use;

e)	Appearance, this being subject to the Service Manager/Project Manager’s approval.

## Fastenings for materials and components

The Contractor shall ensure that:

a)	the fastenings forming part of external construction but not directly exposed to weather shall be of corrosion-resistant material or have a corrosion-resistant finish;

b)	The fastenings directly exposed to the weather shall be of corrosion-resistant material.

### Fixing through finishes

The Contractor shall ensure that fastenings and plugs (if used) have ample penetration into the backing.

### Adhesives

These shall be of a type recommended by the manufacturer of the product being fixed and fixed to. In the absence of such recommendation an adhesive recommended for the purpose by its manufacturer shall be used.

## Scaffolding

### Provision

The Contractor shall provide and adapt all required scaffolding as necessary to suit the execution of all the working operations, including allowance adaptation where necessary.  The Contractor shall ensure the standing scaffolding is erected early enough and/or dismantled late enough to suit the programme and allow for extending the period of scaffold hire as necessary.

The Contractor shall provide all tools, plant, tackle, scaffolding, materials, protective works and security precautions and labour which shall be required for the proper and successful execution of the works.  Security precautions as a minimum will include intruder alarms to the approval of the Service Manager/Project Manager.

### British Standards

The Contractor shall ensure that:

a)	The scaffolding shall conform to BS 5973:1981;

b)	new fittings will conform to BS 1139;

c)	all scaffolding will be “new” or “as new”;

d)	timber scaffold boards shall conform to BS 2482; and

e)	scaffolding shall be fully boarded at all times.

### Scaffold erection

The scaffolding is to be erected and struck outside normal office hours, unless otherwise agreed by the Service Manager/Project Manager.

### Fittings

All loose fittings shall be cleared from the Site on completion of the scaffolding erection, and loose fittings or poles shall not be left on the boards.

### Approvals and consents

The Contractor shall be wholly responsible for obtaining, maintaining and complying with all the necessary Licences relating to scaffolding, approvals and consents, including provision, fittings and maintenance of lighting on the scaffolding for the protection of pedestrians, and maintaining the scaffold register on the Site whether or not the scaffold is in use.

### Protection

Scaffolding shall be independent throughout and the Contractor shall ensure that tubing and fittings do not cause any damage or stains to external walls of the building, roofs, public footpath areas, or public road surfaces.  Where scaffolding comes into contact with the building, adequate protection is to be provided to prevent any damage to either.

On all elevations, the Contractor shall take the necessary precautions to protect the public and occupants of the building from falling debris etc.

The Contractor shall ensure that the ends of the scaffold poles at ground level will have plastic end caps fitted and that scaffolding material will be fully sheeted at all times with clear plastic sheeting or similar approved free from advertisements.

### Windows

Windows shall at no time be partially opened for the scaffold bars to tie in the scaffold.

### Ladders

The Contractor shall remove all ladders from the vicinity of the works and from the bottom lift of the scaffold at the end of each working session and store in a lockable enclosure overnight.  No ladders or other means of climbing shall be left on Site whilst unattended.

### Lighting

The Contractor shall ensure that the scaffolding is adequately lit at night at first level with lights at 5ft centres as direct by the Local Authority.

### Projections

The Contractor shall ensure that there are no projecting scaffold pipes, clips, ties etc. that could be a potential hazard to pedestrians beneath first floor levels.

### Inspection

The Contractor shall notify the Service Manager/Project Manager seven days before any scaffolding is taken down to give the Service Manager/Project Manager or his representative the opportunity of inspecting the works.

### Striking scaffold

On removal of the scaffolding and protection, the Contractor will be liable for making good all disturbed surfaces.

# Programmes

## General

The Contractor submits to the Service Manager/Project Manager, the programme (or Task Order programme in the case of Lot 1) in accordance with clause 33.1 (Lot 1) or clause 31.1 (Lots 2 and 3). The programme shall have sufficient detail to clearly illustrate the planned progress of the works in accordance with the Contract.

The programme are to be prepared and monitored by a suitably qualified person who is to remain in close contact with the project until contract completion and be available upon request for consultation with the Service Manager/Project Manager.

The Contractor shall be responsible for revising its programmes, procurement schedules, method statement and managerial proposals, should any “what if” scenarios or any other circumstances arising which substantially affects the works. These updates must be submitted to the Service Manager/Project Manager in order to ensure full comprehension of the planning and programming issues are known prior to management decisions being made.

Record delays due to adverse weather, including description of the weather, type(s) of work affected and number of hours lost.

The Contractor will arrange for progress meetings to be held as often as necessary for the proper management and co-ordination of the contract, the regularity of which shall be agreed with the Service Manager/Project Manager.

All programme information shall be issued to the Service Manager/Project Manager in hard copy (2 No.) and digital format as agreed.

## The Overall Construction Programme

The programme should be derived from a detailed critical path and will show an overview of the project showing activities how the project is to be carried out including all principle milestones.  The critical path must be indicated and the activities linked.

## Detailed Critical Path Programme

The network will be prepared in accordance with the following criteria:

- The programme must clearly establish the logical sequence of work, display and programme restraints determined by resource limitations, and establish all critical activities and their relationship with all other major activities.

- The programme shall include and indicate clearly all pre-construction and major construction activities, the work of all subcontractors and statutory authorities, all testing and commissioning activities, and any provisional items.

- The programme shall be in the form of a bar chart and if required, a network diagram and be analysed by computer using a recognised critical path analysis software package.

- The network is to be in sufficient detail to satisfy the Service Manager/Project Manager that it demonstrates the logical relationship between all activities.

- Each activity on the network diagram shall be so annotated and coded as to identify its location, trade and activity type e.g. substructures; first floor first fix mechanical, 2nd floor internal partitions and, if so requested by the Service Manager/Project Manager, the resource levels required to achieve completion within the duration indicated.

- The Contractor is to provide to the Service Manager/Project Manager, if requested, neatly drawn or plotted copies of the network.

- In addition to the plotted information the Contractor is to provide (if requested) the logic in a tabulated schedule format showing the following:

- Activity numbers and descriptions

- Activity durations

- All relationships (Predecessor and Successor dependencies) between activities, including lags

- The Contractor shall also provide the programme, including the logic network data on computer compact disk, compatible and usable on a Windows PC computer recognised project management software as agreed with the Service Manager/Project Manager.

- The Contractor shall present the programme bar chart in a suitably structure manner to represent the distinct phases and areas of the project.

- The Contractor will identify how each activity on the Activity Schedule relates to the operations on each programme submitted.

- If, in the opinion of the Service Manager/Project Manager, it becomes reasonably apparent that the progress of the works is being or is likely to be delayed, the Contractor shall, within seven days, submit to the Service Manager/Project Manager a target recovery programme. This programme shall show the amendments he proposes to make to the original programme, to ensure completion of the works by the date for completion, or any later date agreed.

## Programme Support Information

The Contractor is to provide, with the programme, an update of its method statement provided with his tender describing fully the techniques, plant and equipment to be used.

The Contractor shall issue a weekly summary to the Service Manager/Project Manager of the number of operatives and major items of plant in each trade employed on the works including those of all Sub-contractors.

The Contractor shall prepare daily, written labour return sheets, which shall state the names of operatives, their trade and times that they commenced / finished work.

The Contractor shall also prepare daily written plant return sheets which shall state the plant type and their arrival / departure dates from Site.

The format of these daily labour and plant returns shall be subject to the agreement of the Service Manager/Project Manager.

## Programme revisions

In accordance with clause 34.2 (Lot 1) and clause 32.2 (lots 2 and 3)  the Contractor revises the programme and, if requested by the Service Manager/Project Manager, is to update the network in order to demonstrate, where possible, how he intends to overcome any delays which may have occurred.

The changes in logic and/or duration’s will be submitted to the Service Manager/Project Manager in the form of a schedule indicating both the previous and amended data, together with amended network diagrams.

In addition, where the sequence of work on site is varied, the Contractor is to revise the programme prior to the next monthly update to reflect such amendments.

## Method Statement

The Contractor shall prepare a detailed method statement to provide a complete description of the means and methods which he intends to employ.

A plan is to be included showing proposed locations for temporary accommodation, plant hoists, cartage, scaffolds, storage of materials etc., and any major temporary enabling works.

Specific reference should be made to the following:

- Hours and days work

- Plant employed

- Scaffolding

- Labour levels

- Welfare facilities

- Material deliveries

- Storage areas

- Access

- Trade co-ordination

- Office and meeting facilities

- Site security arrangements

- Control of noise, dust, dirt and rubbish removal

- Recycling of waste, materials and packaging not incorporated in the works.

- Car Parking

- Testing and Commissioning

The method statement may also need to cover more specific requirements and the Service Manager/Project Manager reserves the right to request further details as and when required.

# Facilities, Temporary Works and Services

## Mechanical Plant

The Contractor is to supply all Equipment as per NEC3 and/or the Contractor provides all access, lifting and unloading equipment and transportation.

## Temporary Works

The following temporary works are to be provided by the Contractor as required:

- temporary roads;

- temporary walkways;

- access scaffolding;

- support scaffolding and propping;

- hoardings, fans, fencing etc.;

- hardstandings;

- works necessary to comply with traffic Regulations.

## Use of permanent electrical and cold water installations and sanitary facilities

Subject to availability and the prior written approval of the Service Manager/Project Manager, the Contractor and its Sub-Contractors may use the permanent cold water installations for the supply of water used for the carrying out of works and the permanent electrical systems for lighting and power always provided that the systems are operated and maintained in a proper manner, and are left in a satisfactory condition on the Order Completion Date. In the event that the Contractor causes or allows to be caused any damage to the existing water and electricity supplies the Contractor shall make good such damage at the Contractor’s expense.

Where such existing supplies are not available on Site, the Contractor shall make provisions for the supply of water and electricity on Site as instructed by the Service Manager/Project Manager for use by the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers.

The Contractor is to ascertain the location and supply of electricity for works during site visits. The Contractor is to provide an appropriate, safe and secure connection; meter board, metered supply, distribution and termination to the electricity supply for the purposes of supplying electricity for the duration of the works

The Contractor shall provide for all artificial lighting and distribution, electric power and other energy required for the execution of the works and providing lighting of  temporary fences, barriers, scaffolding etc. for safety and for execution of the works. Clear away the temporary installation on completion and make good all works disturbed.

The temporary lighting and power installation shall conform to the following regulations, British Standards and Codes of Practice and the recommendations contained therein including items HI(I), (II), (III) of the I.E.E. Regulations shall be mandatory.

- Electricity (Factories Act) Special Regulations 1908 and 1944

- The edition of the I.E.E. Regulations for the Electrical Equipment of Buildings current at the date of invitation to tender.

- The appropriate British Standards and Codes of Practice for electrical installations including BS4363, CP 1013 and CP 1017.

- Any special requirements of the Electricity Authority.

The Contractor shall appoint a suitably qualified person to be responsible for the temporary installations, their use and maintenance and supervision of tests required by the Regulations imposed; a notice of this person’s name and designation shall be on prominent display adjacent to the main switching device.

The Contractor shall provide a connection to the Client mains water supply so that, fresh potable water for the execution of the works, including the works of the sub-contractors and contractor or others employed direct, together with all necessary receptacles and plumbing, alter as required and maintain and clear away at completion and make good all works disturbed.

The Contractor is deemed to have satisfied himself as to the availability of water supplies before tendering.

The Contractor shall provide all water necessary for the execution of the works and shall pay all charges to the water authorities or otherwise for the temporary water supply. All connections to the Client's water supply shall be metered.

### Electricity supply from the Client's mains

An Electricity supply from the Client's mains may be used for the works as follows subject to the following:

The Client will not be held responsible for the effects of any failure or restriction in supply.

The Contractor shall ascertain the point of supply and anticipated capacity prior to commencement and in the event being unsatisfactory shall make alternative provision at no cost to the Client.

All connections to the Client's Electrical supply shall be metered.  The Contractor shall include for connection, maintenance and disconnection charges.

During finishing work and inspection provide temporary lighting, the intensity and direction of which closely resembles that provided by the permanent installation.

### Water for the Works

A water supply from the Client's mains may be used for the works as follows subject to the following:

The Client will not be held responsible for the effects of any failure or restriction in supply.

The Contractor shall ascertain the point of supply and anticipated capacity prior to commencement and in the event being unsatisfactory shall make alternative provision at no cost to the Client.

All connections to the Client's Water supply shall be metered.  The Contractor shall include for connection, maintenance and disconnection charges.

## Use of lifts

Subject to availability the Contractor shall:

- have use of an existing lift as designated and within the limitations specified by the Service Manager/Project Manager for the transportation of materials and labour;

- take all necessary measures to prevent the cause of any damage or wear to the lift; and

- shall incur the cost for the making good of any such damage.

Where existing lifts are not available on Site, the Contractor shall provide such facilities on Site as instructed by the Service Manager/Project Manager for use by the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers and shall receive remuneration for the related costs of installation and removal of the same in accordance with this Contract.

## Sanitary facilities

The Contractor shall:

- have use of existing sanitary facilities as designated and within the limitations specified by the Service Manager/Project Manager;

- take all necessary measures to prevent the cause of any damage to the existing sanitary facilities; and

- shall incur the cost for the making good of any such damage.

Where existing sanitary facilities are not available on Site, the Contractor shall provide such facilities on Site as instructed by the Service Manager/Project Manager for use by the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers and shall receive remuneration for the related costs of installation and removal of the same in accordance with this Contract.

## Use of permanent telephone installations

Subject to availability and the prior written approval of the Service Manager/Project Manager the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers may use the permanent telephone installations always provided that:

- the system is used in a proper manner and is left in a satisfactory condition on Order Completion Date;

- the Contractor shall incur the cost of the calls made by or on behalf of the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers;

- the Contractor shall incur the cost for the making good of any damage caused to the telephone installations.

Where existing telephone installations are not available on Site, the Contractor shall make temporary provisions on Site as instructed by the Service Manager/Project Manager for use by the Contractor, Named Sub-Contractors, other approved sub-contractors and/or suppliers and shall receive remuneration for the related costs of installation and removal of the same in accordance with this Contract.

## Site accommodation

Subject to availability and the prior written approval of the Service Manager/Project Manager the Contractor and its Sub-Contractors may have use of the existing premises for:

- Site offices;

- cabins for workpeople;

- storage compounds;

Where such existing premises are not available on Site, the Contractor and its Sub-Contractors, shall make arrangements for the supply of such temporary premises as instructed by the Service Manager/Project Manager and shall receive remuneration for the related costs of installation and removal of the same in accordance with this Contract.

The facilities, which will be maintained and kept in a sanitary condition together with use of an area within the Site for accommodation, latrines, drying, mess and first aid facilities in accordance with local regulations for persons employed on the works.

All facilities must be suitable for use by both sexes and kept in a clean and dry condition.

The Contractor must obtain the permission of the Service Manager/Project Manager before siting any offices, huts, stores, latrines, compounds, etc. The Contractor is responsible for maintenance of all offices, huts, stores, etc. and for removal on completion.

## Charges

For the avoidance of doubt the Contractor shall:

- include all costs for charges etc. related to the consumption or usage of water, electricity, telephone, gas etc. in its rates;

- be remunerated for all costs for charges etc. related to the consumption or usage of water, electricity, telephone, gas etc. used by Named Sub-Contractors.

## Advertisements

No temporary or permanent advertisements will be permitted on Site.

## Site name-boards

Name-boards shall not be permitted on Site.

## Route signs

The Contractor shall provide, erect and afterwards remove adequate route signs in approved positions indicating the approved route for pedestrians and vehicles requiring access to and about the Site.  Final layout and positions require the Service Manager/Project Manager’s prior written approval.

## Wayleaves

The Contractor shall obtain all necessary wayleaves including those in connection with cranes where jibs enter the air space over adjoining property.

## Services and other things to be provided by the Contractor

### Contractors Requirements

The Contractor shall provide as soon as practicable after the Access Date e-mail facility, telephones and facsimile machines required by him installation for use by the Contractor and sub-contractors, and pay all charges. He shall make arrangements to ensure that incoming calls are answered promptly.

The Contractor shall provide reasonable unrestricted access to and reasonably limited free use of an on-site all in one printer / scanner and with copying and fax facilities, for those acting on behalf of the Client, which may be located in the Contractor’s own site offices.

The Contractor is to provide, maintain and alter as necessary all plant; scaffolding; temporary road; tracks; paths; hard standings; shed bases; pavement crossings and other temporary works and the like, including those required by subcontractors, suppliers and others.  Reinstate all ground and all works disturbed, at such times agreed with the Service Manager/Project Manager.

The Contractor shall provide and erect, in an agreed location, one number display board, indicating the name of the project and the names of the various firms and persons engaged on the works. The dimensions, design construction and location of the same are to be to the approval of the Service Manager/Project Manager.

The Contractor shall allow for fixing name boards, to be provided by the Consultants, to the display board and for carefully taking down and returning them to the Consultants on completion of the works.

The Contractor shall keep the display board, free from graffiti and bills, and shall redecorate, maintain in good order, move, alter and adapt as necessary during the execution of the works and shall take down, clear away and make good all work disturbed on completion or when no longer required.

The Contractor shall also provide all other directional, safety or security temporary site signage.

The Contractor shall be responsible for obtaining all planning and other consents necessary in respect of the display boards and shall pay all costs and charges in connection therewith.

All combustible materials should be stored on site in a position and a manner agreed.

# Health & Safety, Asbestos and CDM 2015

## Health & Safety

The Contractor shall allow in his rates for the cost of carrying out the works without risk to the health and safety of all persons working on the Site or any person who may be affected by persons working on the Site.

The Contractor shall assume appointment  as the Principal Contractor for all works, and shall carry out all the duties of the Principal Contractor in accordance with the Construction (Design and Management) (“CDM”) Regulations 2015.

The Contractor shall further assume the role of Principal Designer under Projects/Task orders awarded under Lots 1 and 2. The Contractor may be appointed as Principal Designer under Projects awarded under Lot 3, at the discretion of the Client.

Where any part of the works requires the Contractor, or any Sub-Contractor to prepare a design for temporary works, the Contractor shall ensure that all relevant and necessary information is submitted in good time to the Project Manager and the Principal Designer to enable them to discharge their duties under the CDM Regulations 2015.

Without prejudice to its other obligations under this Contract and statute, the Contractor shall take such measures as are reasonably required to prevent the trespass onto the Site of any unauthorised persons.

The Contractor shall comply with the Considerate Contractors Scheme and shall register for the Scheme for the duration of the contract.

The Contractor shall promptly report to the Service Manager/Project Manager any health and safety hazards. The Contractor is required to comply with the specific Health & Safety requirements as set out in the Contract, and in particular in respect of reporting and audits.

The Contractor’s shall implement:

- the completion of a weekly safety monitoring checklist,

- a system for accident and incident reporting, and

- registration of the Project under the Considerate Contractor’s Scheme.

The Contractor is deemed to have allowed for the cost of compliance with these processes.

The Contractor shall inform all persons working on Site of all health and safety hazards and the related safety measures required.

The Contractor shall report all near misses/incidents and accidents to the Service Manager/Project Manager and these shall be recorded on the Client's data base;

The Contractor shall report all notifiable incidents and accidents to the appropriate public body as required by the Reporting of Injuries Diseases and Dangerous Occurrences Regulations and provide details of such reporting to the Service Manager/Project Manager.

The Contractor shall provide the Client with a report on accidents on site or in connection with the works on a quarterly basis.

The Contractor shall take all measures necessary to comply with the requirements of the Health and Safety at Work etc. Act 1974 the law of the Contract and any Approved Codes of Practice relating to health and safety, which may apply in the performance of the works.

The Contractor shall and shall procure that immediately upon arrival at a new Site and/or working area all persons working or visiting Site shall and report their presence on Site to the officer(s) responsible for the Site security.

The Contractor shall and shall procure that all persons working or visiting Site shall act at all times in accordance with the Site security procedures as instructed by the Site security officer(s) or otherwise.

The Contractor shall and shall procure that all persons working or visiting Site shall clearly display on them the security/identity passes provided to them by the Site security officer(s) or otherwise at all times.

The Contractor shall carry out regular health and safety inspections to identify potential hazards and take immediate action as appropriate to prevent any incidents/accidents.

For notifiable projects the Contractor shall display the Health and Safety Executive Form F10 on the site notice board.

The Contractor shall provide competent and appropriately trained personnel to carry out the work in relation to this Contract.

The Contractor shall and shall procure that all persons working or visiting Site shall review on a daily basis the site notice board on which relevant health and safety information is displayed, including without limitation:

- the contact details of the persons responsible for health and safety on Site;

- contact details of the Project Manager;

- contact details of the Contractor’s and all Sub-contractors’ representatives including without limitation for contact during Out of Hours in the event of an emergency;

- the applicable Site security procedures in the event that no Site security officer(s) are present on the Site;

- the emergency evacuation procedures, assembly points and emergency services contact details;

- the details and location of the first aider and fire warden;

- the purpose and location of the Asbestos Register;

- other asbestos related information in accordance with this section;

- fire alarm procedures and fire equipment;

- other Site specific risk information.

- The Contractor shall at all times:

  - maintain a tidy and orderly Site;

  - store materials safely;

  - maintain safe access for pedestrians to areas close to or affected by the works, including without limitation for persons with sight, hearing or other physical impairment, and elderly persons and children;

  - have arrangements for the collection and disposal of waste materials and maintain appropriate records of such presented for review as instructed by the Service Manager/Project Manager from time to time;

  - ensure that all plant and equipment is fit for purpose and inspected as required by legislation and Good Industry Practise;

  - notify the Service Manager/Project Manager of its intention to carry out noisy, dusty or otherwise disruptive work provided that such work shall not be carried out during Business Hours;

  - ensure that no persons working on Site enter any restricted areas without the Service Manager/Project Manager’s consent and the appropriate permit by the Site security officer(s);

  - ensure that no persons working on Site release to other unauthorised persons any security permits, identity cards etc.

The Contractor shall not at any time:

- commence or allow to commence work before suitable risk assessments and/or method statements have been submitted to and approved by the Service Manager/Project Manager in writing;

- carry out or allow to be carried out work involving high risk activities or carried out in high risk areas by persons acting alone;

- bring or allow to be brought on to Site chemicals or substances unless a COSHH assessment has been carried out and the Service Manager/Project Manager has given its prior written consent;

- carry out or allow to be carried out work on live electrical systems by persons who are not competent and appropriately trained and/or without the appropriate permits and authorisation;

- leave or allow to be left plant and equipment unattended and/or in a condition that may cause a risk to health and safety;

- remove or override or allow to be removed or overridden any safety devises, locks etc.;

- remove or allow to be removed from Site or other areas used to provide access to the Site any property of the Client or of Others without the Service Manager/Project Manager’s prior written approval.

## Construction Phase Plan

Prior to the issue of an Order, the Contractor shall take into account the information provided in the Pre-Construction Information (PCI) pack and expand its content to include its arrangements for the monitoring of compliance with all relevant statutory provisions, the health and safety of all the persons on Site, and shall ensure that the information is made available to all persons carrying out works on the Site.

After the issue of an Order, and prior to carrying out any construction work on Site, the Contractor shall prepare the Construction Phase Health and Safety Plan in accordance with the specific relevant regulations contained within the CDM Regulations 2015?, taking into account all the information previously detailed or incorporated in the Pre-Construction Information pack and any further information that becomes available or known to the Contractor.

The Contractor shall develop the Construction Phase Plan in sufficient detail to demonstrate to the Client that it complies with the requirements of the CDM Regulations 2015. The plan must be submitted to the CDM Co-ordinator at least 21 days prior to the commencement of work on site for review.

## Health and Safety File

The Contractor shall ensure at all times that copies of all relevant information required to keep the Health and Safety File updated by the CDM Co-ordinator on a regular basis is submitted in adequate time, and ensure that the Health and Safety File is completed on or before the Order Completion Date so that the Client can discharge its obligations under the CDM Regulations 2015.

## Where the Contractor is the Principal Contractor, completion of an Order is subject to the submission by the Contractor to the CDM Co-ordinator of all the required information so that the Health and Safety File can be updated in compliance with the CDM Regulations 2015.

## Asbestos

When necessary the Client will carry out asbestos surveys prior to the issue of a Task Order or Call Off Contract. The Service Manager/Project Manager shall make such surveys available to the Contractor. The Contractor shall make available to all persons working on Site all or parts of the report as may be necessary to ensure their health and safety at all times.

The following applies:

- specialist contractors approved by the Client shall carry out all work in connection with asbestos removal and disposal;

- in the event that the Contractor becomes aware of the presence and/or the likely presence of any asbestos based materials the Contractor shall and shall procure that:

  - all activities around the area stop immediately;

  - the Service Manager/Project Manager are notified immediately.

- in the event that asbestos containing materials are discovered on Site but have not been disturbed the Contractor shall and shall procure that:

  - a qualified analyst visits Site to establish whether the materials are asbestos based; and if so

  - a qualified analyst carries out air tests to establish whether the area has been affected; and

  - it provides  copies of the air test results to the Service Manager/Project Manager to post on the Site notice board(s);

- in the event that asbestos containing materials are discovered on Site which have been disturbed and/or damaged the Contractor shall and shall procure that a specialist contractor properly licensed for asbestos removal and approved by the Service Manager/Project Manager is immediately appointed to:

  - undertake limited removal, sealing or encapsulation of such materials;

  - carry out air tests to establish whether the area has been affected;

  - if the area has been affected, seal off the area and certify that it is contaminated;

  - if the area has been affected, carry out air tests in the surrounding areas to establish whether they are contaminated; and

  - in any event provide copies of the air results and details of the seal-off to the Service Manager/Project Manager

- without prejudice to the generality of the Contractor’s duties under this Contract and the law of the Contract the Contractor shall and shall procure compliance with all current legislation relating to Asbestos removal at all times..

The Contractor shall ensure that all persons working on Site whether employed directly by the Contractor or a Named Sub-Contractor or other approved sub-contractor are:

- aware of the purpose and location of the Asbestos Register;

- aware that they have at all times access to the Asbestos Register;

- aware that they may contact the Service Manager/Project Manager at all times for any queries or clarifications in relation to asbestos on Site;

The Contractor shall ensure that all persons working on Site that are likely to come into contact with asbestos containing materials have had asbestos awareness training.

The Contractor shall ensure that the following is clearly displayed on Site notice boards situated in an accessible location near the entrance to every floor and is clearly visible to all persons working on that floor:

- a notice indicating the location and/or likely location of asbestos containing materials;

- floor plans taken from the Client's asbestos survey reports indicating the location of asbestos containing materials

# Subcontracting

## Sub-Contractors

Wherein the Scope prepared by the Client and issued to the Contractor as part of a Task Order or Call-off contract for a particular Project provides that certain work must be carried out by a supplier of the Contractor’s choice selected from a list of named firms given therein:

The selected supplier shall be a Sub-contractor as provided for in the Contract.

- The Contractor is required to submit the name(s) of their proposed supplier to the Service Manager/Project Manager as required by the Contract.

- The Service Manager/Project Manager may add additional suppliers to the list not later than 10 days before return of tenders/works package.

- The Contractor may, but only with the consent of the Service Manager/Project Manager or his authorised representative add additional firm(s) to the list and shall, if requested, submit to the Service Manager/Project Manager or his delegated representative (in an approved form) evidence of the suitability of such additional supplier(s).

All subcontractors should be appointed using the NEC subcontract form to ensure they are bound by the same core clauses as the Contractor. While different option clauses may apply it is important to ensure that there is no potential scope for additional cost that may arise in a subcontract package let under a different form of contract that will deal with and treat variations in a different way.

Where the Contractor believes that the NEC subcontract form is inappropriate to any particular subcontract package this should be discussed with the Service Manager/Project Manager beforehand and a statement elicited from the subcontractor to confirm that the subcontractor will act in the spirit of mutual trust and cooperation.

Additionally the Contractor is required to disclose to the Service Manager/Project Manager for comment, prior to subcontract tendering, all z-clauses the Contractor intends to include in subcontracts.

# Completion

## Pre-Completion arrangements

### General

The Contractor shall give not less than 2 weeks’ notice to the Service Manager/Project Manager as an indication of the likely handover date. The Service Manager/Project Manager may stipulate an increase to the minimum notice period dependent upon the size and type of project work being undertaken. The Contractor shall make good all snagging as a prerequisite prior to handover and the issue of the ‘Completion Certificate’.

## Work At Completion/Making Good Defects

### Making good

The Contractor shall make good all damage to the works prior to Completion and shall remove all temporary markings, coverings and protective wrapping arising from the carrying out of the works unless otherwise instructed.

### Cleaning

Before handing over the works to the Client, the Contractor shall:

a)	carry out a clean of the works including all luminaries and accessible ducts and voids on completion and leave in an acceptable and usable condition;

b)	remove all splashes, deposits, efflorescence, rubbish and surplus materials consequent upon the execution of the works,

c)	adjust, ease, and lubricate moving parts to ensure easy and efficient operation; flush all above and below ground drainage; remove all protective casings and wrappings; scrub floors and pavings; clean windows; oil and adjust ironmongery; clean out gutters and rainwater pipes; and

d)	touch up minor faults in newly painted/repainted work, carefully matching colour, and brushing out edges; and

e)	leave the whole of the works in a condition ready for occupation and to the satisfaction of the Service Manager/Project Manager.

The following applies:

a)	cleaning materials and methods are to be as recommended by the manufacturer(s) of products being cleaned;

b)	in the absence of such recommendations cleaning materials and methods are to be approved by the Service Manager/Project Manager prior to their usage;

c)	where there are any oil / fuel leakages or spillages caused by the Contractor, they must use the Cleaning Service Provider in order to carry out the clearance works. All costs are to be  borne by the Contractor.

### Security at completion

The Contractor shall:

a)	ensure that upon Completion the works are secure and that all the accesses are locked;

b)	account for and adequately label all keys and hand over to the Service Manager/Project Manager with itemised schedule, retaining duplicate schedule, signed by the Service Manager/Project Manager as receipt.

### Completion Deliverables

The Contractor is to allow for providing all of the completion deliverables set out in the schedule below.

- The things which the Contractor must provide prior to Completion are identified in the Schedule of Completion Deliverables contained below. This schedule is provided as a starting point for the minimum deliverables only and does not relieve the Contractor from his obligation to deliver all those things required in the Scope documentation whether requested implicitly and explicitly. It is envisaged that the Contractor will manage the Completion Deliverables proactively and from the outset before the works commence on Site.

- The provision of the Completion Deliverables to the Service Manager/Project Manager’s complete satisfaction is a pre-requisite to achieving Completion. Failure to provide any of these documents will constitute a defect and the Client will not be liable to release any amount retained pursuant to Option X16 until such time as all documents have been provided in a satisfactory form.

### Completion Deliverables Schedule

1.0	General

1.1	Contractor’s Collateral Warranties provided

1.2	Copies of a defects list and names of persons responsible for remedial works

1.3	Copies of any failure reports raised during construction, commissioning or proving of compliance with the Scope

1.4	a schedule of outstanding works

2.0	Building, Civil Engineering and Structural

2.1	Handover documentation

2.2	Building Control, Planning and Other Authorities

2.2.1	Building Regulations Completion Certificate

2.2.2	Details of any relaxations, dispensations and determinations from Building Regulations agreed with appropriate certifying authority

2.2.3	Certificate for Listed Building Consent (where appropriate)

2.2.4	Written confirmation that the Inspectorate is satisfied with the works

2.2.5	Certificate of compliance with Building Regulations at Design and Construction Stages.

2.2.6	Written confirmation from the Planning Authority that all Planning Conditions / Reserved Matters have been discharged.

2.2.7	Certificate of Planning Consent including the discharge of all conditions.

2.2.8	Written confirmation that the Contractor has not used deleterious, unsatisfactory, or unsuitable quality material.

2.2.9	Public utilities way-leaves and lease agreements signed off

2.2.10	Public utilities and supplies inspected and signed off.

3.0	Mechanical Services Installations

3.1	General

3.1.1	Controls Commissioning Report

3.1.2	All systems and product warranty documentation

3.1.3	Written confirmation by all professional consultants that the mechanical services (and plumbing and drainage) installations have been tested, commissioned and proven

4.0	Electrical Services Installations

4.1	General

4.1.1	All systems and product warranty documentation

4.1.2	IEE Electrical Systems Safety Test Certificate

4.1.3	Manufacturers Test Certificates for electrical equipment

4.1.4	Written Confirmation by all Professional Consultants that the Electrical Services Installations have been tested, commissioned and proven

4.2	Other

4.2.1	Building Management System Certificate

4.2.2	PAT Certificate (Portable Appliance Test)

5.0	Fire Safety

5.1	Approvals

5.1.1	Fire Certificate

5.1.2	Written confirmation from the Fire Officer confirming compliance with all their regulations.

5.1.4	Fire Consultants Reports and Recommendations

5.1.5	LPCB (Loss Prevention Council Board) Certificates of Conformity for Fire Detection and Alarm.

5.1.6	LPCB Certificate of conformity for sprinkler systems and fire suppression systems

5.1.7	Statement that all fire recommendations have been carried out and all appliances are operational.

5.1.8	Means of Escape Signed Off.

5.2	Alarms

5.2.1	Fire Alarm Certificate

5.2.2	Alarm Panel inspection certificate

5.2.3	Telephone link test certificate

5.2.4	Main Panel Test Certificate

6.0	Security

6.1	Intruder Alarm Certificate

6.2	Schedule of Keys and Security Devices

7.0	Health and Safety

7.1	Health and Safety File

7.2	Risk Assessment Reports

7.3	Certification of removal of any contaminated materials (Asbestos)

7.4	Statement that no detritus [deleterious?] material has been incorporated into the works

8.0	Operation and Maintenance

8.1	Documentation

8.1.1	Schedule of M&E Planned Maintenance Documents

8.1.2	Building Manual(s)

8.1.3	O&M documentation - Complete

8.1.4	Copies of manufacturer’s maintenance and operating instructions for all M&E installations.

8.1.5	Planned preventative maintenance manuals

8.1.6	Maintenance records for the Proving Works.

8.1.7	List of recommended Spares for M&E installations.

8.1.8	Copies of supplier’s installation recommendations and instructions for use / maintenance.

8.1.9	COSHH records (Control of Substances Hazardous to Health)

8.1.10	Noise assessment records

8.2	Training

8.2.1	Induction and Training Certificates for Users and FM staff regarding training and core familiarisation.

8.3	Certificates and Guarantees

8.3.1	Certificate stating date of expiry of contractual maintenance period

8.3.2	Copies of any Guarantees on Materials and Workmanship

8.3.2	Insurers certificates issued, (lifts, access equipment, others)

8.4	Information

8.4.1	Log detailing sprinkler / fire suppression tests

8.4.2	Log detailing emergency lighting tests and examinations

8.4.3	Log detailing smoke extract tests

8.4.4	Log detailing fire hose reel / portable fire extinguishers test

8.4.5	Log detailing fire detection / alarm tests and maintenance.

8.4.6	Log detailing escape route pressurisation tests

8.4.7	Fire training log book containing details of training, special duties and fire drills.

8.4.8	Meters read and fuel stocks noted.

8.5	Other

8.5.1	Servicing contracts established

8.5.2	Handover facilities to management

8.5.3	Provision of Tools, Spares consumables and inventory

## Handover Procedure

The following applies:

- the Contractor shall give the Service Manager/Project Manager ten days prior written notification of its request for a Handover Meeting;

- the Contractor shall attend the Handover Meeting to enable the Service Manager/Project Manager to establish whether the works have reached Completion to enable the Service Manager/Project Manager to certify Completion by the issue of an appropriate certificate under clause 30.2 (a Completion Certificate) or to verify completion of a Task Order (as the case may be);

- the Service Manager/Project Manager  shall notify the Client of any Handover Meeting to allow the Client, its representatives and such Others as the Client deems appropriate to attend and may make such representations as they consider necessary;

- during the Handover Meeting the Service Manager/Project Manager shall inspect the Site to establish whether the Contractor has carried out and completed the works in accordance with the Task Order and the Call-off Contract;

- any outstanding items of work, snags or Defects which the Service Manager/Project Manager consider should be corrected before the issue of a Completion Certificate shall be notified to the Contractor in accordance with the Contract;

- the Contractor shall promptly complete all outstanding items of work, snags and Defects notified as stated above and shall notify the Service Manager/Project Manager in writing that it requests a re-inspection;

- where appropriate the Service Manager/Project Manager may with the approval of the Client issue a Completion Certificate notwithstanding the existence of snags or Defects which do not prejudice the convenient use of the works by the Client's staff and customers;

- the Service Manager/Project Manager shall not be obliged to certify Completion where any documents required to be submitted under this Contract by the Contractor have not been submitted including without limitation any as built drawings, operation and maintenance manuals and health and safety documents.

## Operation and maintenance manuals

The Contractor shall provide the Service Manager/Project Manager on or before Completion with the complete information for operating and maintaining the equipment contained in the works (an O&M Manual).

The O&M Manual shall:

- be provided in electronic format and with three hard colour copies;

- be in plain English;

- clearly arranged in a manner that is user friendly;

- with operating and maintenance instructions that can readily be understood by non-technically qualified people (save where the O&M manual indicates that the plant or equipment should only be operated by trained or qualified personnel); and

- be comprehensive in providing sufficient advice and guidance for the operation and maintenance of all electrical and mechanical plant and equipment installed or provided by the Contractor at the Site.

## Record documents and As Built Information

The Contractor shall provide to the Service Manager/Project Manager at Completion, originals of all documents obtained by the Contractor pertaining to the performance of these obligations, including (for example) Commissioning Certificates, Materials Guarantees, Test Certificates etc. (see Completion Deliverables).

The Contractor shall also provide the formal notice of approval from the Electricity Supply Company to ensure that the installation complies with all relevant regulations and requirements.

The Contractor shall provide ‘as-built’ model, together with additional drawings at Completion of the following installations:

- All external services (to a scale not less than 1:200)

- Drainage (to a scale of not less than 1:200)

- Waste, soil and overflow

- Hot and cold water, including water supplies, positions of meters and stop valves

- Heating, ventilation and air conditioning including gas supplies

- Electrical installation, showing conduit, trunking and final sub-circuits

- Security installations

- Fire Alarm installations

- Telephone & data installation

- Plans, sections and elevations of the completes structure (to a scale not less than 1:50)

- All other detail drawings used to construct the works.

Provide also wiring diagrams and maintenance instructions of any plant or equipment.

The Contractor is to provide 3 No hard copies of Operation and Maintenance manuals and 3 No CD copies.

The Contractor’s attention is also drawn to references in other volumes of the Scope.

## Training

The Contractor shall allow for instructing the Client's staff on the use and maintenance of the equipment and services installed.  A training programme is to be agreed with the Service Manager/Project Manager prior to commencement of training.

Training sessions are to be provided and structured to provide instruction for each element of the buildings and services installations. The Contractor must submit training proposals with his tender.

The training must be co-ordinated by the Contractor; it is not acceptable for a one to one briefing of the user by the Contractor’s Sub-Contractors.

The Contractor will provide Certificates following training for all individuals stating the training provided, date and place.

The Contractor shall allow for instructing maintenance staff on the use of the equipment and services installed.

Allow for repeat session for each topic where operating staff are unavailable or cannot attend simultaneously.

Submit copies of the training presentation for the Client's future reference.

Keep records of the training sessions including any certificates of competence.

Record training sessions on DVD.

## Defects

The Contractor shall use reasonable endeavours to achieve a defect free building and will agree any remaining snag items to be completed post completion with the Service Manager/Project Manager due to the difficulty in arranging access and services shut downs when the building becomes operational.

## Defects Protocol

Defects Reports will be produced by the Service Manager/Project Manager and the Contractor shall action these defects continuously subject to availability of access.  The Contractor will make arrangements with the Service Manager/Project Manager and give reasonable notice of dates and times required for access to carry out remedial works; comply with all procedures instigated by the Client with regard to permits to work and security; inform the Service Manager/Project Manager when remedial works are complete.  The Contractor shall action any defects notified at the expiration of the defects correction period immediately.

The Contractor shall correct defects notified prior to the defects date in accordance with the Contract.  In addition to the Contractor's obligation to correct defects within the defects correction period, the Contractor shall meet the following  response time categories:

(a) 	Emergencies

Any defects prejudicing the satisfactory occupation of the premises or common areas and requiring immediate attention and rectification on the same day as the instruction, e.g.:

water leaks; gas leaks; malfunction of space or water heating installations; malfunction of showers; blockages to drains; fire alarm failures; call system failures; electrical faults; total malfunction of electrical lighting or power circuits; door entry system failures; any defect or malfunction which effects the safety of DWP staff or customers or security of the building: response time 4-hours

(b) 	Urgent defects

Any defects of a less urgent nature but causing some nuisance to building users, e.g.:

boiler or central heating plant malfunctions; ventilation system failures, and the like: response time 12-hours

lift failures: response time 24-hour

(c) 	Routine defects

For example: malfunction of individual electrical lighting or power points or ventilation fans; defective door, window or ironmongery; defective finishes or fittings: response time 7-days