## Tender Clarifications
Tender Questions and Answers Tracker dated: |  | 2024-05-02
Client: | Croydon College
Project Name: | T422 - Window Replacement Works
Clarification No. | Date Query Issued | Query | Response | Answered by | Date Answer Issued | Query Status (Open / Closed)
1 | 2024-04-22 | The window works are to two elevations. Where are the concrete repairs and stone cleaning to be carried out? Is it the whole building or just the two areas (ground and first floor only) where the window replacements are taking place? | This tender relates to window replacement works only. Tenderers are not to price for concrete reparis or stone cleaning. The window replacement works are as per the schedule of works provided. | Fusion | 2024-04-22 | Closed
2 | 2024-05-01 | Could you provide a revised elevation drawing indicating the windows to the rear elevation (6nr windows) | A revised elevation drawing will not be provided as part of the tender information. Tenderers to price based on Baily Garner specification. | Fusion | 2024-05-01 | Closed
3 | 2024-05-01 | The spec calls for 5Pi ADV windows however, after speaking with suppliers they have informed me that one the first phase of replacement windows fitted were Comar 5Pi ECO+ previously. Do you wish to change them to the 5Pi ADV or is the spec to remain 5Pi ECO+. | Spec is same as last year, therefore we have replicated product in the spec. If 5Pi ECO+ was installed then Suggest 5Pi ECO+ is installed to mirror that installed previously. | BG | 2024-05-02 | Open
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18