## Detailed
St Mungo's Broadway Implementation Plan - CAIRS Service |  |  |  |  | PRE-MOBILISATION PHASE |  |  |  | MOBILISATION PHASE | [11 empty] | 1st Quarter
[5 empty] | 2015-12-01 |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01
| Task |  | Responsible Officer | KEY MILESTONE | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4 | wk1 | wk2 | wk3 | wk4
Transition & Implementation Management | A1 | Notification of proposed appointment | Implementation Manager | bar: 2016-01-01 wk1
| A2 | Establish Implementation Group & set up weekly/monthly meetings | Implementation Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk2
| A3 | Circulate Implementation Plan to relevant internal management and commissioners | Implementation Manager | bar: 2016-01-01 wk2 to 2016-01-01 wk3
| A4 | Set Key Milestones for Project Implementation timeline | Implementation Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-01-01 wk2 to 2016-01-01 wk3
| A5 | Meet with relevant internal departments - IT, HR, Comms, Facilities, Outside In | Implementation Manager | bar: 2016-01-01 wk4 to 2016-03-01 wk4
| A6 | Confirm and agree contingency plan for transition with commissioners | Implementation Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk4
| A7 | Agree and set any outstanding KPI's & Performance Targets with commissioner | Implementation Manager | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| A8 | Review Risk Log & confirm contingency plans | Implementation Manager | bar: 2016-01-01 wk1 to 2016-01-01 wk4
| B1 | Confirm IT / telecommunications requirements with IT Manager | Area Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk1
| B2 | Office equipment items supplied | Area Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| B3 | Stationary including headed paper in place | Area Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
Finance & Purchasing | D1 | Re-align budgets | Implementation Manager | bar: 2016-01-01 wk3 to 2016-02-01 wk4
| D3 | Subcontracts agreed and signed | Implementation Manager | bar: 2016-02-01 wk2 to 2016-02-01 wk3
| D4 | Establish Cost Code for service/s | Implementation Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| D5 | Set up project on Ebis (Electronic Purchasing System) | Implementation Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-03-01 wk1 to 2016-03-01 wk2
| D6 | Liaise with Finance re: raising invoices for purchases | Implementation Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| D7 | Send new suppliers forms to local suppliers for entry to Ebis | Implementation Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
IT | E1 | Set up OPAL for monitoring of incidents and complaints | Implementation Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-02-01 wk1 to 2016-03-01 wk4
| E2 | begin review and update of project website | Area manager | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-02-01 wk1 to 2016-03-01 wk4
| E3 | Develop information sharing protocols with partner agencies | Area manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-02-01 wk3 to 2016-03-01 wk2
Communications |  | Service Users
| F1 | Inform service users of administrative changes that may affect them | Service Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-03-01 wk1 to 2016-03-01 wk4
| F2 | Distribute information about new provider to service users | Service Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
Internal Departments
| G1 | Inform all central services | Implementation Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2016-01-01 wk4
| G2 | Prepare new service leaflets | Implementation Manager | bar: 2016-02-01 wk1 to 2016-02-01 wk3
| G3 | Ensure coverage of the project opening in Core Brief | Implementation Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk2
External Stakeholders
| H1 | Construct Communications Plan, with commissioners | Area Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2016-01-01 wk4
| H2 | Agree standard operating procedures and reporting obligations with subcontractors | Area Manager | bar: 2016-02-01 wk1 to 2016-02-01 wk2
| H3 | Arrange meetings with leads from key identified agencies | Area Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H4 | Information sharing at relevant forums | Area Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H5 | Inform key partners of provider change and model changes | Area Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H6 | Ensure coverage of Project opening in The Saint (St Mungo's Broadway Supporter Magazine) | Area Manager
| H8 | Discussions with police, Home Office re partnership arrangements | Area Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk4
| H9 | Identify any additional possible partners and join existing forums | Area Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-02-01 wk1 to 2016-02-01 wk2
| H11 | Contact all other services such as required | Area Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| H13 | Conduct initial stakeholder satisfaction review | Area Manager
Service Users | I1 | Inform Outside In (service user Involvement Group) and consolidate Outside In's role in service marketing | Area Manager, Managers | bar: 2016-01-01 wk2 to 2016-01-01 wk4; 2016-02-01 wk2 to 2016-02-01 wk4
| I5 | Implement service user Involvement Toolkit | Area Manager service user Involvement lead
| I6 | Promote apprenticeships scheme | Area Manager service user Involvement lead
| I7 | Review risk levels of all transferring service users | Service Manager | bar: 2016-02-01 wk3 to 2016-03-01 wk2
| I11 | Seek consent from clients via existing provider regarding data transfer | Area Manager, Managers | bar: 2016-02-01 wk3 to 2016-02-01 wk4
| I12 | Handover of any current safeguarding issues | Area Manager, Managers | bar: 2016-03-01 wk2 to 2016-03-01 wk4
Equality & Diversity | J1 | Align recruitment with equality policy | Head of Equality and Diversity | bar: 2016-02-01 wk3 to 2016-03-01 wk2
| J3 | Ensure communication materials are translated into appropriate languages | Head of Equality and Diversity | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| J4 | Ensure new staff undertake equality and diversity training | Head of Equality and Diversity | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4
| J5 | Appraise property/accommodation sites for accessibility and make suitable adjustments | Head of Equality and Diversity | bar: 2016-02-01 wk1 to 2016-02-01 wk4
| J6 | Undertake Equality Impact Assessment for new service | Head of Equality and Diversity
TUPE Transition Plan | K1 | Final TUPE information received | HR / Area Manager | bar: 2016-03-01 wk1
| K2 | Contact with exiting providers | HR / Area Manager | bar: 2016-01-01 wk3 to 2016-01-01 wk4
| K3 | TUPE applicability determined & measures letter issued | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| K4 | Welcome meetings with TUPE eligible staff | HR / Area Manager | bar: 2016-02-01 wk2; 2016-03-01 wk2
| K5 | Liaise with Trade Unions or recognised representatives | HR / Area Manager | bar: 2016-01-01 wk4 to 2016-02-01 wk1; 2016-03-01 wk1 to 2016-03-01 wk4
| K6 | New starter process implemented | HR / Area Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4; 2016-03-01 wk1 to 2016-03-01 wk4
| K7 | HR database – CIPHR updated & skills audit completed | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| K8 | Staff skills audit completed | HR / Area Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| K9 | Set up new staff on payroll system | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk3
| K10 | Complete safe recruitment of new staff if required (incl DBS and reference security checks) | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| K11 | Induct staff | HR / Area Manager
| K12 | Prepare service structure document for TUPE’d staff | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| K13 | Instigate formal restructuring process | HR / Area Manager
| K14 | Ongoing service management structure confirmed | HR / Area Manager
| K15 | Ongoing service delivery structure confirmed | HR / Area Manager
| K16 | Ongoing service deliver structure fully bedded in | HR / Area Manager
Other Staffing Plans | L1 | Identify staffing gaps e.g. Apprentice roles and recruit to fill | HR / Area Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4
| L2 | IT and email accounts set up | HR / Area Manager | bar: 2016-03-01 wk3 to 2016-03-01 wk4
begin volunteer role recruitment | bar: 2016-03-01 wk3 to 2016-03-01 wk4
| L3 | Plan local and central induction training | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk2
| L4 | Deliver local and central induction training | Area Manager/ Learning and Development
| L5 | Service User Involvement training | HR / Area Manager
| L6 | Implement on-call l and Crysis Lone Working systems | HR / Area Manager
| L7 | Localise quality manuals | HR / Area Manager | bar: 2016-03-01 wk1 to 2016-03-01 wk4
| L8 | Prepare and issue new ID Badges | HR / Area Manager
| L9 | Diarise staff meetings | HR / Area Manager | bar: 2016-03-01 wk4
| L10 | Initial awayday to review performance | HR / Area Manager | KEY MILESTONE | bar: 2015-12-01 wk1 to 2015-12-01 wk4