## Pricing Document
St Catherine's College - Sports Hall Phase 2
|  |  | Unit | Rate | Total
| Tender Addendum 1 |  |  | £ | £
2022-12-15
The following changes are to be made to the tender documents
1.1 | Commencement
Preliminaries A20: Contract Particulars Clause 2.3. This should read 12th March 2023
2 | Completion
Preliminaries A20: Contract Particulars Clause 2.3. This should read 30th June 2023
3 | Tender return date
Form of Tender: This should read Monday 16th January 2023
4 | Add the following items to the end of the Pricing document.
| 133 Provisional sum of £500.00 for electrical supply to future retractable seating | 1 | PS |  | 500
| 134 Provisional sum of £2,000.00 for additional lighting to temporary store 1 | 1 | PS |  | 2000
| 135 Provisional sum of £5,000.00 for door access control by named specialist | 1 | PS |  | 5000
5 | Omit the following items from the tender
| 47 Lockable notice board | 1 | no
| 48 Sundeala aluminium framed noticeboard | 1 | no
| 49 Provisional sum of £500.00 for signs | 1 | PS |  | 500
6 | Note
Architect's Specification P3 it 3.10 should read ". .60 minute fire protection"
Preliminaries A37 110, Delivery of Building manual, should read " . . 30th June 2023"
7 | Amend item
130 "1200 high treated softwood palisade fence and gate to West end of North elevation including gate" to now read
| Extend security fencing from existing security fence to building where shown on drawing T4 at the East end of the north elevation, including single of gates with emergency escape panic latch, all to match existing security fence. This fence is to attach to the existing security fence abd the side of the new building | 1 | item