ROYAL CORNWALL MUSEUM – Our Past, Our Future	 29 December 2023	Version 0.3

PROJECT:  Landscape

SUMMARY

Proposed route to market – Design and Build:

Phase 1: Design

| CORE REQUIREMENTS | KEY ACTIONS REQUIRED | KEY OBJECTIVES | BUDGET | TIMELINE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |
| - Landscape Designer/ architect - Contract administrator - Principal Designer (CDM Regs) | - Finalise budget - Create statements of requirements - Create / issue ITT - Scope out CDM Pre-Construction/ Installation document | - Appointment of lead contractor on design and build basis - Design phase concluded May 2024. | £210,000 Including VAT Design (est. £21 – 40k) Construction (est. £170 – 189k) | ITT |  | E.S | Design |  |  | Design – Contract Admin Planning |  |  |  |  |  |  |

Phase 2: Installation

| CORE REQUIREMENTS | KEY ACTIONS REQUIRED | KEY OBJECTIVES | BUDGET | TIMELINE |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |
| - Main Contractor - Principal Contractor (CDM Regs) |  | - Construction / Installation concluded Jan 2025 | See above |  |  |  |  |  |  | Build phase |  |  |  |  |  |  |

| KEY / LEGEND CDM – Construction Design Management Regulations (2015) ITT – Invitation to Tender E – Evaluation E.S – Evaluation and 10 day Standstill (if above threshold) | Planning JCT – Joint Contracts Tribunal Below Threshold (Services) less than £213,477 (inc. VAT) Design phase Below Threshold (Works) less than £5,336,937 (inc. VAT) Build phase Above Threshold (Services) greater than £213,477 (inc. VAT) | ITT phase |
| --- | --- | --- |