SCHEDULE 2.3

STANDARDS

Standards

- QUALITY PLANS

  - The Supplier shall:

(a)	Submit to the Authority for approval a quality plan for the Mobilisation activities specified in the Mobilisation Plan no later than fifteen (15 Working Days after any request for such plan from the Authority or a date otherwise agreed between the parties in writing;

(b)	Submit to the Authority for approval a quality plan for the Services (Services Description), within forty 40 Working Days after any request for such plan from the Authority or a date otherwise agreed between the parties in writing.

the purpose of which are to ensure that all aspects of the Mobilisation and Services are the subject of quality management systems and are consistent with the Quality Standards (“Quality Plans”).

  - The Supplier shall obtain the Authority Representative’s written approval of the Quality Plans before implementing them. If the Authority does not approve a Quality Plan, the Authority shall inform the Supplier of its reasons for not approving it.  The Supplier shall then within ten (10) Working Days revise the Quality Plan taking those reasons into account and shall re submit the revised plan to the Authority for the Authority's approval.  The Authority shall not unreasonably withhold or delay its approval of the Quality Plan.

  - The Supplier acknowledges and accepts that the Authority's approval shall not act as an endorsement of the Quality Plans and shall not relieve the Supplier of its responsibility for ensuring that the Services are provided to the standard required by this Agreement.

  - Following the approval by the Authority of the Quality Plans:

#### the Supplier shall design and deliver all Deliverables in accordance with the Quality Plans; and

#### any changes to the Quality Plans shall be agreed in accordance with the Change Control Procedure.