# SCHEDULE 6.2

TESTING PROCEDURES

Testing Procedures

# DEFINITIONS

In this Schedule, the following definitions shall apply:

| “Achieve” | - in respect of a Test, to successfully pass a Test without any Test Issues; and - in respect of a Milestone, the issue of a Milestone Achievement Certificate in respect of that Milestone in accordance with the provisions of this Schedule 6.2, and “Achieved” and “Achievement” shall be construed accordingly; |
| --- | --- |
| “Assurance Criteria” | in relation to a Deliverable that is not due to be Tested, the assurance criteria for that Deliverable as set out in the Mobilisation Plan; |
| “Component” | any constituent part of the Deliverables; |
| “Material Test Issue” | a Test Issue of Severity Level 1 or Severity Level 2; |
| “Severity Level” | the level of severity of a Test Issue, the criteria for which are described in Annex 1; |
| “Test Certificate” | a certificate materially in the form of the document contained in Annex 2 issued by the Authority when a Deliverable has satisfied its relevant Test Exit Criteria; |
| “Test Completion Review” | a meeting between the Parties to review the Test Completion Report and to confirm that the Test Exit Criteria have been met; |
| “Test Completion Reports” | the reports to be produced by the Supplier setting out a summary of the results of the Tests as defined in the Test Plan; |
| “Test Specification” | the specification that sets out how Tests will demonstrate that the Test Exit Criteria have been satisfied, as described in more detail in Paragraph 5 of Part A; |
| “Test Entry Criteria” | the criteria that must be met before a Deliverable can be submitted for Testing; |
| “Test Exit Criteria” | in relation to a Test, the test exit criteria for that Test as referred to in Paragraph 4.4 of Part A of this Schedule; |
| “Tests” and “Testing” | any tests required to be carried out pursuant to this Schedule, and “Tested” shall be construed accordingly; |
| “Test Issue” | any variance or non-conformity of a Deliverable from its requirements (such requirements being set out in the relevant Test Exit Criteria); |
| “Test Issue Threshold” | in relation to the Tests applicable to a Milestone, a maximum number of Severity Level 3, Severity Level 4 and Severity Level 5 Test Issues as set out in the relevant Test Plan; |
| “Test Issue Management Log” | a log for the recording of Test Issues as described further in Paragraph 2.1 of Part B; |
| “Test Plan” | a plan: - for the Testing of Deliverables; and - setting out other agreed Assurance Criteria and other criteria related to the achievement of Milestones, as described further in Paragraph 4 of Part A; |
| “Testing Procedures” | the applicable testing procedures, Assurance Criteria and Test Exit Criteria set out in this Schedule; |
| “Test Strategy” | the Supplier's strategy for the conduct of Testing under this Agreement as described further in Paragraph 3 of Part A; |
| “Test Witness” | any person appointed by the Authority pursuant to Paragraph 3.1 of Part B. |

# TESTING OVERVIEW

## All Tests conducted by the Supplier shall be conducted in accordance with the Test Strategy, the Test Plans and the Test Specifications.

## The Supplier shall not submit any Deliverable for Testing:

##### unless the Supplier is reasonably confident that it will satisfy the relevant Test Exit Criteria;

##### until the Authority has issued a Test Certificate in respect of any prior, dependant Deliverable(s) (unless otherwise agreed by the Parties); and

##### until the Parties have agreed the Test Plan and the Test Specification relating to the relevant Deliverable(s).

## The Supplier shall submit each Deliverable for Testing or re-Testing by or before the date set out in the Test Plan or the Detailed Mobilisation Plan (as applicable) for the commencement of Testing in respect of the relevant Deliverable.

## Prior to the issue of a Test Certificate, the Authority shall be entitled to review the relevant Test Completion Reports and the Test Issue Management Log.

# PART A: SUPPLIER'S TEST DOCUMENTATION

# TEST STRATEGY

## The Supplier shall develop the Test Strategy and submit it for the approval of the Authority as soon as practicable after the Effective Date but in any event no later than 20 Working Days after the Effective Date.

## The Test Strategy shall include as a minimum:

##### an overview of how Testing will be conducted in accordance with the Detailed Mobilisation Plan, including the Test scope, objectives, assumptions, principles, governance and controls;

##### the process to be used to capture and record Test results and the categorisation of Test Issues;

##### the procedure to be followed should a Deliverable fail a Test, fail to satisfy the Test Success Criteria or where the Testing of a Deliverable produces unexpected results, including a procedure for the resolution of Test Issues;

##### the procedure to be followed to sign off each Test;

##### the process for the production and maintenance of Test Completion Reports, a sample plan for the resolution of test Issues and a summary of how test information will be communicated to the Authority;

##### the names and contact details of the Supplier's Test representatives; and

##### a high level identification of the resources required for Testing, including Authority and/or third party involvement in the conduct of the Tests;

##### the technical environments required to support the Tests; and

##### the procedure for managing the configuration of the Test environments.

# TEST PLANS

## The Supplier shall develop Test Plans and submit these for the approval of the Authority as soon as practicable but in any event no later than 20 Working Days prior to the start date for the relevant Testing as specified in the Mobilisation Plan.

## Each Test Plan shall include as a minimum:

##### the relevant Test definition and the purpose and scope of the Test, the Milestone to which it relates, the requirements being tested, the approach to be undertaken, and, for each Test, the specific Test Entry Criteria and Test Exit Criteria to be satisfied, the requirements in relation to the environment, tools to support testing, risks that may occur, approach to communications and stakeholder engagement;

##### a detailed procedure for the Tests to be carried out, including:

###### the timetable for the Tests, including start and end dates;

###### the Testing mechanism;

###### dates and methods by which the Authority can inspect Test results or witness the Tests in order to establish that the Test Exit Criteria have been met;

###### the mechanism for ensuring the quality, completeness and relevance of the Tests;

###### the format and an example of Test progress reports and the process with which the Authority accesses daily Test schedules;

###### the process which the Authority will use to review Test Issues and the Supplier’s process in resolving these in a timely basis; and

###### the re-Test procedure, the timetable and the resources which would be required for re-Testing; and

##### the process for escalating Test Issues from a re-Test situation to the taking of specific remedial action to resolve the Test Issue.

## The Authority shall not unreasonably withhold or delay its approval of the Test Plans provided that the Supplier shall incorporate any reasonable requirements of the Authority in the Test Plans.

## The Test Exit Criteria for:

##### each Test that must be Achieved for the Supplier to Achieve the Milestones are set out in the Detailed Mobilisation Plan; and

##### all other Tests shall be agreed between the Parties as part of the relevant Test Plan pursuant to this Paragraph 4.

# TEST SPECIFICATION

## Following approval of a Test Plan, the Supplier shall develop the Test Specification for the relevant Deliverables and submit the Test Specification for the approval of the Authority as soon as reasonably practicable and in any event at least 10 Working Days prior to the start of the relevant Testing (as specified in the Mobilisation Plan).

## Each Test Specification shall include as a minimum:

##### a description of the test conditions;

##### the specification of the Test data, including its source, scope, volume and management, a request (if applicable) for relevant Test data to be provided by the Authority and the extent to which it is equivalent to live operational data;

##### a plan to make the resources available for Testing;

##### Test scripts;

##### Test pre-requisites and the mechanism for measuring them; and

##### expected Test results, including:

###### a mechanism to be used to capture and record Test results; and

###### a method to process the Test results to establish their content.

# PART B: TESTING PROCEDURES

# TESTING

## Before submitting any Deliverables for Testing the Supplier shall subject the relevant Deliverables to its own internal quality control measures.

## The Supplier shall manage the progress of the Testing in accordance with the relevant Test Plan and shall carry out the Tests in accordance with the relevant Test Specification.  Tests may be witnessed by the Test Witnesses in accordance with Paragraph 3 of this Part B.

## The Supplier shall notify the Authority at least 10 Working Days in advance of the date, time and location of the relevant Test.

## The Supplier shall provide to the Authority and, at the Authority's request, any third party, with all reasonable assistance and information necessary for conducting the Tests.

## The Authority may raise and close Test Issues during the Test witnessing process.

## The Supplier shall provide to the Authority in relation to each Test the final Test Completion Report within 5 Working Days of completion of Testing.

## Each Test Completion Report shall provide a full report on the Testing conducted in respect of the relevant Deliverables, including as a minimum:

##### an overview of the Testing conducted;

##### identification of the relevant Test Exit Criteria that have/ have not been satisfied together with the Supplier’s explanation of why any criteria have not been met;

##### the Tests that were not completed together with the Supplier's explanation of why those Tests were not completed;

##### the specification for any hardware and software used throughout Testing and any changes that were applied to that hardware and/or software during Testing; and

##### analysis of result information to allow management decisions, based upon risk, on whether to proceed to the next stage.

## The Supplier shall hold Test Completion Reviews to demonstrate to the Authority that the Test Exit Criteria have been successfully completed and met.

# TEST ISSUES

## Where a Test Completion Report identifies a Test Issue, the Parties shall agree the classification of the Test Issue using the criteria specified in Annex 1 and the Supplier shall log Test Issues reflecting the Severity Level allocated to each Test Issue.

## The Supplier shall be responsible for maintaining the Test Issue Management Log and for ensuring that its contents accurately represent the current status of each Test Issue at all relevant times.  The Supplier shall make the Test Issue Management Log available to the Authority upon request.

## The Authority shall confirm the classification of any Test Issue unresolved at the end of a Test in consultation with the Supplier.  If the Parties are unable to agree the classification of any unresolved Test Issue, the Dispute shall be dealt with in accordance with the Dispute Resolution Procedure using the Expedited Dispute Timetable.

# TEST WITNESSING

## The Authority may, in its sole discretion, require the attendance at any Test of one or more Test Witnesses selected by the Authority, each of whom shall have appropriate skills to fulfil the role of a Test Witness.

## The Supplier shall give the Test Witnesses access to any documentation and Testing environments reasonably necessary and requested by the Test Witnesses to perform their role as a Test Witness in respect of the relevant Tests.

## The Test Witnesses:

##### shall review the Test documentation;

##### shall attend and engage in the performance of the Tests on behalf of the Authority so as to enable the Authority to gain an informed view of whether a Test Issue may be closed or whether the relevant element of the Test should be re-Tested;

##### shall not be involved in the execution of any Test;

##### shall be required to verify that the Supplier conducted the Tests in accordance with the Test Exit Criteria and the relevant Test Plan and Test Specification;

##### may produce and deliver their own, independent reports on Testing, which may be used by the Authority to assess whether the Tests have been Achieved;

##### may raise Test Issues on the Test Issue Management Log in respect of any Testing; and

##### may require the Supplier to demonstrate the modifications made to any defective Deliverable before a Test Issue is closed.

# TEST COMPLIANCE REVIEW

## Without prejudice to its rights pursuant to Clause 12.2(b) (Records, Reports, Audits & Open Book Data), the Authority or contractor appointed by the Authority may perform on-going compliance/quality audits in respect of any part of the Testing (each a “Test Compliance Review”) subject to the provisions set out in the agreed Quality Plan.

## The focus of the Test Compliance Reviews shall be on:

##### adherence to an agreed methodology, the agreed Testing process and any Quality Plan;

##### review of status and key development issues; and

##### identification of key risk areas.

## The Supplier shall allow sufficient time in the Test Plan to ensure that adequate responses to a Test Compliance Review can be provided.

## The Authority will give the Supplier at least 5 Working Days' written notice of the Authority’s intention to undertake a Test Compliance Review.

## The Supplier shall provide all reasonable necessary assistance and access to all relevant documentation required by the Authority to enable it to carry out the Test Compliance Review.

## If the Test Compliance Review gives the Authority concern in respect of the Testing Procedures or any Test, the Authority shall prepare a written report for the Supplier detailing its concerns and the Supplier shall, within a reasonable timeframe, respond in writing to the Authority’s report.

## In the event of an inadequate response to the Authority’s report from the Supplier, the Authority (acting reasonably) may withhold a Test Certificate until the issues in the report have been addressed to the reasonable satisfaction of the Authority.

# OUTCOME OF TESTING

## The Authority shall issue a Test Certificate when the Deliverables satisfy all applicable Test Exit Criteria in respect of that Test without any Test Issues.

## If the Authority deems the Deliverables (or any relevant part) do not satisfy all applicable Test Exit Criteria, the Authority shall notify the Supplier and:

##### the Authority may issue a Test Certificate conditional upon the remediation of the Test Issues;

##### the Authority may extend the Test Plan by such reasonable period or periods as the Parties may reasonably agree and require the Supplier to rectify the cause of the Test Issue and re-submit the Deliverables (or the relevant part) to Testing; or

##### where the failure to satisfy the Test Exit Criteria results, or is likely to result, in the failure (in whole or in part) by the Supplier to meet a Milestone, then without prejudice to the Authority’s other rights and remedies, such failure shall constitute a Notifiable Default for the purposes of Clause 27.1 (Rectification Plan Process).

## The Authority shall be entitled, without prejudice to any other rights and remedies that it has under this Agreement, to recover from the Supplier any reasonable additional costs it may incur as a direct result of further review or re-Testing which is required for the Test Exit Criteria for that Deliverable to be satisfied.

PART C: PROCEDURES FOR MILESTONE ACHIEVEMENT CERTIFICATE

# ISSUE OF MILESTONE ACHIEVEMENT CERTIFICATE

## The Authority shall issue a Milestone Achievement Certificate in respect of a given Milestone as soon as is reasonably practicable following:

##### the issuing by the Authority of Test Certificates and/or conditional Test Certificates in respect of all Deliverables related to that Milestone which are due to be Tested; and

##### achievement to the reasonable satisfaction of the Authority of all Assurance Criteria in respect of all Deliverables related to that Milestone and performance by the Supplier to the reasonable satisfaction of the Authority of any other tasks identified in the Detailed Mobilisation Plan, as associated with that Milestone (which may include the submission of a Deliverable that is not due to be Tested).

## The grant of a Milestone Achievement Certificate shall entitle the Supplier to the receipt of a payment in respect of that Milestone in accordance with the provisions of Schedule 7.1 (Charges and Invoicing).

## If a Milestone is not Achieved, the Authority shall promptly issue a report to the Supplier setting out the applicable Test Issues and any other reasons for the relevant Milestone not being Achieved.

## If there are Test Issues but these do not exceed the Test Issues Threshold, then provided there are no Material Test Issues, the Authority shall issue a Milestone Achievement Certificate.

## If there is one or more Material Test Issue(s), the Authority shall refuse to issue a Milestone Achievement Certificate and, without prejudice to the Authority’s other rights and remedies, such failure shall constitute a Notifiable Default for the purposes of Clause 27.1 (Rectification Plan Process).

## If there are Test Issues which exceed the Test Issues Threshold but there are no Material Test Issues, the Authority may at its discretion (without waiving any rights in relation to the other options) choose to issue a Milestone Achievement Certificate conditional on the remediation of the Test Issues in accordance with an agreed Rectification Plan provided that:

##### any Rectification Plan shall be agreed before the issue of a conditional Milestone Achievement Certificate unless the Authority agrees otherwise (in which case the Supplier shall submit a Rectification Plan for approval by the Authority within 10 Working Days of receipt of the Authority’s report pursuant to Paragraph 1.3 of this Part C; and

##### where the Authority issues a conditional Milestone Achievement Certificate, it may (but shall not be obliged to) revise the failed Milestone Date and any subsequent Milestone Date.

# RISK

## The issue of a Test Certificate, Milestone Achievement Certificate and/or a conditional Milestone Achievement Certificate shall not:

##### operate to transfer any risk that the relevant Deliverable or Milestone is complete or will meet and/or satisfy the Authority's requirements for that Deliverable or Milestone; or

##### affect the Authority's right subsequently to reject all or any element of the Deliverables to which a Test Certificate relates or any Milestone to which the Milestone Achievement Certificate relates.

# ANNEX 1: TEST ISSUES – SEVERITY LEVELS

## Severity Level 1 Test Issue: a Test Issue that causes non-recoverable conditions, e.g. it is not possible to continue using a Component.

## Severity Level 2 Test Issue: a Test Issue for which, as reasonably determined by the Authority, there is no practicable workaround available, and which:

##### causes a Component to become unusable;

##### causes a lack of functionality, or unexpected functionality, that has an impact on the current Test; or

##### has an adverse impact on any other Component(s) or any other area of the Services.

## Severity Level 3 Test Issue: a Test Issue which:

##### causes a Component to become unusable;

##### causes a lack of functionality, or unexpected functionality, but which does not impact on the current Test; or

##### has an impact on any other Component(s) or any other area of the Services;

##### but for which, as reasonably determined by the Authority, there is a practicable workaround available.

## Severity Level 4 Test Issue: a Test Issue which causes incorrect functionality of a Component or process, but for which there is a simple, Component based, workaround, and which has no impact on the current Test, or other areas of the Services.

## Severity Level 5 Test Issue: a Test Issue that causes a minor problem, for which no workaround is required, and which has no impact on the current Test, or other areas of the Services.

# ANNEX 2: TEST CERTIFICATE

To:		[NAME OF SUPPLIER]

FROM:		[NAME OF AUTHORITY]

[Date]

Dear Sirs,

TEST CERTIFICATE

Deliverables: [insert description of Deliverables]

We refer to the agreement (the “Agreement”) relating to the provision of the Services between the [name of Authority] (the “Authority”) and [name of Supplier] (the “Supplier”) dated [date].

Capitalised terms used in this certificate have the meanings given to them in Schedule 1 (Definitions) or Schedule 6.2 ([Testing Procedures]) of the Agreement.

[We confirm that the Deliverables listed above have been tested successfully in accordance with the Test Plan relevant to those Deliverables.]

OR

[This Test Certificate is issued pursuant to Paragraph 5.1 of Part B of Schedule 6.2 ([Testing Procedures]) of the Agreement on the condition that any Test Issues are remedied in accordance with the Rectification Plan attached to this certificate.]*

*delete as appropriate

Yours faithfully

[Name]

[Position]

acting on behalf of [name of Authority]

# ANNEX 3: MILESTONE ACHIEVEMENT CERTIFICATE

To:		[NAME OF SUPPLIER]

FROM:		[NAME OF AUTHORITY]

[Date]

Dear Sirs,

MILESTONE ACHIEVEMENT CERTIFICATE

Milestone: [insert description of Milestone]

We refer to the agreement (the “Agreement”) relating to the provision of the Services between the [name of Authority] (the “Authority”) and [name of Supplier] (the “Supplier”) dated [date].

Capitalised terms used in this certificate have the meanings given to them in Schedule 1 (Definitions) or Schedule 6.2 ([Testing Procedures]) of the Agreement.

[We confirm that all the Deliverables relating to Milestone [number] have been [tested successfully in accordance with the Test Plan relevant to this Milestone] or [that a conditional Test Certificate has been issued in respect of those Deliverables that have not satisfied the relevant Test Exit Criteria] or [been approved by the Authority.]*

OR

[This Milestone Achievement Certificate is granted pursuant to Paragraph 1.1 of Part C of Schedule 6.2 (Testing Procedures) of the Agreement on the condition that any Test Issues are remedied in accordance with the Rectification Plan attached to this certificate.]*

[You may now issue an invoice in respect of the Milestone Payment associated with this Milestone in accordance with the provisions of Schedule 7.1 (Charges and Invoicing)]*

*delete as appropriate

Yours faithfully

[Name]

[Position]

acting on behalf of [Authority]