# Annex A

| Title of project: | Model development to assess the vulnerability of the Cayman Islands to storm surge and inland flooding, and the role and value of natural capital in mitigating the impacts |
| --- | --- |
| Date and time for return of tenders: | Wednesday 6 January 2021 at 17:00 hours |
| Contract Reference No: | C20-0302-1509 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO AMANDA GREGORY, GWAWR JONES OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated email to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Amanda Gregory Joint Nature Conservation Committee Email: Amanda.Gregory@jncc.gov.uk Tel: 01733562626 OR Gwawr Jones Joint Nature Conservation Committee Email: Gwawr.Jones@jncc.gov.uk Tel: 01733562626 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | Week beginning 11th January 2021 |
| Proposed end-date: | 31st March 2021 |

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: https://jncc.gov.uk/about-jncc/

## Project Aims

The Cayman Islands are highly dependent upon the natural environment for their economic and social wellbeing.  They are also reliant on limited manmade assets.  In the Caribbean in particular, these manmade capital assets, and human life, are vulnerable to both natural and manmade hazards.  The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economy and reducing its ability to protect manmade assets and human well-being.

The project will support the Cayman Islands understand the role of natural capital and incorporate this knowledge into plans, policies and procedures by enhancing their ability to prepare for / recover from their impact.  Work will also contribute to the UK Government’s new hurricane preparedness plans for the British Overseas Territories in the Caribbean.

Building upon the work to date, this CSSF-funded project will develop a GIS-based model  to assess the risk to livelihood and infrastructure from storm surge/inland flood and assess the role and economic value of the Cayman Islands’ natural capital in protection of manmade capital – to assess the vulnerability (susceptibility) of manmade capital to natural hazards such as (but not limited to) storm surge, in the coastal zone and landslip or flash flooding in the terrestrial environment; and build upon the British Virgin Islands developed GIS based model and application for the Cayman Islands.

JNCC is supporting the Cayman Island Government by monitoring environmental change in the context of the role of natural capital in mitigating hurricane impacts, with the emphasis on supporting economic reconstruction, preparations for, and recovery from future hurricane impacts. The project aims to demonstrate the monetary and functional value of the natural environment to the Cayman Islands, including the importance of effective land use planning and restoration (nature-based solutions) to mitigate the effects of climate.

This project aims to:

- Research existing surge models to develop and/or refine existing GIS-based models for the Cayman Islands to identify communities and infrastructure at risk from storm surge/inland flood events;

- Undertake an economic assessment of the functional role and value of the natural environment across the Cayman Islands in mitigating terrestrial and coastal hazards (e.g. those associated with disaster resilience and protection) and map these values; and

- Build capacity on Cayman Islands to undertake future analysis.

The study does not intend to cover the wide variety of Cayman Islands’ ecosystems and their associated services but focus on those associated with enhancing disaster resilience against storm surge and inland flooding.

Please note:  There are two component parts to this contract.  Tenderers can submit for one or both component parts, however, ideally the project would be carried out under a single contract:

A: storm surge/inland flood model development; and

B: economic assessment and mapping of the role and value of natural capital in relation to disaster resilience.

## Project Background

Population concentration in coastal areas and the location of the Islands in the Atlantic hurricane belt makes storm surge a significant hazard (Bray et al. 2019). Hurricane Irma for example led to peak surge of over 6m (University of the West Indies 2017; Williams et al. 2018), damaging infrastructure and natural capital assets (Government of the Virgin Islands 2017). It is therefore important to understand how nature-based solutions may attenuate storm surge and improve resilience in the Cayman Islands.

The 2016 Conflict, Stability & Security Fund (CSSF) funded programme of work, ‘Enhancing economic security through environmental resilience’ in the UK Overseas Territories (OTs) (Caribbean Territories of Anguilla, British Virgin Islands, Montserrat and Turks and Caicos Islands and the South Atlantic Territories of Falkland Islands, St Helena, Ascension and Tristan da Cunha) aimed to improve long-term economic planning to support growth and development.  Embedding the role of the natural environment in economic and spatial planning through existing or new policies or legislation was one element, with the objective to protect and enhance the value of the OTs vital natural environment.

The suite of projects mapped and valued the natural assets by integrating satellite data, Geographical Information Systems (GIS) and economic assessments of the priority environmental goods and services (derived from natural capital).  In the Caribbean, a GIS based model was developed to assess the vulnerability to storm surge and flooding events and their impacts on infrastructure and human life in the British Virgin Islands.  For more information see:  https://jncc.gov.uk/our-work/natural-capital-in-the-caribbean-uk-overseas-territories/

This project supports JNCCs suite of CSSF-funded projects which integrate satellite data, Geographic Information Systems (GIS) and economic assessments of environmental goods and services (derived from natural capital) with the following objectives:

- establish the Total Economic Value (TEV) of the terrestrial and marine natural environment to each of the ten listed Territories;

- identify the priority natural capital assets and measurable attributes (Natural Capital Metrics) to monitor changes in value through time;

- integrate natural capital valuations into national mapping (GIS) to define the spatial distribution of these natural assets (Value Mapping) and to promote the integration of such valuations into planning and policy making to improve long-term economic growth.

## Project Objectives

To meet the overall aim of this project (Section 2), the objectives are to:

The objectives of the work to be done under this contract are to build upon the existing GIS-model and application developed for the British Virgin Islands and previous natural capital valuation work to:

      - Investigate the suitability of available models for understanding the role of natural capital in storm surge/inland flood resilience, including the ability to model the impact of potential future changes such as restoration and degradation, and evaluate the potential model against the existing GIS-based model as a prospective tool for Cayman Islands;

- Based on the outcome from 1; develop and refine the hydrological model or existing GIS-based model implemented in the BVI, including creating a user interface, and apply to the Cayman Islands;

- Use the model outputs (2) to create scenarios to understand vulnerability and inform areas at risk of storm surge/inland flood and present opportunities for nature-based solutions to minimise risk; and

- Map and assess the value of natural capital assets (in relation to disaster resilience and response – value for storm protection) across the Cayman Islands.

- Provide training to Cayman Island Government officers in the use and application of the flood model and economic valuation techniques.

## Project Objectives: Detailed tasks

JNCC expects the project will be undertaken by a single contractor.  However, should the tender exercise support two contractors to deliver the work the contractors will be expected to work closely with each other.

There are two component parts to this contract.  Tenderers can submit for one or both component parts.

Component 1:  Storm surge/inland flood model and application

- Develop or enhance a model that captures the role of natural capital for the Cayman Islands to include an uncertainty analysis of the model outputs;

- Investigate and agree a suitable hydrological model for Cayman Islands;

- Create the storm surge/inland flood model for the Cayman Islands;

- Conduct a scenario assessment of the effect natural capital has on the vulnerability of different features to assess how nature-based solutions can mitigate some of the risks associated with such storms;

  - Use habitat maps to assess evidence

  - Evaluate the potential effect of hazards on areas, such as areas with a high proportion of natural habitats, urban areas or other, as agreed with Cayman Islands Government

  - Visualise and report findings to JNCC and Cayman Islands Government.

- Develop an opportunity map for Cayman Islands indicating areas where the natural environment could be best used to enhance resilience

Component 2:  economic assessment

- Using outputs from Component 1, undertake an economic assessment of the functional role and value of the natural environment across Cayman Islands in mitigating terrestrial and coastal hazards (eg those associated with disaster resilience and protection such as coral reef, mangrove, sea grass and salt ponds) and map these values.

  - Identify features relevant to coastal protection and flooding and review associated economic valuation approaches;

  - Select a valuation approach and test in case study sites, as agreed with Cayman Islands Government;

  - Refine and extend to provide a national valuation for Cayman Islands; and

  - Validate economic assessment against previous post-event environmental, financial and economic losses for the Cayman Islands.

All interim and final reports, maps and other outputs to be shared with the Government of Cayman Islands in a timely manner to contribute to recovery planning.

## Potential follow-on work

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake additional work on this contract into the financial year 2021/22.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Tenderers are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

- An updated, functioning, GIS-based model for the Cayman Islands which applies the assessment procedure including assessment of the value of the natural environment in disaster mitigation and is integrated into the Cayman Islands GIS.

- Natural capital valuation (with a focus on coastal protection/inland flooding) with natural resource inventory

- A detailed technical report providing:

  - A non-technical summary of economic valuations and storm surge/inland flood model and application;

  - assessment of the effect natural capital had on the vulnerability of different man-made and natural features;

  - opportunity maps highlighting areas for enhancing Cayman Islands protection services;

  - value maps for the Cayman Island system;

  - assessment of the uncertainty of the model, supported by examples of where the models worked well and where they did not;

  - recommendations for the next stage of development the Cayman Islands.

- A user guide to accompany the storm surge/inland flood application.

- A visual policy-based report for the Cayman Island Government for demonstration of the model and economic valuation of protection services.

- A document detailing the methodology for post hazard economic assessment of environmental financial and economic losses for the Cayman Islands.

- Training and capacity building so relevant users can use the tools developed and delivered by the project.

## Dissemination

The report or tools produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to JNCC, the UK Conservation Agencies and Defra.

All documentation delivered by JNCC to the contractor regarding specification for the new system should be treated as commercial-in-confidence, the contractor should seek JNCC permission before distributing the documentation to any third parties.

Any information delivered to the contractor should not be used for any purposes outside the scope of this contract and should be destroyed on completion of the contract.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (remote) | 11th January 2021 |
| Beta version storm surge/inland flood risk model | 9 February 2021 |
| Economic assessment of the functional role and value of the natural environment across the Cayman Islands | Mid-February 2021 |
| Working storm surge/inland flood risk model completed and delivered to Cayman Islands Government | End March 2021 |
| Remote training in use of model and economic valuation | End March 2021 |
| All reporting and mapping outputs complete | 26 March 2020 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2021/22 is subject to availability of funds.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house  style guidance http://cms/JNCCIntranet63/pdf/NewDesign_JNCC_DesignIDv1.4LowRes.pdf  unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

(Note for author. If research project/contract See EQA Policy Appendix 4 (Communicating Evidence Quality).  Ensure that data management and storage requirements are stipulated, taking into account relevant policy for data access; see https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/).

Copies of documentation associated with the case studies should be provided in electronic format, with an associated reference catalogue.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point will be:

Ms Amanda Gregory

Email: Amanda.Gregory@jncc.gov.uk

Tel: +44 (0)1733 866811

Dr Gwawr Jones

Email:  Gwawr.Jones@jncc.gov.uk

Tel: +44 (0)1733 86

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract. See EQA Policy Appendix 1 (Bias, Conflicting Evidence and uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion).

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough on…

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC staff and staff members from Natural England, Natural Resources Wales, Scottish Natural Heritage and DAERA-NI.  Unless otherwise stated in your tender submission, bids will be forwarded to these agencies for evaluation purposes only. (Please delete if this does not apply)

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs). | 10 |  |
|  | Soundness and logicality of methods | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (20% of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 6 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Totals | 30 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

- On satisfactory completion of a beta-model and draft valuations, expected to be late in February 2021;

- On satisfactory completion of the model, training and valuation delivered to JNCC and Cayman Islands Government, expected to be end of March 2021

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

Hurricane preparedness plans for the British Overseas Territories in the Caribbean, July 2019

Assessment of the value of natural capital in the protective service against coastal and inland flooding in the UK Overseas Territory of the British Virgin Islands: BVI Flood Resilience Modelling Tool, Technical Report Sept 2020

An assessment of the value of natural capital in the protective service against coastal and inland flooding in the UK Overseas Territory of the British Virgin Islands: BVI Flood Resilience Modelling Tool – Technical Report (2020) https://hub.jncc.gov.uk/assets/81fc103c-1d54-421e-997c-b9f7d986ee78

Natural capital in the Overseas Territories: Natural capital in the Caribbean and South Atlantic Overseas Territories: Valuation, Vulnerability and Monitoring Change (2016-2020) https://jncc.gov.uk/our-work/natural-capital-in-the-overseas-territories/