## 1.0
5049 - GREENWAYS PHASE 1, COMMONFIELD LANE TO FBC CENTRE GORSE RIDE, WOKINGHAM
TENDER BILL OF QUANTITIES - Version #1 - 13/03/17
CONTENTS
1.0 - QUALITY ASSURANCE APPROVALS
2.0 - METHODOLOGY
3.0 - COST SUMMARY
4.0 - BILL OF QUANTITIES
1.0 - QUALITY ASSURANCE APPROVALS
1.1 - PREPARATION & AUTHORISATION
| Issue/revision |  | DRAFT | Issue 1
| Date |  | 2017-03-23
| Prepared by |  | O.Baron
Signature
| Checked by |  | T.Allen
Signature
| Authorised by |  | S. Grant
Signature
1.2 - DRAWINGS
| Project: |  | Date of Receipt
| GREENWAYS PHASE 1, WOKINGHAM | Day | 23
|  | Month | 3
|  | Year | 17
| Title: | Number | Revisions ( ini = initial issue)
| General arrangement, sheet 1 of 8 | 5049/GWI/GA/001 | A
| General arrangement, sheet 2 of 8 | 5049/GWI/GA/002 | A
| General arrangement, sheet 3 of 8 | 5049/GWI/GA/003 | A
| General arrangement, sheet 4 of 8 | 5049/GWI/GA/004 | A
| General arrangement, sheet 5 of 8 | 5049/GWI/GA/005 | A
| General arrangement, sheet 6 of 8 | 5049/GWI/GA/006 | A
| General arrangement, sheet 7 of 8 | 5049/GWI/GA/007 | A
| General arrangement, sheet 8 of 8 | 5049/GWI/GA/008 | A
| Approach improvements to Commonfield Lane | 5049/GWI/GA/009 | A
| Trial hole location 1 | 5049/GWI/TH/001 | A
| Trial hole location 2 | 5049/GWI/TH/002 | A
| Trial hole location 3 | 5049/GWI/TH/003 | A
STANDARD DETAILS
| SERVIC DUCTS | WSD/500/001 | B
| ROAD + FOOTWAY GULLY DETAILS | WSD/500/004 | B
| LINED DITCHES AND OUTFALLS | WSD/500/009 | B
| HEADWALL TYPE 3 | WSD/500/012 | B
| CARRIAGEWAY HAUNCHING | WSD/900/003 | B
| KERBS + CHANNELS | WSD/1100/001 | A
| FOOTWAYS, CYCLEWAYS AND VERGES | WSD/1100/013 | B
| TRAFFIC SIGNS | WSD/1200/001 | B
| Typical cross section 1 | TCS/001 | A
| Typical cross section 2 | TCS/002 | A
| Typical cross section 3 | TCS/003 | A
| Typical cross section 4 | TCS/004 | A
| Typical cross section 5 | TCS/005 | A
1.3 - DOCUMENTS
| Project: |  | Date of Receipt
| GREENWAYS PHASE 1, WOKINGHAM | Day
Month
Year
| Title: | Number | Revisions ( ini = initial issue)
Utility information

## 2.0
5049 - GREENWAYS PHASE 1, COMMONFIELD LANE TO FBC CENTRE GORSE RIDE, WOKINGHAM
2.0 - METHODOLOGY
2.1 - INTRODUCTION
The project comprises the upgrade of the Bridelway BA18 from Commonfield Lane, along California Country Park
and the footpath linking to the FBC Centre in Finchampstead, Wokingham
Based on the level of design information provided a number of assumptions have been made regarding item
specification and associated bill descriptions. These assumptions have been detailed in section 2.4.
2.2 - BASIS OF INFORMATION
This bill of quantities has been prepared in accordance with the Manual of Contract Documents for Highway
Works: Volume 4 - Bills of Quantities for Highways Works: Section 1 - Method of Measurement for Highway
Works (MMHW).
There are 'indicative' items included in the bills of quantities. These items have not been quantified.
It is intended that these 'indicative' items are to be used as a guide of further items which may be required.
The items are not exhaustive, the addition or deletion of items should be completed as required.
It is intended that any additional items are to be quantified by the Contractor.
2.3 - EXCLUSIONS
The following are excluded, but should be included within the bill of quantities, where appropriate:
Preliminaries including Traffic Management
Risks including but not limited to:
Further survey works, site investigation or the like
Lowering or diversion of any existing sewers, drainage or services
Further earthworks, landscaping works or the like
2.4 - ASSUMPTIONS
The following assumptions have been made
Series 100: Preliminaries
Indicative' items included for deletion/addition as required
Series 200: Site Clearance
Indicative' items included for deletion/addition as required
Series 500: Drainage and Service Ducts
Indicative' items included for deletion/addition as required
Series 600: Earthworks
All material assumed to be acceptable
Fill to be made up from excavated material
Indicative' items included for deletion/addition as required
Series 700: Pavements
Indicative' items included for deletion/addition as required
Series 800: Road pavements - unbound, cement and other hydraulically bound mixtures
Indicative' items included for deletion/addition as required
Series 1100: Kerbs, Footways and Paved Areas
Indicative' items included for deletion/addition as required
Series 1200: Traffic Signs and Road Markings
Indicative' items included for deletion/addition as required
Series 3000: Landscape and Ecology
Indicative' items included for deletion/addition as required
Series 3100: Other items not included within the schedule
Indicative' items included for deletion/addition as required

## 3.0
5049 - GREENWAYS PHASE 1, COMMONFIELD LANE TO FBC CENTRE GORSE RIDE, WOKINGHAM
3.0 - COST SUMMARY
| SERIES | GROUP/ELEMENT | BROUGHT FORWARD
£
ROADWORKS
| 100 | Preliminaries | 0
| 200 | Site Clearance | 0
| 300 | Fencing | 0
| 400 | Road Restraint Systems (Vehicle and Pedestrian) | 0
| 500 | Drainage and Service Ducts | 0
| 600 | Earthworks | 0
| 700 | Pavements | 0
| 800 | Road pavements - unbound, cement and other hydraulically bound mixtures | 0
| 1100 | Kerbs, Footways and Paved Areas | 0
| 1200 | Traffic Signs and Road Markings | 0
| 1300 | Road Lighting Columns & Brackets, CCTV and Cantilever Masts | 0
| 1400 | Electrical Work for Road Lighting and Traffic Signs | 0
| 1500 | Motorway Communications | 0
| 1600 | Piling and Embedded Retaining Walls | 0
| 1700 | Structural Concrete | 0
| 1800 | Steelwork for Structures | 0
| 1900 | Protection of Steelwork against Corrosion | 0
| 2000 | Waterproofing for Structures | 0
| 2100 | Bridge Bearings | 0
| 2300 | Bridge Expansion Joints and Sealing of Gaps | 0
| 2400 | Brickwork, Blockwork and Stonework | 0
| 2500 | Special Structures | 0
| 2700 | Acc. Works, Works for SU's, Provisional Sums and PC Items | 0
| 3000 | Landscape and Ecology | 0
| 3100 | Other items not included within the schedule | 0
| 5000 | Maintenance Painting of Steelwork | 0
|  | TOTAL: ROADWORKS ESTIMATE (A) | 0

## 100
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 100 | Series_100: Preliminaries |  |  |  | 0
3 | 100_01 | Series_100_01: Temporary Accommodation |  |  |  | 0
| 100_01_01 | Erection of offices and messes for the Contractor | 1 | no |  | Unpriced
| 100_01_02 | Dismantling of offices and messes for the Contractor | 1 | no |  | Unpriced
| 100_01_03 | Erection/relocation of fences, notice an direction boards | 1 | no |  | Unpriced
| 100_01_04 | Temporary installation for vehicular access and hardstanding area | 1 | no |  | Unpriced
| 100_01_05 | Dismantling of fences, notice and direction boards | 1 | no |  | Unpriced
3 | 100_02 | Series_100_02: Vehicles for the Overseeing Organisation
3 | 100_03 | Series_100_03: Communication System for the Overseeing Organisation
3 | 100_04 | Series_100_04: Operatives for the Overseeing Organisation
3 | 100_05 | Series_100_05: Information Board |  |  |  | 0
| 100_05_01 | Information board size not exceeding 10 m² |  | no |  | Unpriced
3 | 100_06 | Series_100_06: Traffic Safety and Management |  |  |  | 0
| 100_06_01 | Establishment, maintenance and removal of Chapter 8 “relaxed” layout, (up to and including 1 km in length) off peak | 1 | no |  | Unpriced
| 100_06_02 | Establishment and removal of temporary traffic signals | 1 | no |  | Unpriced
| 100_06_03 | Obtaining licences and agreements from Wokingham Borough Council streetworks | 1 | no |  | Unpriced
3 | 100_07 | Series_100_07: Temporary Diversion for Traffic
3 | 100_08 | Series_100_08: Recovery Vehicles
3 | 100_09 | Series_100_09: Progress Photographs
| 100_09_01 | Progress Photographs | 1 | no |  | Unpriced
3 | 100_10 | Series_100_10: Temporary CCTV System for the Monitoring of Traffic
3 | 100_11 | Series_100_11: Temporary Automatic Speed Camera System for the Enforcement of Mandatory Speed Limits at Roadworks
|  | Total to carry forward to General Summary |  |  |  | 0

## 200
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 200 | Series_200: Site Clearance |  |  |  | 0
3 | 200_01 | Series_200_01: Site Clearance |  |  |  | 0
| 200_01_01 | General Site Clearance | 400 | sqm |  | Unpriced
3 | 200_02 | Series_200_02: Take Up or Down and Set Aside for Re-use or Remove to Store or Tip Off Site |  |  |  | 0
| 200_02_01 | Cutting back trees, bushes and hedges | 230 | sqm |  | Unpriced
| 200_02_02 | Fell tree and remove tree stump, tree girth not exceeding 1m | 1 | no |  | Unpriced
| 200_02_03 | Take up or down and remove to tip off site precast concrete edgings | 2 | m |  | Unpriced
| 200_02_04 | Take up or down and remove to tip off site timber edgings | 160 | m |  | Unpriced
| 200_02_05 | Take up or down and remove to tip off site post and rail fence | 85 | m |  | Unpriced
| 200_02_06 | Take up or down and remove to tip off site wooden gate | 1 | m |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 500
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 500 | Series_500: Drainage and Service Ducts |  |  |  | 0
3 | 500_01 | Series_500_01: Drains and Service Ducts (excluding Filter Drains, Narrow Filter Drains and Fin Drains) |  |  |  | 0
| 500_01_01 | 150 mm internal diameter PVCU - standard drain as gully connection on bed Type D1 in trench depth to invert not exceeding 2 metres, average depth to invert 1.5 metres | 2 | m |  | Unpriced
| 500_01_02 | 150 mm internal diameter PVCU - standard drain on bed Type D1 in trench depth to invert not exceeding 2 metres, average depth to invert 1.5 metres | 16 | m |  | Unpriced
3 | 500_02 | Series_500_02: Filter Drains
3 | 500_03 | Series_500_03: Fin Drains and Narrow Filter Drains
3 | 500_04 | Series_500_04: Connections
| 500_04_01 | Connection of 150 mm internal diameter pipe to existing chamber depth to invert exceeding 2 metres, average depth to 1.5 metres | 2 | no |  | Unpriced
3 | 500_05 | Series_500_05: Chambers and Gullies |  |  |  | 0
| 500_05_01 | Precast concrete trapped gully as WSD/500/4 with D400 grating and frame | 2 | no |  | Unpriced
3 | 500_06 | Series_500_06: Headwalls and Outfall works
| 500_06_01 | Headwall as WSD/500/12, Type 3, to pipe not exceeding 150mm internal diameter | 2 | m³ |  | Unpriced
3 | 500_07 | Series_500_07: Soft Spots and Other Voids |  |  |  | 0
| 500_07_01 | Provisional rate allowance for excavation of soft spots and other voids in the bottom of trenches, chambers and gullies |  | m³ |  | Unpriced
| 500_07_02 | Provisional rate allowance for filling of soft spots and other voids in the bottom of trenches, chambers and gullies with acceptable excavated material |  | m³ |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 600
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 600 | Series_600: Earthworks |  |  |  | 0
3 | 600_01 | Series_600_01: Excavation |  |  |  | 0
| 600_01_01 | Excavation of acceptable material Class 5A | 875 | m³ |  | Unpriced
| 600_01_02 | Excavation of acceptable material excluding Class 5A in cutting and other excavation | 155 | m³ |  | Unpriced
3 | 600_02 | Series_600_02: Excavation in Hard Material
3 | 600_03 | Series_600_03: Processing of Unacceptable Material Classes U1A and U1B
3 | 600_04 | Series_600_04: Deposition of Fill |  |  |  | 0
| 600_04_01 | Deposition of acceptable material in embankments and other areas of fill | 155 | m³ |  | Unpriced
3 | 600_05 | Series_600_05: Disposal of Material |  |  |  | 0
| 600_05_01 | Disposal of acceptable material excluding Class 5A | 875 | m³ |  | Unpriced
3 | 600_06 | Series_600_06: Imported Fill
3 | 600_07 | Series_600_07: Compaction of Fill |  |  |  | 0
| 600_07_01 | Compaction of acceptable material in embankments and other areas of fill | 155 | m³ |  | Unpriced
3 | 600_08 | Series_600_08: Soil Stabilisation
3 | 600_09 | Series_600_09: Geotextiles
| 600_09_01 | Standard Geotextile, Terram T1000 or similar, in compliance with BS EN 13251 | 5575 | m² |  | Unpriced
3 | 600_10 | Series_600_10: Soft Spots and Other Voids |  |  |  | 0
| 600_10_01 | Provisional rate allowance for excavation of soft spots and other voids below cuttings or under embankments |  | m³ |  | Unpriced
3 | 600_11 | Series_600_11: Disused Sewers, Drains, Cables, Ducts, Pipelines and the Like Occurring at Formation or Sub-formation Level; Disused Basements, Cellars and the Like and Gullies
3 | 600_12 | Series_600_12: Supports Left in Excavation
3 | 600_13 | Series_600_13: Topsoiling and Storage of Topsoil |  |  |  | 0
| 600_13_01 | Topsoiling 150 mm thick to surfaces sloping at 10° or less to the horizontal | 130 | m² |  | Unpriced
| 600_13_02 | Topsoiling 150 mm thick to surfaces sloping at more than 10° to the horizontal | 70 | m² |  | Unpriced
3 | 600_14 | Series_600_14: Completion of Formation and Sub-formation |  |  |  | 0
| 600_14_01 | Provisional allowance rate for completion of sub-formation on material other than Class 1C, 6B or rock in cuttings |  | m² |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 700
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 700 | Series_700: Pavements |  |  |  | 0
3 | 700_01 | Series_700_01: Sub-base |  |  |  | 0
3 | 700_02 | Series_700_02: Pavement |  |  |  | 0
| 700_02_01 | Dense Bitumen Macadam with 20 mm aggregate binder course to Clause 906 60 mm thick in carriageway, hardshoulder and hardstrip | 185 | m² |  | Unpriced
| 700_02_02 | Close graded Bitumen Macadam with 10mm aggregate Surafce Course to Clause 942 40mm thick in carriageway, hard shoulder and hardstrip to Clause 942 | 185 | m² |  | Unpriced
| 700_02_03 | Extra over previous item for red pigmentation | 185 | m² |  | Unpriced
3 | 700_03 | Series_700_03: Regulating Course |  |  |  | 0
| 700_03_01 | Provisional allowance rate for Dense Bitumen Macadam base regulating to Clause 903/907 with 40 mm aggregate laid in carriageway, hard shoulder and hardstrip |  | t |  | Unpriced
3 | 700_04 | Series_700_04: Surface Treatment
| 700_04_01 | Resin Based Surface Treatment to Clause 924, (High Friction Surfaces), in red | 41 | m² |  | Unpriced
3 | 700_05 | Series_700_05: Tack Coat |  |  |  | 0
| 700_05_01 | Tack coat K1-40 to BS434 Pt1 at a uniform rate of spread of 0.35 l/m² (Assummes binder/surface course) | 185 | m² |  | Unpriced
3 | 700_06 | Series_700_06: Cold Milling (Planning) |  |  |  | 0
| 700_06_01 | Milling Pavement to 100mm depth | 185 | m² |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 800
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 800 | Series_800: Road pavements - unbound, cement and other hydraulically bound mixtures |  |  |  | 0
3 | 800_01 | Series_800_01: Unbound mixtures for Subbase |  |  |  | 0
| 800_01_01 | Type 1 unbound mixture subbase in compliance with BS EN 13285 | 166 | m³ |  | Unpriced
| 800_01_02 | Type 3 open graded unbound mixture subbase in compliance with BS EN 13285, aggregates in compliance with BS EN 13242 | 1245 | m³ |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 1100
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 1100 | Series_1100: Kerbs, Footways and Paved Areas |  |  |  | 0
3 | 1100_01 | Series_1100_01: Kerbs, Channels, Edgings, Combined Drainage and Kerb Blocks and Linear Drainage Channel Systems |  |  |  | 0
| 1100_01_01 | Precast concrete 125mm x 255mm half battered kerbs to WSD/1100/001 HB2 laid straight or curved over 15m radius | 24 | m |  | Unpriced
| 1100_01_02 | Precast concrete kerb dropper/taper from 125mm x 255mm HB2 to 125mm x 150mm BN laid straight or curved over 15m radius | 4 | m |  | Unpriced
| 1100_01_03 | Precast concrete 125mm x 255mm bull nosed kerbs to WSD/1100/001 Fig 2 laid straight or curved over 15m radius | 4 | m |  | Unpriced
| 1100_01_04 | Granite setts 100 x 200 on edge to WSD/1100/1, type DS2, laid straight or curved over 15 metre radius | 28 | m |  | Unpriced
| 1100_01_05 | Precast concrete edging 50mm x 150mm with 75mm thick ST1 concrete bed and haunching laid straight or curved over 15m radius | 210 | m |  | Unpriced
| 1100_01_06 | Timber edging 40mm x 90mm laid straight or curved over 15 metre radius | 1850 | m |  | Unpriced
3 | 1100_02 | Series_1100_02: Additional Concrete for Kerbs, Channels, Edgings, Combined Drainage and Kerb Blocks and Linear Drainage Channel Systems
3 | 1100_03 | Series_1100_03: Remove from Store and Relay Kerbs, Channels, Edgings, Combined Drainage and Kerb Blocks and Linear Drainage Channel Systems
3 | 1100_04 | Series_1100_04: Footways and Paved Areas |  |  |  | 0
| 1100_04_01 | 6mm aggregate medium graded bitumen macadam surface course 20mm thick | 137 | m² |  | Unpriced
| 1100_04_02 | 20m aggregate dense bitumen macadam binder course 50mm thick | 137 | m² |  | Unpriced
| 1100_04_03 | Footway comprising Type 1 unbound mixture subbase 150mm thick to Clause 803, Dense Macadam binder course with 20mm aggregate 50mm thick to Clause 906, Dense Macadam surface course with 6mm aggregate 20mm thick to Clause 909 | 212 | m² |  | Unpriced
| 1100_04_04 | Apply approved weed killer to footway formation | 5652 | m² |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 1200
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 1200 | Series_1200: Traffic Signs and Road Markings |  |  |  | 0
3 | 1200_01 | Series_1200_01: Traffic Signs |  |  |  | #REF!
3 | 1200_02 | Series_1200_02: Remove from Store and Re-erect Traffic Signs |  |  |  | #REF!
3 | 1200_03 | Series_1200_03: Road Markings |  |  |  | 0
| 1200_03_01 | Rectangular sign (including flag type) - Class 1 retroreflective. Sign size up to 0.15m2 | 1 | no |  | Unpriced
| 1200_03_02 | Rectangular sign (including flag type) - Class 1 retroreflective. Sign size between 0.15 – 0.25m2 | 1 | no |  | Unpriced
| 1200_03_03 | Rectangular sign (including flag type) - Class 1 retroreflective. Sign size between 1.0 – 2.5m2 | 2 | no |  | Unpriced
| 1200_03_04 | Remove from store and erect traffic sign or street name plate area not exceeding 0.5sq.m. on tubular steel post/posts/lamp column/offset bracket | 2 | no |  | Unpriced
| 1200_03_05 | Remove from store and erect traffic sign area exceeding 1.0sq.m. but not exceeding 2.0sq.m. on tubular steel post/posts/offset bracket | 2 | no |  | Unpriced
| 1200_03_06 | Tubular galvanised steel post 76mm diameter to WSD/1200/1 height above ground level not exceeding 3.0m | 5 | no |  | Unpriced
| 1200_03_07 | Adjust per 500mm for above or below ground level | 7 | no |  | Unpriced
| 1200_03_08 | Continuous line in white thermoplastic screed with applied ballotini up to 100mm wide | 90 | m |  | Unpriced
| 1200_03_09 | Intermittent line in white thermoplastic screed with applied ballotini 100mm wide | 25 | no |  | Unpriced
| 1200_03_10 | Letters/Numerals in white thermoplastic screed with applied ballotini 2800mm high | 16 | no |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 3000
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 3000 | Series_3000: Landscape and Ecology |  |  |  | 0
3 | 3000_01 | Series_3000_01: Ground Preparation and Cultivation
3 | 3000_02 | Series_3000_02: Seeding and Turfing |  |  |  | 0
| 3000_02_01 | Grass seeding by conventional sowing to surfaces sloping at 10° or less to the horizontal | 170 | m² |  | Unpriced
| 3000_02_02 | Grass seeding by conventional sowing to surfaces sloping at more than 10° to the horizontal | 30 | m² |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0

## 3100
LEVEL | ITEM REF. | BILL DESCRIPTION | BILL QUANTITY | UNIT | RATE | AMOUNT
1 |  | GREENWAYS PHASE 1, WOKINGHAM
2 | 3100 | Series_3100: Other items not in the schedule |  |  |  | 0
3 | 3100_01 | Series_3100_01: Other items not in the schedule |  |  |  | 0
| 3100_01_01 | provide and erect RB150 "lift out" post : 2x RB/150 1500mm overall height, 139mm diameter lift out posts powder coated in white, from BROXAP or similar | 2 | no |  | Unpriced
| 3100_01_02 | Self-binding gravel mixture surface course material, limestone base, graded 14mm to fines, Golden Amber Footpath Gravel from Cedex or similar, average 50mm thickness | 166 | m² |  | Unpriced
| 3100_01_03 | Provide and erect Glasdon Glenwood post - dark oak - 830mm, with red and white reflective bands | 2 | no |  | Unpriced
| 3100_01_04 | Provide and erect Glasdon mini-ensgin bollard with 150mm signface to specified diagram | 1 | no |  | Unpriced
| 3100_01_05 | Provide and erect timber post and rail as specified : post and rail (x3) fencing 1.2m high fence, rails at 300mm center with top rail 150mm below top of the post | 85 | m² |  | Unpriced
|  | Total to carry forward to General Summary |  |  |  | 0